## Sheet1
Public Utility Commission of Texas
ORA proposed schedule for April cases
2026-07-28
Internal Draft
Cases | Filing Date | Referral | Generic | List of | Supplemental | OPD | Objection to | Commission | Preliminary | Brief | Preliminary | Technical | Settlement | Settlement | Intervenor | ORA | Rebuttal | Hearing | PFD | Interim | Final
|  | Order | Prehearing | issues | Filing | order to | filing related to | Workshop | Order | on Legal | Order | conference | Issues | conference | testimony | Testimony | testimony |  |  | Order | Order
|  | issued |  | filed |  | request | interim code of |  | if | & Policy | if |  | list
[6 empty] | briefing | conduct |  | no briefing | issues | briefing
|  | (1) |  | (2) |  | (3) | (4) | (5) | (6) | (6) | (6) | [6 empty] | (7) |  |  | (8)
TXU/SESCO | 2000-03-31 | 2000-04-05 | The | 2000-04-26 |  | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-06-21 | 2000-07-14 | 2000-07-21 | 2000-08-14 | 2000-08-28 | 2000-09-05 | 9/7-9/28 | 2000-12-15 | 2000-02-08 | 2001-08-31
SESCO | 2000-04-01 | [9 empty] | 2000-05-11 | 2000-05-25 | 2000-06-22 | 2000-06-29 | 2000-07-07 | 2000-08-28 |  | 9/4-9/14 | 2000-11-06 | 2001-12-09 | 2001-04-01
Week
TNMP | 2000-03-31 | 2000-04-05 | of | 2000-04-26 |  | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-07-21 | 2000-08-14 | 2000-08-21 | 2000-09-11 | 2000-09-25 | 2000-10-02 | 10/4-10/16 | 2000-12-15 | 2000-02-08 | 2001-08-31
2000-04-17
Reliant | 2000-03-31 | 2000-04-05 |  | 2000-04-26 |  | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-08-07 | 2000-08-30 | 2000-09-06 | 2000-09-29 | 2000-10-13 | 2000-10-20 | 10/23-11/13 | 2000-01-15 | 2000-02-22 | 2001-08-31
Non-IOU TCOS Cases (10)
STEC | 2000-05-08 | [9 empty] | 2000-06-22 |  | 2000-09-04 | 2000-09-12 | 2000-10-12 | 2000-10-19 |  | 10/26-11/2 | 2000-01-02 | 2000-03-08 | 2001-08-31
Brazos | 2000-05-08 | [9 empty] | 2000-06-22 |  | 2000-09-12 | 2000-09-19 | 2000-10-19 | 2000-10-26 |  | 11/2-11/9 | 2000-01-09 | 2000-03-08 | 2001-08-31
COA | 2000-05-08 | [9 empty] | 2000-06-22 |  | 2000-09-18 | 2000-09-25 | 2000-10-26 | 2000-11-02 |  | 11/9-11/16 | 2000-01-16 | 2000-03-08 | 2001-08-31
CPS | 2000-05-08 | [9 empty] | 2000-06-22 |  | 2000-09-25 | 2000-10-02 | 2000-11-02 | 2000-11-09 |  | 11/16-11/23 | 2000-02-08 | 2000-03-08 | 2001-08-31
LCRA | 2000-05-08 | [9 empty] | 2000-06-22 |  | 2000-10-02 | 2000-10-09 | 2000-11-09 | 2000-11-16 |  | 11/30-12/7 | 2000-02-08 | 2000-03-08 | 2001-08-31
CPL | 2000-03-31 | 2000-04-05 |  | 2000-04-26 | 2000-05-15 | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-09-06 | 2000-09-29 | 2000-10-06 | 2000-10-27 | 2000-11-10 | 2000-11-17 | 11/20-12/20 | 2000-02-28 | 2000-03-28 | 2001-08-31
WTU | 2000-03-31 | 2000-04-05 | The | 2000-04-26 | 2000-05-15 | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-09-06 | 2000-09-29 | 2000-10-06 | 2000-10-27 | 2000-11-10 | 2000-11-17 | 11/20-12/20 | 2000-02-28 | 2000-03-28 | 2001-08-31
SWEPCO | 2000-03-31 | 2000-04-05 | Week | 2000-04-26 | 2000-06-01 | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-09-06 | 2000-09-29 | 2000-10-06 | 2000-10-27 | 2000-11-10 | 2000-11-17 | 11/20-12/20 | 2000-02-28 | 2000-03-28 | 2001-08-31
of
EGS | 2000-03-31 | 2000-04-05 | 2000-04-17 | 2000-04-26 |  | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-10-01 | 2000-10-25 | 2000-11-01 | 2000-11-21 | 2000-12-08 | 2000-12-15 | 1/5-1/26 | 2000-03-26 | 2000-04-26 | 2001-08-31
SPS | 2000-03-31 | 2000-04-05 |  | 2000-04-26 |  | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-10-29 | 2000-11-22 | 2000-11-29 | 2000-12-20 | 2000-01-08 | 2000-01-15 | 1/17-2/7 | 2000-04-07 | 2000-05-07 | 2001-08-31
Sharyland | 2000-03-31 | 2000-04-05 |  | 2000-04-26 |  | 2000-05-01 | 2000-05-01 | 5/3-5/5 | 2000-05-10 | 2000-05-10 | 2000-05-24 | 2000-10-29 | 2000-11-22 | 2000-11-29 | 2000-12-20 | 2000-01-08 | 2000-01-15 | 1/17-2/7 | 2000-04-07 | 2000-05-07 | 2001-08-31
[11 empty] | Issues | Prehearing | Briefing | testimony | Hearing | Post |  | Interim |  |  | Final
[11 empty] | transferred |  | due | due |  | hearing |  | Order |  |  | Order
briefing
Generic Docket (9) | [10 empty] | 2000-05-11: 5/10-5/24; 2000-05-25: To be determined |  | 2000-09-07 |  |  | 2001-08-31
Notes
(1) The Referral Order will include a request to the parties to file a list of preliminary order issues and a list of generic issues that can be addressed by the Commission in a generic docket.
(2) The list of issues will include a list of preliminary order issues and a list of generic issues that can be addressed by the Commission in a generic docket.
(3) If necessary, OPD will issue an order requesting briefing on legal and policy preliminary issues raised by the parties.
(4) If objections are filed, SOAH will establish a procedural schedule to resolve the objections.
(5) The format of the workshop will be determined at a later date.
(6) The Preliminary Order will include a list of generic issues to be transferred to the generic proceeding. OPD will establish a procedural schedule(including prehearing, briefing, and hearing) for the generic proceeding which will remain with the Commission.
If there is no briefing requested for any preliminary order issues, the Preliminary Order will be issued on May 10. Otherwise, briefs will be due on May 10 and the Preliminary Order will be issued on May 24.
(7) Briefs are expected to be due 14 days after the final day of the hearing and reply briefs are expected to be due 7 days after initial briefs.
(8) The last round of the interim orders is expected to be issued around the beginning of May 2001.
(8) Final Orders will be issued on or around 8/31/2001 to allow for the review of the annual reports for 2000(to be filed on 4/1/2001) and adjustments, if any, to final CTC charges, in accordance with 39.261 (c)(1).
(9) There may be multiple interim orders issued in the generic docket. Some issues may need to be addressed by the Commission before the hearing of the first case and other issues can be addressed later.
(10) The possibility exists that not all of the Non-IOUs will file TCOS cases.