## FR_3_2b_1
Schedule H-6.2b
Page 1 of 2
TEXAS-NEW MEXICO POWER COMPANY
TOTAL TEXAS
FOSSIL UNIT PLANNED OUTAGE HISTORY
FOR THE RECONCILIATION PERIOD OF
OCTOBER 1993 TO DECEMBER 1996
SPONSOR: R. M. WILSON
Line | Unit | Scheduled | Scheduled | Scheduled |  | Actual | Actual | Actual |  | Reason
No. |  | Start | End | Length |  | Start | End | Length
| (a) | (b) | (c) | (d) |  | (e) | (f) | (g) |  | (h)
Reconciliation Period
1 | Unit 1 | 1993-10-30 | 1993-11-14 | 15 | Days | 1993-10-30 | 1993-11-14 | 15.8383 | Days | Annual Outage.
2 | Unit 1 | 1994-02-15 | 1994-02-19 | 4.5 | Days | 1994-02-15 | 1994-02-19 | 4.3446 | Days | Maintenance Outage on EID Fan.
3 | Unit 1 | 1994-10-25 | 1994-11-15 | 21 | Days | 1994-10-25 | 1994-11-15 | 20.5237 | Days | Annual Outage
4 | Unit 1 | 1995-07-04 | 1995-07-06 | 2 | Days | 1995-07-04 | 1995-07-06 | 2.2687 | Days | Repair rear FBHE tube leak.
5 | Unit 1 | 1995-09-12 | 1995-09-12 | 0.04 | Days | 1995-09-12 | 1995-09-12 | 0.027917 | Days | Disconnect 1AP.
6 | Unit 1 | 1995-10-28 | 1995-11-06 | 9 | Days | 1995-10-28 | 1995-11-06 | 8.1329 | Days | Annual Outage.
Test Period
7 | Unit 1 | 1996-09-16 | 1996-09-19 | 3.5 | Days | 1996-09-16 | 1996-09-19 | 3.2154 | Days | SA fan expansion joint replacement.
[11 empty] | Page 1 of 2 | Schedule H-6.2b

## FR_3_2b_2
Schedule H-6.2b
Page 2 of 2
TEXAS-NEW MEXICO POWER COMPANY
TOTAL TEXAS
FOSSIL UNIT PLANNED OUTAGE HISTORY
FOR THE TEST YEAR ENDED DECEMBER 31, 1996
SPONSOR: R. M. WILSON
Line | Unit | Scheduled | Scheduled | Scheduled |  | Actual | Actual | Actual |  | Reason
No. |  | Start | End | Length |  | Start | End | Length
| (a) | (b) | (c) | (d) |  | (e) | (f) | (g) |  | (h)
Reconciliation Period
1 | Unit 2 | 1994-03-10 | 1994-04-04 | 25 | Days | 1994-03-10 | 1994-04-04 | 24.5917 | Days | Annual Outage.
2 | Unit 2 | 1994-06-14 | 1994-06-17 | 3.5 | Days | 1994-06-14 | 1994-06-17 | 3.3875 | Days | PA Fan Expansion Joint repairs.
3 | Unit 2 | 1995-03-18 | 1995-04-10 | 23 | Days | 1995-03-18 | 1995-04-10 | 23.0929 | Days | Annual Outage.
4 | Unit 2 | 1995-12-12 | 1995-12-12 | 0.5 | Days | 1995-12-12 | 1995-12-12 | 0.55833 | Days | Reheat Safety valve repairs.
Test Period
5 | Unit 2 | 1996-03-23 | 1996-04-04 | 12.5 | Days | 1996-03-23 | 1996-04-04 | 12.2554 | Days | Annual Outage.
6 | Unit 2 | 1996-10-18 | 1996-11-10 | 23 | Days | 1996-10-18 | 1996-11-10 | 22.8958 | Days | Annual Outage.
[11 empty] | Page 2 of 2 | Schedule H-6.2b