TO:		Interested Parties

FROM:		Therese Harris, Director, Infrastructure Division

DATE:		April 25, 2023

RE:	Project No. 38578 – Energy Efficiency Implementation Project (EEIP) – Request for Comments

As a reminder, updates to the current Technical Reference Manual (TRM) are due by May 1, 2023 and should be sent to Therese Harris, Lark Lee, and Tina Yoder (Therese.Harris@puc.texas.gov, lark.lee@tetratech.com, Tina.Yoder@tetratech.com).

Updates to the TRM are for use in program year 2024 and made to ensure deemed savings estimates are based on the best information available while addressing changing baselines. The draft TRM version 11 update schedule is as follows:

| TRM Process | Date 2023 |
| --- | --- |
| EEIP spring – call for updates | March 28 |
| TRM working group begins | May 9 |
| Electric Utility Marketing Managers of Texas (EUMMOT) meeting | June TBD |
| EUMMOT finalize scope | June 1 |
| TRM working group starts updating TRM | July 11 |
| Submit redlines to EUMMOT | Sept 18 |
| Send redlines to PUCT | Sept 18 |
| EEIP fall | Sept/Oct TBD |
| Feedback from EUMMOT | 14 days from EEIP |
| Feedback from EEIP | 14 days from EEIP |
| Finalize and send to PUCT | Nov 1 |
| PUCT publishes | Nov 8 |
| Final | Dec 16 |

The process to submit a new measure or changes to an existing measure for consideration by the TRM working group and eventual inclusion in the TRM requires a utility sponsor. Please contact a utility in the working group to discuss sponsorship of new measures or changes to existing measures.

- Develop a work paper – that describes the technology, outlines the savings methodology, and quantifies the savings estimates.

  - Note: weather-affected measures should have savings adjusted for TX weather zones and calibrated with performance data from actual Texas installs.

- Obtain a Utility Sponsor – Utility sponsorship is important to ensure:

  - that the measure is offered in utility programs; and

  - utility approval for their collective funds to be used for review of the proposed measure.

- Approval from the TRM working group – a collaborative group of utility representatives, EM&V team (Tetra Tech), and Frontier work together to prioritize measures and overall update activities.

- EM&V review (Tetra Tech) – a thorough review of the savings methodology and savings values. If approved,

- Inclusion in the TRM.

For questions regarding the TRM update process, please contact:

therese.harris@puc.texas.gov, lark.lee@tetratech.com, or tina.yoder@tetratech.com.