## ETI MCPRF 07-11
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
TL5400 | Proposed Merlin Substation to L-17 138kV Transmission Line | Orange County, Texas | Construct new 138kV single pole double circuit transmission line from the new proposed Merlin Substation to the existing line 17 | 2009-09-01 | 2010-10-22 | 2010-10-22 | 3142673 | 4649648 |  |  | 100% | na | 138 | 2.6 | Bundled 666 ACSR | Single Pole Steel & Concrete | na | na | 100 | 2.6 | 31241 | Working on final costs.
TLX001 | L-824 Upgrades | Montgomery County, TX | Replace double circuit h-frame with double circuit single pole. H-frame only has one circuit (L-824). Install new conductor in vacant circuit position and renumber to L-824. Transfer existing conductor to new single pole and renumber to L-87 to allow for cut-in of new Lewis Creek Substation. All work is in existing R/W. | 2010-12-01 |  |  | 4150000 | 4135000 |  |  | 100% | 138 | 230 | 3 | 1272 ACSR | Single Pole Dbl Ckt Concrete | 250 | 3 | na | na | 25.101(c)(5)(B)(i)(ii)(C)(i)(ii) | Working on final Costs.
TLX002 | L-587 Cut-in to New Caney Creek Substation | Montgomery County, TX | Cut-in 138kV L-587 into new SHECO Caney Creek Substation | 2010-04-01 | 2010-05-20 | 2010-05-20 | 1100000 |  |  |  | 100% | 138 |  | 0.1 | 1272 ACSR | Steel | na | na | na | na | 25.101(c)(5)(A)(i)(ii) | SHECO has relocated their Caney Creek Substation to be served from 138kV as part of the L-824 conversion to 230kV.
TLX003 | L-824 bypass of old Caney Creek Substation | Montgomery County, TX | Install one pole in old Caney Creek Substation and bypass old substation | 2010-12-01 | 2011-02-03 | 2011-02-03 | 120000 |  |  |  | 100% | 138 | 230 | na | 2-649 ACAR | Steel | na | na | na | na | 25.101(c)(5)(B)(i)(ii) | Working on final Costs.
TLX004 | Tie existing Lewis Creek 138kV Switchyard to new Lewis Creek Substation | Montgomery County, TX | Install three spans from existing Lewis Creek 138kV switchyard to the New Lewis Creek 230/138kV Substation | 2010-12-01 |  |  | 830000 | 970000 |  |  | 100% | 138 | na | 0.2 | 1272 ACSR | Steel | 100 | 0.2 | na | na | 25.101(c)(5)(A)(i)(ii) | Working on final Costs.
TL1298 | Bentwater L-112 Cut-in | Montgomery County, TX | Cut-in 138kV L-112 to new Bentwater Substation | 2010-04-05 | 2010-04-22 | 2010-04-23 | 461371 |  |  |  | 100% | 138 | na | 0.03 | 1272 ACSR | Concrete | na | na | na | na | 25.101(c)(5)(A)(i)(ii) | Working on final costs.
TLM003 | L-804 Raise Line | Orange County, TX | L-804 Raise line for highway overpass project | 2010-07-05 | 2010-07-09 |  | 300098 |  | 253784 | -15.4% | 100% | 69 | na | 0.01 | 795 ACSR | Concrete | 100 | 0.01 | na | na | 25.101(c)(5)(F)(i)(ii) | Work was completed faster than expected.
TLM004 | L-525 Raise Line | Orange County, TX | L-525 Raise line for highway overpass project | 2010-09-20 | 2010-09-24 |  | 173000 |  | 116559 | -32.6% | 100% | 69 | na | 0.01 | 395 ACAR | Concrete | 80 | 0.01 | na | na | 25.101(c)(5)(F)(i)(ii) | Work was completed fasted than expected.
TLM002 | Cut L-57 into Customer Owned Daisy substation | Liberty County , TX | Tap existing 69 Kv Line 57 and construct single pole double circuit line into new Customer Owned Daisy Substation | 2010-11-30 |  |  | 1375815 | 1375815 |  |  | 100% | 69 | na | 0.45 | 666 ACSR | Steel | 60 | na | 60 | 0.45 | 25.101(c)(5)(A)(i)(ii) | Working on final costs.
TLM005 | Cut L-114 into customer owned Gladys substation | Jefferson County, Texas | Tap existing 69kV L-114 and construct single pole double circuit line into customer owned Gladys Substation | 2011-01-01 | 2011-02-16 | 2011-02-16 | 1053000 |  |  |  | 100% | 69 | na | 0.23 | 666 ACSR | Steel and Concrete | 60 | na | 60 | 0.23 | 25.101(c)(5)(A)(i)(ii) | Working on final costs.
TL9821 | L-886 Rebuild from Tamina Substation to Cedar Hill | Montgomery County, TX | Rebuild 138Kv H-Frame L-886 from Tamina Substation to Cedar Hill | 2011-01-01 |  |  | 4700541 |  |  |  | 75% | 138 | na | 4.45 | 1272 ACSS | Steel | 150 | 4.45 | na | na | 25.101(c)(5)(B)(i)(ii) | This project will be worked in two phases due to outage constraints.
TLZ002 | 230kV line 195 Reconductor for new line rating | Orange & Newton Counties | Reconductor 230 kV Line 195 From McLewis Substation to Hartburg Substation | 2011-02-28 |  |  | 7801731 |  |  |  | 70% | 230 | 230 | 12 | 1461 ACCC & 1272 ACSS | na | 150 | 12 | na | na | 25.101(c)(5)(B)(i)(ii) | This work has been divided into two phases due to outage constraints. Phase I from McLewis to Inland Orange is complete and in service as of may 3, 2011. Phase II is scheduled to begin 10-31-2011. This will continue to show up as 70% complete for the next few months until Phase two begins.
TLV096 | L-96 shield Wire Replacement | Montgomery County, TX | Replace h-frame structure with a single pole for the Navasota bypass switch project and install one pole at Longmire Substation for the OPGW shield iwre replacement. | 2011-08-15 |  |  | 423885 |  |  |  |  | 138 | 138 | 3.3 | OPGW fiber Optic Shield Wire | Concrete | 150 & 100 | 3.3 | na | na | 39382 | This project involves replacing one pole at Navasota for the new bypass switch and one pole at Longmire for the replacement of the shield wire with OPGW fiber Optic. All of this work is in existing R/W.
TLV094 | L-94 Install Pole,GOAB Switch and One Span of conductor | Grimes County, TX | Replace one h-frame structure with a single pole and install GOAB Switch and one span of conductor | 2011-08-15 |  |  | 535844 |  |  |  |  | 138 | 138 | 0.001 | 649 ACAR | Concrete | 150 | na | na | na | 39382 | This project involves replacing on h-frame structure with a single pole and install a GOAB Switch. All of this work is non Entergy owned property.
TLV111 | Install tie line to the City of College Station | Brazos County, TX | Install one pole and two spans of conductor between Entergy's College Station Junction Switch Station and the City of College Station's Substation | 2011-08-15 |  |  | 1452352 |  |  |  |  | na | 138 | 0.003 | 1272 ACSR | Concrete | na | na | na | na | 39382 | This project has changed since the original filing. The city of College Station has decided to install a new bay and a breaker in their substation. Entergy will install one pole and two spans of wire between the two substations.
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.