## MonthlyReportForm_NOV 2017
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number
1012504 | Warda - Giddings Transmission Line Overhaul (T137) | Lee/Fayette | Transmission line overhaul, replace poles, cross arms, X-braces and knee braces. | 2017-05-01 | 2018-06-30 |  |  | 1700000 |  |  | 62 | 69 | 69 | 9.7 | 3x1-4/0 "Penguin" | Wood H-Frames | 100' | 9.7 | 0 | 0 | 25.101 (C)(5)(B)
1010656 | Blumenthal TL Addition (T637) | Gillespie, Kendall, Blanco | Construct a new 138-kV transmission line connecting the new Blumenthal (CTEC) Substation to a tap point on the Kendall - Mountain Top 138-kV transmission line (T-342). | 2015-12-07 | 2018-12-31 |  | $21,536,000 T-line; $3,936,000 Substation; $1,634,000 Tap |  |  |  | 0 | 0 | 138 | 14.4 | 3x1-795 ACSR "Drake" | Poles and H-Frames | 0 | 0 | 100 | 14.4 | 43599
1014204 | Goldthwaite-Lampasas TL Upgrade (T629/T461/T138) | Lampasas, Mills, San Saba | Rebuild the existing 69 kV transmission lines (T461/T138), to 138 kV with new structures and conductor. | 2016-03-01 | 2017-11-28 | 2017-10-31 |  | 63000000 |  |  | 95 | 69 | 138 | 51.52 | Single 795 ACSR "Drake" | Steel H-frames and Poles | Varies | 51.52 | 0 | 0 | 25.101 (C)(5)(B)
1015965 | San Marcos-R Brown - Storm Restoration | Guadalupe | Repair damaged transmission line, T220, due to storm. | 2016-10-10 | 2016-11-04 | 2016-10-14 |  | 645000 | 565558 | -12.32% | 100 | 69 | 69 | 0.25 | 3x1- 4/0 "Penguin" | Primarily Wood H-Frames | CL | 0.25 | 0 | 0 | 25.83 (D)
1014954 | Lon Hill-Nueces Bay TL Maintenance | Nueces | Modify existing transmission line, T437, Lon Hill-Nueces Bay, to meet NESC and LCRA TSC minimum clearances. | 2016-04-18 | 2016-05-05 | 2016-04-29 |  | 394243 |  |  | 100 | 138 | 138 | 17.3 | 3x2- 795 ACSR "Drake" | Steel and Concrete Poles | Varies | 17.3 | 0 | 0 | 25.83 (a)(3)
1015822 | Castillo Substation Addition | Cranue, Upton | Modify existing transmission line, T452, Crane LCRA-North McCamey, and T455, Crane LCRA-North McCamey to accommodate substation construction at the new Castillo Substation. | 2016-03-01 | 2017-09-30 | 2017-09-30 |  | 3934493 |  |  | 100 | 138 | 138 | 23.17 mi | 3x2- 795 ACSR "Drake" | Steel and Concrete Poles | CL & 80' | 23.17 mi | 0 | 0.00 mi | 25.101 (C)(5)(A)
1016048 | Castillo-SP-TX-12B TL Add | Cranue, Upton | Extend a gen-tie line from Castillo Substation to SP-TX-12B to accomodate construction at the new Castillo Substation. | 2016-03-01 | 2017-06-30 | 2017-05-31 |  | 1500000 |  |  | 100 | 138 | 138 | 0.99 | 3x1- 795 ACSR "Drake" | Steel and Concrete Poles | 0 | 0 | 100 | 0.9 | 25.101 (C)(5)(A)
1015884 | Schneeman Draw Sub Addition | Crocket | Modify existing transmission line, T21421, Bakersfield-Big Hill to accommodate substation construction at the new Schneeman Draw Substation. | 2016-04-01 | 2018-04-30 | 2017-08-11 |  | 8660000 |  |  | 100 | 345 | 345 | 0.1 mi | 3x2- 795 ACSR "Drake" | Steel Poles | Varies | 0.1 mi | 0 | 0.00 mi | 25.101 (C)(5)(A)
1015208 | Zorn-Marion 345kV TL (CCN - Docket No. 45601) | Guadalupe | Construct a new 345-kV transmission line to provide a transmission point of interconnection between Central Texas and San Antonio area. | 2018-06-01 | 2019-05-30 |  | T-Line $43.26 - 55.11 M ; Substation $7,905,000 |  |  |  | 0 |  | 345 | 18 - 24 Mi | 3x2-959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7 - 11 mi |  | 10 - 14 mi | 45601
1014910 | TXDOT US 83 Relief Route Rio Grande City-La Grulla(T485) | Starr | Modify existing transmission line, T485, Rio Grande City-La Grulla, to accommodate road expansion by TXDOT. | 2018-06-01 | 2018-06-27 |  |  | 220000 |  |  | 0 | 138 | 138 | 31.66 | 3x1-795 ACSR/AW "Drake/AW" | Steel Poles | Varies | 31.66 | 0 | 0 | 25.101 (C)(5)(B)
1015830 | Bow Wood Substation Addition | McCulloch | Modify existing transmission line, T424, Comanche Switch-Red Creek, and T551, Brown-Twin Buttes to accommodate substation construction at the new Bow Wood Substation. | 2016-06-01 | 2017-05-30 | 2017-05-05 |  | 2945851 | 1977528 | -32.87% | 100 | 345 | 345 | T424: 71.5 mi T551: 88.24 mi | T424: 3x2- 1590 ACSR "Falcon" T551: 3x2- 1926 ACSS/TW "CUMBERLAND" | Primarily Steel Lattice Towers | 160 | T424: 71.5 mi T551: 88.24 mi | 0 | 0 | 25.101 (C)(5)(A)
1014447 | Lockhart - Luling TL Upgrade (T184) | Caldwell | Rebuild the existing transmission line, T184, Luling - Lockhart, to achieve the full MVA capability of the existing conductor. | 2017-04-01 | 2017-12-18 |  |  | 5530000 |  |  | 85 | 138 | 138 | 16.9 | 3x1- 795 ACSR/SD "Condor" & 3x1- 795 ACSR "Drake" | Wood H-Frames, Steel Poles, Steel Lattice Towers | 80- 100' | 16.9 | 0 | 0 | 25.101 (C)(5)(B)
1014352 | Leander - Round Rock TL Addition (CCN) | Williamson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to two load-serving substations | 2019-06-03 | 2019-11-20 |  | T-Line $ 67.8 - 99.6 M ; Substations $ 14.9 - 17.4 M |  |  |  | 0 | 0 | 138 | 11-22 mi | 3x2- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 60-100' | 11-22 mi | 45866
1013275 | Elgin Switch-Sim Gideon-Paige TL OH (T260/T151) | Bastrop, Williamson | Transmission line overhaul, replace poles, cross arms, X-braces, insulators and conductor. | 2016-08-26 | 2017-04-17 | 2017-04-11 |  | 15101304 | 10087591 | -33.2% | 100 | 138 | 138 | 31.32 | 3x1-795 ACSR "Drake" | Wood H-Frames & Concrete Poles | 100' | 31.32 | 0 | 0 | 25.101 (C)(5)(B)
1012407 | Luling-Nixon TL OH (T538) | Caldwell, Gonzales, Guadalupe | Transmission line overhaul, replace poles, cross arms, X-braces, insulators and conductor. | 2016-11-01 | 2017-05-31 | 2017-05-30 |  | 16500000 | 12190050 | -26.12% | 100 | 69 | 138 (continue 69 operate) | 16.00 mi | 3x1-795 ACSR "Drake" | Steel/Concrete Poles | 60' | 16.0 mi | 60' | 16.0mi | 25.101 (C)(5)(B)
1011918 | Altair-Glidden TL OH (T113/T544) | Colorado | Transmission line overhaul, replace poles, cross arms, X-braces, insulators and conductor. | 2016-11-17 | 2017-07-21 | 2017-06-30 |  | 10544507 |  |  | 100 | 69 | 69 | 12.38 mi | 3x1-795 ACSR "Drake" | Concrete and Steel Poles | Blanket | 12.38 | 0 | 0 | 25.101 (C)(5)(B)
1015126 | Rincon - Rockport TL Relocate (T473) | Aransas | Modify existing transmission line, T473, Rincon-Rockport, to accommodate substation construction by AEP. | 2016-12-05 | 2017-03-31 | 2017-03-17 |  | 1057500 | 720000 | -31.91% | 100 | 138 | 138 | 15.1 | 3x1- 795 ACSR/AW "Drake" | Steel poles | Unknown | 15.1 | 0 | 0 | 25.101 (C)(5)(A)
1016186 | Chappell Hill Double Circuit Break-Off Structure - Highway 36 TL OH (T215) | Washington | Replace deteriorated wood poles/structures, add/replace cross-arms, X-braces, knee braces and dampers, overhaul line to meet storm hardening requirements, install OPGW, and modify to accommodate substation construction at the Chappell Hill Substation. | 2016-12-29 | 2017-06-30 | 2017-06-30 |  | 1296000 |  |  | 100 | 138 | 138 | 9.1 | 3x1- 795 kcmil ASCR "Drake", 1-Alcoa 52, 1-3/8" HS | Wood H-frames | 75'-85' | 3.20 mi | 0 | 0.00 mi | 25.101 (C)(5)(B)
1016180 | Brenham North - Chappell Hill Double Circuit Break-Off Structure TL OH (T232) | Washington | Replace and overhaul lattice structures as needed to meet storm hardening requirements, install OPGW, and modify to accommodate substation construction at the Chappell Hill Substation. | 2017-01-04 | 2017-07-09 | 2017-06-30 |  | 5346000 |  |  | 100 | 138 | 138 | 9.1 | 3x1-795 kcmil ASCR "Drake" | Lattice steel, concrete poles | 80'-132' | 5.90 mi | 0 | 0.00 mi | 25.101 (C)(5)(B)
1016221 | Cuero Hydro - Luling TL OH (T542) | DeWitt, Gonzales, Caldwell | Rebuild the 10 miles (phase 1) of existing 69 kV transmission line (T542), to 138 kV capable with new structures, conductor, and OPGW. | 2017-01-15 | 2017-05-31 | 2017-06-02 |  | 9022000 |  |  | 100 | 69 | 69 | 53.9 mi | 3x1- 795 ASCR "Drake" & 3x1- 2/0 ACSR "Quail" | Steel & Concrete Poles | Blanket/Centerline/50'/ 30' | 53.9 mi | 0 | 0 | 25.101 (C)(5)(B)
1016226 | Cuero -Yoakum Gartner Road TL OH (T198) | DeWitt | Replace deteriorated wood poles/structures, add/replace cross-arms, X-braces, knee braces and dampers, and install OPGW. | 2017-01-15 | 2017-05-31 | 2017-05-22 |  | 8201713 | 3364087 | -58.98% | 100 | 138 | 138 | 13.84 | 3x1- 795 ACSR "Drake" | Wood H-Frames & Lattice Towers | 100' Centerline | 13.84 | 0 | 0 | 25.101 (C)(5)(B)
1014216 | Elgin Switch-Gilleland Creek TL OH (T421) | Bastrop, Travis, Williamson | Transmission line overhaul, replace poles, cross arms, X-braces, insulators and conductor. | 2017-01-27 | 2017-05-25 | 2017-06-30 |  | 1857309 |  |  | 100 | 138 | 138 | 12.9 mi | 3x1- 1433.6 ACSS/TW "Merrimack" | Wood H-Frames & Steel Single Poles | 100' | 12.9 mi | 0 | 0 | 25.101 (C)(5)(B)
1016205 | Shadow Glen Circuit Breaker Addition (T574) | Travis | Replace approximately 0.5 miles of OPGW outside of Harris Branch Substation | 2017-03-14 | 2017-08-30 | 2017-08-11 |  | 1788544 |  |  | 100 | 138 | 138 | 7.76 | 3x1- 795 ACSR "Drake" | Concrete Poles and a Lattice Tower | 100' | 7.76 | 0 | 0 | 25.101 (C)(5)(B)
1016215 | Georgetown S Circuit Breaker Add (T223) | Williamson | Modify existing transmission line, T223, Georgetown East-Round Rock (TXU), to accommodate substation construction at the Georgetown South Substation. | 2017-03-30 | 2017-06-15 | 2017-06-15 |  | 1374605 | 937033 | -31.83% | 100 | 138 | 138 | 0.1 | 3x1- 795 ACSR "Drake" | Steel Poles | Varies | 0.1 | 0 | 0 | 25.101 (C)(5)(A)
1015455 | Upton Circuit Breaker Addition (T441) | Upton | Modify existing transmission line, T441, Benedum-Crane LCRA, to accommodate substation construction at the Upton Substation. | 2017-03-10 | 2017-08-04 | 2017-08-14 |  | 1241839 |  |  | 100 | 138 | 138 | 26.99 | 3x1- 1233.6 ACSS/TW "Yukon" | Steel Poles | 80' CL | 26.99 | 80' CL | 0.08 | 25.101 (C)(5)(A)
1016210 | Cushman - Seguin TL Storm Hardening (T309) | Guadalupe | Replace twenty (20) transmission line structures on T309 to meet NESC storm hardening requirements. | 2017-03-01 | 2017-06-30 | 2017-06-28 |  | 2736729 |  |  | 100 | 138 | 138 | 1.96 mi | 3x1- 795 ACSR "Drake" & 3x1- 959.6 ACSS/TW "Suwannee" | Steel Poles | In city ROW | 1.96 mi | 0 | 0 | 25.101 (C)(5)(B)
1016541 | Pharr North - Weslaco Sw TL Reloc (T479) | Hidalgo | Relocate tranmission facilities on T479 to accommodate AEP's expansion of the Pharr North substation. | 2017-03-15 | 2017-06-30 | 2017-04-28 |  | 608908 | 590423 | -3.036% | 100 | 138 | 138 | 10.45 | 3x1-795 ACSS/HS "Drake" | Steel Poles | CL | 10.45 mi | 60' | 0.04 | 25.101 (C)(5)(A)
1016207 | Smithville - Winchester (T175) | Bastrop, Fayette, Lee | Transmission line overhaul, replace poles, cross arms, X-braces, insulators and conductor. | 2017-08-01 | 2018-03-30 |  |  | 10677730 |  |  | 42 | 138 | 138 | 14.56 | 3x1- 795 ACSR "Drake" | Steel and Concrete Poles | Varies | 14.56 | 0 | 0 | 25.101 (C)(5)(B)
1017382 | FPP - Lytton Springs Storm Hardening (T255) | Bastrop, Caldwell, Fayette | Modify a number of existing lattice tower structures on T255 to meet storm hardening requirements. | 2017-04-03 | 2017-06-30 | 2017-06-30 |  | 1088000 |  |  | 100 | 345 | 345 | 61.12 | 3x2-715.5 ACSR "Redwing" | Steel Lattice | 100' | 61.12 | 0 | 0 | 25.83(a)(3)
1016195 | Sim Gideon - Winchester (T615) | Bastrop, Fayette, Lee | Replace deteriorated wood poles/structures, add/replace cross-arms, X-braces, knee braces and dampers | 2017-05-15 | 2017-08-17 | 2017-08-17 |  | 3908000 |  |  | 100 | 138 | 138 | 14.85 | 3x2- 336 ACSR "Linnet" & 3x1- 795 ACSR "Drake" | Wood H-Frames and Concrete Poles | 100' | 14.85 | 0 | 0 | 25.101 (C)(5)(B)
1005486 | Sherwood Shores CB Add (T187) | Burnet | Modify existing transmission line, T187, Ferguson-Coronado, to accommodate substation construction at the Sherwood Shores Substation. | 2017-07-10 | 2018-02-12 |  |  | 528355 |  |  | 56 | 138 | 138 | 21.54 | 3x1- 795 ACSR "Drake" | Steel H-frames and Poles | Varies | 21.54 | 80 | N/A | 25.101 (C)(5)(A)
1016176 | Arco Tap Circuit Breaker Addition (T442) | Crane | Modify existing transmission line, T442, Crane LCRA-Pleasant Farms, to accommodate substation construction at the new Arco Tap Substation. | 2017-05-03 | 2018-04-10 |  |  | 1175206 |  |  | 49 | 138 | 138 | 24.25 | 3x1- 1233.6 ACSS/TW "Yukon" | Steel and Concrete Poles | Varies | 24.25 | 50 | N/A | 25.101 (C)(5)(A)
1017957 | Buchanan - Pittsburgh – Stucture Replacement (T267) | Llano | Replace one damaged transmission line structure on the T267, Buchananc-Pitsburg transmission line. | 2017-06-26 | 2017-07-14 | 2017-07-14 |  | 171000 |  |  | 100 | 69 | 69 | 14.49 mi | 3x1- 4/0 "Penguin" | Steel Poles | 100 | 14.49 | 0 | 0 | 25.101 (C)(5)(B)
1016539 | Flood Remedation Phase 1 (T495) | Travis | On T495 remove (structure #112) concrete pole and replace with two concrete poles. | 2017-07-05 | 2017-10-28 | 2017-10-19 |  | 387000 |  |  | 100 | 138 | 138 | 8.21 mi | 3x1-795 ACSR "Drake" | Concrete Poles, Steel Poles and a Lattice Tower | 100' | 8.21 mi | 0 | 0.00 mi | 25.101(C)(5)(B)
1015477 | Henne-McCarty Lane TL Upg (T233) | Comal, Hayes | Rebuild the existing 138kV transmission line, T233, with new structures and conductor. | 2017-08-01 | 2017-12-29 |  |  | 7353155 |  |  | 30 | 138 | 138 | 6.6 mi | 3x1- 959.6 ACSS/TW "Suwannee" | Concrete Poles, Steel Poles and a Lattice Tower | 100' | 6.6 mi | 0 | 0.00 mi | 25.101(C)(5)(B)
1016189 | Fayette Power Project 345kV BUS Tie (CCN - Docket No. 47218) | Fayette | Construct a new single circuit 345-kilovolt (kV) transmission line to increase the bus capacity between the existing Fayette Power Project Yard #1 and Yard #2 substations | 2018-03-01 | 2018-05-31 |  | T-Line $1.1 M; Substations $3.6 M |  |  |  | 0 | 0 | 345 | 0.26mi | 3x2- 1590 Kcmil ASCR Falcon | Steel Poles | 0 | 0 | 100 | 0.26mi | 47218
1015961 | Lincoln Substation Addition (T155) | Lee | Modify existing transmission line, T155, Giddings-Lexington, to accommodate substation construction at the new Lincoln Substation. | 2017-08-01 | 2017-10-10 | 2017-10-24 |  | 1181500 |  |  | 100 | 138 | 138 | 18.24 mi | 3x1-795 ACSR "Drake" | Steel Lattice, Steel Poles, and Wood H-Frames | Varies | 18.24 mi | 80 | 0.4 mi | 25.101 (C)(5)(A)
1016925 | Altair-Garwood T546 TL Upg (PHII) | Colorado | Structure replacement & addition to meet NESC required clearances for safe distance and system reliability. (PHII - GOAB Switch Install) | 2017-09-18 | 2017-11-24 |  |  | 746316 |  |  | 52 | 69 | 69 | 9.27 mi | Raven ASCR & 1/0 & Single | Wood Hframes, Single Pole Wood DE | 10' Centerline, 60' Centerline, & Blanket Easements | 9.27 | NA | N/A | 25.101(C)(5)(B)
1017377 | Flatonia-Waelder TL OH (T513) | Fayette, Gonzales | Tear-down/rebuild. Upgrade to 138-kV capable with OPGW shield wire | 2017-11-01 | 2017-06-30 |  |  | 8802782 |  |  | 0 | 69 | 69 | 11.79 mi | 3x1-795 ACSR "Drake" | Concrete Poles & Steel Poles | Centerline | 11.79 mi | NA | N/A | 25.101(C)(5)(B)
1018589 | Clear Springs-Hutto Bolt Tightening (T510) | Guadalupe, Caldwell, Hays, Travis, Williamson | Climb and inspect all lattice towers, retighten bolts, and install locking mechanisms to prevent bolts from becoming loose or falling out. | 2017-09-11 | 2018-05-31 |  |  | $1, 200,000 |  |  | 15 | 345 | 345 | 85.19 | 3x2-959.6 ACSS/TW "Suwannee" | Steel Lattice, and Steel Poles | 100'-200' | 85.19 | NA | NA | 25.83(a)(3)
1018730 | Fulton-Rockport 69kV TL Restoration (T474) | Aransas | Emergency storm repairs to replace failed hardware. | 2017-08-31 | 2017-09-13 | 2017-09-06 |  | 1000000 |  |  | 100 | 69 | 69 | 7.35 | 3x1-795 ACSR "Drake" | Steel Poles | Varies | 7.35 | NA | NA | 25.101(C)(3)
1017388 | Harwood-Waelder TL OH (T145) | Gonzales | Tear-down/rebuild. Upgrade to 138-kV capable with OPGW shield wire | 2017-12-08 | 2018-05-31 |  |  | 8884835 |  |  | 0 | 69 | 69 | 12.39 | 3x1-795 ACSR "Drake" | Concrete Poles & Steel Poles | Centerline | 12.39 | NA | N/A | 25.101(C)(5)(B)
1017338 | Austrop-Bastrop City-Sim Gideon Storm Hardening (T171/T172/T231) | Bastrop, Travis | Replace 24 double-circuit lattice tower strutures with 21 steel tower pole structures and 3 lattice deadend towers, Install OPGW | 2017-12-08 | 2018-05-31 |  |  | 4795575 |  |  | 0 | 138 | 138 | 34.42 | 3x1-795 ACSR "Drake" | Steel Lattice | 125' | 34.42 | NA | N/A | 25.101(C)(5)(B)
1017374 | Fayetteville-FPP 138kV TL OH (T253) | Fayette | Tear-down/rebuild. Upgrade to 138-kV capable with OPGW shield wire | 2018-01-09 | 2018-05-01 |  |  | 5670000 |  |  | 0% | 69 | 138 | 6.9 mi | 3x1- 959.6 ACSS/TW "Suwannee" | Concrete tangents with steel deadends | 85', 95', 125' | 6.9 mi | NA | NA | 25.101(C)(5)(B)
1017381 | FPP - Fayetteville (T210/T211) | Fayette | Storm Hardening of lattice towers | 2017-12-15 | 2017-02-27 |  |  | 349235 |  |  | 0% | 345 | 345 | 8.89 mi | 3x1- 795 ACSR "Drake" | Steel Lattice | 100' Centerline, 200' , Triangular, and T-Shaped Easements | 8.89 mi | NA | NA | 25.101(C)(5)(B)
1017998 | Hamilton Road - Uvalde Fiber Addition (T570), (T624) & (T464) | Val Verde, Kinney, Uvalde | Replace 25 structures to support new OPGW | 2018-01-15 | 2018-08-31 |  |  | 9391760 |  |  | 0% | 138 | 138 | 70.6 mi | 3x1-ACSS "Drake" | Steel Poles | Varies | 70.6 mi | NA | NA | 25.101 (C)(5)(B)
1017838 | Kendall - Fredericksburg TL Fiber Build Out (T120) | Kendall, Gillespie | Replace static arm on 70 H-frame structures, install 1 new steel deadend pole, and install 2 new guyed wood h-frames to support new OPGW | 2017-12-05 | 2018-03-26 |  |  | 2577512.25 |  |  | 0% | 138 | 138 | 20.55 mi | 3x1- 795 ACSR "Drake" | Wood Hframes, Single Pole Wood DE | Centerline | 20.55 mi | NA | NA | 25.101 (C)(5)(B)
1017449 | Sim Gideon - Winchester (T152/T175) | Bastrop, Fayette, Lee | Replace deteriorated OPGW suspension shoes and dampers from structure 60 to Winchester substation. | 2017-12-01 | 2018-02-01 |  |  | 835559 |  |  | 0% | 138 | 138 | 20.60 mi | 3x1- 795 ACSR "Drake" | Steel Lattice | Varies | 14.56 mi | NA | NA | 25.101 (C)(5)(B)
1017409 | Tippett Circuit Breaker Addittion (T552)(T674)(T666) | Pecos | Modify existing transmission line, T552, North McCamey-West Yates Switch, to accommodate construction at Tippett Substation. | 2018-01-26 | 2018-07-30 |  |  | 2714234 |  |  | 0% | 138 | 138 | 10.76 mi | 3x2- 795 ACSR "Drake" | Concrete & Steel Poles | Centerline | 10.76 mi | NA | NA | 25.101 (C)(5)(B)
1017392 | Lon Hill – Nueces Bay TL Upg (T437) | Nueces | Replace 22 structures to increase clearances on transmission line spans in order to meet LCRA TSC minimum design clearances | 2018-02-09 | 2018-05-31 |  |  | 4379646 |  |  | 0% | 138 | 138 | 17.3 mi | 3x2- 795 ACSR "Drake" | Concrete & Steel Poles, Steel DE H-Frame | Varies | 17.3 mi | NA | NA | 25.101 (C)(5)(B)
1015487 | Kerrville Stadium-Harper Rd TL Upg (T144) | Kerr | Rebuild the existing 138kV transmission line, T144, with new structures and conductor. | 2019-01-10 | 2019-03-07 |  |  | 3742315 |  |  | 0% | 138 | 138 | 1.5 mi | 3x2- 795 ACSR "Drake" | Steel Poles | Varies | 1.5 mi | NA | NA | 25.101 (C)(5)(B)
1015116 | Henne-Comal TL Upg (T235) | Comal | Rebuild the existing 138kV transmission line, T235, with new structures and conductor. | 2018-01-07 | 2018-05-24 |  |  | 9574929 |  |  | 0% | 138 | 138 | 7.51 mi | 3x1- 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7.51 | NA | NA | 25.101 (C)(5)(B)
1017347 | Mendoza-Colton-Elroy (T397) | Caldwell, Travis | Add circuit breakers at Colton Substation. Add OPGW to T397 Mendoza - Colton - Elroy. Replace structures that are currently not capable of supporting OPGW. | 2018-02-05 | 2018-05-31 |  |  | 8900000 |  |  | 0% | 138 | 138 | 12.9 mi | 3x1- 795 ACSR "Drake" | Concrete Poles, Steel Poles and Wood H-frames | Varies | 12.9 mi | NA | NA | 25.101 (C)(5)(B)
1017387 | Harwood-Luling Double Circuit TL OH | Caldwell, Gonzales | Replace 45 double-circuit lattice tower structures with double circuit steel poles and add OPGW on T145, Luling-Waelder, and T173, Luling-Gonzales transmission lines. | 2018-02-26 | 2018-06-04 |  |  | 2015000 |  |  | 0% | 138 | 138 | 12.9 mi | 3x2- 795 ACSR "Drake" | Concrete Poles, Steel Poles and Wood H-frames | Varies | 19.4492 | NA | NA | 25.101 (C)(5)(B)
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.