## ETT00315
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
ETT- 072A 39116 | Barney Davis to Naval Base Substation 138-kV Transmission Line | Nueces | Construct new 138-kV transmission line (overhead/underground) from Barney Davis to Naval Base Substations | 2016-10-06 | 2017-08-31 |  | 43955000 | 43955000 |  |  | 90 |  | 138 | 5.2 (ov hd) 2.5 (under grd) | 959.6 ACSS/TW/AW (ov hd) 5000kcmil enameled copper cable (undergrd) | Typical Single Steel Pole w/ few h-type around t-line crossings (ovhd) concrete duct (under grd) |  |  | Typical 100 (ovhd) 50 (undergrd) | 5.2 (ovhd) 2.5 (undergrd) | 42467 | CCN approval on 05/28/2015
ETT-127 ET15093006 | Santa Cruz 138-kV Collector Station | Nueces | Install Metering, RTU, SDR and DME equipmnet | 2016-02-22 | 2016-11-01 |  |  | 614830 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
ETT - 129 P15093004 | Barney Davis to Nelson Sharpe 138-kV Line | Nueces | Install second circuit on the existing line for gen tie | 2016-04-29 | 2016-11-01 |  |  | 3180000 |  |  | 0 | 138 |  | 6.5 | Bundled (2) 954 ACSR with OPGW | Single Steel Pole | 100 | 6.25 mi | 100 | 0.01 | 16 TAC 25.101 (c)(5)(C) | Consent obtained
ETT-123 P14075001 | Horse Creek Wind Farm/Panadero Collector Station | Haskell | Install RTU, SDR and DME equipment at Pandero Collector Station | 2016-08-02 | 2016-10-31 | 2016-09-19 |  | 1111489 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
ETT-123 P14075002 | Clear Crossing to Edith Clark: Panadero Tap Line | Haskell | Temporary tap connection for generator transmission line from Panadero Collector Station | 2016-08-02 | 2016-09-30 | 2016-09-19 |  | 194640 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.101 (c)(5)(A) | Temprary tap will be within the confines of AEP purchased property
ETT-125 ET1503701 | East Pecos Solar Interconnection | Pecos | Station work inside LCRA Bakersfield Station to terminate new solar generation. Generator constructed the transmission line being terminated. | 2016-08-20 | 2016-11-11 | 2016-11-18 |  | 4050000 |  |  | 98 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | ETT - LCRA TSC CREZ Agreement
ETT-142 P15153001 | Falfurrias 69-kV SVC | Brooks | Replace DSTATCOM with Static VAR Compensator (SVC) and install bus tie to SVC | 2016-11-29 | 2019-05-31 |  |  | 19066707 |  |  | 5 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Corrected Voltage
ETT-141 ETT800213 | BM Davis Station Upgrades | Nueces | Replace five circuit breakers and replace differential relays | 2016-11-29 | 2018-05-04 |  |  | 3166162 |  |  | 65 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | New Property Acquired for DICM
ETT-123 P14075004 | Smoky Hill Substation | Haskell | Build new 345-kV substation | 2017-01-05 | 2017-08-01 | 2017-07-18 |  | 14137607 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
ETT-123 P14075006 | Clear Crossing to Edith Clark: Cut In to Smoky Hill Sub. | Haskell | Permanent cut in to Smoky Hill | 2017-01-05 | 2017-08-01 | 2017-09-20 |  | 1272294 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.101 (c)(5)(A) | Construction within the Confines of AEP Purchased Property
ETT-128 P15131001 | Salvation Collector Station | Haskell | Install RTU, SDR equipment at Salvation Collector Station | 2017-03-01 | 2017-08-01 | 2017-08-30 |  | 360742 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
ETT-123 P15131002 | Add Terminal to Smoky Hill | Haskell | Add new 345-kV line terminal for collector station | 2017-01-05 | 2017-08-01 | 2017-08-30 |  | 1661628 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
ETT-140 ETT800211 | Oklaunion Substation | Wilbarger | Replace 138-kV and 345-kV breakers and switches | 2017-10-06 | 2017-12-31 |  |  | 10440000 |  |  |  | 345 / 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42598598 | SW Vernon Connect, Oklaunion | Wilbarger | Oklaunion: Add wave trap. Connection to SW Vernon. | 2018-01-22 | 2019-01-31 |  |  | 1200000 |  |  |  | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42681304 | Yelllow Jacket Station | Menard/Menard | Replace relays and Carrier Equipment to match Temporary Cactus Flats Tap and future Treadwell station relays | 2108-03-20 | 2018-05-05 |  |  | 506892 |  |  |  | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-143 P16132001 | Waymark Solar Interconnection: LCRA TSC Bakersfield Station | Pecos | LCRA TSC Bakersfield Station: Install 345-kV Station Terminal to serve new Waymark Solar Interconnection. | 2018-02-01 | 2018-06-30 |  | 2870000 | 2810000 |  |  | 0 |  | 345 | [7 empty] | 47603 | PUCT Docket 47603 Approved on 12/27/2017
ETT-143 P16132002 | Waymark Solar Interconnection: Waymark IPP-Owned Station | Pecos | Waymark Station: Install RTU, SDR, and DME in customer owned station. Install 345-kV EPS Metering. | 2018-04-09 | 2018-06-30 |  | 672000 | 650000 |  |  | 0 |  | 345 | [7 empty] | 47603 | PUCT Docket 47603 Approved on 12/27/2017
ETT-143 P16132003 | Waymark Solar Interconnection: New T-Line Construction | Pecos | Construct new 345-kV transmission line from Bakersfield to the point of interconnection at Waymark. 1.94 miles of this transmission line will be build double-circuit capable | 2018-02-05 | 2018-06-30 |  | 7261000 | 6865000 |  |  | 0 |  | 345 | 3.94 | 2-bundled Cardinal 954 KCM 54/7 ACSR | Steel Mono Poles |  |  | 150 | 3.94 | 47603 | PUCT Docket 47603 Approved on 12/27/2017
ET1600803 | Maplewood Interconnection: Add 2nd Circuit to serve Red Barn IPP-Owned Station | Pecos | Add new 345-kV transmission line circuit from the LCRA TSC Bakersfield Station to the point of interconnection at Red Barn | 2018-04-09 | 2019-12-20 |  | 2401000 | 2270000 |  |  | 0 |  | 345 | 1.94 | 2-bundled Cardinal 954 KCM 54/7 ACSR |  | 150 | 1.94 |  |  | 47603 | PUCT Docket 47603 Approved on 12/27/2017
ETT-144 P16141001 | Live Oak Interconnect | Schleicher | Install one 345-kV terminal at LCRA TSC's Big Hill 345-kV Station to provide a permenant interconnection for the Live Oak Wind Project, LLC wind farm | 2018-03-18 | 2018-09-20 |  |  | 5333559 |  |  | 2 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-130 ETT2015126 | Rio Bravo 1 Wind Generator Temp Connection | Starr | Construct new 345-KV POI temporary tap on the Cenizo-Del Sol 345-kV transmission line for Long Road Energy (Rio Bravo 1) | 2018-04-18 | 2018-09-30 |  |  | 1400000 |  |  | 10 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Utilizing Existing Easement
ETT-149 P17102001 | Ajo-Zorillo 345-kV Line Tap | Kenedy | Create Hard Tap in Ajo-Zorillo 345-kV line to interconnect Stella Wind Farm transmission line. | 2018-09-05 | 2018-09-23 |  |  | 1381571 |  |  | 0 | 345 |  | 0.1 |  | Steel Mono Pole | 150 | 0.1 |  |  | 16 TAC 25.101 (c)(5)(A) | Written consent acquired from landowner with the right to construct.
ETT-149 P17102002 | Ajo Station: Remote-End Work | Kenedy | Install new relay equipment to create a three-terminal line protection scheme. Remove and warehouse existing old generation L90/311L relay panels. | 2048-07-05 | 2018-09-23 |  |  | 551342 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property Owned
ETT-149 P17102003 | Zorillo Station: Remote-End Work | Kenedy | Install new relay equipment to create a three-terminal line protection scheme. Remove and warehouse existing old generation L90/311L relay panels. | 2018-07-05 | 2018-09-23 |  |  | 606865 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property Owned
ETT-149 P17102004 | Stella Collector Station: Metering | Kenedy | Install metering, SDR, ME and RTU at the IPP collector station | 2018-07-05 | 2018-09-23 |  |  | 821224 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property owned by generator. Written agreement for equipment installation acquired.
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.