## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
TPSU.14.005775 | Tall City to Glass 138 kV New T-Line | Martin and Midland Counties | Construct new 138 kV Line from Tall City to Glass | 2018-07-23 |  |  | 14602259 | 13142033.1 |  |  | 10 | na | 138 | 13.06 | 959.6 kcmil Aluminum Conductor Steel Supported (ACSS/TW) "Suwannee"; Single Circuit | Concrete or Steel Monopole | na | na | 100 | 13.06 | 45308
TPSU.14.005844 | Sale Ranch to Natural Dam 138 kV Transmission Line | Howard and Martin Counties | Construct new 138-kV line from Sale Ranch to Natural Dam | 2018-07-23 |  |  | 17497000 | 15747300 |  |  | 10 | na | 138 | 16.98 | 959.6 kcmil Aluminum Conductor Steel Supported (ACSS/TW) "Suwannee"; Single Circuit | Concrete or Steel Monopole | na | na | 100 | 16.98 | 45397
TPSU.15.006048 | Phase 1 Upgrade Ogallala - Tule Canyon T-Line | Briscoe and Swisher Counties | SU will install a second circuit to the existing 345kv T-line to accommodate the Phase 1 upgrade of the existing CREZ line from OGA-TCN. | 2017-09-01 | 2018-03-09 | 2018-03-09 | 16900000 | 14044210 | 14044159.91 | -0.00035666 | 100 | 345 | na | 46.6 | 1926.9 kcmil Aluminum Conductor Steel Reinforced (ACSR/TW) "Cumberland". | na | 175 | 46.6 | na | na | 45622
TPSU.15.006117 | Telephone Rd Upgrade Transformer | Midland County | Replace existing 138/25 kV transformer with new transformer, upgrade distribution 25 kV feeders. | 2016-11-04 | 2017-08-24 | 2017-08-24 |  | 3906751 | 6526495.44 | 67.0569 | 100 | 345, 138, 25 | na | na | na | na | na | na | na | na | 25.101(c)(2)
TPSU.16.006132 | Salt Mine Sub Upgrade | Mitchell County | Upgrade communication to fiber and update relays. | 2017-10-30 | 2018-02-13 | 2018-02-13 |  | 1136247 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(2) | Awaiting Final Cost
TPSU.15.006003 | Bulldog Sub Rebuild | Howard County | New 6 breaker ring bus with 5 breakers installed initially | 2017-06-19 | 2018-02-13 | 2018-02-13 |  | 8663469 | 9619664.12 | 11.0371 | 100 | 138, 25 | na | na | na | na | na | na | na | na | 25.101(c)(2)
TPSU.15.006023 | Alibates Synchronous Condenser | Carson County | Install synchronous condenser | 2017-01-09 | 2018-02-15 | 2018-02-15 |  | 31849680 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.101(c)(2) | Awaiting Final Cost
TPSU.15.006024 | TCN Bay Addn/Line for Synchronous Condenser | Briscoe County | Extend bus, install multi-bus A-frame, add breakers | 2017-06-08 | 2018-03-09 | 2018-03-09 |  | 7246453 | 5306824.72 | -26.7666 | 100 | 345 | na | na | na | na | na | na | na | na | 25.101(c)(2)
TPSU.15.006025 | TCN Synchronous Condenser | Briscoe County | Install synchronous condenser | 2017-01-09 | 2018-04-05 | 2018-04-05 |  | 31840823 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.101(c)(2) | Awaiting Final Cost
TPSU.14.005659 | Stiles to Coates T-Line | Reagan County | New 138kV transmission line from Stiles Station to new Coates Station | TBD |  |  | 9682000 |  |  |  | 0 | na | 138 | 8 | 959.6 kcmil Aluminum Conductor Steel Supported (ACSS/TW) "Suwannee"; Single Circuit | Concrete or Steel Monopole | na | na | 100 | 8 | 46726 | The Final Order approving the CCN for this project was issued prior to the Sharyland/Oncor Asset Transaction. The project is not under construction and there are no specific plans to commence construction. Sharyland and Oncor will need to coordinate the timing for constructing both the Coates Substation (ONCOR) and Stiles to Coates T-Line (SU).
TPSU.15.006116 | Vealmoor Second Autotransformer | Howard County | Install new 3-Phase Autotransformer | 2017-11-27 |  |  |  | 16958405 |  |  | 70 | 345, 138 | na | na | na | na | na | na | na | na | 25.101(c)(2)
TPSU.17.006392 | Stillman Substation and Interconnect Line | Cameron County | New 138 kV substation and transmission line connection with Palmito substation | 2017-11-13 |  |  |  | 12918462 |  |  | 79 | 138 | na | 0.43 | 954 kcmil All Aluminum Conductor (AAC) "Magnolia"; Single Circuit | Concrete or Steel Monopole | 150 | 0.5 | na | na | 25.101(c)(2) 25.101(c)(5)(A)
TPSU.16.006143 | Palmito 2nd Autotransformer | Cameron County | Install new 3-Phase Autotransformer | 2017-11-14 |  |  |  | 8814750 |  |  | 94 | 345, 138 | na | na | na | na | na | na | na | na | 25.101(c)(2)
TPSU.17.006393 | Driver Third Transformer | Midland County | Install additional 138/25 kV transformer to the Driver Substation | 2018-02-05 |  |  |  | 2875000 |  |  | 96 | 138, 25 | na | na | na | na | na | na | na | na | 25.101(c)(2)
TPSU.17.006397 | Farmland Switch Yard | Lynn County | New switchyard with two bay positions and an extension of the north end of the dead-ended SPS line. | 2018-03-12 |  |  |  | 10276006 |  |  | 55 | 345 | 345 | na | na | Steel Monopole | na | na | na | na | 25.101(c)(2) 25.101(c)(5)(A)
TPSU.18.006402 | Taylor Substation Upgrade | Cameron County | Upgrade line protection relays per AEP request | 2018-06-18 |  |  |  | 300000 |  |  | 60 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
TPSU.18.006401 | Bentsen Substation Upgrade | Cameron County | Upgrade line protection relays per AEP request | 2018-06-20 |  |  |  | 300000 |  |  | 60 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
TPSU.18.006419 | Canal Rd. Cap bank | Upton County | Expand the two existing cap banks from the installed 13250 KVAR to their ultimate 26500 KVAR | 2018-05-31 | 2018-07-26 | 2018-07-26 |  | 500000 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B) | Awaiting Final Cost
TPSU.18.006423 | Railroad Substation Upgrade | Hidalgo County | Replace aging transformer and upgrade the protection and control infrastructure | 2018-09-04 |  |  |  | 4000000 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(2)

## OGA-TCN Cost Analysis
Project No.: | TPSU.15.006048
Project Name: | Phase 1 Upgrade Ogallala - Tule Canyon T-Line
PUC Docket No.: | 45622
2017-09-01
| Estimated Cost Included in Final Order | Estimated Cost at Construction Start | Final Cost
Transmission Facilities
ROW & Land Acquisition | 349354.0052 | 57000 | 63930.71
Engineering & Design - Utility | 0 | 0 | 0
Engineering & Design - Contract | 524031.0078 | 191413.06 | 224913.28
Material & Equipment Procurement | 8231653.7468 | 6859632.91 | 6507479.11
Construction of Facilities - Utility | 0 | 0 | 0
Construction of Facilities - Contract | 7631201.5504 | 6895898.51 | 7190293.91
Other | 163759.6899 | 40265.52 | 57542.9
TOTAL | 16900000 | 14044210 | 14044159.91
| 0 | 0 | 0
| 16900000 | 14044210 | 14044159.91
Cost Variance |  | -16.9% | -0.0003567%
Cost Variance Discussion:
n/a

## Cost Analysis - TPSU.15.006050 (hidden)
Project No.: | TPSU.15.006050
Project Name: | Bay Additions for Windmill Phase 1 Upgrade
PUC Docket No.: | 45622
2016-10-13
| Estimated Cost Included in Final Order | Estimated Cost at Construction Start | Final Cost
Substation
ROW & Land Acquisition | 0 | 0 | 0
Route Development / CCN Acquisition | 0 | 0 | 0
Engineering & Design - Utility | 0 | 0 | 0
Engineering & Design - Contract | 201162.33 | 201162.33 | 236633.43
Material & Equipment Procurement | 1485537.96 | 1485537.96 | 1022384.35
Construction of Facilities - Utility | 25612.72 | 25612.72 | 0
Construction of Facilities - Contract | 1023655.18 | 1023655.18 | 1113633.66
Other | 64031.81 | 64031.81 | 84879.76
TOTAL | 2800000 | 2800000 | 2457531.2
| 0 | 0 | 0
| 2800000 | 2800000 | 2457531.2
Cost Variance |  | 0% | -12.23%
Cost Analysis - Material costs were lower than projected which resulted in the -12% variance between the project estimate and the final project cost.