## MCPR April 2019
MCPR Row Number | Project Manager | Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number
2 | Joshua Cobb | 1010656 | Blumenthal TL Addition (T637) | Gillespie, Kendall, Blanco | Construct a new 138-kV transmission line connecting the new Blumenthal (CTEC) Substation to a tap point on the Kendall - Mountain Top 138-kV transmission line (T342). | 2017-10-02 08:00 | 2018-05-18 | 2018-05-18 | $21,536,000 T-line; $3,936,000 Substation; $1,634,000 Tap | $20,438,000 T-line; $3,742,000 Substation; $1,836,000 Tap |  |  | 100 | 0 | 138 | 14.4 | 3x1-795 ACSR "Drake" | Poles & H-Frames | 0 | 0 | 100' | 14.4 | 43599
3 | Vicki O'Connor | 1014204 | Goldthwaite-Lampasas TL Upgrade (T629/T461/T138) | Lampasas, Mills, San Saba | Rebuild the existing 69-kV transmission lines (T461/T138) to 138-kV with new structures and conductor. | 2016-03-01 | 2017-10-31 | 2017-10-31 | 63000000 | 37517739.17 |  |  | 100 | 69 | 138 | 51.52 | Single 795 ACSR "Drake" | Steel H-Frames & Poles | Varies | 51.52 | n/a | n/a | 25.101 (C)(5)(B)
4 | Martin Lindig | 1015208 | Zorn-Marion 345kV TL Addition (CCN - Docket No. 45601) | Guadalupe | Construct a new 345-kV transmission line to provide a transmission point of interconnection between Central Texas and San Antonio area. | 2018-06-01 08:00 | 2019-05-24 |  | T-Line $43.26 - 55.11 M ; Substation $7,905,000 |  |  |  | 90 | 0 | 345 | 18-24 mi | 3x2-959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7-11 mi |  | 10 - 14 mi | 45601
5 | Josh Bollich | 1014910 | TXDOT US 83 Relief Route Rio Grande City-La Grulla (T485) | Starr | Modify existing transmission line (T485), Rio Grande City-La Grulla, to accommodate road expansion by TXDOT. | 2018-11-09 | 2018-11-30 | 2018-11-30 | 220000 | 317464 |  |  | 100 | 138 | 138 | 31.66 | 3x1-795 ACSR/AW "Drake/AW" | Steel Poles | Varies | 31.66 | n/a | n/a | 25.101 (C)(5)(B)
6 | James Landess | 1014447 | Lockhart - Luling TL Upgrade (T184) | Caldwell | Rebuild existing transmission line (T18) Luling - Lockhart, to achieve the full MVA capability of the existing conductor. | 2017-03-31 12:00 | 2018-01-16 12:00 | 2018-01-16 12:00 | 5530000 | 4028655 |  |  | 100 | 138 | 138 | 16.9 | 3x1- 795 ACSR/SD "Condor" & 3x1- 795 ACSR "Drake" | Wood H-Frames, Steel Poles, Steel Lattice Towers | 80- 100' | 16.9 | n/a | n/a | 25.101 (C)(5)(B)
7 | Michael Griswold | 1014352 | Leander - Round Rock TL Addition (CCN) | Williamson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to two load-serving substations | 2019-01-02 | 2020-02-20 |  | T-Line $ 67.8 - 99.6 M ; Substations $ 14.9 - 17.4 M |  |  |  | 20 | 0 | 138 | 11-22 mi | 3x2- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 60' -100' | 11-22 mi | 45866
8 | Bo Beauregard | 1016221 | Cuero Hydro - Luling TL Overhaul (T542) | DeWitt, Gonzales, Caldwell | Rebuild the 10 miles (phase 1) of existing 69 kV transmission line (T542), to 138 kV capable with new structures, conductor, and OPGW. | 2017-01-15 | 2017-05-31 | 2017-06-02 | 9022000 | 6329390.25 |  |  | 100 | 69 | 69 | 53.9 mi | 3x1- 795 ASCR "Drake" & 3x1- 2/0 ACSR "Quail" | Steel & Concrete Poles | Blanket/Centerline/50'/ 30' | 53.9 mi | n/a | n/a | 25.101 (C)(5)(B)
9 | Vicki O'Connor | 1014216 | Elgin Switch-Gilleland Creek TL Overhaul (T421) | Bastrop, Travis, Williamson | Transmission line overhaul, replace poles, cross arms, X-braces, insulators and conductor. | 2017-01-27 | 2017-05-25 | 2017-06-30 | 1857309 | 1678488.83 |  |  | 100 | 138 | 138 | 12.9 mi | 3x1- 1433.6 ACSS/TW "Merrimack" | Wood H-Frames & Steel Single Poles | 100' | 12.9 mi | n/a | n/a | 25.101 (C)(5)(B)
10 | Bo Beauregard | 1016205 | Shadow Glen Circuit Breaker Addition (T574) | Travis | Replace approximately 0.5 miles of OPGW outside of Harris Branch Substation | 2017-03-14 | 2017-08-30 | 2017-08-11 | 1788544 | 1459578.8 |  |  | 100 | 138 | 138 | 7.76 | 3x1- 795 ACSR "Drake" | Concrete Poles & Lattice Tower | 100' | 7.76 | n/a | n/a | 25.101 (C)(5)(B)
11 | Glenda Champagne | 1015455 | Upton Circuit Breaker Addition (T441) | Upton | Modify existing transmission line (T441) Benedum-Crane LCRA, to accommodate substation construction at the Upton Substation. | 2017-03-10 | 2017-08-04 | 2017-08-14 | 1241839 | 681180.57 |  |  | 100 | 138 | 138 | 26.99 | 3x1- 1233.6 ACSS/TW "Yukon" | Steel Poles | 80' CL | 26.99 | 80' Centerline | 0.08 | 25.101 (C)(5)(A)
12 | Mary Beth Nickel | 1016207 | Smithville - Winchester (T175) | Bastrop, Fayette, Lee | Transmission line overhaul, replace Poles, cross arms, X-braces, insulators and conductor. | 2017-08-16 17:00 | 2018-04-06 17:00 | 2018-04-06 | 10677730 | 5738552.24 |  |  | 100 | 138 | 138 | 14.56 | 3x1- 795 ACSR "Drake" | Steel & Concrete Poles | Varies | 14.56 | n/a | n/a | 25.101 (C)(5)(B)
13 | Vicki O'Connor | 1017382 | FPP - Lytton Springs Storm Hardening (T255) | Bastrop, Caldwell, Fayette | Modify a number of existing lattice tower structures on T255 to meet storm hardening requirements. | 2017-04-03 | 2017-06-30 | 2017-06-30 | 1088000 | 745873.21 |  |  | 100 | 345 | 345 | 61.12 | 3x2-715.5 ACSR "Redwing" | Steel Lattice | 100' | 61.12 | n/a | n/a | 25.83(a)(3)
14 | Jessica McLarty | 1005486 | Sherwood Shores Circuit Breaker Addition (T187) | Burnet | Modify existing transmission line (T187) Ferguson-Coronado, to accommodate substation construction at the Sherwood Shores Substation. | 2017-07-17 10:14 | 2018-06-01 13:14 | 2018-05-29 |  | 528355 |  |  | 100 | 138 | 138 | 21.54 | 3x1- 795 ACSR "Drake" | Steel H-frames & Poles | Varies | 21.54 | 80' | n/a | 25.101 (C)(5)(A)
15 | Elizabeth Duron | 1016176 | Arco Tap Circuit Breaker Addition (T442) | Crane | Modify existing transmission line (T442) Crane LCRA-Pleasant Farms, to accommodate substation construction at the new Arco Tap Substation. | 2018-03-15 08:00 | 2018-05-02 | 2018-04-13 |  | 1175206 |  |  | 100 | 138 | 138 | 24.25 | 3x1- 1233.6 ACSS/TW "Yukon" | Steel & Concrete Poles | Varies | 24.25 | 50' | n/a | 25.101 (C)(5)(A)
16 | Brian Good | 1017026 | Manor-Cedar Hills TL Addition (T495) Phase 1 (Flood Remediation Substation Upgrade – 1016539) | Travis | On T495 remove (structure #112) concrete pole and replace with two concrete Poles. | 2017-07-05 | 2017-10-28 | 2017-10-19 | 387000 | 197611.21 |  |  | 100 | 138 | 138 | 8.21 mi | 3x1-795 ACSR "Drake" | Concrete Poles, Steel Poles & Lattice Tower | 100' | 8.21 mi | n/a | n/a | 25.101(C)(5)(B)
17 | Venice Henderson | 1015477 | Henne-McCarty Lane TL Upgrade (T233) | Comal, Hayes | Rebuild the existing 138kV transmission line, T233, with new structures and conductor. | 2017-08-01 08:00 | 2018-01-08 17:00 | 2018-01-08 17:00 | 7353155 | 7014259.46 | 6985533.46 | -0.4095% | 100 | 138 | 138 | 6.6 mi | 3x1- 959.6 ACSS/TW "Suwannee" | Concrete Poles, Steel Poles & Lattice Tower | 100' | 6.6 mi | n/a | n/a | 25.101(C)(5)(B)
18 | Lindsay Mijares | 1016189 | Fayette Power Project 345kV BUS Tie (CCN - Docket No. 47218) | Fayette | Construct a new single circuit 345-kilovolt (kV) transmission line to increase the bus capacity between the existing Fayette Power Project Yard #1 and Yard #2 substations | 2018-03-05 | 2018-06-15 | 2018-06-27 | T-Line $1.1 M; Substations $3.6 M | T-Line $1.8 M; Substations $4.3 M |  |  | 100 | 0 | 345 | 0.26mi | 3x2- 1590 Kcmil ASCR Falcon | Steel Poles | 0 | 0 | 100' | 0.26mi | 47218
19 | Mary Beth Nickel | 1015961 | Lincoln Substation Addition (T155) | Lee | Modify existing transmission line, T155, Giddings-Lexington, to accommodate substation construction at the new Lincoln Substation. | 2017-08-01 | 2017-10-10 | 2017-10-24 | 1181500 | 1556253.37 |  |  | 100 | 138 | 138 | 18.24 mi | 3x1-795 ACSR "Drake" | Steel Lattice, Steel Poles, & Wood H-Frames | Varies | 18.24 mi | 80' | 0.4 mi | 25.101 (C)(5)(A)
20 | Bo Beauregard | 1016925 | Altair-Garwood T546 TL Upgrade (PHII) | Colorado | Structure replacement & addition to meet NESC required clearances for safe distance and system reliability. (PHII - GOAB Switch Install) | 2017-09-18 | 2017-11-24 | 2017-11-24 | 746316 | 1073009.62 |  |  | 100 | 69 | 69 | 9.27 mi | Raven ASCR & 1/0 & Single | Wood H-frames, Single Pole Wood DE | 10' Centerline, 60' Centerline, & Blanket Easements | 9.27 mi | n/a | n/a | 25.101(C)(5)(B)
21 | Elizabeth Duron | 1017377 | Flatonia-Waelder TL Overhaul (T513) | Fayette, Gonzales | Tear-down/rebuild (T513) and upgrade to 138-kV capable with OPGW shield wire | 2017-12-27 17:00 | 2018-03-30 17:00 | 2018-03-30 17:00 |  | 8802782 |  |  | 100 | 69 | 69 | 11.79 mi | 3x1-795 ACSR "Drake" | Concrete Poles & Steel Poles | Centerline | 11.79 mi | n/a | n/a | 25.101(C)(5)(B)
22 | Vicki O'Connor | 1018730 | Fulton-Rockport 69kV TL Restoration (T474) | Aransas | Emergency storm repairs to replace failed hardware. | 2017-08-31 | 2017-09-06 | 2017-09-06 | 1000000 | 985284.29 |  |  | 100 | 69 | 69 | 7.35 mi | 3x1-795 ACSR "Drake" | Steel Poles | Varies | 7.35 mi | n/a | n/a | 25.101(C)(3)
23 | Elizabeth Duron | 1017388 | Harwood-Waelder TL Overhaul (T145) | Gonzales | Tear-down/rebuild. Upgrade to138-kV capable with OPGW shield wire | 2018-01-08 17:00 | 2018-05-31 17:00 | 2018-05-18 |  | 8884835 |  |  | 100 | 69 | 69 | 12.39 mi | 3x1-795 ACSR "Drake" | Concrete Poles & Steel Poles | Centerline | 12.39 mi | n/a | n/a | 25.101(C)(5)(B)
24 | Josh Bollich | 1017338 | Austrop-Bastrop City-Sim Gideon Storm Hardening (T171/T172/T231) | Bastrop, Travis | Replace 24 double-circuit lattice tower structures with 21 steel tower pole structures and 3 lattice dead-end towers, Install OPGW | 2018-02-09 | 2018-06-29 | 2018-06-29 | 4795575 | 7692219.74 |  |  | 100 | 138 | 138 | 34.42 mi | 3x1-795 ACSR "Drake" | Steel Lattice | 125' | 34.42 mi | n/a | n/a | 25.101(C)(5)(B)
25 | Bryan Cooley | 1016108 | Fayetteville-FPP 138kV TL Overhaul (T253) (Fayetteville-FPP 138kV TL Overhaul - 1016108) | Fayette | Tear-down/rebuild and upgrade to138-kV capable with OPGW shield wire | 2018-01-12 10:00 | 2018-05-25 10:00 | 2018-06-01 | 5670000 | 6700000 |  |  | 100 | 69 | 138 | 6.9 mi | 3x1- 959.6 ACSS/TW "Suwannee" | Concrete tangents with steel deadends | 85', 95', 125' | 6.9 mi | n/a | n/a | 25.101(C)(5)(B)
26 | Mary Beth Nickel | 1017381 | FPP - Fayetteville (T210/T211) | Fayette | Storm Hardening of lattice towers | 2018-04-03 | 2018-06-29 | 2018-06-27 |  | 349235 |  |  | 100 | 345 | 345 | 8.89 mi | 3x1- 795 ACSR "Drake" | Steel Lattice | 100' Centerline, 200' , Triangular, and T-Shaped Easements | 8.89 mi | n/a | n/a | 25.101(C)(5)(B)
27 | Brian Good | 1017998 | Hamilton Road - Uvalde Fiber Addition (T570), (T624) & (T464) | Val Verde, Kinney, Uvalde | Replace 25 structures to support new OPGW | 2018-01-29 | 2019-03-10 | 2019-03-10 |  | 9391760 |  |  | 100 | 138 | 138 | 70.6 mi | 3x1-ACSS "Drake" | Steel Poles | Varies | 70.6 mi | n/a | n/a | 25.101 (C)(5)(B)
28 | Tony Rhodes | 1017838 | Kendall - Fredericksburg TL Fiber Build Out (T120) | Kendall, Gillespie | Replace static arm on 70 H-frame structures, install 1 new steel dead-end pole, and install 2 new guyed wood h-frames to support new OPGW | 2018-04-16 08:00 | 2018-06-28 17:00 | 2018-06-19 |  | 2577512.25 |  |  | 100 | 138 | 138 | 20.55 mi | 3x1- 795 ACSR "Drake" | Wood H-Frames, Single Pole Wood DE | Centerline | 20.55 mi | n/a | n/a | 25.101 (C)(5)(B)
29 | Bo Beauregard | 1017449 | Sim Gideon - Winchester (T152/T175) | Bastrop, Fayette, Lee | Replace deteriorated OPGW suspension shoes and dampers from structure 60 to Winchester substation. | 2017-09-01 | 2018-04-24 | 2018-04-17 |  | 835559 |  |  | 100 | 138 | 138 | 20.60 mi | 3x1- 795 ACSR "Drake" | Steel Lattice | Varies | 14.56 mi | n/a | n/a | 25.101 (C)(5)(B)
30 | Elizabeth Duron | 1017409 | Tippett Circuit Breaker Addition (T552)(T674)(T666) | Pecos | Modify existing transmission line (T552) North McCamey-West Yates Switch, to accommodate construction at Tippett Substation. | 2018-03-20 | 2018-05-29 | 2018-05-25 |  | 2714234 |  |  | 100 | 138 | 138 | 10.76 mi | 3x2- 795 ACSR "Drake" | Concrete & Steel Poles | Centerline | 10.76 mi | n/a | n/a | 25.101 (C)(5)(B)
31 | Elizabeth Duron | 1017392 | Lon Hill – Nueces Bay TL Upgrade (T437) | Nueces | Replace 22 structures to increase clearances on transmission line spans in order to meet LCRA TSC minimum design clearances | 2018-01-08 08:00 | 2018-04-25 | 2018-04-25 |  | 4379646 |  |  | 100 | 138 | 138 | 17.3 mi | 3x2- 795 ACSR "Drake" | Concrete & Steel Poles, Steel DE H-Frame | Varies | 17.3 mi | n/a | n/a | 25.101 (C)(5)(B)
32 | Aubre Williams | 1015487 | Kerrville Stadium-Harper Rd TL Upgrade (T144) | Kerr | Rebuild the existing 138kV transmission line (T144) with new structures and conductor. | 2018-02-06 17:00 | 2018-04-17 | 2018-04-11 |  | 3742315 |  |  | 100 | 138 | 138 | 1.5 mi | 3x2- 795 ACSR "Drake" | Steel Poles | Varies | 1.5 mi | n/a | n/a | 25.101 (C)(5)(B)
33 | Jason Bolen | 1015116 | Henne-Comal TL Upgrade (T235) | Comal | Rebuild the existing 138kV transmission line (T235) with new structures and conductor. | 2018-01-10 | 2019-05-14 |  | 9574929 | 10813314 |  |  | 80 | 138 | 138 | 7.51 mi | 3x1- 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7.51 | n/a | n/a | 25.101 (C)(5)(B)
34 | Bo Beauregard | 1017347 | Mendoza-Colton-Elroy (T397) | Caldwell, Travis | Add circuit breakers at Colton Substation. Add OPGW to (T397) Mendoza - Colton - Elroy. Replace structures that are currently not capable of supporting OPGW. | 2018-02-08 17:00 | 2018-05-18 | 2018-05-18 |  | 8900000 |  |  | 100 | 138 | 138 | 12.9 mi | 3x1- 795 ACSR "Drake" | Concrete Poles, Steel Poles and Wood H-frames | Varies | 12.9 mi | n/a | n/a | 25.101 (C)(5)(B)
35 | Brian Good | 1017387 | Harwood-Luling Double Circuit TL OH Phase 1(T145)(173) ; Luling-Waelder TL Add Phase 2 (T145) | Caldwell, Gonzales | Replace 45 double-circuit lattice tower structures with double circuit steel Poles and add OPGW on (T145/T173) Harwood-Luling and Luling-Waelder | 2018-02-26 | 2019-05-10 | Ph. 1 6/29/2018 | $ 2,555,441 (phase 1 & 2) | $ 7.3M (phase 1 & 2) |  |  | Phase 1 - 100 ; Phase 2 - 0 | 138 | 138 | Phase 1 -12.9 mi; Phase 2 - 21.85 | Phase 1 - 3x2- 795 ACSR "Drake"; Phase 2 Drake 795 ACSR & 26/7 & Single | Concrete Poles, Steel Poles & Wood H-frames | 100' Centerline | Phase 1-19.4 mi; Phase 2 - 21.85 mi | n/a | n/a | 25.101 (C)(5)(B)
36 | Mary Beth Nickel | 1016106 | Gonzalez - Luling TL Overhaul (T173) | Caldwell, Gonzales | Replace 24 single circuit H-Frame structures and 1 lattice structure. Repair 11 H-Frame structures and 1 lattice structures. | 2018-03-02 08:00 | 2018-05-24 17:00 | 2018-05-18 |  | 1412000 |  |  | 100 | 138 | 138 | 19.45 mi | 3x1- 795 ACSR "Drake" | Wood H-frames & Steel Lattice | Varies | 19.49 mi | n/a | n/a | 25.101 (C)(5)(B)
37 | Tony Rhodes | 1017859 | Clear Springs-Marion TL Addition (419) | Guadalupe | Replace 3 double-circuit lattice tower structures with 3 CREZ F5 lattice dead-end tower structures, Install OPGW, Repair 1 cage/arm member at Structure #88, Install new bundled Drake between new spans between A-Frames and new Towers and between #108A & #108B. | 2018-02-15 08:00 | 2018-11-18 | 2018-11-18 |  | 3446680 |  |  | 100 | 345 | 345 | 8.5 mi | 3x2- 795 ACSR "Drake" | Steel Lattice | 100' Centerline | 8.5 mi | n/a | n/a | 25.101(C)(5)(B)
38 | Elizabeth Duron | 1016350 | Cuero-Guadalupe TL Overhaul (T542) | Dewitt | Replace 28 wood structures with single pole steel structures. Add new 795 ACSR conductor and OPGW fiber to new structures. | 2018-02-19 08:00 | 2018-04-26 17:00 | 2018-04-26 |  | 2200817 |  |  | 100 | 69 | 69 | 3.07 mi | 3x1- 795 ACSR "Drake" | Steel Poles | Blanket | 3.07 mi | n/a | n/a | 25.101 (C)(5)(B)
39 | Mary Beth Nickel | 1016330 | Bastrop West - Bluebonnet (T516) | Bastrop | Replace (2) lattice towers with two steel H-frame structures at Hwy 71 to meet ground clearances across the highway | 2018-06-15 17:00 | 2018-06-29 17:00 | 2018-06-25 |  | 685345 |  |  | 100 | 138 | 138 | 6.1 mi | 3x1-795 ACSR "Drake" | Wood/steel H-Frames and steel lattice | Centerline | 6.1 mi | n/a | n/a | 25.101(C)(5)(B)
40 | Bo Beauregard | 1017345 | Butler Circuit Breaker Addition (T260) | Bastrop | Add ring bus at Butler Substation, transmission line required new terminations | 2018-02-20 17:00 | 2018-04-03 17:00 | 2018-03-22 |  | 346747 |  |  | 100 | 138 | 138 | 31.32 mi | 3x1-795 ACSR "Drake" | Wood/steel H-Frames, steel lattice, steel Poles | Varies | 31.32 mi | n/a | n/a | 25.101(C)(5)(B)
41 | Bryan Cooley | 1017375 | Fayetteville - Salem TL Storm Hardening (T177/T211/T210) | Austin, Fayette, Washington | Replace bracing on 40 lattice transmission line structures to meet NESC storm hardening requirements | 2018-11-16 | 2019-02-25 | 2019-02-25 | 854229 | 4247676 |  |  | 100 | 138/345 | 138/345 | 19.35 mi | 3x1 - 795 ACSR "Condor" & 3x2 -795 ACSR "Condor" | Steel Lattice | Varies | 19.35 mi | n/a | n/a | 25.101 (C)(5)(B)
42 | Tony Rhodes | 1017856 | San Marcos - Kyle Fiber Build-Out (T322) | Hays | Add OPGW from San Marcos to Canyon | 2018-03-19 | 2018-05-18 | 2018-05-18 | 718484 | 1078863.26 |  |  | 100 | 138 | 138 | 3.46 mi | 2x1- 795 ACSR "Drake" | Steel Poles, Concrete Poles | Varies | 3.46 mi | n/a | n/a | 25.101 (C)(5)(B)
43 | Lindsay Mijares | 1016357 | Giddings-Lexington (T155) | Lee | Increase the reliability of transmission facilities on the Giddings-Lexington (T155)138kV transmission line | 2018-01-25 12:00 | 2018-04-19 12:00 | 2018-04-12 |  | 350000 |  |  | 100 | 138 | 138 | 17.62 mi | 3x1-795 ACSR "Drake" | Steel lattice & wood H-Frames | 100' | 17.62 mile | n/a | n/a | 25.101 (C)(5)(B)
44 | Bo Beauregard | 1017412 | Webberville Circuit Breaker Addition (T673/T231) | Travis | Add OPGW to T231 | 2018-01-30 09:36 | 2018-06-19 09:36 | 2018-05-11 |  | 300000 |  |  | 100 | 138 | 138 | 0.2 mi | 3x1-795 ACSR "Drake" | Steel Poles | Varies | .2 mi | n/a | n/a | 25.101 (C)(5)(B)
45 | Josh Bollich | 1019417 | US 385 Hwy Widening TXDOT (T451/T452/T455) | Crane | Remove and replace 4 Poles to allow TXDOT widening of US 385 | 2018-07-10 | 2018-08-21 | 2018-08-21 | 300000 | 861425 |  |  | 100 | 138 | 138 | 23.9/ mi (T451) 23.3 mi (T452) | Bundled Drake ASCR | Concrete Poles | 80' Centerline | 23.9/mi (T451) 23.3 mi (T452) | 80' Centerline | 23.9 mi (T451) 23.3 mi (T452) | 25.101 (C)(5)(B)
46 | Jason Bolen | 1017403 | Sim Gideon-Smithville TL Storm Hardening - (T150) | Bastrop | Increase the reliability of transmission facilities on the Sim Gideon – Smithville 13.8-mile 138-kV transmission line (T150). | 2018-07-17 | 2019-03-18 | 2019-03-18 | 2438690 | 3514428.1 |  |  | 100 | 138 | 138 | 13.8 mi | 795 ACSR Drake | Steel Poles & Hybrid Poles | 80' | 13.8 mi | 80 | 13.8 mi | 25.101 (C)(5)(B)
47 | Tony Rhodes | 1017854 | Fairland-Lago Vista TL Addition (T414) | Travis, Burnett | OPGW add and Tower replacements | 7/15/18 | 2019-03-27 | 2019-03-27 | 4630000 | 7938338 |  |  | 100 | 138 | 138 | 21.38 | 795 CONDOR ACSR/SD | Lattice Towers & Steel Poles | 100' Centerline | 21.38 mi | 100' Centerline | 21.38 mi | 25.101 (C)(5)(B)
48 | Manny Garcia | 1017348 | Cooks Point TL Addition (CCN) | Burleson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2020-10-05 | 2022-01-27 |  | T-Line $ 35.1 - 43.5M ; Substation $ 6.1 - 6.7 M |  |  |  | 0 | 0 | 138 | 17-23 mi | 2x1- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 80' | 17-23 mi | 45838
49 | Martin Lindig | 1016356 | Bellville S-Glidden TL Addition (T113) (Bellville S-Glidden TL Storm Hardening - 1016355) | Austin County/Colorado | Replace eleven (11) lattice tangent tower structures with steel pole structures to meet storm hardening requirements; the existing rating of the transmission circuit will be maintained at 110 MVA. | 2018-08-23 | 2019-06-19 |  | 4900000 | 5581304.34 |  |  | 65 | 69 | 69 | 31.24 mi | Existing: (1)795 ACSR “Drake” New: Bellville-Str 26 (1)959 ACSS “Suwannee” and Str.27-Glidden (1)795 ACSR “Drake” | Bellville-Str.26 Concrete H-Frame and Steel DE Str. 27-Glidden Steel DE, Lattice Towers, and concrete tangents | 120’ | 31.24 mi | 120’ | 31.24 mi | 25.101 (C)(5)(B)
50 | Tony Rhodes | 1017847 | Coronado-Fairland TL Addition (T110) (LCRA TSC Fiber Build-Out FY18-1017418) | Burnet/Llano | OPGW is being installed and multiple structures are being replaced or repaired to support the added fiber as part of the FY18 Fiber Build Out program. | 2018-08-29 | 2019-05-15 |  | $3.2M | $5.6M |  |  | 75 | 138 | 138 | 12.41 mi | 795 ACSR CONDOR, 795 ACSR Drake, 72 ct OPGW | Steel lattice, & steel Poles | Varies | 12.41 mi | n/a | n/a | 25.101 (C)(5)(B)
51 | Tony Rhodes | 1017842 | Gillespie-Horseshoe Bay TL Addition (T448) (LCRA TSC Fiber Build-Out FY18-1017418) | Gillespie/Llano | OPGW is being installed and multiple structures are being replaced or repaired to support the added fiber as part of the FY18 Fiber Build Out program. | 2018-08-01 | 2019-04-16 |  | $4.5M | $7.6M |  |  | 90 | 138 | 138 | 36.43 mi | 795 ACSR Drake, 72 Ct OPGW | Steel lattice | Varies | 36.43 mi | n/a | n/a | 25.101 (C)(5)(B)
52 | Martin Lindig | 1017658 | Burnet-Wirtz TL Overhaul (T218) (Burnet-Wirtz TL Overhaul - 1017657) | Burnet | Structure replacement and add OPGW | 2019-01-04 | 2019-12-17 |  | 3400000 | 2925344.75 |  |  | 10 | 138 | 138 | 16.4 mi | 795 ACSR Drake | Steel & Wood Poles | Varies | 16.4 mi | n/a | n/a | 25.101 (C)(5)(B)
53 | Alfred Mackey | 1016322 | Bellville South - Waller TL Storm Hardening (T213) (Bellville South - Waller TL Storm Hardening - 1016321) | Austin/Waller | Increase reliability and capacity of transmission facilities on Bellville South to Waller | 2018-09-04 | 2019-05-15 |  | 13162000 | 32512265 |  |  | 20 | 138 | 138 | 15.77 mi | 795 ACSR Drake | Concrete & steel Poles | Varies 85' | 15.77 mi | n/a | n/a | 25.101 (C)(5)(B)
54 | Cody Mcneil | 1010353 | Bighill to Kendall Bolt Tightening (T558/T559) | Williamson | Inspect each tower to tighten bolts and install designed locking mechanisms | 2018-09-24 | 2018-12-21 | 2018-12-21 |  | 676064 |  |  | 100 | 345 | 345 | 138 mi | Bundled 1926.9 Cumberland | Lattice Towers & Steel Poles | Varies 60' -130' | 138 mi | n/a | n/a | 25.101(C)(5)(B)
55 | Vaibhav Pitale | 1018931 | Flatonia-Moulton South TL Addition (T134) (Shiner Circuit Breaker Addition - 1017402) | Lavaca | Increase transmission service reliability to the Shiner Substation | 2018-10-09 | 2019-02-11 | 2019-02-11 |  | 191071.02 |  |  | 100 | 138 | 138 | 11.1 mi | 795 ACSR Drake | Concrete/Steel Poles | 30',40',45', 60', 100' | 11.1 mi | n/a | n/a | 25.101 (C)(5)(A)
56 | Dave Ilges | 1017830 | North McCamey – LCRA Crane TL Addition (T455) King Mountain Circuit Breaker Addition Addition 1017830) | Upton | LCRA will install three circuit breakers, provide real-time monitoring at King Mountain Substation. | 2018-10-01 | 2019-06-28 |  |  | 819692.46 |  |  | 90 | 138 | 138 | 23.08 mi | (2) 795 kcmil ACSR "Drake" | Concrete & steel monoPoles | Centerline, 80' | 23.08 mi | n/a | n/a | 25.101 (C)(5)(A)
57 | Josh Bollich | 1017513 | Airline-Naval Base TL Addition (T475) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-10-01 | 2019-10-29 |  | 178226.25 | 200390 |  |  | 0 | 69 | 138 | 6.39 mi | (1) 795kcmil ACSR/AW "Drake" | Steel Monopole | Centerline, 16' | 6.39 mi | n/a | n/a | 25.101 (C)(5)(D)
58 | Josh Bollich | 1017515 | Airline-Naval Base TL Addition (T476) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-03-28 | 2019-04-11 |  | 135000 | 164343.83 |  |  | 75 | 69 | 138 | 7.98 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole | Centerline | 7.98 mi | n/a | n/a | 25.101 (C)(5)(D)
59 | Josh Bollich | 1018756 | Heines-Naval Base TL Addition (T685) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. (Once Heines Substation Addition is complete, the transmission assets on (T476) will be renumbered to T685 Heines - Naval Base) | 2018-10-03 | 2019-10-25 |  | 468085 | 598491.79 |  |  | 60 | 69 | 138 | 5.3 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole | Centerline | 5.3 mi | n/a | n/a | 25.101 (C)(5)(A)
60 | Josh Bollich | 1018755 | Airline-Heines TL Addition (T476) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. | 2018-10-11 | 2019-10-25 |  | 519285 | 780358 |  |  | 60 | 69 | 138 | 2.57 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole |  | 2.57 mi | n/a | n/a | 25.101 (C)(5)(A)
61 | Josh Bollich | 1018663 | RioPecos-HorseCrossing TL Addition (T451/ future T682) | Crane | Provide transmission service to a generator. (This circuit will be added to the open position on the structures on the (T451) Rio Pecos - Crane, after the project is complete the transmission line will be numbered T682 Rio Pecos - Horse Crossing) | 2019-09-23 | 2019-12-09 |  | 952311.92 | 1310978.91 |  |  | 0 | 0 | 138 | 0.76 mi | (2) 795 ACSR Drake | Steel/Concrete MonoPoles | 80' CL | 0.76 mi | n/a | n/a | 25.101 (C)(5)(C)
62 | Michael Griswold | 1019260 | Winchester-Salem T170 TL Addition (T170) (Winchester Autotransformer Addition - 1017413) | Fayette | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-04-13 |  | 749379 | 2065559.26 |  |  | 50 | 138 | 138 | 37.28 mi | (1) 795 kcmil ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100' Centerline | 37.16 mi | n/a | n/a | 25.101 (C)(5)(A)
63 | Michael Griswold | 1017777 | Winchester-Fayetteville TL Addition (T165) (Winchester Autotransformer Addition - 1017413) | Fayette | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-04-13 |  | 1012865.49 | 1945182.95 |  |  | 50 | 138 | 138 | 18.92 mi | (1) 795 kcmil ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100' Centerline | 18.75 mi | n/a | n/a | 25.101 (C)(5)(A)
64 | Brad Wallner | 1017550 | Raymond F Barker-Comfort TL Addition (T121) (Cypress Creek Circuit Breaker Project 1017351) | Lee/Fayette | Acquire 5 acres and expand new LCRA TSC facilities with a three-ring bus configuration. | 2019-03-01 | 2019-05-10 |  |  | 230513 |  |  | 30 | 138 | 138 | 10.03 mi | 1-795 ACSR "Drake" | Steel MonoPoles | Varies | 10.03 mi | n/a | n/a | 25.101 (C)(5)(A)
65 | Brian Good | 1017495 | Brenham North - Waller TL Addition (T232) (Flood Mitigation - FY2018 System Upgrade 1017378) | Waller, Washington | Reduce flood risk and potential damage to substation equipment | 2019-09-16 | 2019-11-05 |  | 1619269.84 | 2157648 |  |  | 0 | 1.38 | 138 | 12.94 mi | 795 Drake ACSR & 630.0 TYPE 21 ACCS/TW/C7 (BETWEEN #17/1 TO #18/1) | Concrete Poles, Wood H-frame, Steel H-frame | 75' @ single circuit. 85' @ double circuit | 12.94 mi | 75' @ single circuit. 85' @ double circuit | 12.94 mi | 25.101 (C)(5)(B)
66 | Jacob Miller | 1019038 | Plum - La Grange TL Addition (T208) (Riverside Circuit Breaker Addition - 1018925) | Fayette | Increase the reliability of substation equipment at the Riverside Substation. | 2019-01-28 | 2019-05-23 |  | 356355.26 | 1589877 |  |  | 70 | 138 | 138kv | 8.39 mi | 795 ACSR. GA2 Drake. 3/8 EHS. OPGW | Wood H-frame | Undefined Centerline | 5.58 mi | undefined Centerline | 5.58 mi | 25.101 (C)(5)(B)
67 | Alfred Mackey | 1019276 | Harwood-Gonzales (T542) (Gonzales - Harwood TL Overhaul - 1018965) | Gonzales | Increase the reliability and capability of circuit (T542) on Cuero – Luling 53.9-miles of 69-kV transmission line for the 10 miles between City of Gonzales (S31) & Harwood Station (S397). | 2019-04-01 | 2019-10-25 |  | 4350428.5 | 5484500 |  |  | 3 | 69 | 69 (138kV Capable) | 9.97 mi | Single 795 ACSR "Drake" | Concrete & Steel Pole | Blanket, Centerline | 9.97 mi | n/a | n/a | 25.101 (C)(5)(B)
68 | Manny Garcia | 1017695 | North McCamey-Robbns SW TL Addition (T456) (Robbins Switch Circuit Breaker Addition Addition 1017400) | Upton | Provide transmission service to a generator by constructing substation for interconnection. | 2018-10-31 | 2019-05-13 |  |  | 77017.11 |  |  | 30 | 138kV | 138 | 5.68 mi | 2x 795 Drake ACSR | Concrete Poles | 80' | 5.68 mi | n/a | n/a | 25.101 (C)(5)(A)
69 | Pete Zepeda | 1017510 | Tunas Creek - Mesa View TL Addition (T620) (Fourmile Circuit Breaker Addition 1017380) | Pecos | Increase transmission service reliability to the Fourmile Substation (formerly Indian Mesa/Orion/NWP Tap). | 2018-11-27 | 2019-09-30 |  |  | 4679000 |  |  | 15 | 138 | 138 | 11.68 mi | 3x2, 795 kcmil "Drake" | Steel & Concrete Poles | 80' | 11.68 mi | n/a | n/a | 25.101 (C)(5)(B)
70 | Josh Bollich | 1017588 | Tunas Creek-Mesa View SW TL Addition (T620) (Desert Mesa Circuit Breaker Addition 1017353) | Pecos | Increase transmission service reliability to the Desert Mesa Substation (formerly Desert Sky Tap #1). Provide real-time monitoring facilities at the Desert Mesa Substation. Increase the reliability of transmission facilities on the T620 Tunas Creek – Mesa View transmission line. | 2018-10-31 | 2019-05-15 |  |  | 264333 |  |  | 50 | 138 | 138 | 18.40 mi | 3x2, 795 kcmil "Drake" | Steel & Concrete Poles | 80' | 18.4 mi | n/a | n/a | 25.101 (C)(5)(A)
71 | Michael Griswold | 1019213 | Round Rock TL Relocation (T527, T378) | Williamson | Increase the transmission service reliability to the Round Rock substation and to support the expansion of the substation by Oncor. | 2019-01-07 | 2019-04-30 |  | 446000 | 1529331.89 |  |  | 90 | 138 | 138 | 5.1 mi | (1) 795 ACSR "Drake" | Steel Lattice, Steel H-Frame | 100' | 5.1 mi | n/a | n/a | 25.101 (C)(5)(B)
72 | Clint Meyer | 1016702 | Altair - Nada TL Addition (T545) (Glidden Area TL Upgrade - 1016219) | Colorado | OPGW (fiber) installation (T545) and Substation upgrade at Nada and Altair substations from 69kV to 138kV | 2018-12-03 | 2019-05-31 |  | 2312000 | 6632944 |  |  | 80 | 69 | 138 | 14.12 mi | 795 Drake ASCR & 26/7 & Single | Steel, Wood, & Lattice | Blanket | 14.12 mi | Blanket | 14.1 mi | 25.101 (C)(5)(B)
73 | Alfred Mackey | 1019321 | Lakeway-Marshall Ford T179 Addition (T179) (Lakeway AE Marshall Ford TL SH - 1019096) | Travis | Increase the reliability of circuit (T179) on the Lakeway (AE) – Marshall Ford 2.4 mile138 kV transmission line. | 2019-01-25 | 2019-05-17 |  | 438000 | 2339497.44 |  |  | 10 | 138 | 138 | 2.4 mi | (6x1) 795 ACSR "Drake" | Steel Towers | 100' | 2.4 mi | n/a | n/a | 25.101 (C)(5)(B)
74 | Alfred Mackey | 1019603 | Lakeway-Marshall Ford Fiber Addition (T179) (LCRA Fiber Backbone FY 19 Telecom Upgrade - 1019084) | Travis | LCRA will Install 2.42 miles of 72-count OPGW from Lakeway (AE) to Marshall Ford (T179). | 2019-02-13 | 2019-05-17 |  |  | 392000 |  |  | 10 | 138 | 138 | 2.4 mi | (6x1) 795 ACSR "Drake" | Steel Towers | 100' | 2.4 mi | n/a | n/a | 25.101 (C)(5)(B)
75 | Manny Garcia | 1017760 | Warda-Salem TL Addition (T667,T170) (Warda Circuit Breaker Addition - 1017411) | Fayette | Increase reliability of transmission facilities on the (T170) Winchester-Salem 34.8 mile 138kV transmission line. Cut-in to new A-frames at existing Warda Sub and renumber Warda to Salem as (T667). | 2018-12-01 | 2018-12-20 | 2018-12-20 |  | 663000 |  |  | 100 | 138 | 138 | 34.8 mi | Single (1/phase) 795kcmil ACSR "Drake" | Steel monopole | 100' | 34.8 mi | n/a | n/a | 25.101 (C)(5)(B)
76 | Robert Badger | 1019317 | Rockport-Fulton T474 TL Addition (T474) Hurricane Response System Upgrade - 1019095 | Nueces, Aransas | Increase reliability, repair storm damage, & upgrade circuit (T477) on the N Padre Tap-Port Aransas 18.23-mile 69-kV TL and circuit (T474) on the Fulton-Rockport 138-kV 7.36-mile 69-kV TL. | 2019-02-07 | 2019-08-20 |  |  | 852895 |  |  | 18 | 69 | 69 | 7.4 mi | (1x) 795 ACSR/AW Drake | Steel Monopole, Concrete Monopole | Unknown (AEP-owned) | - | - | - | 25.101 (C)(5)(B)
77 | Manny Garcia | 1017557 | Deer Creek-Luling TL Addition (T538) (Darst Creek Circuit Breaker Addition - 1017352) | Guadalupe | Add four 138-kV, 3000A, 40kAIC circuit breakers in a ring bus configuration to Darst Creek substation | 2019-02-22 | 2019-05-17 |  |  | 717517.4 |  |  | 40 | 69 | 69 | 15.84 mi | Drake 795 ACSR, Single | Concrete & Steel | Blanket | 15.84 mi | Blanket | 15.84 mi | 25.101 (C)(5)(B)
78 | Brian Good | 1017499 | Bastrop West-Sim Gideon TL Addition (T410) (Flood Mitigation - FY2018 System Upgrade - 1017378) | Bastrop | Reduce flood risk and potential damage to substation equipment | 2019-01-04 | 2019-03-08 | 2019-03-08 | 897995.63 | 1400020.01 |  |  | 100 | 138 | 138 | 6.76 mi | Drake 795 ACSR, Single | Steel (New) & Wood H-frame(Existing) | 100' | 100' | 100' | 6.76 mi | 25.101 (C)(5)(B)
79 | Jacob Miller | 1019133 | Rim Rock - Turtle Creek TL Addition (T270) (Rim Rock - Turtle Creek TL Storm Hardening - 1018968) | Kerr | Increase the reliability of circuit (T270) on the Rim Rock - Turtle Creek 7.6 mile 138kV transmission line | 2020-09-16 | 2021-02-10 |  | 6523068.22 | 7002025 |  |  | 0 | 138 | 138 | 7.6 mi | (1x) 795 ACSR Drake | Steel Monopole | 60' , 100' | 7.6 mi | 60, 100 | 7.6 mi | 25.101 (C)(5)(B)
80 | Brad Wallner | 1020430 | Marshall Ford-McNeil TL Addition (T161) (Summit T161 TL Relocation - 1020390) | Travis | Relocation of the Marshall Ford to McNeil 69-kV transmission line (T161) at the Austin Energy Summit Substation. The proposed relocation of the line was requested by Austin Energy to the northern section of Summit Sub. | 2019-03-04 | 2019-11-27 |  |  | 831439 |  |  | 50 | 69 | 69 | 13.42 mi | Bundled 795 Drake ACSR | Steel Poles | 100' CL | 0.9 mi | 100' Centerline | 0.9 mi | 25.101 (C)(5)(B)
82 | Brian Good | 1018599 | Bakersfield to Solstice (CCN) (Bakersfield-Solstice TL Addition - 1018599) | Pecos | Construct a new 345-kV transmission line to connect LCRA TSC's existing Bakersfield station and AEP Texas' Solstice Switch Station | 2019-12-20 | 2020-12-23 |  |  | T-line $148 - $192M; Bakersfield Substation - $6M; Solstice Switch Station - $38M |  |  | 0 | 0 | 345 | 130-190 mi | 1926.9 kcmil ACSS/Cumberland (LCRA TSC) and 1590 ACSS (AEP Texas) | Double-circuit steel lattice towers | 0 | 0 | 150' | 68 - 92 mi | 48787
83 | Josh Bollich | 1017897 | Culberson-Kunitz TL Addition (T271) (Culberson-KunitzTL Overhaul - 1017896) | Culberson | Structure replacement upgrades to steel and concrete Poles | 2019-05-28 | 2019-08-09 |  | 507000 | 593494 |  |  | 0 | 138 | 138 | 28.88 mi | Linnet; 336kcmil; 0.721” | Wood | 100' | 28.88 mi | n/a | n/a | 25.101 (C)(5)(B)
89 | Robert Badger | 1019319 | N. Padre Tap - Port A. (T-477) (Hurricane Response System Upgrade - 1019095) | Nueces | Increase the reliability, repair storm damage, and upgrade circuit (T477) on the North Padre Tap – Port Aransas 18.23-mile 69-kV transmission line and circuit (T474) on the Fulton – Rockport 138-kV 7.36-mile 69-kV transmission line. | 2019-08-05 | 2019-10-25 |  |  | 3193000 |  |  | 0 | 69 | 69 | 15 mi | 795 ACSS/AW Drake x1 | Steel monopole, Concrete Monopole, Hybrid Steel/Concrete | (AEP-owned) | NA | n/a | n/a | 25.101 (C)(5)(B)
90 | Robert Badger | 1019337 | Elroy - Wolf Lane (T-582) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-03-18 | 2019-05-15 |  | 31898000 | 1317604 |  |  | 15 | 138 | 138 | 3.78 mi | 795 Drake ACSR GA2 | Wood H-frame, LD Steel H-frame, Steel Pole, Tower | 100' | 3.78 mi | 100 | 3.78 mi | 25.101 (C)(5)(B)
91 | Robiin Mims | 1020260 | Red Creek-Amos Creek TL Addition (T424) (Amos Creek Substation Addition - 1020230) | Concho | Transmission line cute-in to provide transmission service to a generator. | 2019-08-05 | 2020-04-22 |  |  | 1737273 |  |  | 0 | 345 | 345 | 49 mi | 1590 ACSR Falcon x2 | Steel Lattice tower | 100' | 49 mi | n/a | n/a | 25.101 (C)(5)(B)
92 | Robert Badger | 1019327 | Austrop-Garfield (T182) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-04-15 | 2019-11-22 |  | 31898000 | 2561186 |  |  | 0 | 345 | 345 | 8.33 mi | Bundled 795 ACSR "Drake" | Lattice Tower | 170' Centerline | 8.33 mi | n/a | n/a | 25.101 (C)(5)(B)
93 | Seth Delcambre | 1019374 | Marshal Ford - McNeil T161 TL Addition (T161) (Marshall Ford-McNeil TL Relocation - 1019212) | Travis | Increase transmission service reliability to the Austin Energy Hamilton Substation. | 2019-05-01 | 2019-07-08 |  |  | 951759 |  |  | 0 | 69 | 69 | 13.4 mi | 4/0 & 795 kcmil ACSR | Lattice Towers & Steel Poles | 100' | 13.4 mi | n/a | n/a | 25.101 (C)(5)(B)
94 | Seth Delcambre | 1017655 | Winchester-Salem TL Addition (T170) (T667) (Salem-Winchester T170 TL OH - 1017654) | Fayette | Increase the reliability and capability of circuit T170 on the Salem - Winchester 37.16-mile 138-kV transmission line. | 2019-06-03 | 2020-02-20 |  |  | 5700000 |  |  | 0 | 138 | 138 | 37.18 | 795 ACSR Drake (single) | Wood H-frame, Steel Lattice, Steel Monopole | Varies | 37.18 mi | n/a | n/a | 25.101 (C)(5)(B)