## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
GV03-13 | Gillette to Nopal Tap Transmission Line | Gonzales | Construct 138kV Radial Tap from LCRA Gillette Substation to a new Nopal Substation, add Gillette Sub 138 Terminal for GVEC |  |  |  | 9.5 Mill |  | - |  | 100% | 0 | 138kV | 10 | 795 ACSR | Concrete and Steel Mono-poles | 0 | 0 | 80 | 10 | Docket # 42287 | Construction Complete. Line Energized
GV03-15 | Nopal Substation | Gonzales | New Substation with 1 - 30mVA PWT, includes four distribution circuits, and 138 transmission terminal and bus |  |  |  | 4.45 Mill |  | - |  | 100% | 0 | 138kV | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Construction Complete. Station Energized
GV07-15 | Moulton South Substation | Lavaca | New Substation with 1 - 30mVA PWT and four distribution circuits |  |  |  | 5.5 Mill |  | - |  | 100% | 0 | 138 | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Construction Complete. Station Energized
GV09-15 | Marion Substation PWT Addition | Guadalupe | Add 1 - 40 MVA PWT and four distribution circuits to existing 138 bus |  |  |  | 3.1 Mill |  | - |  | 98% | 138 | 138 | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | PWT energized 5/24/2019 , follow-up engineering in progress
GV01-16 | Meadow Lake Substation | Guadalupe | New Substation, w 30MVA PWT, distribution bays 4 circuits |  |  |  | 4.9 Mill |  | - |  | 10% | 0 | 138 | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Substation property site acquisition coordination in progress; Re-zoning coordination w City of Seguin successful
GV01-17 | Moulton South Substation Autotransformer | Lavaca | Add new 138-69 kVAutotransormer, cut-in 69 t-line ckts |  |  |  | 1.5 Mill |  | - |  | 100% | 0 | 138/69 | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Complete; Autotransformer energized
GV01-18 | Marion to Cibolo 138 Transmission Line Circuit Addition | Guadalupe | Add 4.8 mile 138kV transmission line circuit to existing transmission line, Terminal at Marion breakers/bus, 2 Terminals at Cibolo breakers/bus, replace underrated switches |  |  |  | 4.9 Mil |  |  |  | 100% | 138 | 138 | 4.8 | 1192 ACSR | Steel | 80 | 4.7 | 0 | 0 |  | Construction Complete. Line and Terminals energized 5/24/2019
GV02-18 | Schertz 138 Terminal Addition | Guadalupe | Add breaker and relaying to terminal looking at Cibolo, replace switches |  |  |  | 325k |  |  |  | 100% | 138 | 138 | 0 | 0 | Steel | 0 | 0 | 0 | 0 |  | Construction Complete. Energized 5/24/2019
GV03-18 | Nixon-LCRA Sub Relocation of Hallettsville Auto to Nixon | Gonzales | Move 138/69 Auto from Halletsville to Nixon-LCRA |  |  |  | 125k |  | - |  | 100% | 138/69 | 138/69 |  | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Complete; Autotransformer energized Sept 19, 2018