## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
CCEC17001 | Enterprise Pipeline Service Millersview Pump Station | Rural/Concho County | Tap existing 69 kV transmission line and construct 0.85 mile extension to provide service to Enterprise Pipeline pump station. Overbuild existing distribution line with 69kV transmission circuit. | 2019-04-17 | 2019-05-18 | 2019-05-18 |  | 913000 |  |  | 100% | 69 | n/a | 0.85 | #4/0 ACSR 'Penguin' conductor, Single | Replace existing wood distribution structures with 65' wood monopole structures | 20 | 0.85 | 40 | 0.85 | 25.101(c)(5)(B)(ii)