## MCPR August 2019
MCPR Row Number | Project Manager | Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number
2 | Bo Beauregard | 1010656 | Blumenthal TL Addition (T637) | Gillespie, Kendall, Blanco | Construct a new 138-kV transmission line connecting the new Blumenthal (CTEC) Substation to a tap point on the Kendall - Mountain Top 138-kV transmission line (T342). | 2017-10-02 08:00 | 2018-05-18 | 2018-05-18 | $21,536,000 T-line; $3,936,000 Substation; $1,634,000 Tap | $21,510,000 T-line; $4,146,000 Substation; $1,836,000 Tap |  |  | 100 | 0 | 138 | 14.4 | 3x1-795 ACSR "Drake" | Poles & H-Frames | 0 | 0 | 100' | 14.4 | 43599
4 | Martin Lindig | 1015208 | Zorn-Marion 345kV TL Addition (CCN - Docket No. 45601) | Guadalupe | Construct a new 345-kV transmission line to provide a transmission point of interconnection between Central Texas and San Antonio area. | 2018-06-01 08:00 | 2019-05-30 | 2019-05-30 | T-Line $43.26 - 55.11 M ; Substation $7,905,000 | 46000000 |  |  | 100 | 0 | 345 | 18-24 mi | 3x2-959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7-11 mi |  | 10 - 14 mi | 45601
5 | Josh Bollich | 1014910 | TXDOT US 83 Relief Route Rio Grande City-La Grulla (T485) | Starr | Modify existing transmission line (T485), Rio Grande City-La Grulla, to accommodate road expansion by TXDOT. | 2018-11-09 | 2018-11-30 | 2018-11-30 | 220000 | 317464 |  |  | 100 | 138 | 138 | 31.66 | 3x1-795 ACSR/AW "Drake/AW" | Steel Poles | Varies | 31.66 | n/a | n/a | 25.101 (C)(5)(B)
7 | Michael Griswold | 1014352 | Leander - Round Rock TL Addition (CCN) | Williamson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to two load-serving substations | 2019-01-02 | 2020-04-03 |  | T-Line $ 67.8 - 99.6 M ; Substations $ 14.9 - 17.4 M |  |  |  | 60 | 0 | 138 | 11-22 mi | 3x2- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 60' -100' | 11-22 mi | 45866
16 | Brian Good | 1017026 | Manor-Cedar Hills TL Addition (T495) Phase 1 (Flood Remediation Substation Upgrade – 1016539) | Travis | On T495 remove (structure #112) concrete pole and replace with two concrete Poles. | 2017-07-05 | 2017-10-28 | 2017-10-19 | 387000 | 197611.21 |  |  | 100 | 138 | 138 | 8.21 mi | 3x1-795 ACSR "Drake" | Concrete Poles, Steel Poles & Lattice Tower | 100' | 8.21 mi | n/a | n/a | 25.101(C)(5)(B)
27 | Brian Good | 1017998 | Hamilton Road - Uvalde Fiber Addition (T570), (T624) & (T464) | Val Verde, Kinney, Uvalde | Replace 25 structures to support new OPGW | 2018-01-29 | 2019-03-10 | 2019-03-10 |  | 9391760 |  |  | 100 | 138 | 138 | 70.6 mi | 3x1-ACSS "Drake" | Steel Poles | Varies | 70.6 mi | n/a | n/a | 25.101 (C)(5)(B)
28 | Tony Rhodes | 1017838 | Kendall - Fredericksburg TL Fiber Build Out (T120) | Kendall, Gillespie | Replace static arm on 70 H-frame structures, install 1 new steel dead-end pole, and install 2 new guyed wood h-frames to support new OPGW | 2018-04-16 08:00 | 2018-06-28 17:00 | 2018-06-19 |  | 2577512.25 |  |  | 100 | 138 | 138 | 20.55 mi | 3x1- 795 ACSR "Drake" | Wood H-Frames, Single Pole Wood DE | Centerline | 20.55 mi | n/a | n/a | 25.101 (C)(5)(B)
33 | Bo Beauregard | 1015116 | Henne-Comal TL Upgrade (T235) | Comal | Rebuild the existing 138kV transmission line (T235) with new structures and conductor. | 2018-01-10 | 2019-05-15 | 2019-05-15 | 9574929 | 10817000 |  |  | 100 | 138 | 138 | 7.51 mi | 3x1- 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7.51 | n/a | n/a | 25.101 (C)(5)(B)
34 | Bo Beauregard | 1017347 | Mendoza-Colton-Elroy (T397) | Caldwell, Travis | Add circuit breakers at Colton Substation. Add OPGW to (T397) Mendoza - Colton - Elroy. Replace structures that are currently not capable of supporting OPGW. | 2018-02-08 17:00 | 2018-05-18 | 2018-05-18 |  | 8900000 |  |  | 100 | 138 | 138 | 12.9 mi | 3x1- 795 ACSR "Drake" | Concrete Poles, Steel Poles and Wood H-frames | Varies | 12.9 mi | n/a | n/a | 25.101 (C)(5)(B)
35 | Brian Good | 1017387 | Harwood-Luling Double Circuit TL OH Phase 1(T145)(173) ; Luling-Waelder TL Add Phase 2 (T145) | Caldwell, Gonzales | Replace 45 double-circuit lattice tower structures with double circuit steel Poles and add OPGW on (T145/T173) Harwood-Luling and Luling-Waelder | 2018-02-26 | 2019-05-14 | Phase 1: 6/29/2018 Phase 2: 5/14/2019 | $ 2,555,441 (phase 1 & 2) | $ 9.3M (phase 1 & 2) |  |  | Phase 1 - 100 ; Phase 2 - 100 | 138 | 138 | Phase 1 -12.9 mi; Phase 2 - 21.85 | Phase 1 - 3x2- 795 ACSR "Drake"; Phase 2 Drake 795 ACSR & 26/7 & Single | Concrete Poles, Steel Poles & Wood H-frames | 100' Centerline | Phase 1-19.4 mi; Phase 2 - 21.85 mi | n/a | n/a | 25.101 (C)(5)(B)
37 | Tony Rhodes | 1017859 | Clear Springs-Marion TL Addition (419) | Guadalupe | Replace 3 double-circuit lattice tower structures with 3 CREZ F5 lattice dead-end tower structures, Install OPGW, Repair 1 cage/arm member at Structure #88, Install new bundled Drake between new spans between A-Frames and new Towers and between #108A & #108B. | 2018-02-15 08:00 | 2018-11-18 | 2018-11-18 |  | 3446680 |  |  | 100 | 345 | 345 | 8.5 mi | 3x2- 795 ACSR "Drake" | Steel Lattice | 100' Centerline | 8.5 mi | n/a | n/a | 25.101(C)(5)(B)
41 | Bryan Cooley | 1017375 | Fayetteville - Salem TL Storm Hardening (T177/T211/T210) | Austin, Fayette, Washington | Replace bracing on 40 lattice transmission line structures to meet NESC storm hardening requirements | 2018-11-16 | 2019-02-25 | 2019-02-25 | 854229 | 4247676 |  |  | 100 | 138/345 | 138/345 | 19.35 mi | 3x1 - 795 ACSR "Condor" & 3x2 -795 ACSR "Condor" | Steel Lattice | Varies | 19.35 mi | n/a | n/a | 25.101 (C)(5)(B)
42 | Tony Rhodes | 1017856 | San Marcos - Kyle Fiber Build-Out (T322) | Hays | Add OPGW from San Marcos to Canyon | 2018-03-19 | 2018-05-18 | 2018-05-18 | 718484 | 1078863.26 |  |  | 100 | 138 | 138 | 3.46 mi | 2x1- 795 ACSR "Drake" | Steel Poles, Concrete Poles | Varies | 3.46 mi | n/a | n/a | 25.101 (C)(5)(B)
46 | Vicki O'Connor | 1017403 | Sim Gideon-Smithville TL Storm Hardening - (T150) | Bastrop | Increase the reliability of transmission facilities on the Sim Gideon – Smithville 13.8-mile 138-kV transmission line (T150). | 2018-07-17 | 2019-03-18 | 2019-03-18 | 2438690 | 3514428.1 |  |  | 100 | 138 | 138 | 13.8 mi | 795 ACSR Drake | Steel Poles & Hybrid Poles | 80' | 13.8 mi | 80 | 13.8 mi | 25.101 (C)(5)(B)
47 | Tony Rhodes | 1017854 | Fairland-Lago Vista TL Addition (T414) | Travis, Burnett | OPGW add and Tower replacements | 7/15/18 | 2019-03-27 | 2019-03-27 | 4630000 | 7938338 |  |  | 100 | 138 | 138 | 21.38 | 795 CONDOR ACSR/SD | Lattice Towers & Steel Poles | 100' Centerline | 21.38 mi | 100' Centerline | 21.38 mi | 25.101 (C)(5)(B)
48 | Manny Garcia | 1017348 | Cooks Point TL Addition (CCN) | Burleson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2020-10-05 | 2022-01-27 |  | T-Line $ 35.1 - 43.5M ; Substation $ 6.1 - 6.7 M |  |  |  | 0 | 0 | 138 | 17-23 mi | 2x1- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 80' | 17-23 mi | 45838
49 | Martin Lindig | 1016356 | Bellville S-Glidden TL Addition (T113) (Bellville S-Glidden TL Storm Hardening - 1016355) | Austin County/Colorado | Replace eleven (11) lattice tangent tower structures with steel pole structures to meet storm hardening requirements; the existing rating of the transmission circuit will be maintained at 110 MVA. | 2018-08-23 | 2019-09-19 |  | 4900000 | 7916770 |  |  | 85 | 69 | 69 | 31.24 mi | Existing: (1)795 ACSR “Drake” New: Bellville-Str 26 (1)959 ACSS “Suwannee” and Str.27-Glidden (1)795 ACSR “Drake” | Bellville-Str.26 Concrete H-Frame and Steel DE Str. 27-Glidden Steel DE, Lattice Towers, and concrete tangents | 120’ | 31.24 mi | 120’ | 31.24 mi | 25.101 (C)(5)(B)
50 | Tony Rhodes | 1017847 | Coronado-Fairland TL Addition (T110) (LCRA TSC Fiber Build-Out FY18-1017418) | Burnet/Llano | OPGW is being installed and multiple structures are being replaced or repaired to support the added fiber as part of the FY18 Fiber Build Out program. | 2018-08-29 | 2019-05-24 | 2019-05-24 | $3.2M | $5.6M |  |  | 100 | 138 | 138 | 12.41 mi | 795 ACSR CONDOR, 795 ACSR Drake, 72 ct OPGW | Steel lattice, & steel Poles | Varies | 12.41 mi | n/a | n/a | 25.101 (C)(5)(B)
51 | Tony Rhodes | 1017842 | Gillespie-Horseshoe Bay TL Addition (T448) (LCRA TSC Fiber Build-Out FY18-1017418) | Gillespie/Llano | OPGW is being installed and multiple structures are being replaced or repaired to support the added fiber as part of the FY18 Fiber Build Out program. | 2018-08-01 | 2019-05-13 | 2019-05-13 | $4.5M | $7.6M |  |  | 100 | 138 | 138 | 36.43 mi | 795 ACSR Drake, 72 Ct OPGW | Steel lattice | Varies | 36.43 mi | n/a | n/a | 25.101 (C)(5)(B)
52 | Martin Lindig | 1017658 | Burnet-Wirtz TL Overhaul (T218) (Burnet-Wirtz TL Overhaul - 1017657) | Burnet | Structure replacement and add OPGW | 2019-01-04 | 2019-12-19 |  | 3400000 | 2925344.75 |  |  | 10 | 138 | 138 | 16.4 mi | 795 ACSR Drake | Steel & Wood Poles | Varies | 16.4 mi | n/a | n/a | 25.101 (C)(5)(B)
53 | Alfred Mackey | 1016322 | Bellville South - Waller TL Storm Hardening (T213) (Bellville South - Waller TL Storm Hardening - 1016321) | Austin/Waller | Increase reliability and capacity of transmission facilities on Bellville South to Waller | 2018-09-04 | 2019-06-21 | 2019-06-28 | 13162000 | 29066545.24 |  |  | 100 | 138 | 138 | 15.77 mi | 795 ACSR Drake | Concrete & steel Poles | Varies 85' | 15.77 mi | n/a | n/a | 25.101 (C)(5)(B)
54 | Cody McNeil | 1010353 | Bighill to Kendall Bolt Tightening (T558/T559) | Williamson | Inspect each tower to tighten bolts and install designed locking mechanisms | 2018-09-24 | 2018-12-21 | 2018-12-21 |  | 676064 |  |  | 100 | 345 | 345 | 138 mi | Bundled 1926.9 Cumberland | Lattice Towers & Steel Poles | Varies 60' -130' | 138 mi | n/a | n/a | 25.101(C)(5)(B)
55 | Vaibhav Pitale | 1018931 | Flatonia-Moulton South TL Addition (T134) (Shiner Circuit Breaker Addition - 1017402) | Lavaca | Increase transmission service reliability to the Shiner Substation | 2018-10-09 | 2019-02-11 | 2019-02-11 |  | 191071.02 |  |  | 100 | 138 | 138 | 11.1 mi | 795 ACSR Drake | Concrete/Steel Poles | 30',40',45', 60', 100' | 11.1 mi | n/a | n/a | 25.101 (C)(5)(A)
56 | Dave Ilges | 1017830 | North McCamey – LCRA Crane TL Addition (T455) King Mountain Circuit Breaker Addition Addition 1017830) | Upton | LCRA will install three circuit breakers, provide real-time monitoring at King Mountain Substation. | 2018-10-01 | 2019-06-28 | 2019-05-10 | 819692.46 | 1600000 |  |  | 100 | 138 | 138 | 23.08 mi | (2) 795 kcmil ACSR "Drake" | Concrete & steel monoPoles | Centerline, 80' | 23.08 mi | n/a | n/a | 25.101 (C)(5)(A)
57 | Josh Bollich | 1017513 | Airline-Naval Base TL Addition (T475) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-09-24 | 2019-10-08 |  | 178226.25 | 209000 |  |  | 0 | 69 | 138 | 6.39 mi | (1) 795kcmil ACSR/AW "Drake" | Steel Monopole | Centerline, 16' | 6.39 mi | n/a | n/a | 25.101 (C)(5)(D)
58 | Josh Bollich | 1017515 | Airline-Naval Base TL Addition (T476) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-03-28 | 2019-04-16 | 2019-04-16 | 135000 | 173000 |  |  | 100 | 69 | 138 | 7.98 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole | Centerline | 7.98 mi | n/a | n/a | 25.101 (C)(5)(D)
59 | Josh Bollich | 1018756 | Heines-Naval Base TL Addition (T685) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. (Once Heines Substation Addition is complete, the transmission assets on (T476) will be renumbered to T685 Heines - Naval Base) | 2018-10-03 | 2019-10-25 |  | 468085 | 598491.79 |  |  | 60 | 69 | 138 | 5.3 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole | Centerline | 5.3 mi | n/a | n/a | 25.101 (C)(5)(A)
60 | Josh Bollich | 1018755 | Airline-Heines TL Addition (T476) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. | 2018-10-11 | 2019-10-25 |  | 519285 | 853000 |  |  | 60 | 69 | 138 | 2.57 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole | Centerline | 2.57 mi | n/a | n/a | 25.101 (C)(5)(A)
61 | Josh Bollich | 1018663 | RioPecos-HorseCrossing TL Addition (T451/ future T682) | Crane | Provide transmission service to a generator. (This circuit will be added to the open position on the structures on the (T451) Rio Pecos - Crane, after the project is complete the transmission line will be numbered T682 Rio Pecos - Horse Crossing) | 2019-10-20 | 2020-01-09 |  | 952311.92 | 1310978.91 |  |  | 0 | 0 | 138 | 0.76 mi | (2) 795 ACSR Drake | Steel/Concrete MonoPoles | 80' CL | 0.76 mi | n/a | n/a | 25.101 (C)(5)(C)
62 | Michael Griswold | 1019260 | Winchester-Salem T170 TL Addition (T170) (Winchester Autotransformer Addition - 1017413) | Fayette | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-05-15 |  | 749379 | 2153902.77 |  |  | 50 | 138 | 138 | 37.28 mi | (1) 795 kcmil ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100' Centerline | 37.16 mi | n/a | n/a | 25.101 (C)(5)(A)
63 | Michael Griswold | 1017777 | Winchester-Fayetteville TL Addition (T165) (Winchester Autotransformer Addition - 1017413) | Fayette | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-05-15 |  | 1012865.49 | 2392472.59 |  |  | 50 | 138 | 138 | 18.92 mi | (1) 795 kcmil ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100' Centerline | 18.75 mi | n/a | n/a | 25.101 (C)(5)(A)
64 | Brad Wallner | 1017550 | Raymond F Barker-Comfort TL Addition (T121) (Cypress Creek Circuit Breaker Project 1017351) | Lee/Fayette | Acquire 5 acres and expand new LCRA TSC facilities with a three-ring bus configuration. | 2019-03-01 | 2019-05-14 | 2019-05-14 | 230513 | 330000 |  |  | 100 | 138 | 138 | 10.03 mi | 1-795 ACSR "Drake" | Steel MonoPoles | Varies | 10.03 mi | n/a | n/a | 25.101 (C)(5)(A)
65 | Brian Good | 1017495 | Brenham North - Waller TL Addition (T232) (Flood Mitigation - FY2018 System Upgrade 1017378) | Waller, Washington | Reduce flood risk and potential damage to substation equipment | 2019-09-23 | 2019-11-12 |  | 1619269.84 | 2157648 |  |  | 0 | 1.38 | 138 | 12.94 mi | 795 Drake ACSR & 630.0 TYPE 21 ACCS/TW/C7 (BETWEEN #17/1 TO #18/1) | Concrete Poles, Wood H-frame, Steel H-frame | 75' @ single circuit. 85' @ double circuit | 12.94 mi | 75' @ single circuit. 85' @ double circuit | 12.94 mi | 25.101 (C)(5)(B)
66 | Jacob Miller | 1019038 | Plum - La Grange TL Addition (T208) (Riverside Circuit Breaker Addition - 1018925) | Fayette | Increase the reliability of substation equipment at the Riverside Substation. | 2019-01-28 | 2020-02-28 |  | 356355.26 | 1589877 |  |  | 70 | 138 | 138kv | 8.39 mi | 795 ACSR. GA2 Drake. 3/8 EHS. OPGW | Wood H-frame | Undefined Centerline | 5.58 mi | undefined Centerline | 5.58 mi | 25.101 (C)(5)(B)
67 | Seth Delcambre | 1019276 | Harwood-Gonzales (T542) (Gonzales - Harwood TL Overhaul - 1018965) | Gonzales | Increase the reliability and capability of circuit (T542) on Cuero – Luling 53.9-miles of 69-kV transmission line for the 10 miles between City of Gonzales (S31) & Harwood Station (S397). | 2019-04-01 | 2020-02-20 |  | 4350428.5 | 5484500 |  |  | 40 | 69 | 69 (138kV Capable) | 9.97 mi | Single 795 ACSR "Drake" | Concrete & Steel Pole | Blanket, Centerline | 9.97 mi | n/a | n/a | 25.101 (C)(5)(B)
68 | Manny Garcia | 1017695 | North McCamey-Robbns SW TL Addition (T456) (Robbins Switch Circuit Breaker Addition Addition 1017400) | Upton | Provide transmission service to a generator by constructing substation for interconnection. | 2018-10-31 | 2019-05-10 | 2019-05-10 |  | 77017.11 |  |  | 100 | 138kV | 138 | 5.68 mi | 2x 795 Drake ACSR | Concrete Poles | 80' | 5.68 mi | n/a | n/a | 25.101 (C)(5)(A)
69 | Josh Bollich | 1017510 | Tunas Creek - Mesa View TL Addition (T620) (Fourmile Circuit Breaker Addition 1017380) | Pecos | Increase transmission service reliability to the Fourmile Substation (formerly Indian Mesa/Orion/NWP Tap). | 2018-11-27 | 2019-09-30 |  |  | 4679000 |  |  | 65 | 138 | 138 | 11.68 mi | 3x2, 795 kcmil "Drake" | Steel & Concrete Poles | 80' | 11.68 mi | n/a | n/a | 25.101 (C)(5)(B)
70 | Josh Bollich | 1017588 | Tunas Creek-Mesa View SW TL Addition (T620) (Desert Mesa Circuit Breaker Addition 1017353) | Pecos | Increase transmission service reliability to the Desert Mesa Substation (formerly Desert Sky Tap #1). Provide real-time monitoring facilities at the Desert Mesa Substation. Increase the reliability of transmission facilities on the T620 Tunas Creek – Mesa View transmission line. | 2018-10-31 | 2019-05-15 | 2019-05-15 |  | 264333 |  |  | 100 | 138 | 138 | 18.40 mi | 3x2, 795 kcmil "Drake" | Steel & Concrete Poles | 80' | 18.4 mi | n/a | n/a | 25.101 (C)(5)(A)
71 | Michael Griswold | 1019213 | Round Rock TL Relocation (T527, T378) | Williamson | Increase the transmission service reliability to the Round Rock substation and to support the expansion of the substation by Oncor. | 2019-01-07 | 2019-05-07 | 2019-05-07 | 446000 | 1529331.89 |  |  | 100 | 138 | 138 | 5.1 mi | (1) 795 ACSR "Drake" | Steel Lattice, Steel H-Frame | 100' | 5.1 mi | n/a | n/a | 25.101 (C)(5)(B)
72 | Clint Meyer | 1016702 | Altair - Nada TL Addition (T545) (Glidden Area TL Upgrade - 1016219) | Colorado | OPGW (fiber) installation (T545) and Substation upgrade at Nada and Altair substations from 69kV to 138kV | 2018-12-03 | 2019-05-31 | 2019-05-31 | 2312000 | 6688538.17 |  |  | 100 | 69 | 138 | 14.12 mi | 795 Drake ASCR & 26/7 & Single | Steel, Wood, & Lattice | Blanket | 14.12 mi | Blanket | 14.1 mi | 25.101 (C)(5)(B)
73 | Alfred Mackey | 1019321 | Lakeway-Marshall Ford T179 Addition (T179) (Lakeway AE Marshall Ford TL SH - 1019096) | Travis | Increase the reliability of circuit (T179) on the Lakeway (AE) – Marshall Ford 2.4 mile138 kV transmission line. | 2019-01-25 | 2019-06-21 17:00 | 2019-06-21 | 438000 | 3040713.32 |  |  | 100 | 138 | 138 | 2.4 mi | (6x1) 795 ACSR "Drake" | Steel Towers | 100' | 2.4 mi | n/a | n/a | 25.101 (C)(5)(B)
74 | Alfred Mackey | 1019603 | Lakeway-Marshall Ford Fiber Addition (T179) (LCRA Fiber Backbone FY 19 Telecom Upgrade - 1019084) | Travis | LCRA will Install 2.42 miles of 72-count OPGW from Lakeway (AE) to Marshall Ford (T179). | 2019-02-13 | 2019-06-21 08:00 | 2019-06-21 | 392000 | 450000 |  |  | 100 | 138 | 138 | 2.4 mi | (6x1) 795 ACSR "Drake" | Steel Towers | 100' | 2.4 mi | n/a | n/a | 25.101 (C)(5)(B)
75 | Manny Garcia | 1017760 | Warda-Salem TL Addition (T667,T170) (Warda Circuit Breaker Addition - 1017411) | Fayette | Increase reliability of transmission facilities on the (T170) Winchester-Salem 34.8 mile 138kV transmission line. Cut-in to new A-frames at existing Warda Sub and renumber Warda to Salem as (T667). | 2018-12-01 | 2018-12-20 | 2018-12-20 |  | 663000 |  |  | 100 | 138 | 138 | 34.8 mi | Single (1/phase) 795kcmil ACSR "Drake" | Steel monopole | 100' | 34.8 mi | n/a | n/a | 25.101 (C)(5)(B)
76 | Robert Badger | 1019317 | Rockport-Fulton T474 TL Addition (T474) Hurricane Response System Upgrade - 1019095 | Nueces, Aransas | Increase reliability, repair storm damage, & upgrade circuit (T477) on the N Padre Tap-Port Aransas 18.23-mile 69-kV TL and circuit (T474) on the Fulton-Rockport 138-kV 7.36-mile 69-kV TL. | 2019-02-07 | 2019-09-30 |  |  | 852895 |  |  | 65 | 69 | 69 | 7.4 mi | (1x) 795 ACSR/AW Drake | Steel Monopole, Concrete Monopole | Unknown (AEP-owned) | - | - | - | 25.101 (C)(5)(B)
77 | Manny Garcia | 1017557 | Deer Creek-Luling TL Addition (T538) (Darst Creek Circuit Breaker Addition - 1017352) | Guadalupe | Add four 138-kV, 3000A, 40kAIC circuit breakers in a ring bus configuration to Darst Creek substation | 2019-02-22 | 2019-05-23 | 2019-05-23 |  | 717517.4 |  |  | 100 | 69 | 69 | 15.84 mi | Drake 795 ACSR, Single | Concrete & Steel | Blanket | 15.84 mi | Blanket | 15.84 mi | 25.101 (C)(5)(B)
78 | Brian Good | 1017499 | Bastrop West-Sim Gideon TL Addition (T410) (Flood Mitigation - FY2018 System Upgrade - 1017378) | Bastrop | Reduce flood risk and potential damage to substation equipment | 2019-01-04 | 2019-03-08 | 2019-03-08 | 897995.63 | 1400020.01 |  |  | 100 | 138 | 138 | 6.76 mi | Drake 795 ACSR, Single | Steel (New) & Wood H-frame(Existing) | 100' | 100' | 100' | 6.76 mi | 25.101 (C)(5)(B)
79 | Jacob Miller | 1019133 | Rim Rock - Turtle Creek TL Addition (T270) (Rim Rock - Turtle Creek TL Storm Hardening - 1018968) | Kerr | Increase the reliability of circuit (T270) on the Rim Rock - Turtle Creek 7.6 mile 138kV transmission line | 2020-09-16 | 2021-05-05 |  | 6523068.22 | 7002025 |  |  | 0 | 138 | 138 | 7.6 mi | (1x) 795 ACSR Drake | Steel Monopole | 60' , 100' | 7.6 mi | 60, 100 | 7.6 mi | 25.101 (C)(5)(B)
80 | Brad Wallner | 1020430 | Marshall Ford-McNeil TL Addition (T161) (Summit T161 TL Relocation - 1020390) | Travis | Relocation of the Marshall Ford to McNeil 69-kV transmission line (T161) at the Austin Energy Summit Substation. The proposed relocation of the line was requested by Austin Energy to the northern section of Summit Sub. | 2019-03-04 | 2019-11-27 |  | 831439 | 1553000 |  |  | 50 | 69 | 69 | 13.42 mi | Bundled 795 Drake ACSR | Steel Poles | 100' CL | 0.9 mi | n/a | n/a | 25.101 (C)(5)(B)
82 | Brian Good | 1018599 | Bakersfield to Solstice (CCN) (Bakersfield-Solstice TL Addition - 1018599) | Pecos | Construct a new 345-kV transmission line to connect LCRA TSC's existing Bakersfield station and AEP Texas' Solstice Switch Station | 2019-12-20 | 2020-12-23 |  | T-line $148 - $192M; Bakersfield Substation - $6M; Solstice Switch Station - $38M | $78M |  |  | 0 | 0 | 345 | 130-190 mi | 1926.9 kcmil ACSS/Cumberland (LCRA TSC) and 1590 ACSS (AEP Texas) | Double-circuit steel lattice towers | 0 | 0 | 150' | 68 - 92 mi | 48787
83 | Josh Bollich | 1017897 | Culberson-Kunitz TL Addition (T271) (Culberson-KunitzTL Overhaul - 1017896) | Culberson | Structure replacement upgrades to steel and concrete Poles | 2019-05-28 | 2019-09-09 |  | 507000 | 593494 |  |  | 60 | 138 | 138 | 28.88 mi | Linnet; 336kcmil; 0.721” | Wood | 100' | 28.88 mi | n/a | n/a | 25.101 (C)(5)(B)
89 | Robert Badger | 1019319 | N. Padre Tap - Port A. (T-477) (Hurricane Response System Upgrade - 1019095) | Nueces | Increase the reliability, repair storm damage, and upgrade circuit (T477) on the North Padre Tap – Port Aransas 18.23-mile 69-kV transmission line and circuit (T474) on the Fulton – Rockport 138-kV 7.36-mile 69-kV transmission line. | 2019-10-14 | 2019-11-28 |  |  | 3193000 |  |  | 0 | 69 | 69 | 15 mi | 795 ACSS/AW Drake x1 | Steel monopole, Concrete Monopole, Hybrid Steel/Concrete | (AEP-owned) | NA | n/a | n/a | 25.101 (C)(5)(B)
90 | Robert Badger | 1019337 | Elroy - Wolf Lane (T-582) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-03-18 | 2019-05-13 | 2019-05-13 | 31898000 | 1317604 |  |  | 100 | 138 | 138 | 3.78 mi | 795 Drake ACSR GA2 | Wood H-frame, LD Steel H-frame, Steel Pole, Tower | 100' | 3.78 mi | n/a | n/a | 25.101 (C)(5)(B)
91 | Robin Mims | 1020260 | Red Creek-Amos Creek TL Addition (T424) (Amos Creek Substation Addition - 1020230) | Concho | Transmission line cute-in to provide transmission service to a generator. | 2019-10-15 | 2020-04-22 |  | 1737273 | 1833576.23 |  |  | 0 | 345 | 345 | 49 mi | 1590 ACSR Falcon x2 | Steel Lattice tower | 100' | 49 mi | n/a | n/a | 25.101 (C)(5)(B)
92 | Robert Badger | 1019327 | Austrop-Garfield (T182) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-04-15 | 2019-11-22 |  | 31898000 | 3820639.2313 |  |  | 65 | 345 | 345 | 8.33 mi | Bundled 795 ACSR "Drake" | Lattice Tower | 170' Centerline | 8.33 mi | n/a | n/a | 25.101 (C)(5)(B)
93 | Robert Badger | 1019374 | Marshal Ford - McNeil T161 TL Addition (T161) (Marshall Ford-McNeil TL Relocation - 1019212) | Travis | Increase transmission service reliability to the Austin Energy Hamilton Substation. | 2019-05-01 | 2019-06-12 | 2019-06-12 | 951759 | 1754446.45 |  |  | 100 | 69 | 69 | 13.4 mi | 4/0 & 795 kcmil ACSR | Lattice Towers & Steel Poles | 100' | 13.4 mi | n/a | n/a | 25.101 (C)(5)(B)
94 | Bryan Cooley | 1017655 | Winchester-Salem TL Addition (T170) (T667) (Salem-Winchester T170 TL OH - 1017654) | Fayette | Increase the reliability and capability of circuit T170 on the Salem - Winchester 37.16-mile 138-kV transmission line. | 2019-06-17 | 2020-02-26 |  | 5700000 | 5749000 |  |  | 19 | 138 | 138 | 37.18 | 795 ACSR Drake (single) | Wood H-frame, Steel Lattice, Steel Monopole | Varies | 37.18 mi | n/a | n/a | 25.101 (C)(5)(B)
95 | Tony Rhodes | 1021300 | Granite Mountain – Marble Fall TL Upgrade [Marble Falls Double Circuit TL Upgrade - 1020559] | Burnet | Increase the reliability of transmission facilities on the T195 Granite Mountain – Marble Falls 4.1-mile 138-kV transmission line | 2019-10-09 | 2020-03-20 |  |  | 3295621.32 |  |  | 0 | 138 | 138 | 4.08 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies 80' - 100' | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
96 | Robin Mims | 1016579 | Fair Oaks Ranch - Esparanza TL Addition (T503) [Esperanza Substation Addition - 1016187] | Kendall | LCRA TSC will build a 138kV substation and cut-in T503 to provide transmission/ metering services and real-time monitoring facilities | 2019-09-06 | 2019-11-11 |  |  | 1053522.44 |  |  | 0 | 138 | 138 | 8.25 | Single 795 kcmil ACSR | Steel Poles | 100' | 8.11 | 80' | 8.25 | 25.101 (C)(5)(B)
97 | Bo Beauregard | 1016745 | Flatonia-Hallettsville TL Addition (T132) [Flatonia - Hallettsville TL Upgrade - 1016188] | Fayette, Lavaca | Upgrade the capacity of the 18.7 mile Flatonia-Hallettsville 138-kV transmission line from 128 MVA to 380 MVA using 959 ACSS Suwannee conductors and OPGW | 2019-09-27 | 2020-05-14 |  |  | 9338490 |  |  | 0 | 138 | 138 | 18.68 | Single 959.6 kcmil ACSS/TW | Wood H-frame & Steel Poles | 100' | 18.68 | 100' | 18.68 | 25.101 (C)(5)(B)
98 | Brad Wallner | 1017708 | Geronimo-Seguin TL Addition T499 [Jim Briley Substation Addition - 1017404] | Guadalupe | LCRA TSC will construct a new 138-kV substation between the Geronimo Substation and Seguin Substation. LCRA TSC will extend (T-499) Geronimo to Seguin 138-kV transmission line for approximately 500 feet in and out of the Strempel Substation to terminate on A-frame structures at the substation. | 2019-09-16 08:00 | 2019-10-28 17:00 |  |  | 887000 |  |  | 0 | 138 | 138 | 2.79 | 1433.6 kcmil ACSS/TW | DC Concrete Poles | 100' | 2.79 mi | n/a | n/a | 25.101 (C)(5)(B)
99 | Seth Delcambre | 1019301 | Kendall-Comfort T243 TL AddAddition (T243) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-mile 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-mile 138-kV transmission circuit (T243) | 2019-09-01 | 2020-05-18 17:00 |  |  | 4784350.08 |  |  | 0 | 138 | 138 | 1.08 mi | Bundled 959.6 SUWANNEE ACSS/TW | Steel Single Poles/ Tower/ Steel H-frame | 100' | 1.08 mi | n/a | n/a | 25.101 (C)(5)(B)
100 | Seth Delcambre | 1019303 | BoerneCico-Comfort T148 TL Addition (T148) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-mile 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-mile 138-kV transmission circuit (T243) | 2019-10-01 | 2020-05-11 17:00 |  |  | 4415710.33 |  |  | 0 | 138 | 138 | 16.93 mi | Bundled 795 DRAKE ACSR | Steel Single Poles | 100' | 16.93 mi | n/a | n/a | 25.101 (C)(5)(B)
101 | Seth Delcambre | 1018934 | Fayetteville - Winchester TL Upgrade (T165) [Fayetteville-Winchester TL Upgrade - 1018933] | Fayette | Increase capacity and capability of circuit T165 on the Fayetteville – Winchester 138-kV upgrade | 2019-09-01 | 2020-06-23 |  |  | 14670055.92 |  |  | 0 | 138 | 138 | 18.9 mi | 1433 kcmil ACSS/TW Merrimack | steel monopoles | 100' | 18.9 mi | n/a | n/a | 25.101 (C)(5)(B)
102 | Martin Lindig | 1019122 | T155 Giddings - Lyle Wolz Addition (T155) [Lexington CB Addition - 1018914] | Lee | Add two new structures to accommodate substation expansion. Increase transmission service reliability to the Lexington Substation. | 2019-08-12 | 2019-12-26 |  |  | 625546 |  |  | 5 | 138 | 138 | 21 mi | 795 ASCR | steel monopoles | 100' | 21 mi | n/a | n/a | 25.101 (C)(5)(B)
103 | Michael Griswold | 1017394 | Mountain Home TL Addition (CCN) | Kerr, Gillespie, Kimble | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2021-04-14 | 2022-12-27 17:00 |  | T-line $46.5 - $58.5M; Substation $7.1 - $7.5M |  |  |  | 0 | 0 | 138 | 21-29 mi | 795 Kcmil 26/7 ACSR “Drake” | tbd; steel or concrete poles | 0 | 0.00 MI | varies; 100' | 21-29 mi | 49523
104 | Bo Beauregard | 1021664 | Rim Rock-Jack Furman TL Add (T381) [Flood Mitigation - 1021663] | Kerr | Replace structure 38 on T381 due to storm water erosion. | 2019-11-04 | 2019-11-15 |  | 181000 |  |  |  | 0 | 138 | 138 | 5.689 | 336.4 ACSR (26/7) “Linnet”/ Single | Steel Monopoles & Tower | 60' | 5.689 | n/a | n/a | 25.101 (C)(5)(B)
105 | Bryan Cooley | 1019026 | Fayetteville - Glidden TL Addittion (T176) [Fayette Area TL Upgrades - 1018913] | Fayette, Colorado | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) | 2019-09-20 | 2020-05-15 |  | 8708509.35 |  |  |  | 0 | 138 | 138 | 20.02 | Single 959.6 ACSS/TW Suwannee & Single OPGW (AFL DNO-11243) Static | Steel Monopoles, Hybrid H-Frames | 100' | 20 | n/a | n/a | 25.101 (C)(5)(B)
106 | Robin Mims | 1020270 | Amos Creek-Bow Wood TL Add (T709) [Amos Creek Substation Addition - 1020230 ] | Concho, Tom Green | Provide transmission service to a generator | 2019-10-15 | 2020-02-05 |  | 211644.52 |  |  |  | 0 | 138 | 138 | 49.33 | (2x) - 1590 kcmil ACSR Falcon | Steel Lattice, Steel monopole | 160 | 49.33 | n/a | n/a | 25.101 (C)(5)(B)
107 | Robert Badger | 1019325 | McNeil - Gilleland Creek (T147) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-09-23 | 2019-12-20 |  | 642000 |  |  |  | 0 | 138 | 138 | 7.62 | 1433.6 ACSS/TW "MERRIMACK" / Single | Steel Monopoles & Tower | 100' | 7.62 | n/a | n/a | 25.101 (C)(5)(B)
108 | Robert Badger | 1019431 | Paige - Winchester TL Addition (T615) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Bastrop | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-09-16 | 2019-12-20 |  | 1449231.7284 |  |  |  | 0 | 138 | 138 | 14.85 | Bundled Linnit and Single Drake | Steel Mono Pole, Wood H-Frames, Concrete # Poles | 100 | 14.85 | n/a | n/a | 25.101 (C)(5)(B)
109 | Robert Badger | 1019335 | Wells Branch - Round Rock (T527) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis, Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-09-16 | 2019-12-20 |  | 385406.9994 |  |  |  | 0 | 138 | 138 | 5.28 | (2) 795 KCMIL ACSR/GA2 “DRAKE” | Steel/concrete Pole, Concrete H-Frame | 100' | 5.28 | n/a | n/a | 25.101 (C)(5)(B)
110 | Michael Griswold | 1017767 | Sim Gideon-Winchester TL Addition (T152) [Winchester Autotransformer Additions - 1017413] | Bastrop | LCRA TSC will install a new autotransformer capacity, add new strucutures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 2013964.12 |  |  |  | 0 | 138 | 138 | 20.74 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (75ft & 100ft) | 20.74 | Varies (75ft & 100ft) | 20.84 | 25.101 (C)(5)(B)
111 | Michael Griswold | 1017769 | Smithville-Winchester TL Addition (T175) [Winchester Autotransformer Additions - 1017413] | Bastrop | LCRA TSC will install a new autotransformer capacity, add new strucutures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 643444.51 |  |  |  | 0 | 138 | 138 | 15.1 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (80ft & 100ft) | 15.1 | Varies (80ft, 100ft, Aerials to 180ft) | 14.7 | 25.101 (C)(5)(B)
112 | Michael Griswold | 1017771 | Winchester - Piney Creek TL Addition (T186) [Winchester Autotransformer Additions - 1017413] | Fayette | LCRA TSC will install a new autotransformer capacity, add new strucutures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 562421.39 |  |  |  | 0 | 138 | 138 | 1.38 | Single 1433.6 54/19 ACSR/TW Merrimack/TW | Lattice Towers & Steel Poles | 100ft | 1.38 | 100ft | 1.59 | 25.101 (C)(5)(B)
113 | Michael Griswold | 1017773 | Winchester - Giddings TL Addition (T222) [Winchester Autotransformer Addition - 1017413] | Bastrop | LCRA TSC will install a new autotransformer capacity, add new strucutures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 774103.46 |  |  |  | 0 | 138 | 138 | 10.51 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (75ft & 100ft) | 10.51 | Varies (75ft, 100ft) | 10.68 | 25.101 (C)(5)(B)
114 | Michael Griswold | 1017775 | Paige-Winchester TL Addition (T615) [Winchester Autotransformer Additions - 1017413] | Lee | LCRA TSC will install a new autotransformer capacity, add new strucutures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 807090.7 |  |  |  | 0 | 138 | 138 | 14.83 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | 100ft CL | 14.83 | 100ft CL | 15.09 | 25.101 (C)(5)(B)
115 | Dave Ilges | 1018759 | Crane-Rio Pecos TL Add (T451) Castle Mountain Substation Addition - 1018744 | Upton, Crane | Cut-in T451 to a new substation, Provide transmission service (new Castle Mountain substation) for Solar Prime LLC. | 2019-09-05 | 2020-06-12 |  | 2746880.16 |  |  |  | 0 | 138 | 138 | 0.044 | Bundled 795 ACSR Drake, Single 3/8 EHS Static & Single DNO-11243 OPGW | Steel Monopole Dead End | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
116 | Jacob Miller | 1017649 | LaGrange - FPP 138kV TL Addition (T263) [FPP 138kV - La Grange TL Overhaul - 1017648] | Fayette | Increase the reliability and capability of circuit T263 on the FPP 138kV – La Grange 7.9-mile 138-kV transmission line | 2020-01-24 | 2020-03-20 |  | 1520674.1957 |  |  |  | 0 | 138 | 138 | 7.89 | Single 795 ACSR Drake & 2 OPGW (AFL DNO-11243) & (ALCOA 52 OPT-GW) | Steel Monopole Dead Ends, Wooden H-Frame Tangents | 100' | 7.8 | n/a | n/a | 25.101 (C)(5)(B)
117 | Robert Badger | 1019333 | Round Rock - Chief Brady (T378) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-11-04 | 2020-01-10 |  | 469500 |  |  |  | 0 | 138 | 138 | 1.2 | (1) 795 ACSR/GA2 "Drake"; RR AF to #55B has (2) 959 ACSS/TW HS "Suwannee" | steel H-frame, steel lattice | 100' CL | 1.2 | n/a | n/a | 25.101 (C)(5)(B)
118 | Robert Badger | 1019329 | Chief Brady - Georgetown (T355) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2020-01-13 | 2020-02-28 |  | 960000 |  |  |  | 0 | 138 | 138 | 3.17 | (1) 795 ACSR/GA2 "Drake" | Steel Lattice and pole, Steel H-Frame | 100' | 3.0 | n/a | n/a | 25.101 (C)(5)(B)
119 | Robert Badger | 1019339 | Georgetown - Rivery (T597) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2020-04-30 | 2020-05-26 |  | 1367300 |  |  |  | 0 | 138 | 138 | 5.1 | (1) 795 ACSR/GA2 "Drake" | steel H-frame, concrete pole, steel pole | 50' CL, blanket | 5.10 | n/a | n/a | 25.101 (C)(5)(B)