## WETT
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
Farmland | Long Draw Substation Farmland Expansion | Borden County | Expand Long Draw station footprint to add Bay 7 to allow connection of a 345 kV line coming from Sharyland's "Farmland" station | 2018-06-05 |  | 2018-10-26 | 3130000 | 3135000 |  |  | 99 | 345 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Sub. Rule 25.83(a)(3)
LDSolar | Long Draw Solar Station to Long Draw Switching Station Transmission Line Project | Borden County | This project is to construct the new single-circuit 138 kV transmission line connecting the Long Draw Solar Collector Station to the Long Draw Switching Station | 2019-10-31 | 2020-05-31 |  | 14587478 |  |  |  | 0 | n/a | 138 | 1.8 | 959 kcmil ACSS/TW Suwannee | Steel Monopoles | n/a | n/a | 100 | 1.8 | 49238 | CCN application Notice of Approval filed on 06/18/19
Solar Nova | Solar Nova Project | Kent County | New 345/138 Nova Prime station to be connected to the existing Cottonwood to Dermott 345 kV line | 2019-10-31 | 2021-03-31 |  | 23514208 |  |  |  | 0 | 345 | 345/138 | 0.7 miles at 138 kV | 959 kcmil ACSS/TW Suwannee | Steel Monopoles | n/a | n/a | 100 | 0.7 | Sub. Rule 25.83(a)(3)