## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
TPSU.17.006392 | Stillman Substation and Interconnect Line | Cameron County | New 138 kV substation and transmission line connection with Palmito substation | 2017-01-17 |  |  |  | 12918462 |  |  | 97 | 138 | na | 0.21 | 954 kcmil All Aluminum Conductor (AAC) "Magnolia"; Single Circuit | Concrete or Steel Monopole | 150 | 0.03 | 80 | 0.1 | 25.101(c)(2) 25.101(c)(5)(A)
TPSU.18.006402 | Taylor Substation Upgrade | Hidalgo County | Upgrade line protection relays per AEP request | 2018-06-01 |  |  |  | 300000 |  |  | 76 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(2)
TPSU.18.006401 | Bentsen Substation Upgrade | Hidalgo County | Upgrade line protection relays per AEP request | 2018-06-20 |  |  |  | 300000 |  |  | 76 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(2)
TPSU.18.006423 | Railroad Substation Upgrade | Hidalgo County | Replace aging transformer and upgrade the protection and control infrastructure | 2018-09-05 |  | 2019-04-24 |  | 4000000 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(2) | Awaiting final costs.

## Cost Analysis - TPSU.15.006050 (hidden)
Project No.: | TPSU.15.006050
Project Name: | Bay Additions for Windmill Phase 1 Upgrade
PUC Docket No.: | 45622
2016-10-13
| Estimated Cost Included in Final Order | Estimated Cost at Construction Start | Final Cost
Substation
ROW & Land Acquisition | 0 | 0 | 0
Route Development / CCN Acquisition | 0 | 0 | 0
Engineering & Design - Utility | 0 | 0 | 0
Engineering & Design - Contract | 201162.33 | 201162.33 | 236633.43
Material & Equipment Procurement | 1485537.96 | 1485537.96 | 1022384.35
Construction of Facilities - Utility | 25612.72 | 25612.72 | 0
Construction of Facilities - Contract | 1023655.18 | 1023655.18 | 1113633.66
Other | 64031.81 | 64031.81 | 84879.76
TOTAL | 2800000 | 2800000 | 2457531.2
| 0 | 0 | 0
| 2800000 | 2800000 | 2457531.2
Cost Variance |  | 0% | -12.23%
Cost Analysis - Material costs were lower than projected which resulted in the -12% variance between the project estimate and the final project cost.