## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
W.O. #1405221 | Mustang Prairie to Weldon 138 kV Transmission Line Dkt 45247 | Houston County | New 138 kV transmission line from existing HCEC Mustang Prairie Substation to the new HCEC Weldon Substation | 2016-09-01 | 2018-10-31 | 2019-02-14 | $15,526,800 T-Line; $3,418,000 Substation |  |  |  | 90 | na | 138 | 13.62 | 795 kcmil ACSR 26/7 "Drake" | Single pole, 85-115 ft, steel/concrete | na | na | 100 | 13.62 | 45247 | CCN Amendment Final Order Issued by PUCT on 7-20-16. Construction cleanup in progress.