## MCPR Oct. 2019
MCPR Row Number | Project Manager | Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number
2 | Bo Beauregard | 1010656 | Blumenthal TL Addition (T637) | Gillespie, Kendall, Blanco | Construct a new 138-kV transmission line connecting the new Blumenthal (CTEC) Substation to a tap point on the Kendall - Mountain Top 138-kV transmission line (T342). | 2017-10-02 08:00 | 2018-05-18 | 2018-05-18 | $21,536,000 T-line; $3,936,000 Substation; $1,634,000 Tap | $21,510,000 T-line; $4,146,000 Substation; $1,836,000 Tap |  |  | 100 | 0 | 138 | 14.4 | 3x1-795 ACSR "Drake" | Poles & H-Frames | 0 | 0 | 100' | 14.4 | 43599
4 | Martin Lindig | 1015208 | Zorn-Marion 345kV TL Addition (CCN - Docket No. 45601) | Guadalupe | Construct a new 345-kV transmission line to provide a transmission point of interconnection between Central Texas and San Antonio area. | 2018-06-01 08:00 | 2019-05-30 | 2019-05-30 | T-Line $43.26 - 55.11 M ; Substation $7,905,000 | 46000000 |  |  | 100 | 0 | 345 | 18-24 mi | 3x2-959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7-11 mi |  | 10 - 14 mi | 45601
5 | Ellie Ross | 1014910 | TXDOT US 83 Relief Route Rio Grande City-La Grulla (T485) | Starr | Modify existing transmission line (T485), Rio Grande City-La Grulla, to accommodate road expansion by TXDOT. | 2018-11-09 | 2018-11-30 | 2018-11-30 | 220000 | 317464 |  |  | 100 | 138 | 138 | 31.66 | 3x1-795 ACSR/AW "Drake/AW" | Steel Poles | Varies | 31.66 | n/a | n/a | 25.101 (C)(5)(B)
7 | Michael Griswold | 1014352 | Leander - Round Rock TL Addition (CCN) | Williamson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to two load-serving substations | 2019-01-02 | 2020-04-03 |  | T-Line $ 67.8 - 99.6 M ; Substations $ 14.9 - 17.4 M |  |  |  | 61 | 0 | 138 | 11-22 mi | 3x2- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 60' -100' | 11-22 mi | 45866
16 | Brian Good | 1017026 | Manor-Cedar Hills TL Addition (T495) Phase 1 (Flood Remediation Substation Upgrade – 1016539) | Travis | On T495 remove (structure #112) concrete pole and replace with two concrete Poles. | 2017-07-05 | 2017-10-28 | 2017-10-19 | 387000 | 197611.21 |  |  | 100 | 138 | 138 | 8.21 mi | 3x1-795 ACSR "Drake" | Concrete Poles, Steel Poles & Lattice Tower | 100' | 8.21 mi | n/a | n/a | 25.101(C)(5)(B)
27 | Brian Good | 1017998 | Hamilton Road - Uvalde Fiber Addition (T570), (T624) & (T464) | Val Verde, Kinney, Uvalde | Replace 25 structures to support new OPGW | 2018-01-29 | 2019-03-10 | 2019-03-10 |  | 9391760 |  |  | 100 | 138 | 138 | 70.6 mi | 3x1-ACSS "Drake" | Steel Poles | Varies | 70.6 mi | n/a | n/a | 25.101 (C)(5)(B)
28 | Tony Rhodes | 1017838 | Kendall - Fredericksburg TL Fiber Build Out (T120) | Kendall, Gillespie | Replace static arm on 70 H-frame structures, install 1 new steel dead-end pole, and install 2 new guyed wood h-frames to support new OPGW | 2018-04-16 08:00 | 2018-06-28 17:00 | 2018-06-19 |  | 2577512.25 |  |  | 100 | 138 | 138 | 20.55 mi | 3x1- 795 ACSR "Drake" | Wood H-Frames, Single Pole Wood DE | Centerline | 20.55 mi | n/a | n/a | 25.101 (C)(5)(B)
33 | Bo Beauregard | 1015116 | Henne-Comal TL Upgrade (T235) | Comal | Rebuild the existing 138kV transmission line (T235) with new structures and conductor. | 2018-01-10 | 2019-05-15 | 2019-05-15 | 9574929 | 10817000 |  |  | 100 | 138 | 138 | 7.51 mi | 3x1- 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7.51 | n/a | n/a | 25.101 (C)(5)(B)
34 | Bo Beauregard | 1017347 | Mendoza-Colton-Elroy (T397) | Caldwell, Travis | Add circuit breakers at Colton Substation. Add OPGW to (T397) Mendoza - Colton - Elroy. Replace structures that are currently not capable of supporting OPGW. | 2018-02-08 17:00 | 2018-05-18 | 2018-05-18 | 8900000 | 4900000 |  |  | 100 | 138 | 138 | 12.9 mi | 3x1- 795 ACSR "Drake" | Concrete Poles, Steel Poles and Wood H-frames | Varies | 12.9 mi | n/a | n/a | 25.101 (C)(5)(B)
35 | Brian Good | 1017387 | Harwood-Luling Double Circuit TL OH Phase 1(T145)(173) ; Luling-Waelder TL Add Phase 2 (T145) | Caldwell, Gonzales | Replace 45 double-circuit lattice tower structures with double circuit steel Poles and add OPGW on (T145/T173) Harwood-Luling and Luling-Waelder | 2018-02-26 | 2019-05-14 | Phase 1: 6/29/2018 Phase 2: 5/14/2019 | $ 2,555,441 (phase 1 & 2) | $ 9.3M (phase 1 & 2) |  |  | Phase 1 - 100 ; Phase 2 - 100 | 138 | 138 | Phase 1 -12.9 mi; Phase 2 - 21.85 | Phase 1 - 3x2- 795 ACSR "Drake"; Phase 2 Drake 795 ACSR & 26/7 & Single | Concrete Poles, Steel Poles & Wood H-frames | 100' Centerline | Phase 1-19.4 mi; Phase 2 - 21.85 mi | n/a | n/a | 25.101 (C)(5)(B)
37 | Tony Rhodes | 1017859 | Clear Springs-Marion TL Addition (419) | Guadalupe | Replace 3 double-circuit lattice tower structures with 3 CREZ F5 lattice dead-end tower structures, Install OPGW, Repair 1 cage/arm member at Structure #88, Install new bundled Drake between new spans between A-Frames and new Towers and between #108A & #108B. | 2018-02-15 08:00 | 2018-11-18 | 2018-11-18 |  | 3446680 |  |  | 100 | 345 | 345 | 8.5 mi | 3x2- 795 ACSR "Drake" | Steel Lattice | 100' Centerline | 8.5 mi | n/a | n/a | 25.101(C)(5)(B)
41 | Bryan Cooley | 1017375 | Fayetteville - Salem TL Storm Hardening (T177/T211/T210) | Austin, Fayette, Washington | Replace bracing on 40 lattice transmission line structures to meet NESC storm hardening requirements | 2018-11-16 | 2019-02-25 | 2019-02-25 | 854229 | 4247676 | 4292054.99 | 1.045% | 100 | 138/345 | 138/345 | 19.35 mi | 3x1 - 795 ACSR "Condor" & 3x2 -795 ACSR "Condor" | Steel Lattice | Varies | 19.35 mi | n/a | n/a | 25.101 (C)(5)(B)
42 | Tony Rhodes | 1017856 | San Marcos - Kyle Fiber Build-Out (T322) | Hays | Add OPGW from San Marcos to Canyon | 2018-03-19 | 2018-05-18 | 2018-05-18 | 718484 | 1078863.26 |  |  | 100 | 138 | 138 | 3.46 mi | 2x1- 795 ACSR "Drake" | Steel Poles, Concrete Poles | Varies | 3.46 mi | n/a | n/a | 25.101 (C)(5)(B)
46 | Vicki O'Connor | 1017403 | Sim Gideon-Smithville TL Storm Hardening - (T150) | Bastrop | Increase the reliability of transmission facilities on the Sim Gideon – Smithville 13.8-mile 138-kV transmission line (T150). | 2018-07-17 | 2019-03-18 | 2019-03-18 | 2438690 | 3514428.1 |  |  | 100 | 138 | 138 | 13.8 mi | 795 ACSR Drake | Steel Poles & Hybrid Poles | 80' | 13.8 mi | 80 | 13.8 mi | 25.101 (C)(5)(B)
47 | Tony Rhodes | 1017854 | Fairland-Lago Vista TL Addition (T414) | Travis, Burnett | OPGW add and Tower replacements | 7/15/18 | 2019-03-27 | 2019-03-27 | 4630000 | 7938338 |  |  | 100 | 138 | 138 | 21.38 | 795 CONDOR ACSR/SD | Lattice Towers & Steel Poles | 100' Centerline | 21.38 mi | 100' Centerline | 21.38 mi | 25.101 (C)(5)(B)
48 | Manny Garcia | 1017348 | Cooks Point TL Addition (CCN) | Burleson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2020-10-05 | 2022-01-27 |  | T-Line $ 35.1 - 43.5M ; Substation $ 6.1 - 6.7 M |  |  |  | 0 | 0 | 138 | 17-23 mi | 2x1- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 80' | 17-23 mi | 45838
49 | Martin Lindig | 1016356 | Bellville S-Glidden TL Addition (T113) (Bellville S-Glidden TL Storm Hardening - 1016355) | Austin County/Colorado | Replace eleven (11) lattice tangent tower structures with steel pole structures to meet storm hardening requirements; the existing rating of the transmission circuit will be maintained at 110 MVA. | 2018-08-23 | 2019-09-20 | 2019-09-20 | 4900000 | 7916770 |  |  | 100 | 69 | 69 | 31.24 mi | Existing: (1)795 ACSR “Drake” New: Bellville-Str 26 (1)959 ACSS “Suwannee” and Str.27-Glidden (1)795 ACSR “Drake” | Bellville-Str.26 Concrete H-Frame and Steel DE Str. 27-Glidden Steel DE, Lattice Towers, and concrete tangents | 120’ | 31.24 mi | 120’ | 31.24 mi | 25.101 (C)(5)(B)
50 | Tony Rhodes | 1017847 | Coronado-Fairland TL Addition (T110) (LCRA TSC Fiber Build-Out FY18-1017418) | Burnet/Llano | OPGW is being installed and multiple structures are being replaced or repaired to support the added fiber as part of the FY18 Fiber Build Out program. | 2018-08-29 | 2019-05-24 | 2019-05-24 | $3.2M | $5.6M |  |  | 100 | 138 | 138 | 12.41 mi | 795 ACSR CONDOR, 795 ACSR Drake, 72 ct OPGW | Steel lattice, & steel Poles | Varies | 12.41 mi | n/a | n/a | 25.101 (C)(5)(B)
51 | Tony Rhodes | 1017842 | Gillespie-Horseshoe Bay TL Addition (T448) (LCRA TSC Fiber Build-Out FY18-1017418) | Gillespie/Llano | OPGW is being installed and multiple structures are being replaced or repaired to support the added fiber as part of the FY18 Fiber Build Out program. | 2018-08-01 | 2019-11-30 | 2019-05-13 | $4.5M | $7.9M |  |  | 98 | 138 | 138 | 36.43 mi | 795 ACSR Drake, 72 Ct OPGW | Steel lattice | Varies | 36.43 mi | n/a | n/a | 25.101 (C)(5)(B)
52 | Martin Lindig | 1017658 | Burnet-Wirtz TL Overhaul (T218) (Burnet-Wirtz TL Overhaul - 1017657) | Burnet | Structure replacement and add OPGW | 2019-01-04 | 2019-12-19 |  | 3400000 | 2925344.75 |  |  | 33 | 138 | 138 | 16.4 mi | 795 ACSR Drake | Steel & Wood Poles | Varies | 16.4 mi | n/a | n/a | 25.101 (C)(5)(B)
53 | Alfred Mackey | 1016322 | Bellville South - Waller TL Storm Hardening (T213) (Bellville South - Waller TL Storm Hardening - 1016321) | Austin/Waller | Increase reliability and capacity of transmission facilities on Bellville South to Waller | 2018-09-04 | 2019-06-21 | 2019-06-28 | 13162000 | 29066545.24 |  |  | 100 | 138 | 138 | 15.77 mi | 795 ACSR Drake | Concrete & steel Poles | Varies 85' | 15.77 mi | n/a | n/a | 25.101 (C)(5)(B)
54 | Cody McNeil | 1010353 | Bighill to Kendall Bolt Tightening (T558/T559) | Williamson | Inspect each tower to tighten bolts and install designed locking mechanisms | 2018-09-24 | 2018-12-21 | 2018-12-21 |  | 676064 |  |  | 100 | 345 | 345 | 138 mi | Bundled 1926.9 Cumberland | Lattice Towers & Steel Poles | Varies 60' -130' | 138 mi | n/a | n/a | 25.101(C)(5)(B)
55 | Vaibhav Pitale | 1018931 | Flatonia-Moulton South TL Addition (T134) (Shiner Circuit Breaker Addition - 1017402) | Lavaca | Increase transmission service reliability to the Shiner Substation | 2018-10-09 | 2019-02-11 | 2019-02-11 |  | 191071.02 |  |  | 100 | 138 | 138 | 11.1 mi | 795 ACSR Drake | Concrete/Steel Poles | 30',40',45', 60', 100' | 11.1 mi | n/a | n/a | 25.101 (C)(5)(A)
56 | Dave Ilges | 1017830 | North McCamey – LCRA Crane TL Addition (T455) King Mountain Circuit Breaker Addition Addition 1017830) | Upton | LCRA will install three circuit breakers, provide real-time monitoring at King Mountain Substation. | 2018-10-01 | 2019-06-28 | 2019-05-10 | 819692.46 | 1600000 |  |  | 100 | 138 | 138 | 23.08 mi | (2) 795 kcmil ACSR "Drake" | Concrete & steel monopoles | Centerline, 80' | 23.08 mi | n/a | n/a | 25.101 (C)(5)(A)
57 | Josh Bollich | 1017513 | Airline-Naval Base TL Addition (T475) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-09-24 | 2019-09-30 | 2019-09-30 | 178226.25 | 209000 |  |  | 100 | 69 | 138 | 6.39 mi | (1) 795kcmil ACSR/AW "Drake" | Steel Monopole | Centerline, 16' | 6.39 mi | n/a | n/a | 25.101 (C)(5)(D)
58 | Josh Bollich | 1017515 | Airline-Naval Base TL Addition (T476) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-03-28 | 2019-04-16 | 2019-04-16 | 135000 | 173000 |  |  | 100 | 69 | 138 | 7.98 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole | Centerline | 7.98 mi | n/a | n/a | 25.101 (C)(5)(D)
59 | Josh Bollich | 1018756 | Heines-Naval Base TL Addition (T685) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. (Once Heines Substation Addition is complete, the transmission assets on (T476) will be renumbered to T685 Heines - Naval Base) | 2018-10-03 | 2019-10-25 |  | 468085 | 598491.79 |  |  | 60 | 69 | 138 | 5.3 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole | Centerline | 5.3 mi | n/a | n/a | 25.101 (C)(5)(A)
60 | Josh Bollich | 1018755 | Airline-Heines TL Addition (T476) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. | 2018-10-11 | 2019-10-25 |  | 519285 | 853000 |  |  | 60 | 69 | 138 | 2.57 mi | (1) 795 kcmil ACSR/AW "Drake" | Steel Monopole | Centerline | 2.57 mi | n/a | n/a | 25.101 (C)(5)(A)
61 | Josh Bollich | 1018663 | RioPecos-HorseCrossing TL Addition (T451/ future T682) | Crane | Provide transmission service to a generator. (This circuit will be added to the open position on the structures on the (T451) Rio Pecos - Crane, after the project is complete the transmission line will be numbered T682 Rio Pecos - Horse Crossing) | 2019-10-20 | 2021-01-21 |  | 952311.92 | 1310978.91 |  |  | 0 | 0 | 138 | 0.76 mi | (2) 795 ACSR Drake | Steel/Concrete Monopoles | 80' CL | 0.76 mi | n/a | n/a | 25.101 (C)(5)(C)
62 | Michael Griswold | 1019260 | Winchester-Salem T170 TL Addition (T170) (Winchester Autotransformer Addition - 1017413) | Fayette | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-05-15 |  | 749379 | 2153902.77 |  |  | 63 | 138 | 138 | 37.28 mi | (1) 795 kcmil ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100' Centerline | 37.16 mi | n/a | n/a | 25.101 (C)(5)(A)
63 | Michael Griswold | 1017777 | Winchester-Fayetteville TL Addition (T165) (Winchester Autotransformer Addition - 1017413) | Fayette | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-05-15 |  | 1012865.49 | 2392472.59 |  |  | 63 | 138 | 138 | 18.92 mi | (1) 795 kcmil ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100' Centerline | 18.75 mi | n/a | n/a | 25.101 (C)(5)(A)
64 | Brad Wallner | 1017550 | Raymond F Barker-Comfort TL Addition (T121) (Cypress Creek Circuit Breaker Project 1017351) | Lee/Fayette | Acquire 5 acres and expand new LCRA TSC facilities with a three-ring bus configuration. | 2019-03-01 | 2019-05-14 | 2019-05-14 | 230513 | 330000 |  |  | 100 | 138 | 138 | 10.03 mi | 1-795 ACSR "Drake" | Steel Monopoles | Varies | 10.03 mi | n/a | n/a | 25.101 (C)(5)(A)
65 | Brian Good | 1017495 | Brenham North - Waller TL Addition (T232) (Flood Mitigation - FY2018 System Upgrade 1017378) | Waller, Washington | Reduce flood risk and potential damage to substation equipment | 2019-09-23 | 2019-11-12 |  | 1619269.84 | 2157648 |  |  | 30 | 1.38 | 138 | 12.94 mi | 795 Drake ACSR & 630.0 TYPE 21 ACCS/TW/C7 (BETWEEN #17/1 TO #18/1) | Concrete Poles, Wood H-frame, Steel H-frame | 75' @ single circuit. 85' @ double circuit | 12.94 mi | 75' @ single circuit. 85' @ double circuit | 12.94 mi | 25.101 (C)(5)(B)
66 | Jacob Miller | 1019038 | Plum - La Grange TL Addition (T208) (Riverside Circuit Breaker Addition - 1018925) | Fayette | Increase the reliability of substation equipment at the Riverside Substation. | 2019-01-28 | 2020-05-15 |  | 356355.26 | 1589877 |  |  | 70 | 138 | 138kv | 8.39 mi | 795 ACSR. GA2 Drake. 3/8 EHS. OPGW | Wood H-frame | Undefined Centerline | 5.58 mi | undefined Centerline | 5.58 mi | 25.101 (C)(5)(B)
67 | Seth Delcambre | 1019276 | Harwood-Gonzales (T542) (Gonzales - Harwood TL Overhaul - 1018965) | Gonzales | Increase the reliability and capability of circuit (T542) on Cuero – Luling 53.9-miles of 69-kV transmission line for the 10 miles between City of Gonzales (S31) & Harwood Station (S397). | 2019-04-01 | 2019-10-31 |  | 4350428.5 | 5484500 |  |  | 49 | 69 | 69 (138kV Capable) | 9.97 mi | Single 795 ACSR "Drake" | Concrete & Steel Pole | Blanket, Centerline | 9.97 mi | n/a | n/a | 25.101 (C)(5)(B)
68 | Manny Garcia | 1017695 | North McCamey-Robbins SW TL Addition (T456) (Robbins Switch Circuit Breaker Addition Addition 1017400) | Upton | Provide transmission service to a generator by constructing substation for interconnection. | 2018-10-31 | 2019-05-10 | 2019-05-10 |  | 77017.11 |  |  | 100 | 138kV | 138 | 5.68 mi | 2x 795 Drake ACSR | Concrete Poles | 80' | 5.68 mi | n/a | n/a | 25.101 (C)(5)(A)
69 | Josh Bollich | 1017510 | Tunas Creek - Mesa View TL Addition (T620) (Fourmile Circuit Breaker Addition 1017380) | Pecos | Increase transmission service reliability to the Fourmile Substation (formerly Indian Mesa/Orion/NWP Tap). | 2018-11-27 | 2019-10-15 |  |  | 4679000 |  |  | 65 | 138 | 138 | 11.68 mi | 3x2, 795 kcmil "Drake" | Steel & Concrete Poles | 80' | 11.68 mi | n/a | n/a | 25.101 (C)(5)(B)
70 | Josh Bollich | 1017588 | Tunas Creek-Mesa View SW TL Addition (T620) (Desert Mesa Circuit Breaker Addition 1017353) | Pecos | Increase transmission service reliability to the Desert Mesa Substation (formerly Desert Sky Tap #1). Provide real-time monitoring facilities at the Desert Mesa Substation. Increase the reliability of transmission facilities on the T620 Tunas Creek – Mesa View transmission line. | 2018-10-31 | 2019-05-15 | 2019-05-15 |  | 264333 |  |  | 100 | 138 | 138 | 18.40 mi | 3x2, 795 kcmil "Drake" | Steel & Concrete Poles | 80' | 18.4 mi | n/a | n/a | 25.101 (C)(5)(A)
71 | Michael Griswold | 1019213 | Round Rock TL Relocation (T527, T378) | Williamson | Increase the transmission service reliability to the Round Rock substation and to support the expansion of the substation by Oncor. | 2019-01-07 | 2019-05-07 | 2019-05-07 | 446000 | 1529331.89 |  |  | 100 | 138 | 138 | 5.1 mi | (1) 795 ACSR "Drake" | Steel Lattice, Steel H-Frame | 100' | 5.1 mi | n/a | n/a | 25.101 (C)(5)(B)
72 | Clint Meyer | 1016702 | Altair - Nada TL Addition (T545) (Glidden Area TL Upgrade - 1016219) | Colorado | OPGW (fiber) installation (T545) and Substation upgrade at Nada and Altair substations from 69kV to 138kV | 2018-12-03 | 2019-05-31 | 2019-05-31 | 2312000 | 6688538.17 |  |  | 100 | 69 | 138 | 14.12 mi | 795 Drake ASCR & 26/7 & Single | Steel, Wood, & Lattice | Blanket | 14.12 mi | Blanket | 14.1 mi | 25.101 (C)(5)(B)
73 | Alfred Mackey | 1019321 | Lakeway-Marshall Ford T179 Addition (T179) (Lakeway AE Marshall Ford TL SH - 1019096) | Travis | Increase the reliability of circuit (T179) on the Lakeway (AE) – Marshall Ford 2.4 mile138 kV transmission line. | 2019-01-25 | 2019-06-21 17:00 | 2019-06-21 | 438000 | 3040713.32 |  |  | 100 | 138 | 138 | 2.4 mi | (6x1) 795 ACSR "Drake" | Steel Towers | 100' | 2.4 mi | n/a | n/a | 25.101 (C)(5)(B)
74 | Alfred Mackey | 1019603 | Lakeway-Marshall Ford Fiber Addition (T179) (LCRA Fiber Backbone FY 19 Telecom Upgrade - 1019084) | Travis | LCRA will Install 2.42 miles of 72-count OPGW from Lakeway (AE) to Marshall Ford (T179). | 2019-02-13 | 2019-06-21 08:00 | 2019-06-21 | 392000 | 450000 |  |  | 100 | 138 | 138 | 2.4 mi | (6x1) 795 ACSR "Drake" | Steel Towers | 100' | 2.4 mi | n/a | n/a | 25.101 (C)(5)(B)
75 | Manny Garcia | 1017760 | Warda-Salem TL Addition (T667,T170) (Warda Circuit Breaker Addition - 1017411) | Fayette | Increase reliability of transmission facilities on the (T170) Winchester-Salem 34.8 mile 138kV transmission line. Cut-in to new A-frames at existing Warda Sub and renumber Warda to Salem as (T667). | 2018-12-01 | 2018-12-20 | 2018-12-20 |  | 663000 |  |  | 100 | 138 | 138 | 34.8 mi | Single (1/phase) 795kcmil ACSR "Drake" | Steel monopole | 100' | 34.8 mi | n/a | n/a | 25.101 (C)(5)(B)
76 | Robert Badger | 1019317 | Rockport-Fulton T474 TL Addition (T474) Hurricane Response System Upgrade - 1019095 | Nueces, Aransas | Increase reliability, repair storm damage, & upgrade circuit (T477) on the N Padre Tap-Port Aransas 18.23-mile 69-kV TL and circuit (T474) on the Fulton-Rockport 138-kV 7.36-mile 69-kV TL. | 2019-02-07 | 2019-09-23 | 2019-09-23 |  | 852895 |  |  | 100 | 69 | 69 | 7.4 mi | (1x) 795 ACSR/AW Drake | Steel Monopole, Concrete Monopole | Unknown (AEP-owned) | - | - | - | 25.101 (C)(5)(B)
77 | Manny Garcia | 1017557 | Deer Creek-Luling TL Addition (T538) (Darst Creek Circuit Breaker Addition - 1017352) | Guadalupe | Add four 138-kV, 3000A, 40kAIC circuit breakers in a ring bus configuration to Darst Creek substation | 2019-02-22 | 2019-05-23 | 2019-05-23 |  | 717517.4 |  |  | 100 | 69 | 69 | 15.84 mi | Drake 795 ACSR, Single | Concrete & Steel | Blanket | 15.84 mi | Blanket | 15.84 mi | 25.101 (C)(5)(B)
78 | Brian Good | 1017499 | Bastrop West-Sim Gideon TL Addition (T410) (Flood Mitigation - FY2018 System Upgrade - 1017378) | Bastrop | Reduce flood risk and potential damage to substation equipment | 2019-01-04 | 2019-03-08 | 2019-03-08 | 897995.63 | 1400020.01 |  |  | 100 | 138 | 138 | 6.76 mi | Drake 795 ACSR, Single | Steel (New) & Wood H-frame(Existing) | 100' | 100' | 100' | 6.76 mi | 25.101 (C)(5)(B)
79 | Jacob Miller | 1019133 | Rim Rock - Turtle Creek TL Addition (T270) (Rim Rock - Turtle Creek TL Storm Hardening - 1018968) | Kerr | Increase the reliability of circuit (T270) on the Rim Rock - Turtle Creek 7.6 mile 138kV transmission line | 2020-09-16 | 2021-05-05 |  | 6523068.22 | 7002025 |  |  | 0 | 138 | 138 | 7.6 mi | (1x) 795 ACSR Drake | Steel Monopole | 60' , 100' | 7.6 mi | 60, 100 | 7.6 mi | 25.101 (C)(5)(B)
80 | Brad Wallner | 1020430 | Marshall Ford-McNeil TL Addition (T161) (Summit T161 TL Relocation - 1020390) | Travis | Relocation of the Marshall Ford to McNeil 69-kV transmission line (T161) at the Austin Energy Summit Substation. The proposed relocation of the line was requested by Austin Energy to the northern section of Summit Sub. | 2019-03-04 | 2019-12-10 |  | 831439 | 1553000 |  |  | 50 | 69 | 69 | 13.42 mi | Bundled 795 Drake ACSR | Steel Poles | 100' CL | 0.9 mi | n/a | n/a | 25.101 (C)(5)(B)
82 | Brian Good | 1018599 | Bakersfield to Solstice (CCN) (Bakersfield-Solstice TL Addition - 1018599) | Pecos | Construct a new 345-kV transmission line to connect LCRA TSC's existing Bakersfield station and AEP Texas' Solstice Switch Station | 2019-12-20 | 2020-12-23 |  | T-line $148 - $192M; Bakersfield Substation - $6M; Solstice Switch Station - $38M | $78M |  |  | 0 | 0 | 345 | 130-190 mi | 1926.9 kcmil ACSS/Cumberland (LCRA TSC) and 1590 ACSS (AEP Texas) | Double-circuit steel lattice towers | 0 | 0 | 150' | 68 - 92 mi | 48787
83 | Josh Bollich | 1017897 | Culberson-Kunitz TL Addition (T271) (Culberson-KunitzTL Overhaul - 1017896) | Culberson | Structure replacement upgrades to steel and concrete Poles | 2019-05-28 | 2019-12-20 |  | 507000 | 593494 |  |  | 60 | 138 | 138 | 28.88 mi | Linnet; 336kcmil; 0.721” | Wood | 100' | 28.88 mi | n/a | n/a | 25.101 (C)(5)(B)
89 | Robert Badger | 1019319 | N. Padre Tap - Port A. (T-477) (Hurricane Response System Upgrade - 1019095) | Nueces | Increase the reliability, repair storm damage, and upgrade circuit (T477) on the North Padre Tap – Port Aransas 18.23-mile 69-kV transmission line and circuit (T474) on the Fulton – Rockport 138-kV 7.36-mile 69-kV transmission line. | 2019-10-14 | 2019-12-20 |  |  | 3193000 |  |  | 10 | 69 | 69 | 15 mi | 795 ACSS/AW Drake x1 | Steel monopole, Concrete Monopole, Hybrid Steel/Concrete | (AEP-owned) | NA | n/a | n/a | 25.101 (C)(5)(B)
90 | Robert Badger | 1019337 | Elroy - Wolf Lane (T-582) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-03-18 | 2019-05-13 | 2019-05-13 | 31898000 | 1317604 |  |  | 100 | 138 | 138 | 3.78 mi | 795 Drake ACSR GA2 | Wood H-frame, LD Steel H-frame, Steel Pole, Tower | 100' | 3.78 mi | n/a | n/a | 25.101 (C)(5)(B)
91 | Robin Mims | 1020260 | Red Creek-Amos Creek TL Addition (T424) (Amos Creek Substation Addition - 1020230) | Concho | Transmission line cute-in to provide transmission service to a generator. | 2019-09-03 | 2020-02-05 |  | 1737273 | 1833576.23 |  |  | 23 | 345 | 345 | 49 mi | 1590 ACSR Falcon x2 | Steel Lattice tower | 100' | 49 mi | n/a | n/a | 25.101 (C)(5)(B)
92 | Robert Badger | 1019327 | Austrop-Garfield (T182) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-04-15 | 2019-11-22 |  | 31898000 | 3820639.2313 |  |  | 80 | 345 | 345 | 8.33 mi | Bundled 795 ACSR "Drake" | Lattice Tower | 170' Centerline | 8.33 mi | n/a | n/a | 25.101 (C)(5)(B)
93 | Robert Badger | 1019374 | Marshal Ford - McNeil T161 TL Addition (T161) (Marshall Ford-McNeil TL Relocation - 1019212) | Travis | Increase transmission service reliability to the Austin Energy Hamilton Substation. | 2019-05-01 | 2019-06-12 | 2019-06-12 | 951759 | 1754446.45 |  |  | 100 | 69 | 69 | 13.4 mi | 4/0 & 795 kcmil ACSR | Lattice Towers & Steel Poles | 100' | 13.4 mi | n/a | n/a | 25.101 (C)(5)(B)
94 | Bryan Cooley | 1017654 | Winchester-Salem TL Addition (T170) (T667) (Salem-Winchester T170 TL OH - 1017654) | Fayette | Increase the reliability and capability of circuit T170 on the Salem - Winchester 37.16-mile 138-kV transmission line. | 2019-06-17 | 2020-02-26 |  | 5700000 | 5749000 |  |  | 44 | 138 | 138 | 37.18 | 795 ACSR Drake (single) | Wood H-frame, Steel Lattice, Steel Monopole | Varies | 37.18 mi | n/a | n/a | 25.101 (C)(5)(B)
95 | Tony Rhodes | 1021300 | Granite Mountain – Marble Fall TL Upgrade [Marble Falls Double Circuit TL Upgrade - 1020559] | Burnet | Increase the reliability of transmission facilities on the T195 Granite Mountain – Marble Falls 4.1-mile 138-kV transmission line | 2019-11-01 | 2020-03-20 |  |  | 3295621.32 |  |  | 0 | 138 | 138 | 4.08 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies 80' - 100' | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
96 | Robin Mims | 1016579 | Fair Oaks Ranch - Esparanza TL Addition (T503) [Esperanza Substation Addition - 1016187] | Kendall | LCRA TSC will build a 138kV substation and cut-in T503 to provide transmission/ metering services and real-time monitoring facilities | 2019-09-06 | 2019-11-22 |  |  | 1053522.44 |  |  | 42 | 138 | 138 | 8.25 | Single 795 kcmil ACSR | Steel Poles | 100' | 8.11 | 80' | 8.25 | 25.101 (C)(5)(B)
97 | Bo Beauregard | 1016745 | Flatonia-Hallettsville TL Addition (T132) [Flatonia - Hallettsville TL Upgrade - 1016188] | Fayette, Lavaca | Upgrade the capacity of the 18.7 mile Flatonia-Hallettsville 138-kV transmission line from 128 MVA to 380 MVA using 959 ACSS Suwannee conductors and OPGW | 2019-09-27 | 2020-05-14 |  | 9338490 | 7000000 |  |  | 5 | 138 | 138 | 18.68 | Single 959.6 kcmil ACSS/TW | Wood H-frame & Steel Poles | 100' | 18.68 | 100' | 18.68 | 25.101 (C)(5)(B)
98 | Brad Wallner | 1017708 | Geronimo-Seguin TL Addition T499 [Jim Briley Substation Addition - 1017404] | Guadalupe | LCRA TSC will construct a new 138-kV substation between the Geronimo Substation and Seguin Substation. LCRA TSC will extend (T-499) Geronimo to Seguin 138-kV transmission line for approximately 500 feet in and out of the Strempel Substation to terminate on A-frame structures at the substation. | 2019-09-16 08:00 | 2019-10-11 |  |  | 887000 |  |  | 85 | 138 | 138 | 2.79 | 1433.6 kcmil ACSS/TW | DC Concrete Poles | 100' | 2.79 mi | n/a | n/a | 25.101 (C)(5)(B)
99 | Seth Delcambre | 1019301 | Kendall-Comfort T243 TL Addition (T243) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-mile 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-mile 138-kV transmission circuit (T243) | 2019-10-21 | 2020-03-11 |  |  | 4784350.08 |  |  | 0 | 138 | 138 | 1.08 mi | Bundled 959.6 SUWANNEE ACSS/TW | Steel Single Poles/ Tower/ Steel H-frame | 100' | 1.08 mi | n/a | n/a | 25.101 (C)(5)(B)
100 | Seth Delcambre | 1019303 | BoerneCico-Comfort T148 TL Addition (T148) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-mile 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-mile 138-kV transmission circuit (T243) | 2019-10-21 | 2020-05-15 17:00 |  |  | 4415710.33 |  |  | 0 | 138 | 138 | 16.93 mi | Bundled 795 DRAKE ACSR | Steel Single Poles | 100' | 16.93 mi | n/a | n/a | 25.101 (C)(5)(B)
101 | Seth Delcambre | 1018934 | Fayetteville - Winchester TL Upgrade (T165) [Fayetteville-Winchester TL Upgrade - 1018933] | Fayette | Increase capacity and capability of circuit T165 on the Fayetteville – Winchester 138-kV upgrade | 2019-09-01 | 2020-04-27 |  |  | 14670055.92 |  |  | 15 | 138 | 138 | 18.9 mi | 1433 kcmil ACSS/TW Merrimack | steel monopoles | 100' | 18.9 mi | n/a | n/a | 25.101 (C)(5)(B)
102 | Martin Lindig | 1019122 | T155 Giddings - Lyle Wolz Addition (T155) [Lexington CB Addition - 1018914] | Lee | Add two new structures to accommodate substation expansion. Increase transmission service reliability to the Lexington Substation. | 2019-08-12 | 2019-10-01 | 2019-10-01 |  | 625546 |  |  | 100 | 138 | 138 | 21 mi | 795 ASCR | steel monopoles | 100' | 21 mi | n/a | n/a | 25.101 (C)(5)(B)
103 | Michael Griswold | 1017394 | Mountain Home TL Addition (CCN) | Kerr, Gillespie, Kimble | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2021-08-01 | 2022-12-27 17:00 |  | T-line $46 - $53M; Substation $7.3 - $7.4M |  |  |  | 0 | 0 | 138 | 21-29 mi | 795 Kcmil 26/7 ACSR “Drake” | tbd; steel or concrete poles | 0 | 0.00 MI | varies; 100' | 21-29 mi | 49523
104 | Bo Beauregard | 1021664 | Rim Rock-Jack Furman TL Add (T381) [Flood Mitigation - 1021663] | Kerr | Replace structure 38 on T381 due to storm water erosion. | 2019-11-04 | 2019-11-15 |  | 181000 |  |  |  | 0 | 138 | 138 | 5.689 | 336.4 ACSR (26/7) “Linnet”/ Single | Steel Monopoles & Tower | 60' | 5.689 | n/a | n/a | 25.101 (C)(5)(B)
105 | Bryan Cooley | 1019026 | Fayetteville - Glidden TL Addition (T176) [Fayette Area TL Upgrades - 1018913] | Fayette, Colorado | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) | 2019-09-20 | 2020-05-26 |  | 8708509.35 |  |  |  | 8 | 138 | 138 | 20.02 | Single 959.6 ACSS/TW Suwannee & Single OPGW (AFL DNO-11243) Static | Steel Monopoles, Hybrid H-Frames | 100' | 20 | n/a | n/a | 25.101 (C)(5)(B)
106 | Robin Mims | 1020270 | Amos Creek-Bow Wood TL Add (T709) [Amos Creek Substation Addition - 1020230 ] | Concho, Tom Green | Provide transmission service to a generator | 2019-09-03 | 2020-02-05 |  | 211644.52 |  |  |  | 23 | 138 | 138 | 49.33 | (2x) - 1590 kcmil ACSR Falcon | Steel Lattice, Steel monopole | 160 | 49.33 | n/a | n/a | 25.101 (C)(5)(B)
107 | Robert Badger | 1019325 | McNeil - Gilleland Creek (T147) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2020-01-13 | 2020-04-01 |  | 642000 |  |  |  | 0 | 138 | 138 | 7.62 | 1433.6 ACSS/TW "MERRIMACK" / Single | Steel Monopoles & Tower | 100' | 7.62 | n/a | n/a | 25.101 (C)(5)(B)
108 | Robert Badger | 1019341 | Paige - Winchester TL Addition (T615) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Bastrop | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-09-23 | 2019-12-20 |  | 1449231.7284 |  |  |  | 25 | 138 | 138 | 14.85 | Bundled Linnit and Single Drake | Steel Mono Pole, Wood H-Frames, Concrete # Poles | 100 | 14.85 | n/a | n/a | 25.101 (C)(5)(B)
109 | Robert Badger | 1019335 | Wells Branch - Round Rock (T527) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis, Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-09-16 | 2019-11-01 |  | 385406.9994 |  |  |  | 30 | 138 | 138 | 5.28 | (2) 795 KCMIL ACSR/GA2 “DRAKE” | Steel/concrete Pole, Concrete H-Frame | 100' | 5.28 | n/a | n/a | 25.101 (C)(5)(B)
110 | Michael Griswold | 1017767 | Sim Gideon-Winchester TL Addition (T152) [Winchester Autotransformer Additions - 1017413] | Bastrop | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 2013964.12 |  |  |  | 14 | 138 | 138 | 20.74 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (75ft & 100ft) | 20.74 | Varies (75ft & 100ft) | 20.84 | 25.101 (C)(5)(B)
111 | Michael Griswold | 1017769 | Smithville-Winchester TL Addition (T175) [Winchester Autotransformer Additions - 1017413] | Bastrop | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 643444.51 |  |  |  | 14 | 138 | 138 | 15.1 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (80ft & 100ft) | 15.1 | Varies (80ft, 100ft, Aerials to 180ft) | 14.7 | 25.101 (C)(5)(B)
112 | Michael Griswold | 1017771 | Winchester - Piney Creek TL Addition (T186) [Winchester Autotransformer Additions - 1017413] | Fayette | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 562421.39 |  |  |  | 14 | 138 | 138 | 1.38 | Single 1433.6 54/19 ACSR/TW Merrimack/TW | Lattice Towers & Steel Poles | 100ft | 1.38 | 100ft | 1.59 | 25.101 (C)(5)(B)
113 | Michael Griswold | 1017773 | Winchester - Giddings TL Addition (T222) [Winchester Autotransformer Addition - 1017413] | Bastrop | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 774103.46 |  |  |  | 14 | 138 | 138 | 10.51 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (75ft & 100ft) | 10.51 | Varies (75ft, 100ft) | 10.68 | 25.101 (C)(5)(B)
114 | Michael Griswold | 1017775 | Paige-Winchester TL Addition (T615) [Winchester Autotransformer Additions - 1017413] | Lee | LCRA TSC will install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-05-15 |  | 807090.7 |  |  |  | 14 | 138 | 138 | 14.83 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | 100ft CL | 14.83 | 100ft CL | 15.09 | 25.101 (C)(5)(B)
115 | Dave Ilges | 1018759 | Crane-Rio Pecos TL Add (T451) [Castle Mountain Substation Addition - 1018744] | Upton, Crane | Cut-in T451 to a new substation, Provide transmission service (new Castle Mountain substation) for Solar Prime LLC. | 2019-09-05 | 2020-03-26 |  | 2746880.16 |  |  |  | 3 | 138 | 138 | 0.044 | Bundled 795 ACSR Drake, Single 3/8 EHS Static & Single DNO-11243 OPGW | Steel Monopole Dead End | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
116 | Jacob Miller | 1017649 | LaGrange - FPP 138kV TL Addition (T263) [FPP 138kV - La Grange TL Overhaul - 1017648] | Fayette | Increase the reliability and capability of circuit T263 on the FPP 138kV – La Grange 7.9-mile 138-kV transmission line | 2020-01-24 | 2020-05-14 |  | 1520674.1957 |  |  |  | 0 | 138 | 138 | 7.89 | Single 795 ACSR Drake & 2 OPGW (AFL DNO-11243) & (ALCOA 52 OPT-GW) | Steel Monopole Dead Ends, Wooden H-Frame Tangents | 100' | 7.8 | n/a | n/a | 25.101 (C)(5)(B)
117 | Robert Badger | 1019333 | Round Rock - Chief Brady (T378) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-11-04 | 2020-01-10 |  | 469500 |  |  |  | 0 | 138 | 138 | 1.2 | (1) 795 ACSR/GA2 "Drake"; RR AF to #55B has (2) 959 ACSS/TW HS "Suwannee" | steel H-frame, steel lattice | 100' CL | 1.2 | n/a | n/a | 25.101 (C)(5)(B)
118 | Robert Badger | 1019329 | Chief Brady - Georgetown (T355) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2020-01-13 | 2020-02-28 |  | 960000 |  |  |  | 0 | 138 | 138 | 3.17 | (1) 795 ACSR/GA2 "Drake" | Steel Lattice and pole, Steel H-Frame | 100' | 3.0 | n/a | n/a | 25.101 (C)(5)(B)
119 | Robert Badger | 1019339 | Georgetown - Rivery (T597) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2020-03-02 | 2020-05-26 |  | 1367300 |  |  |  | 0 | 138 | 138 | 5.1 | (1) 795 ACSR/GA2 "Drake" | steel H-frame, concrete pole, steel pole | 50' CL, blanket | 5.10 | n/a | n/a | 25.101 (C)(5)(B)
120 | Bryan Cooley | 1019210 | Altair-Glidden TL Addition (T544) [Kleimann (Columbus) CB Addition - 1018910] | Upton, Crockett | Increase reliability of transmission facilities on the T544 Glidden-Altair 12.22-mile 69-kV TL. | 2019-11-04 | 2020-02-10 |  |  | 1254000 |  |  | 0 | 69 | 138 | 3.33 | 795 ACSR Drake, single | Steel & Concrete monopoles | 80' Blanket | 12.41 | 80' Blanket | n/a | 25.101 (C)(5)(B)
121 | Bryan Cooley | 1017538 | Goforth-Turnersville TL Addition (T272) [Crosswinds Substation Addition-1017349] | Hays | Acquire 7.5 acres and expand new LCRA TSC facilities with a three-ring bus configuration | 2019-11-04 | 2020-01-24 |  |  | 975000 |  |  | 0 | 138 | 138 | 3.77 | 795 ACSR Drake, single | Lattice, Wood H-frame, Steel monopole | 100' | 6.69 | 100' | 3.77 | 25.101 (C)(5)(B)
123 | Bryan Cooley | 1017540 | Crosswinds-Goforth TL Addition (T661) [Crosswinds Substation Addition-1017349] | Hays | Acquire 7.5 acres and expand new LCRA TSC facilities with a three-ring bus configuration | 2019-11-04 | 2020-01-24 |  |  | 101718 |  |  | 0 | 138 | 138 | 3.31 | 795 ACSR Drake, single | Wood H-frame, Steel monopole | 100 | n/a | 100' | n/a | 25.101 (C)(5)(B)
125 | Clint Meyer | 1014015 | Camp Wood - Leakey TL Addition (T269) [Camp Wood - Leakey TL Overhaul - 1016183] | Real | Increase the reliability of transmission facilities on the T269 Camp Wood-Leakey 17.3 mile 69-kV transmission line and upgrade the line to 795 ACSR Drake conductor (111 MVA at 69-kV), 138-kV capable with an OPGW shield wire. | 2020-01-13 | 2021-06-25 |  |  | 26526469 |  |  | 0 | 69 | 138 | 17.32 | Single 795 ACSR Drake | Steel & Lattice | Varies - 60' | 17.32 | n/a | n/a | 25.101 (C)(5)(B)
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156