## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
N/A | Martinsville to Chireno 138 kV Transmission Line Docket 46750 | Nacogdoches | New 138 kV transmission line from DETEC Martinsville Substation to Tex-La's proposed Chireno Switching Station | 2019-08-12 | TBD |  | $11,342,000-$14,204,000 T-Line; $6,350,000 Substation Upgrades | $11,648,000 T-Line; $6,350,000 Substation Upgrades |  |  | 0 | na | 138 | 10.8 | 795 kcmil ACSR 26/7 "Drake" | Single pole, 85-115 ft, steel/concrete | na | na | 100 | 10.8 | 46750 | ROW clearing is in progress, Material is on order, Line construction anticipated to start in December 2019