## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
GV01-16 | Meadow Lake Substation | Guadalupe | New Substation, w 30MVA PWT, distribution bays 4 circuits |  |  |  | 4.9 Mill |  | - |  | 15% | 0 | 138 | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Site Civil engineering in progress; Substation design in progress
GV01-18 | Marion to Cibolo 138 Transmission Line Circuit Addition | Guadalupe | Add 4.8 mile 138kV transmission line circuit to existing transmission line, Terminal at Marion breakers/bus, 2 Terminals at Cibolo breakers/bus, replace underrated switches |  |  |  | 4.9 Mil |  |  |  | 100% | 138 | 138 | 4.8 | 1192 ACSR | Steel | 80 | 4.7 | 0 | 0 |  | Construction Complete. Line and Terminals energized 5/24/2019
GV02-18 | Schertz 138 Terminal Addition | Guadalupe | Add breaker and relaying to terminal looking at Cibolo, replace switches |  |  |  | 325k |  |  |  | 100% | 138 | 138 | 0 | 0 | Steel | 0 | 0 | 0 | 0 |  | Construction Complete. Energized 5/24/2019
GV03-18 | Nixon-LCRA Sub Relocation of Hallettsville Auto to Nixon | Gonzales | Move 138/69 Auto from Halletsville to Nixon-LCRA |  |  |  | 125k |  | - |  | 100% | 138/69 | 138/69 |  | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Complete; Autotransformer energized Sept 19, 2018