## FilingInstructions
Construction Progress Report Form
for Transmission Projects
In Compliance With Substantive Rule §25.83
Instructions
File two printed copies and one electronic copy of this form in the Commission's Central Records
Project 27250 - 2003 Construction Reporting
Submit an electronic copy of this form to:
mailto:monthlyreports@puc.state.tx.us
The electronic file name shall have the acronym of the reporting utility followed by the two digit month and two digit year and then the letter "m."
File this form by the 15th of each month for activities occurring through the end of the previous month. Interim reports may be filed as needed to comply with the 45 day advance notice reporting requirement of Substantive Rule 25.83(c).
Direct any questions to:
mailto:monthlyreports@puc.state.tx.us

## MonthlyReportForm-North
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
42053511 | Yucca Area Improvement Project | Crockett | Esmeralda to Yucca: Build 138-kV line | 2016-05-01 | 2016-12-31 | 2017-06-30 | 12500000 |  |  |  | 99 |  | 138 | 14.7 | 2 Bundled 959.6 Suwannee ACSS/TW | Single Pole Brace Post |  |  | 100 | 14.7 | 42265 | CCN approved on 06/16/2014
42431334 | Yucca Area Improvement Project | Crockett | Big Lake to Friend Ranch: Cut in to Esmeralda | 2016-10-01 | 2016-12-31 | 2017-06-30 |  | 509800 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.101 (c)(5)(A) | Prior consent from UT lands for Cut-Ins
42431649 | Yucca Area Improvement Project | Crockett | Big Lake: New relay panels | 2016-10-01 | 2016-12-31 |  |  | 1664000 |  |  | 90 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3)
42431682 | Yucca Area Improvement Project | Crockett | Friend Ranch: New relay panels | 2016-10-01 | 2016-12-31 | 2017-06-30 |  | 1185800 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3)
42264092 | Yucca Area Improvement Project | Crockett | Esmeralda: Build new 138-kV station | 2016-01-01 | 2016-12-31 | 2017-06-30 |  | 7313000 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3)
42431821 | Yucca Area Improvement Project | Crockett | Yucca: Convert station to 138-kV - T asset | 2016-10-01 | 2016-12-31 | 2017-06-30 |  | 608000 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3)
42316002 | Red Creek Auto | Tom Green | Replace two 345-kV Autos and Relay Upgrades at Red Creek Substation | 2016-08-01 | 2018-03-28 |  |  | 14716608 |  |  | 65 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | No property purchase required, existing station.
42425030 | North Brady: Install New CB | McCulloch | Install a 3000 A, 40 kA, circuit breaker for termination of future new 69-kV circuit to the City of Brady Substation | 2016-09-19 | 2017-05-01 |  |  | 843328 |  |  | 25 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
42409249a | Abilene NW to Capella POD | Taylor | Rebuild Abilene NW to Capella POD | 2016-07-25 | 2016-12-30 | 2017-02-03 |  | 5500000 |  |  | 95 | 69 | 69 | 9 | 959.6 ACSS/TW | Steel Single Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(B) | Rebuild east of Capella POD Landowners noticed & consent obtained
42505132 | Abilene NW to Oak Creek | Taylor | Raise Abilene NW to Oak Creek | 2016-07-25 | 2016-11-18 | 2017-12-02 |  | 900000 |  |  | 95 | 138 | 138 |  | 795ACSS | Steel Single Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(B) | Existing easement landowner noticed
42505145 | Abilene NW to Elm Creek | Taylor | Raise Abilene NW to Elm Creek | 2016-07-25 | 2016-11-18 | 2016-12-02 |  | 900000 |  |  | 95 | 138 | 138 |  | 795ACSS | Steel Single Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(B) | Existing easement landowner noticed
42535467 | Alpine Upgrade Terminal | Brewster | Alpine: Upgrade 69-kV Line Terminal | 2016-08-08 | 2016-08-28 | 2017-03-15 |  | 3060000 |  |  | 95 | 69 | 69 | [7 empty] | 16 TAC 25.83(a)(3)
42300631 | Barrilla Junction Improvements | Pecos | Barrilla Junction to Permian Basin: Reterminate 138-kV Line into New Solstice Station | 2016-12-01 | 2017-06-30 | 2017-02-02 |  | 647546 |  |  | 95 | 138 | 138 | 0.3 | 477 KCMIL ACSR | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Construction within station property
42352834 | Barrilla Junction Improvements | Pecos | Barrilla Junction Station: Accommodations for the New Line for the 138/69-kV Auto | 2016-12-01 | 2017-06-30 | 2017-05-24 |  | 964071 |  |  | 90 | 138 / 69 | 138 / 69 | [7 empty] | 16 TAC 25.83(a)(3)
42483912 | Bison to Powell Field Rebuild | Crockett/Reagan | Upgrade Powell Field Station | 2016-12-01 | 2017-05-31 | 2017-08-08 |  | 539000 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
42486619 | Pig Creek Station | Pecos | Pig Creek Station | 2016-12-01 | 2017-09-29 | 2017-10-20 |  | 7075000 |  |  | 99 | 138 | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42486608 | Pig Creek Station | Pecos | Cut Barrilla to Permain Basin 138-kV T-Line into new Pig Creek Station | 2016-12-01 | 2017-09-29 | 2017-10-20 |  | 888000 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.101 (c)(5)(A) | Construction within Purchased Property
42396666 | Cassava Station | Irion | Build New 69-kV Station | 2017-01-05 | 2017-12-01 |  |  | 6200000 |  |  |  |  | 138 / 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42425002 | Cassava-Yucca: Rebuild | Irion, Crockett | Rebuild 12 miles of existing 69-kV Transmission Line to 138-kV Operation | 2017-01-05 | 2017-12-01 |  |  | 9804000 |  |  |  | 69 | 138 | 12 | 795 ACSS | Steel Mono Pole | 50 | 12 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Consent Obtained
42471045 | Cassava-Yucca: Rebuild | Irion | Install 138/68-kV, 90MVA Autotransformer with LTC and one 138-kV Breaker at New Cassava Station | 2017-01-05 | 2017-12-01 |  |  | 3335000 |  |  |  |  | 138 / 69 | [7 empty] | 16 TAC 25.83(a)(3)
42425035 | City of Brady-N. Brady: Rebuild | McCulloch | Rebuild the City of Brady tap to North Brady as a double circuit with 959.6 ACSR/TW and OPGW (approximately 0.4 mi), 138-kVconstruction | 2017-01-05 | 2015-05-01 |  |  | 1711536 |  |  |  | 69 |  | 0.4 | 959.6 ACSR/TW | Steel Mono Pole | 100 | 0.4 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed Consent and Easement Supplements were acquired as necessary
42533342 | Crowell-Truscott Humble Tap 69-kV Rebuild | Foard, Knox | Rebuild 16.22 Miles of 69-kV Transmission Line to 138-kV Standards | 2016-01-05 | 2017-12-31 |  |  | 8754993 |  |  | 70 | 69 |  | 16.22 | 795 ACSS | Steel Mono Pole | 100 | 16.22 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42535492 | Lasso Station: Install DME, SDR, RTU, & Metering | Brewster | Lasso Station: Install DME, SDR, RTU, & Metering | 2017-01-28 | 2017-03-31 | 2017-04-17 |  | 800000 |  |  | 90 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
42536164 | Alpine - Ft. Stockton: Cut-In to Bronco | Brewster | Cut-In 68-kV Line to New Bronco Station | 2016-11-28 | 2017-12-31 | 2017-09-25 |  | 500000 |  |  | 90 | 69 |  | 0.01 | 796 ACSS | Steel Mono Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(A) | Cut-In within Existing Easement
42536135 | Paint Creek Auto Replacement Accommodation | Haskell | Upgrade Equipment associated with New Auto Transformer | 2017-01-28 | 2017-06-30 | 2017-04-28 |  | 1461169 |  |  | 95 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42532596 | Jayton-Clairmont Tap 69-kV Rebuild | Kent | Rebuild 69-kV Transmission Line to 138-kV Standards and Partial Relocation to Mitigate Encroachments | 2017-02-01 | 2017-12-31 |  |  | 6986986 |  |  | 80 | 69 |  | 10.83 | 795 ACSS | Steel Mono Pole | Varies | 10.83 | 100 | 1.84 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowners Noticed Consent and New Easement & Supplements were acquired as necessary
42502137 | Alpine REA to Barrilla Junction 69-kV Rebuild | Brewter / Pecos | Rebuild 69-kV Transmission Line to 138-kV Capability & Install Temporary Tap Switches | 2017-02-25 | 2017-12-31 |  |  | 23247632 |  |  | 75 | 69 |  | 41.92 | 795 ACSS | Steel Mono Pole |  | 41.92 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed Necessary Easements Acquired
42535309 | Solaire-Holman Interconnect | Brewster | Bronco Station: Construct a 138-kV-capable, three breaker ring bus station | 2017-02-25 | 2017-09-01 | 2017-09-25 |  | 5224996 |  |  | 90 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42502807 | Red Creek: Replace Circuit Breaker | Tom Green | Replace 345-kV Circuit Breaker 5940 & 6 x 138-kV Circuit Breakers | 2017-04-19 | 2018-05-21 |  |  | 3344832 |  |  | 65 | 345 / 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42536715 | Cassava - Mertzon REA 69-kV Rebuild | Irion | Rebuild 69-kV Transmission Line, 138-kV Capable, but continue to operate at 69 kV | 2017-03-20 | 2018-06-01 | 2017-12-18 |  | 13584339 |  |  | 85 | 69 |  | 16.45 | 795 ACSS | Steel Mono Pole | Centerline | 16.45 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed Easements with Consent Acquired Where Necessary
42300621 | Barrilla Area Improvements | Pecos | Alamito Creek - Barrilla Junction: Reterminate 138-kV Line into New Solstice Station | 2017-03-17 | 2017-03-31 |  |  | 450000 |  |  |  | 138 |  | 0.2 | 477 KCMIL ACSR | Steel Mono Pole |  |  | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42493261 | Ft. Stockton Plant: Replace Breakers | Pecos | Replace 69-kV Breakers | 2017-03-30 | 2017-06-30 |  |  | 1257567 |  |  | 50 | 69 | 69 | [7 empty] | 16 TAC 25.83(a)(3)
42535472 | Solaire-Holman Interconnect | Pecos | Ft. Stockton Plant: Upgrade 69-kV Terminal | 2017-03-20 | 2017-06-30 |  |  | 1101534 |  |  | 45 | 69 | 69 | [7 empty] | 16 TAC 25.83(a)(3)
42480723 | Ft. Griffin 69-kV Station | Shackelford | Build New Ft. Griffin 69-kV Station | 2017-06-06 | 2017-12-15 |  |  | 6425897 |  |  |  |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42481588 | Quaint 69-kV Switch Station | Jones | Build New Quaint 69-kV Station | 2017-11-03 | 2018-05-26 |  |  | 9096276 |  |  |  |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42483918 | Abilene South to Abilene West | Taylor | Construct 138-kV Box Bay at Abilene West Texas Gulf Tap. Will be operated at 69 kV (Sawgrass Box Bay) | 2017-07-26 | 2017-11-01 |  |  | 1735461 |  |  | 45 | 69 | 69 |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.83(a)(3) | Constructed within existing easements. Landowners noticed.
42479030 | Moran - Putman 69-kV Rebuild | Shackelford / Callahan | Rebuild 69-kV Transmission Line to 138-kV standards but continue to operate at 69-kV. Reroute a 600' section of this Rebuild to avoid an encroachment. | 2017-08-05 | 2017-12-22 |  |  | 14170922.17 |  |  |  | 69 | 69 | 12.86 | 795 ACSS | Steel Mono Pole | Centerline | 12.86 | 100 | 0.1 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowners Noticed Consent, New Easement & Supplements were acquired as necessary
42594762 | Russek Street: Add Breakers | Reagan | Add Breakers, DICM, CT's, and CCVT's to Russek Station | 2017-09-08 | 2018-03-15 |  |  | 2999921 |  |  |  | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42499906 | Sonora Station: Replace Three Breakers | Sutton | Construct control house. Replace (3) 69-kV Breakers | 2017-09-08 | 2017-12-31 |  |  | 2104600 |  |  |  | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42624777 | Abilene Distribution Automation Circuit Reconfiguration - Transmission Assets Only | Taylor | Transmission High-Side work to automate distribution feeder breakers and station regulators at 8 Abilene area stations | 2017-11-15 | 2018-08-15 |  |  | 2374000 |  |  |  | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42493257 | Alpine CB Upgrades | Brewster | Replace CB's 4720, 3310, 3165 | 2017-09-08 | 2017-12-31 |  |  | 2500000 |  |  | 45 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42578948 | Upgrade Elm Creek Station | Taylor | Upgrade Elm Creek Station: Upgrade RTU, terminal equipment and relay | 2017-10-22 | 2017-12-30 |  |  | 1541401 |  |  | 35 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42578950 | Abilene NW to Elm Creek : Rebuild | Taylor | Rebuild Abilene NW to Elm Creek 69-kV Line | 2017-11-18 | 2017-12-30 |  |  | 3598571 |  |  |  | 138 / 69 |  | 3.1 | 795 ACSS | Steel Mono Pole | Centerline | 3.1 | 100 | 0.13 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowners Noticed Consent, New Easement & Supplements were acquired as necessary
42651519 | Solstice-Permian Basin: Rebuild 138-kV Line | Pecos,Reeves,Ward | Rebuild and Upgrade 37.47 miles of 138-kV transmission line double circuit capable between Solstice Substation and Permian Basin ONCOR POI | 2017-11-20 | 2018-12-01 |  |  | 40439378.85 |  |  |  | 138 |  | 37.47 | 795 ACSS (Bundled) | Steel Mono Pole & Concrete | 80 | 37.47 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42486571 | Abilene South - Abilene West Texas Gulf Tap | Abilene/Taylor | Rebuild approximately 2.35 miles of 69-kV transmission line to 138-kV standards and double circuit capability but continue to operate at 69 kV | 2017-12-07 | 2018-01-26 |  |  | 1941787 |  |  | 0.4 | 69 |  | 2.35 | 795 ACSS | Steel Mono Pole | Centerline | 2.35 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42578946 | Abilene NW to Elm Creek: Station | Abilene/Taylor | Upgrade Abilene NW Station | 2017-12-07 | 2018-01-02 |  |  | 1121026 |  |  | 0.4 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42611234 | Rankin Sub | Upton | Upgrade fuses and circuit switcher | 2017-12-11 | 2018-06-30 |  |  | 650000 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42598596 | SW Vernon | Wilbarger | Upgrade transformer and equipment (replace existing station). | 2018-01-02 | 2018-12-31 |  |  | 7700000 |  |  | 0 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42601759 | Verhalen Substation | Reeves | Verhalen Distribution Substation is being upgraded. T - Station Asset Only. | 2017-12-07 | 2018-04-22 |  |  | 1460276 |  |  | 0.25 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42667612 | Owls: Build Station | Big Lake / Reagan | Build a new 138 kV 3 circuit breaker ring bus with one 69-kV circuit breaker and a 138/69 kV, 90 MVA, autotransformer. Use 3000 A, 40 kA, circuit breakers. | 2017-12-07 | 2018-12-31 |  |  | 6624004 |  |  | 10 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Purchased Property
42599271 | Clairmont Tap to Wolfgang Rebuild | Kent | Rebuild and reconductor approximately 7.65 miles of 69-kV transmission line to 138-kV standards. Continue to operate at 69 kV | 2017-12-07 | 2018-12-31 |  |  | 6913000 |  |  | 0 | 69 |  | 7.65 | 795 ACSS | Steel Mono Pole | Centerline | 7.65 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42604478 | Mertzon REA to Mertzon to Tankersley, Rebuild 69-kV Line | Mertzon / Irion, Tom Green | Rebuild, Reconductor, and Partially Relocate 13.47 Miles of 69-kV T-Line to 138-kV Standards Continue to Operate at 69 kV | 2018-01-31 | 2018-12-31 |  |  | 10300120 |  |  | 5 | 69 |  | 13.47 | 795 ACSS | Steel Mono Pole | Centerline | 13.47 | 100 | 0.39 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowners Noticed Consent, New Easement & Supplements were acquired as necessary
42484594 | Ft. Griffin 69KV Station | Albany, Shackleford | Reterminate the Albany-Putnam 69kV line into the new Ft. Griffin station approximately 0.2 miles | 2018-01-03 | 2018-01-23 |  |  | 803137.78 |  |  | 0 | 69 |  | 0.2 | 795 ACSS | Steel Mono Pole |  |  | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Consent Obtained
42484598 | Ft. Griffin 69KV Station | Albany / Shackleford | Rebuild and reconductor approximately 0.81 mile section of the Albany-Putnam 69-kV transmission line between Albany and new Ft. Griffin Station to 138-kV standards. Continue to operate at 69 kV | 2018-01-03 | 2018-01-23 |  |  | 1817812.51 |  |  | 0 | 69 |  | 0.81 | 795 ACSS | Steel Mono Pole | Centerline | 0.81 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42484593 | Ft. Griffin 69KV Station | Albany / Shackleford | Reterminate the Albany-Rainey Creek 68kV line into the new Ft. Griffin station approximately 0.45 miles | 2017-12-07 | 2017-12-31 |  |  | 1034349.79 |  |  | 0 | 69 |  | 0.45 | 795 ACSS | Steel Mono Pole |  |  | 100 | 0.45 | 16 TAC 25.101 (c)(5)(A) | Consent Obtained
42618416 | Ft. Griffin 69KV Station | Albany / Shackleford | Rebuild and reconductor approximately 0.86 mile section of the Albany-Rainey Creek 69-kV transmission line between Albany and new Ft. Griffin Station to 138-kV standards. Continue to operate at 69 kV | 2017-12-07 | 2017-12-31 |  |  | 1880819.13 |  |  | 0 | 69 |  | 0.86 | 795 ACSS | Steel Mono Pole |  |  | 100 | 0.9 | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42479024a | Albany Foundry-Moran | Moran / Shackleford | Rebuild and reconductor approximately 8.90 miles of the Albany-Putnam 69-kV line from Albany Foundry-Moran | 2018-01-25 | 2018-04-18 |  |  | 8040670 |  |  | 0 | 69 |  | 8.9 | 795 ACSS | Steel Mono Pole | Centerline | 9.23 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42484591 | Quaint | Jones | Reterminate the Anson-Northwest Abilene 69kV line into the new Quaint Station approximately 0.6 miles | 2018-02-12 | 2018-06-20 |  |  | 3748249.51 |  |  | 0 | 69 |  | 0.6 | 795 ACSS | Steel Mono Pole |  |  | 100 | 0.6 | 16 TAC 25.101 (c)(5)(A) | Consent Obtained
42619328 | Quaint | Jones | Reterminate the Onyx-Ft. Phantom 69-kV line into the new Quaint Station approximately 0.3 miles | 2018-02-12 | 2018-06-20 |  |  | 1449249.13 |  |  | 0 | 69 |  | 0.3 | 795 ACSS | Steel Mono Pole |  |  | 100 | 0.3 | 16 TAC 25.101 (c)(5)(A) | Consent Obtained
42611959 | Truscott Humble Tap to Benjamin Tap Rebuild | Truscott / Knox | Rebuild and reconductor approximately 12.11 miles of the Truscott Humble Tap-Benjamin Tap 69-kV transmission line to 138-kV standards. Continue to operate at 69 kV | 2017-12-10 | 2018-06-29 |  |  | 8857917 |  |  | 20 | 69 |  | 12.11 | T2 477 ACSR HAWK | Steel Mono Pole | Varies | 12.11 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed. Utilizing Existing Easements
42724179 | Tardis 138-kV Station | Knox | Build a new 138-kV three breaker ring bus 3000 Amps/ 40 kA (ultimate design will be limited to a four breaker ring bus). Add SCADA at the station. | 2018-01-03 | 2019-11-09 |  |  | 6263000 |  |  |  |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42724196 | Benjamin 69-kV Substation | Benjamin/Knox | Expand existing Benjamin 69-kV station with 138-kV bus and switches and add a 138/12-kV transformer | 2018-01-03 | 2018-08-18 |  |  | 3282000 |  |  |  | 69 | 69 / 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42551751 | Abilene Plant: Change Relay Settings | Abilene/Taylor | Abilene Plant: Change relay settings to accommodate Abilene South to Abilene West Texas Gulf Tap 69-kV Rebuild | 2018-01-03 | 2018-03-31 |  |  | 293839 |  |  |  | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42611170a | Ely REA Tap (Capella Box Bay)-Merkel 69-kV Rebuild | Taylor | Rebuild and Reconductor the Ely REA Tap (Capella Box Bay) to Merkel 4.55 mile segment of the Ely REA Tap (Capella Box Bay) to Eskota 69-kV transmission line to 138-kV standards. Will continue to be operated at 69 kV. | 2018-01-02 | 2018-04-30 |  |  | 3000000 |  |  |  | 69 |  | 4.55 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 4.55 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42707021 | Cedar Hill-Edith Humble 69-kV Rebuild | Coke | Rebuild and Reconductor the Cedar Hill to Edith Humble 69-kV transmission line to 138-kV standards. Will continue to be operated at 69 kV. | 2018-01-08 | 2018-05-30 |  |  | 11937365 |  |  |  | 69 |  | 12.94 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 12.94 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42578959 | Carver Station | Sutton | Carver Station: Construct new 138kV-3000 amp, 40 kA four breaker-ring station | 2018-02-05 | 2018-12-31 |  |  | 9527329 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42578960 | Carver Station | Sutton | Sonora Station: Replace 138kV circuit breakers | 2018-02-05 | 2018-12-31 |  |  | 1054914 |  |  | 0 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42578953 | Carver Station | Sutton | Reterminate the Friend Ranch-Sonora 138kV Transmission Line into New Carver Station | 2018-02-05 | 2018-12-31 |  |  | 820481 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42578954 | Carver Station | Sutton | Reterminate the Live Oak-Sonora 138kV Transmission Line into New Carver Station | 2018-02-05 | 2018-12-31 |  |  | 848021 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42578957 | Carver Station | Sutton | Reterminate the Hamilton Road-Sonora 138kV Transmission Line into New Carver Station | 2018-02-05 | 2018-12-31 |  |  | 640456 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42578963 | Carver Station | Sutton | Friend Ranch Station:Update relay towards Sonora Station | 2018-02-05 | 2018-12-31 |  |  | 250725 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42729882 | Carver Station | Sutton | El Dorado Live Oak Station: Update relay towards Sonora Station | 2018-02-05 | 2018-12-31 |  |  | 272399 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42730541 | Carver Station | Sutton | Carver Bus Tie: Install a bus tie from Sonora Station 138kV bus to New Carver Station 138kV bus | 2018-02-05 | 2018-12-31 |  |  | 815390 |  |  | 0 |  | 138 | 0.2 | 477 KCM ACSR "Hawk" | Steel Monopole |  |  |  |  | 16 TAC 25.83(a)(3) | Within station property
42579281 | Vernon Main St. Substation | Vernon/Wilbarger | Install two 14.4 MVAR Capacitor Banks to the Vernon Main St. Substation 138kV bus | 2018-02-05 | 2018-06-29 |  |  | 2113300 |  |  | 0 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42630204 | Vernon Main St. Substation | Vernon/Wilbarger | Relocate transmission line structures on Vernon Main St - Oklaunion 138kV line to accommodate 1-14.4 MVAR capacitor bank. | 2018-02-05 | 2018-06-29 |  |  | 382057 |  |  | 0 | 138 |  | 0.03 | 795 KCM ACSR "Drake" | Steel H-Frame |  |  |  |  | 16 TAC 25.83(a)(3) | Within station property
42719352 | Abilene South - Asset Health Center Retrofit | Abilene/Taylor | Install Asset Health monitoring equipment on the 138kV Transformers | 2018-02-05 | 2018-03-01 |  |  | 451873 |  |  |  | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42681634 | Valentine Tap - DACR Gridsmart upgrades - Transmission Assets Only | Presidio | Transmission High-Side work for Distribution Automation Circiut Reconfiguration upgrades and associated circuit breaker upgrades | 2018-02-28 | 2018-06-21 |  |  | 262355 |  |  |  | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42738417 | Abilene Maple St station - DACR Gridsmart upgrades - Transmission Assets Only | Abilene/Taylor | Transmission High-Side work for Distribution Automation Circiut Reconfiguration upgrades and associated circuit breaker upgrades | 2018-02-26 | 2018-06-29 |  |  | 368611 |  |  |  | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42680890 | Abilene Oil Mill station - DACR Gridsmart upgrades - Transmission Assets Only | Abilene/Taylor | Transmission High-Side work for Distribution Automation Circiut Reconfiguration upgrades and associated circuit breaker upgrades | 2018-02-24 | 2018-08-08 |  |  | 246687 |  |  |  | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42680875 | Abilene Vogel St. station - DACR Gridsmart upgrades - Transmission Assets Only | Abilene/Taylor | Transmission High-Side work for Distribution Automation Circiut Reconfiguration upgrades and associated circuit breaker upgrades | 2018-04-19 | 2018-09-24 |  |  | 402175 |  |  |  | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42682644 | Walnut St. station - DACR Gridsmart upgrades - Transmission Assets Only | Abilene/Taylor | Transmission High-Side work for Distribution Automation Circiut Reconfiguration upgrades and associated circuit breaker upgrades | 2018-04-19 | 2018-09-24 |  |  | 373160 |  |  |  | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42680891 | Clyde station - DACR Gridsmart upgrades - Transmission Assets Only | Clyde/Taylor | Transmission High-Side work for Distribution Automation Circiut Reconfiguration upgrades and associated circuit breaker upgrades | 2018-03-12 | 2018-09-12 |  |  | 717806 |  |  |  | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42598869 | Alpine - Alpine REA 69-KV | Alpine/Brewster | Rebuild, Reconductor and Partially Relocate of 69-kV transmission line to 138-kV Standards. Continue to be Operate at 69-kV. | 2018-02-05 | 2018-06-01 |  |  | 9079106 |  |  | 1 | 69 |  | 8.16 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 8.16 | 100 | 1.32 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowners Noticed Consent, New Easement & Supplements were acquired as necessary
42629573a | Paint Creek - Haskell Tap 69-kV | Haskell | Rebuild 2.03 miles of wood double circuit H-frame and 9.53 miles of wood single circuit single pole transmission line from Paint Creek to Haskell Tap. New structures will be steel single pole with the 2 mile section rebuilt for continued double circuit operation and capable of 138-kV operation, but will continue to be operated at 69-kV at this time. One circuit reconductor is included for this project.. | 2018-02-05 | 2018-06-08 |  |  | 14204835 |  |  | 0 | 69 |  | 11.56 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 11.56 | 100 | 2 | 16 TAC 25.101 (c)(5)(B) | Landowner consent aquired as necessary for Blow-Out requirements Landowners Noticed
42629583 | Haskell to Paint Creek | Haskell | Reconductor of 2.03 miles of the rebuilt double circuit H-frame in Project No. 42629573a that goes from Paint Creek to Haskell. | 2018-02-05 | 2018-06-08 |  |  | 2334222 |  |  | 0 | 69 |  | 2.03 | 795 KCM ACSS "Drake" |  |  | 2.03 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42579891 | McElroy: Upgrade Station | Crane | Upgrade McElroy station terminal equipment with a minimum of 1200 Amps. Upgrade switches to 1200 Amps. | 2018-02-05 | 2018-03-10 |  |  | 597468 |  |  |  | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42690805 | Sawgrass - WTX Gulf | Abilene/Taylor | Replace two poles on structures 1/1 and 1/2 on the Sawgrass 69kV Line. Remove and install Conductor between 5A/2 and 1/2 structure. | 2018-02-05 | 2018-03-31 |  |  | 455658.84 |  |  |  | 69 |  |  | 795 ACSS | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Consent Obtained
42578730 | Lotebush Station | Reeves | Lotebush 138-kV Station: Construct a New 11-Breaker, 5-Ring Bus 138-kV Station | 2018-02-24 | 2018-11-02 |  |  | 15564172 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42578748 | Lotebush Station | Reeves | Pig Creek-Permian Basin 138-kV: Terminate the Pig Creek-Permian Basin 138-kV transmission line into new Lotebush 138-kV Station | 2018-02-24 | 2018-11-02 |  |  | 882118 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within New Station Property
42625103 | Bronte-Bronte Atlantic 69-kV Rebuild | Coke | Rebuild and Reconductor the Bronte to Bronte Altantic 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2018-02-24 | 2018-10-17 |  |  | 4929565 |  |  | 0 | 69 |  | 3.75 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 3.75 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42583744 | Crane-McElroy 69-kV Rebuild | Crane | Rebuild and Reconductor the Crane to McElroy 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2018-02-24 | 2018-04-18 |  |  | 5331005 |  |  | 0 | 69 |  | 2.27 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 2.27 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42694371 | Radium - replace CB 5905 and upgrade relays | Jones | Replace CB-5905, Disconnect Switches; Install New Hamlin line Circuit Breaker; Install 69kV bus CCVT's; Add 16ft x 18ft DICM expansion. Remove old control house | 2018-03-05 | 2018-05-31 |  |  | 1966260 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42677375 | Cactus Flats Temporary Interconnect: SAPS to Yellow Jacket 138-kV Line Tap | Concho | Install jumpers on the APS to Yellow Jacket 138-kV transmission line to provide a temporary interconnect to RES Cactus Flats, LLC 150-MW Wind Farm | 2018-03-20 | 2018-05-05 |  |  | 221905 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Generator-Owned Station Property
42681178 | Cactus Flats Temporary Interconnect: Metering | Concho | Install metering, RTU, SDR and DME inside Cactus Flats Station (generator-owned station) | 2018-03-20 | 2018-05-05 |  |  | 780000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Generator-Owned Station Property
42677378 | Cactus Flats Temporary Interconnect: San Angleo Power Station Substation Relay Upgrade | San Angelo/Tom Green | Replace relays and carrier equipment to match Cactus Flats Temporary Tap and future Treadwell Station relays | 2108-03-20 | 2018-05-05 |  |  | 393599 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42625104 | Robert Lee-Bronte 69-kV Rebuild | Coke | Rebuild and Reconductor the Robert Lee to Bronte 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2018-03-19 | 2018-12-21 |  |  | 9023449 |  |  | 0 | 69 |  | 9.1 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 9.1 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42583750 | Kinnison Box Bay | Crane | Construct 138-kV Box Bay at Crane Tap #2. Will be operated at 69 kV | 2018-03-19 | 2018-06-28 |  |  | 1326140 |  |  | 0 |  | 69 |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.83(a)(3) | Constructed within existing easements. Landowners Noticed
42583736 | Crane-Kinnison 69-kV Rebuild | Crane | Rebuild and Reconductor the Crane to New Kinnison Box Bay 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2018-03-19 | 2018-06-28 |  |  | 3566650 |  |  | 0 | 69 |  | 1.09 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 1.09 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42583730 | Texas-New Mexico Pipeline (TXNMP) - Sage 69-kV Rebuild | Crane | Rebuild and Reconductor the TXNMP to Sage 69-kV transmission line to 138-kV standards. Will continue to operate at 69-kV. | 2018-03-19 | 2018-06-28 |  |  | 6625576 |  |  | 0 | 69 |  | 2.53 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 2.53 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42583749 | Cardona Switch | Crane | Construct 138-kV platform switch with H frame structure at Cardona (formerly Crane Airport SW 6698). All series equipment shall be rated for a minimum of 1200 Amps. Will continue to be operated at 69-kV. | 2018-03-19 | 2018-06-28 |  |  | 469838 |  |  | 0 | 69 | 69 |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.83(a)(3) | Constructed within existing easements. Landowners Noticed
42681653 | Kelton Switch | Crane | Construct 138-kV platform switch with H frame structure at Kelton (formerly Crane Airport SW 6697).All series equipment shall be rated for a minimum of 1200 Amps. Will continue to be operated at 69-kV. | 2018-03-19 | 2018-06-28 |  |  | 469840 |  |  | 0 | 69 | 69 |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.83(a)(3) | Constructed within existing easements. Landowners Noticed
42584089 | Hawley Tap - Quaint Switch Station 69-kV Rebuild | Hawley/Jones | Rebuild and reconductor the Hawley Tap to Delk Tap 69-kV transmission line to 138-kV standards and terminate into new Quaint Switch Station. Will continue to be operated at 69-kV. | 2018-03-18 | 2018-06-30 |  |  | 3377434 |  |  | 0 | 69 |  | 4.22 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 4.22 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42584095 | Onyx Switch Station - Onyx Tap 69-kV Rebuild | Jones | Rebuild and reconductor Onyx Switch Station to Onyx Tap 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2018-03-18 | 2018-05-12 |  |  | 1731192 |  |  | 0 | 69 |  | 1.41 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 1.41 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42624965a | San Angelo Concho - San Angelo Lake Nasworthy (CVREA) 69-kV Rebuild | San Angelo/Tom Green | Rebuild and reconductor the San Angelo Concho to San Angelo Lake Nasworthy (CVREA) 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2018-04-02 | 2018-06-01 |  |  | 3351265.74 |  |  | 0 | 69 |  | 5.3 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 5.3 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42705005 | Rio Pecos - Sun Valley 69-kV Rebuild | Crane,Pecos | Rebuild and reconductor the Rio Pecos to Sun Valley 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2018-05-04 | 2018-10-10 |  |  | 7886632 |  |  | 0 | 69 |  | 9.5 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 9.5 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42705002 | Sun Valley - Masterson Field 69-kV Rebuild | Pecos | Rebuild and reconductor the Sun Valley to Masterson Field 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2018-08-23 | 2018-12-21 |  |  | 6032579 |  |  | 0 | 69 |  | 7.2 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 7.2 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42629566a | Onyx SW-Ft. Phantom Clear Fork Pump Station 69-kV Rebuild | Abilene/Jones | Rebuild and reconductor the Onyx SW to Ft. Phantom Clear Fork Pump Station 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2019-02-22 | 2019-04-24 |  |  | 17283518 |  |  | 0 | 69 |  | 6.82 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 6.82 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## EntryInstructions
Column: | General Instructions for Entering Information
NOTE: Please use "na" whenever appropriate to reduce ambiguity.
Utility's Project Number | Enter the Utility's Project Number.
Project Name | Enter the name of the project. If possible, use the same name as was reported to ERCOT in any reports.
Location (City/County) | Enter the names of the counties where the project is located. Also enter the names of cities, if appropriate. Please delineate all county and city names with commas only. (e.g., Liberty, Chambers, Anahuac, etc.)
Description | Describe the project in enough detail to allow the Commission to ensure that the work does not require a CCN, if the utility does not intend to apply for a CCN. Include any significant or relevant detail not being considered in the individual column entries.
Estimated (or Actual) Start Date | Enter the estimated project starting date. When construction begins, please replace the estimated date with the actual date of the start of construction.
Finish Date (Construction Complete) | Enter the date (dd/mm/yy) when the construction related to the project has been completed.
Date Energized (If Applicable) | Enter the date (dd/mm/yy) the project was energized or restored to service (if applicable).
Initial Estimated Project Cost | Enter the estimated cost from the CCN application or the first estimate for exempt projects, whichever is applicable. This number should not be changed in future months.
Final Estimated Project Cost | Enter the latest available estimated cost for the month that construction starts. This number should not be changed after construction begins.
Final Actual Project Cost | Enter the actual project cost after all final costs have been determined.
% Variance | The cells contain a formula for calculating the percent variance of the final actual cost with respect to the final estimated cost. This is essentially a calculation of the percent of the cost over-run.
Percent Complete | State the construction progress of the report as a percent. Please use only an integer and do not write"%." Do not report the percent of money spent.
Existing Voltage | Enter the nominal system existing voltage, if any. In the event of a voltage upgrade, this will be the "before" voltage. If the project is for a new line, enter "na." For projects involving multiple voltages, please delineate the voltages by a comma, e.g., "69,138" and explain further in comments or project description, if needed for clarification. Please do not write "volts."
Upgraded or New Voltage | Enter the nominal system voltage after upgrading or if new line construction is involved. Please use the same practices described in the"Existing Voltage" column.
Circuit Length (Miles) | Enter the total circuit length. Example: For a new double-circuit line using 10 miles of new ROW, the circuit length would be 20 miles. Please enter only a number, if possible. Do not write "miles."
Conductor Type & Size & Bundling | Describe the conductor characteristics, including whether double or single circuit or mixed. Length explanations should be made in the Project Description column.
Structure Type(s) | Describe structures types and materials used.
Existing ROW Width (Feet) | Enter width of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Entries such as "60,80,100" or "60 - 100" or "centerline" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
Existing ROW Length (Miles) | Enter length of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Make detailed explanations, if needed, elsewhere. Please do not write "miles."
New ROW Width (Feet) | Enter width of new ROW. The entry type is unrestricted. Entries such as "60,80,100" or "60 - 100" or "centerline" or "railroad" or "street" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
New ROW Length (Miles) | Enter new (additional) ROW length, in miles. Please do not write "miles."
Rule Section or PUC Control Number | Enter the PUC Rule 25.101 section(s) which are applicable. For multiple section applicability, please delineate by commas, e.g., "25.101(c)(5)(A),25.101(c)(5)(B)" for a project incorporating a line extension (A) and a voltage upgrade on the existing line which is being extended(B). If the project is approved under a CCN, please enter the 5-digit control number. Please do not write "docket," "CCN" or other indicators. Should the project encompass work done under both CCN and exempted sections, follow the same practices and delineate with commas.
Comments | Enter information not included elsewhere, including reimbursed costs.
Note on A16: aboling: If applicable.

## Sugg.Practices(TabNotOnWebsite)
SUGGESTED SPREADSHEET PRACTICES
VERY IMPORTANT: Any new or revised entry MUST be entered using a red font. In the month following the red font entry, change the previous month's red entries back to black and make any new entries for the new month in red. This aids PUCT staff in quickly identifying any changes from the previous month’s report.
Please enter your Utility Name and Month in the top center header. Also, please enter the appropriate data in the bottom left footer. Your personal contact information WILL NOT appear in the report posted at the PUC website. Please do not change the right-hand header and footer.
Adjust Row and Column Heights and Widths to a pleasing dimension as you wish. Vertical centering is recommended to improve readability when using the "Wrap Text" Feature.
Please do not use multiple Rows for any project. Each project should occupy only one line. If necessary, however, multiple project numbers may be entered in the same cell in the "Project Number" column. Use the "Wrap Text" feature throughout the spreadsheet and the "Row Height Autofit" feature for all lines except for the header.
Please do not insert extra rows between projects. PUCT staff must delete any extra lines to properly compile report data.
Please do not enter “NA” or any other text in the "Estimated," "Final" or "% Variation" numerical columns. Text in those columns must be manually removed before PUC staff can compile the report.
A percent variation calculation formula is contained within the "% VAR." column. Please leave this formula as it is.
In the "Rule Section...." column, enter the PUC assigned docket number (if project requires a CCN) or the PUC exemption qualifying section or sections (if the project is exempt from CCN requirements). Do not enter "EXEMPT."
Monthly Construction Progress Reports may be found at the PUCT website. Individual utility MCPR worksheets for each utility are contained within each month's compiled report at: http://www.puc.state.tx.us/electric/reports/cpr/index.cfm.
Please contact Allen Boling at (512)936-7402 or allen.boling@puc.state.tx.us for assistance or clarification, including questions about MS Excel spreadsheets.
For Subst. Rule §25.83(c)(3) notice compliance purposes, the PUC contact will be Allen Boling, at (512) 936-7402 or (888) 782-8477. Hearing and speech-impaired individuals with text telephones (TTY) may contact Mr. Boling at (512) 936-7136 or Relay Texas at (800) 75-2989.
Suggested Language (after providing utility contact information with the utility as the primary contact): "In the event you have unresolved questions or complaints after discussing theses activities with (utility name), you may contact Allen Boling at the PUCT, at P.O. Box 13326, Austin, Texas 78711-3326, or call Mr. Boling at (512)936-7402 or (888)782-8477 or by e-mail at allen.boling@puc.state.tx.us. Hearing and speech-impaired individuals with text telephones (TTY) may contact Mr. Boling at the PUCT and (512)936-7136 or Relay Texas at (800)735-2989.