## SWEPCO TEXAS MPR
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
42782325 | Hallsville South POD 138-kV Box Bay | Harrison | Install 138-kV Station Box Bay (Low Bay), with 2-3000A, Auto-sectionalized switches, 1- Scada controlled tap switch, and 1-combo unit maintenance switch. Install fence, grid, and rock and tie grid with URECC. | 2019-04-15 | 2019-07-14 |  |  | 3053090 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Written consent acquired to begin construction activites
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.