SOAH DOCKET NO.   473-19-3864

PUC DOCKET NO. 49421

| APPLICATION OF CENTERPOINT ENERGY HOUSTON ELECTRIC FOR AUTHORITY TO CHANGE RATES | § § § § § | BEFORE THE STATE OFFICE OF ADMINISTRATIVE HEARINGS |
| --- | --- | --- |

##### DIRECT TESTIMONY OF

##### TOM SWEATMAN

INFRASTRUCTURE AND RELIABILITY DIVISION

PUBLIC UTILITY COMMISSION OF TEXAS

JUNE  12, 2019

TABLE OF CONTENTS

I. STATEMENT OF QUALIFICATIONS	3

II. PURPOSE OF TESTIMONY	4

III.  TRANSMISSION INVESTED CAPITAL	6

IV.  SUMMARY	9

ATTACHMENTS

TS-1 Qualifications of Tom Sweatman

TS-2 16 Texas Administrative Code § 25.231(c)(2)(A)

TS-3 List of Dockets Containing Testimony of Tom Sweatman

TS-4 Worksheet of Recommended Disallowances

TS-5 Selected RFI Responses

I. STATEMENT OF QUALIFICATIONS

Q. 	Please state your name, occupation and business address.

A. 	My name is Tom Sweatman. I am employed by the Public Utility Commission of Texas (PUC) as an Engineering Specialist in the Infrastructure and Reliability Division. My business address is 1701 North Congress Avenue, Austin, Texas 78701.

Q. 	Please briefly outline your educational and professional background.

A. 	I have a Bachelor of Science degree in Electrical Engineering from Texas A&M University. I was an engineer at Texas Electric Service Company (TESCO-now Oncor) for ten years, a Lieutenant in the U.S Army for two years, Director of Engineering for the Texas PUC for eight years, and Executive Director for the Electric Reliability Council of Texas (ERCOT) for 14 years.  I have currently been employed by the PUC on a part time basis since February 2015. A more detailed summary of my experience is provided in Attachment TS-1.

Q. 	Are you a registered professional engineer?

A. 	I was a Registered Professional Engineer in the State of Texas, Serial Number 31083, from approximately 1968 to 2002.  I allowed my license to expire following my retirement from ERCOT.

Q. 	Have you previously filed testimony before the Commission?

A.	I provided written Staff testimony on two occasions since returning to the PUC. One was on May 23, 2016 in Docket 45787, Application of AEP Texas Central Company for Approval of a Distribution Cost Recovery Factor.  The other was in docket 47691:  Joint Application of Brazos Electric Power Cooperative, Inc. and AEP Texas Inc. to Amend Certificates of Convenience and Necessity for the Gyp to Benjamin 138-kv Transmission in King and Knox Counties, Texas.  I also provided staff testimony on a few occasions during my initial employment with the Commission during 1975 – 1983 in my position as Chief Engineer and Director of Engineering on the subjects of depreciation and natural gas as a boiler fuel.  I supervised the engineers in the Engineering Division as they testified regarding service area certification, depreciation, rate design, service quality, transmission line certification and other electric, telephone and water utility issues.  Attachment TS-3 is a list of additional PUC dockets for which I have provided testimony.

II. PURPOSE OF TESTIMONY

Q. 	Please briefly describe the application in this docket.

A.	In this docket, CenterPoint Energy Houston Electric (CEHE) is seeking approval from the Commission to change its utility rates for its service area. CEHE provides service to customers in Houston, Texas and the outlying areas, and is a member of ERCOT.

Q. 	What is the purpose of your testimony in this proceeding?

A. 	The purpose of my testimony is to present recommendations concerning several project costs overruns CEHE is seeking to recover in this rate case.

Q. 	What regulations have you referred to in making your evaluation and arriving at your conclusions and recommendations?

A.	I have referred to 16 Texas Administrative Code (TAC) § 25.231(c)(2)(A) and the Public Utility Regulatory Act (PURA) § 36.112(a)-(b) (Attachments TS-2 and TS-3, respectively).

Q. 	What else did you rely upon to reach your conclusions?

A. 	I have relied upon the CEHE’s testimony, intervenor testimony, and CEHE’s responses to requests for information (RFIs).

Q. 	What issues identified by the Commission in the Preliminary Order of this docket will you address?

A.	In my testimony, I partially address the following issues that the Commission identified in the Preliminary Order:

Issue 10: What are the reasonable and necessary components of CenterPoint’s rate base?

Issue 12: What amount of CenterPoint’s invested capital has not previously been subject to a prudence review by the Commission? If there are any such amounts, what are the amounts, for what facilities, property, or equipment were the investments made, and were the amounts prudently incurred? What amount, if any, of allowance for funds used during construction (AFUDC) is being transferred to invested capital in this proceeding? If AFUDC is being transferred, for what facilities and at what rate was the AFUDC accrued?

Q.	How is your testimony organized?

A. 	My testimony begins in Section I with a statement of my qualifications. In Section II,

I discuss the purpose of my testimony, and in Section III, I discuss several transmission and substation projects that CEHE is attempting to include in the calculation of rates and why those particular projects, or portions of them, should not be included. A summary and conclusion of my testimony are found in Section IV.

Q. 	Have you prepared attachments related to your testimony?

A. 	Yes, Attachment TS-4 is a spreadsheet I created that lists several projects for which CEHE is seeking to capitalize and add to its rate base to obtain rate relief.  These are projects that have been completed since the last rate case and experienced a greater than 10% difference in the estimated cost and the final cost.  The attachment contains calculations I performed based on information provided by CEHE.

III.  TRANSMISSION INVESTED CAPITAL

Q.	Which projects are you addressing in your testimony?

A.	I am addressing those projects listed in Attachment TS-4, which include the Alexander Island Substation, the La Marque Substation, the Sandy Point Substation, the Dow Substation, the Flewellen-Fort Bend Line, the Fort Bend- Rosenberg Line, the W.A. Parrish Substation, the Jones Creek Substation, the Springwood Station, and the Tanner Station.

Q.	What is your recommendation?

A.	I am recommending disallowance of the amount of cost overruns exceeding 10% of the estimated cost of the projects listed in Attachment TS-4.  The amounts I am recommending for disallowance have been broken down by FERC accounts.  The overall disallowance that I am recommending totals $20, 328,742.

Q.	What is the basis for your recommendation of disallowance?

A.	It may be reasonable for the final cost of major utility projects to be somewhat different than the estimate for obvious reasons.  In this instance I recommend that a reasonable project cost overrun be limited to 10% of the estimate for ratemaking purposes, absent a well-substantiated justification.  I base this recommendation on my own experience of project involvement and management. Additionally, this approach is consistent with my review of numerous Certificate of Convenience and Necessity dockets in which companies typically include a cost contingency for overruns of 10-15% and is the same as the PUC’s rules regarding allowance for contingency for nuclear decommissioning costs in 16 TAC 25.304(h).

Q.	Please summarize your recommended disallowances.

A.	For each of the nine projects listed on Attachment TS-4, I calculated the amount of the final cost greater than 110% of the estimate.  It is these amounts for which I am recommending disallowance.

Q.	Has CEHE addressed these cost overruns?

A.	Yes, in response to PUC RFI 06-24.  I will address CEHE’s response for each project, and provide my opinion:

a) Alexander Island Substation: CEHE stated that the reason for the overrun was an error in which it, or its contractors, mistakenly located the foundations in the wrong place, which had to be removed and replaced.  In my opinion, the cost for this mistake should not be paid by the CEHE’s customers.

b)  La Marque Substation:  CEHE explained that tower designs and relocation were the reasons for the cost overrun.  Again, CEHE should have foreseen these design errors earlier and corrected them.  In my opinion, the cost for this mistake in siting should not be paid by CEHE’s customers.

c)  Sandy Point Substation:  CEHE explained the substation site changed after the initial estimate, requiring more temporary work than expected and resulting in increased labor costs.  In my opinion, better management and oversight should have caught this problem and compensated for it; thus, the cost for these mistakes should not be paid by CEHE’s customers.

d)  Dow Substation:  In response to PUC RFI 1-38 CEHE stated, “The project carried a system wide benefit and was not specific to a single customer.”  Additionally, that response indicates that no Cost in Aid of Construction was charged.  In response to PUC RFI 6-24, CEHE stated that, “The final actual cost was paid in full by the customer for this project.  The company is not seeking recovery of these costs in this case.”  These two answers are contradictory, making it unclear whether CEHE is seeking recovery of costs associated with the Dow Substation project.  Consistent with my analysis of cost overruns presented for other projects in my testimony, I am recommending the disallowance of cost overruns in excess of 10% for this project.

e)  Flewellen - Fort Bend:  CEHE fails to explain the cost overrun for this project; thus, I am recommending the disallowance.

f)  Fort Bend – Rosenberg:  CEHE explains that following the initial filing of the project, significant changes in the line routing were made due to ROW “constraints,” requiring negotiations with parties and requiring additional “bypass work” and increased labor costs following the filing of the project.  In my opinion, better management and oversight should have caught this problem and compensated for it; thus, the cost for these changes should not be paid by the CEHE’s customers.

g)  W. A. Parrish Substation:  CEHE explained that a variety of small cost differences to labor and materials was the reason for this cost overrun.  In my opinion, this explanation is insufficient. CEHE has not carried its burden of proving that these additional costs were prudent, and therefore, these costs should not be paid by CEHE’s customers.

h)  Jones Creek:  CEHE explains that the project included in its response to PUC 1-38 covered only the transmission work to connect Jones Creek Substation for which the cost overrun was less than 10% of the estimate.  This does not explain the 89% in cost overruns for the entire project.  Additionally, in response to PUC RFI 11-2, CEHE mentioned that part of the cost overruns was associated with the addition of a distribution substation, but no information regarding the need for this substation was included in CEHE’s Application or discovery response.  For these reasons, I am recommending the disallowance of the overrun costs associated with this project.

i)  Springwood:  The Company has indicated the 15.8% cost overrun reported is for the transmission construction only, and not the entire project.  However, no explanation for the transmission cost overrun was provided in CEHE’s Application or discovery response.  Therefore, I am recommending disallowance for the overrun greater than 10%.

j)  Tanner:  CEHE has indicated the 16.3% cost overrun reported is for the transmission construction only, and not the entire project.  However, no explanation for the transmission cost overrun was provided in CEHE’s Application or discovery response.  Therefore, I am recommending disallowance for the overrun greater than 10%.

k)  Sandy Point:  CEHE explained the substation site changed, requiring more temporary work than expected and increased labor costs.  In my opinion, this oversight requires greater explanation, and I am therefore recommending disallowance for the overrun greater than 10%.

Q.	Your worksheet lists Sandy Point twice with different information and disallowances.  Please explain.

A.	In its original response, Sandy Point was listed twice, as if it were two separate projects.  I can only surmise that it was indeed two separate projects, or the sets of information are separate parts of the same project.  Either way, I used both sets of CEHE’s numbers to make my calculations and recommend disallowances for both.

Q.	What information did you rely on for your recommendations?

A.	I used the information provided by CEHE in its Application and in its responses to PUC RFIs 1-38, 1-40, 6-24, and 11-2, which are attached in TS-5.

IV.  SUMMARY

Q.	Please summarize your testimony.

A.	I recommend that the aforementioned cost overruns be removed from CEHE’s Transmission Invested Capital.

Q.	Does this conclude your testimony?

A.	Yes, it does.

ATTACHMENT TS-1

Qualifications of Tom Sweatman

TOM SWEATMAN

ENGINEERING SPECIALIST

Public Utility Commission of Texas

1701 North Congress Avenue

Austin, TX 78701

512-762-4646

Tom.Sweatman@puc.texas.gov

Education

Texas A&M University in College Station, Texas

B.S. Electrical Engineering

Professional Experience

Public Utility Commission of Texas (February 1, 2015 – present):

Engineering Specialist, Engineering Section, Infrastructure and Reliability Division

Electric Power Consultant (2002 – 2014):

August to November 2013

Submitted expert testimony for landowner client in Texas PUCT Docket 41606: Joint Application of Electric Transmission Texas, LLC and Sharyland Utilities, L.P. to Amend Their CCNs for the North Edinburg to Loma Alta Double-Circuit 345-kv Transmission Line in Hidalgo and Cameron Counties.  The final order was favorable to client.

February to April 2013:  Submitted expert testimony for landowner client in Texas PUCT Docket No. 40685: Application of SWEPCO to Amend its CCN for a Proposed 345kV Double-Circuit Transmission Line within Bowie County.  The final order was favorable to the client.

September to November, 2010

Provided expert testimony for landowner clients in Texas PUC Docket 38354 – Amend CCN for 345-kv CREZ McCamey D to Kendall to Gillespie Transmission Line.  Final order was favorable to the client.

July to November, 2010

Provided expert testimony for landowner clients in Texas PUC Docket 38290 – Amend CCN for 345-kv CREZ Hereford to White Deer Transmission Line.  Final order was favorable to the client.

2008-2009

Successfully assisted Stirling Energy Systems in finding suitable land for a solar project near Marfa, TX.

Oct 2008 – Mar 2009

Provided expert testimony for Occidental Power Marketing, L.P. in Texas SOAH Docket 473-08-3165, PUC Docket 35690, Petition of Big Country Electric Cooperative, Inc. for a Cease and Desist Order

February 2006

Submitted written expert testimony for Franklin County Power of Illinois vs Sierra Club concerning status of construction of 600 MW Coal Fired Power Plant.

January and April, 2002

Provided expert testimony in Texas PUC Docket No. 24815, Complaint of Fayette Electric Cooperative, Inc. against The City of Schulenburg, Texas concerning service area boundary dispute re PUC Docket 17.  Deposition in January, 2002.  Live hearing testimony April 16, 2002.

Electric Reliability Council of Texas (1986 – 2002):

December 1986 to January 1996

Executive Director:  First and only individual to hold this position.  Established a technical staff to support the ERCOT Board of Directors, committees, subcommittees, task forces and working groups.  Provided liaison with ERCOT members to deal with competitive pressures in a regulated industry.  Coordinated the transition of ERCOT from an all utility organization to one that included cogeneraters, independent power producers and power marketers.  Performed duties as the ERCOT Regional Manager for the North American Electric Reliability Council (NERC).

January 1996 to July 2000

Administrative Director:  Persuaded the Texas PUC to designate ERCOT to establish an Independent System Operator (ISO) for the region. Directed the reorganization of ERCOT to become the nation’s first ISO, including assembling the initial 30 member ISO operating staff and leading the diverse selection committee to choose an ISO Director.  This required intense coordination of the ERCOT Board, committees and working groups.  Provided liaison with the PUC Chairman, Pat Wood, to insure a smooth transition to retail deregulation.

July 2000 to November 2002

Director of New Facilities:  Represented ERCOT management to insure success in the design and construction of the facilities to house the ERCOT Primary and Backup ISO facilities in Taylor and Austin, Texas.  Insured liaison between ERCOT personnel and architect/engineer, contractor and subs.  Made design/cost decisions at the level below top management.  Advised the project team concerning the electric power industry as necessary.

Utility Consultant (July 1984 - December 1986):

Provided managerial, rate and certification assistance to electric I.O.U.’s, municipalities, electric cooperatives, and private water utilities when dealing with regulatory authorities.

Texas Public Utility Commission (December 1975 to July 1984):

Chief Engineer and Director of Engineering:   First individual to hold this position following the legislation creating a public utility commission for Texas.  Established and supervised the Engineering Division of approximately 20 engineers and support staff which provided technical expertise and testimony in rate review, depreciation techniques and licensing of electric, telephone and water utilities.  Reported directly to the three commissioners.  Along with the commissioners and other directors, created the Substantive Rules governing pricing and service of electric, telephone and private water utilities.  Personally testified in certification and rate cases and supervised other engineers in doing the same.

Texas Electric Service Co. (now TXU Energy)  (May, 1963 to December 1975);

Executive Level Special Projects Team:  Followed legislation and provided presentations to mid and upper management.

Manager of Power Plant Construction:  Completed the successful construction of the Permian Basin Unit #6 540 megawatt gas-fired base load generating unit and the Handley Units #4 and #5 400 megawatt peaking units.

Plant Electric Maintenance Engineer:  Inspected and approved all electrical work done by contractor in the construction of Eagle Mountain Unit #3 400 megawatt gas-fired peaking unit and Permian Basin Unit #6.

Electric Distribution Design Engineer:  Designed relay systems commensurate with distribution system additions.

Protective Relay Engineer:  Designed protective relay systems for the Odessa Transmission Division.

Facilities Testing Engineer:  Supervised and conducted oil, DC, ohm resistance and gas testing of high voltage transformers and circuit breakers.

(From May 1964 to May 1966, served as a Second and First Lieutenant in the U.S. Army Air Defense School at Fort Bliss, Texas as a Branch Chief and basic electricity instructor.)

Field Inspection Engineer:  Provided field inspection of construction of the 90-mile Odessa-Big Spring 345kv transmission line.

Publications

“Progressive Test Program Pays Off”, Transmission & Distribution magazine, December, 1968

“Automatic Carrier Testers Increase Transmission Line Reliability”, Transmission & Distribution magazine, May, 1972

ATTACHMENT TS-2

16 TAC § 25.231(c)(2)(A)

16 TAC § 25.231(c)(2)(A)

ATTACHMENT TS-3

List of Dockets Containing Testimony of

Tom Sweatman

List of Dockets Containing Testimony of Tom Sweatman

Docket 24814:  Complaint of Fayette Electric Cooperative, Inc., Against the City7 of Schulenburg, Texas

Docket 35690: Petition of Big Country Electric Cooperative, Inc., for a Cease and Desis Order Against Tenaska-Oxy Power REP Services, L.P. and TXU Energy

Docket 38354:  Application of LCRA Transmission Services Corporation to Amend Its Certificate of Convenience and Necessity for the Proposed McCamey D to Kendall to Gillespie 345-kv CREZ Transmission Line in Schleicher, Sutton, Menard, Kimble, Mason Gillespie, Kerr, and Kendall Counties, Texas

Docket 40685:  Application of Southwestern Electric Power Company to Amend its Certificate of Convenience and Necessity for a Proposed 345-kv Double-Circuit Transmission Line in Bowie County

Docket 45787:  Application of AEP Texas Central Company for Approval of a Distribution Cost Recovery Factor

Docket 47691:  Joint Application of Brazos Electric Power Cooperative, Inc. and AEP Texas Inc. to Amend Certificates of Convenience and Necessity for the Gyp to Benjamin 138-kv Transmission in King and Knox Counties, Texas

ATTACHMENT TS-4

Worksheet of Recommended Disallowances

ATTACHMENT TS-5

Selected RFI Responses

# CenterPoint’s Responses to PUC RFIs 1-38, 1-39, 1-40, 1-42, 6-24, 11-1, and 11-2

The information in TS-4 was derived from CEHE’s responses to PUC RFI’s 1-38, 1-40, and 6-24.