## Staff 18-3
Row Number | Project Name, (with CCN Docket No., if any) | Total "Life to Date" Project Cost as of December 31, 2019 in dollars | Estimate of Remaining Trailing Costs Yet to be Incurred on Project in dollars | Description of the Types of Charges that Comprise the Remaining Trailing Costs Yet to be Incurred
1 | Outpost Substation | 5478304.82 | 51000 | Trailing vendor invoices for necessary relay changes at Coulter Substation, final material issues and returns, and completion of as-built drawings and records
2 | Atoka to Eagle Creek 115-kV Line | 24926178.73 | 2500 | Final material issues and returns and completion of as-built drawings and records
3 | Carlisle to Wolfforth 230-kV Line, CCN Docket 42729 | 30610705.23 | 2500 | Final material issues and returns and completion of as-built drawings and records
4 | Needmore Switching Station | 30610.95 | -30611 | Have agreement with customer to pay total cost of the project - final true-up of project costs pending
5 | Blanco Switching Station | -21958.55 | 21959 | Have agreement with customer to pay total cost of the project - final true-up of project costs pending
6 | Lost Draw Switching Station | -85976.24 | 85976 | Have agreement with customer to pay total cost of the project - final true-up of project costs pending
7 | Ink Basin Interchange | 15050944.88 | 100000 | Trailing vendor invoices for necessary relay changes at Yoakum County Interchange and Denver City Interchange, final material issues and returns, and completion of as-built drawings and records
8 | Quincy Switching Station | 8949545.99 | 355000 | Costs to extend road and underground municipal utilities to City of Lubbock specifications, final material issues and returns, and completion of as-built drawings and records
9 | Mahoney Switching Station | 5509302.06 | 45000 | Trailing vendor invoices for materials and services, final material issues and returns, and completion of as-built drawings and records
10 | Mustang to Shell CO2 115-kV Line, CCN Docket 47585 | 18989709.06 | 100000 | Storm water pollution protection plan inspection and closeout, trailing vendor invoices for required relay upgrades at Yoakum County Interchange and Denver City Interchange, final material issues and returns, and completion of as-built drawings and records
11 | NE Hereford to La Plata 115-kV Line, CCN Docket 45158 | 9034037.57 | 2500 | Final material issues and returns and completion of as-built drawings and records
12 | La Plata Substation | 4116240.9 | 1500 | Final material issues and returns and completion of as-built drawings and records
13 | Livingston Ridge to Sage Brush 115-kV Line | 16808132.21 | 1500 | Final material issues and returns and completion of as-built drawings and records
14 | Hobbs Plant to Kiowa 345-kV Line | 53187061.45 | 140000 | Storm water pollution protection plan inspection and closeout, right of way remediation, final material issues and returns, and completion of as-built drawings and records
15 | Kiowa Interchange | 12342480.26 | 1500 | Final material issues and returns and completion of as-built drawings and records
16 | Kiowa to North Loving 345-kV Line | 29491611.495 | 76500 | Storm water pollution protection plan inspection and closeout, right of way remediation, final material issues and returns, and completion of as-built drawings and records
17 | North Loving to China Draw 345-kV Line | 29838359.765 | 50000 | Storm water pollution protection plan inspection and closeout, right of way remediation, final material issues and returns, and completion of as-built drawings and records
18 | Yoakum to Hobbs Plant 345-kV Line, CCN Docket 44726 | 77685845.53 | 100000 | Storm water pollution protection plan inspection and closeout, right of way remediation, final material issues and returns, and completion of as-built drawings and records
19 | Greyhound to Kilgore 115-kV Line | 9368812.95 | 2000 | Final material issues and returns and completion of as-built drawings and records
20 | Capitan To Chaves Co. 115-kV Line | 13387851.09 | 0 | Cost listed is final cost for project
21 | Carpenter Switching Station | 14164320.09 | 1500 | Final material issues and returns and completion of as-built drawings and records