## MonthlyReportForm
Utility Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
17T63124 | Wink to Culberson 138 kV: West of Pecos Point of Interconnection | City of Orla | Establish a point of interconnection to the West of the Pecos Solar LLC generating facility from the Riverton Switching Station on the Wink - Riverton - Culberson 138 kV transmission line. | 2019-07-25 | 2019-11-08 | 2019-11-08 | 650000 | 650000 |  |  | 100 | na | 138 | 0.9 | 795 ACSR | Steel Poles | na | na | 70 | 0.71 | 25.101(c)(5)(A)
16T65092 | Cedar Hill - Liggett 138 kV Line: Upgrade Venus Tap - Liggett Section | City of Grand Prairie, Dallas County | Upgrade the 5.5 mile section of Cedar Hill Switch - Liggett Switch 138 kV Line of double-circuit steel lattice towers and single-circuit wood h-frame structures. | 2019-10-03 | 2019-12-23 | 2019-12-23 | 10342023 | 8063582 |  |  | 100 | 138 | na | 7.2 | 1926.9 ACSS/TW | Steel Poles | 100 | 7.2 | na | na | 25.101(c)(5)(B)
15T62065 | Graham - Archer City 69 kV | City of Graham, Young County | Replace existing wood pole H-frames with Two (2) new single-circuit, concrete H-frame tangent structures (Str. 36/7 & 36/8). | 2021-03-09 | 2021-08-31 |  | 266075.7 | 253850 |  |  | 0 | 69 | na | 0.38826 | 4/0 ACSS | Concrete H-frames | 100 | 0.38826 | na | na | 25.101(c)(5)(B)
17T64042 0PT38881 | Trinidad-Kaufman Crossarm Replacement | City of Kaufman, Kaufman and Henderson Counties | Replace approximately 352 wood cross arms with steel cross arms on the Trinidad - Kaufman 138 kV line. The existing line is 37 miles of primarily single-circuit wood H-frame structures with wood cross-arms. Any degraded wood poles may be replaced. Cross bracing will be installed as necessary to meet current NESC strength requirements. | 2018-09-27 | 2019-12-09 | 2019-12-09 | 2151752 | 2141137 |  |  | 100 | 138 | na | 37 | 1033.5 ACSR | Wood H-Frames | 70 | 37 | na | na | 25.101(c)(5)(B)
17T65164 | Norwood - Denton Drive 138 kV: Install OPGW | City of Dallas, Dallas County | Replace 3/8" shield wire with OPGW on the Norwood - Denton Drive138 kV Transmission Line. | 2020-04-20 | 2020-06-10 | 2020-06-10 | 318269.74 | 318270 |  |  | 100 | 138 | 138 | 3.9 | OPGW | Steel Poles | 100 | 3.9 | na | na | 25.101(c)(5)(B)
17T62153 | Mitchell Bend - Rocky Creek HT Upgrade | City of Cresson & Granbury, Hood & Somervell County | Upgrade the Mitchell Bend - Benbrook Junction portion of the Comanche Peak - Benbrook 345 kV Line for High Temperature operation. | 2018-03-12 | 2019-06-19 | 2019-06-19 | 7264911.98 | 7267945 |  |  | 100 | 345 | 345 | 25.1 7.8 | (2) 795 kcmil ACSR & (2) 1590 kcmil ACSR | Steel Lattice | 150 | 25.1 7.8 | na | na | 25.101(c)(5)(B)
17T65143 0PT38735 | Cedar Crest Switching Station - Industrial Blvd Switching Station - Wall Street Switching Station 138 kV Line Upgrade | City of Dallas, Dallas County | Upgrade the 3.1-mile Cedar Crest Sw. Sta. – Industrial Blvd Sw. Sta. double-circuit line and the 0.3-mile Industrial Blvd Sw. Sta. – Wall Street Double-circuit line with a conductor rated 1649 A or greater. Upgrade all 138 kV line terminal and associated equipment to meet or exceed 2000 A. | 2018-04-04 | 2019-12-16 | 2019-12-16 | 3164089 | 3105152 |  |  | 100 | 138 | 138 | 3.5 | 959.6 kcmil ACSS/TW | Steel or Concrete Poles | Varies | 3.5 | Varies | na | 25.101(c)(5)(B)
17T65216 0PT38736 | Cedar Crest Switching Station - Wall Street Switching Station 69 kV Line Upgrade | City of Dallas, Dallas County | Upgrade the Cedar Crest Sw. Sta. – Wall Street 69 kV line for 138 kV operations, it will continue to be operated at 69 kV until Compton Street and Wall Street are converted to 138 kV operation. | 2018-04-05 | 2019-12-11 | 2019-12-11 | 2643096 | 2324328 |  |  | 100 | 69 | 69 | 3.5 | 959.6 kcmil ACSS/TW | Steel or Concrete Poles | Varies | 3.5 | Varies | na | 25.101(c)(5)(B)
18T64006 | Flat Branch (LaTexo) 138 kV POI | Houston County | Install a new 138 kV point of interconnection for Houston County Electric (HCEC) to their existing Latexo 138 kV Substation on the Lufkin Switch - Crockett 138 kV Line. HCEC has requested to switch grids. They are currently in SPP and wish to switch to ERCOT. Install three line sectionalizing switches. | 2018-05-01 | 2020-12-15 |  | 800000 | 726000 |  |  | 99 | 138 | na | 0.06 | 795 kcmil ACSR | Steel Poles | 100 | na | 100 | 0.06 | 25.101(c)(5)(A)
18T64091 | Jewett Switch - Crockett 138 kV Line: Rebuild Grapeland Magnolia Tap to Crockett | Crockett and Houston County | Rebuild the 9.2 mile section from Grapeland Magnolia Tap to Crockett of the Jewett - Crockett 138 kV Line using double-circuit monopole construction with only one circuit installed. | 2019-01-02 | 2019-06-29 | 2019-06-29 | 9845000 | 9931000 | 25527239.15 | 157% | 100 | 138 | 138 | 9.2 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 9.2 | na | na | 25.101(c)(5)(B) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to unexpected weather conditions and access issues.
18T61034 0PT37605 | TxDOT Relocation, Liggett-Saginaw 138 kV Line | City of Irving, Dallas County | Install new double-circuit, steel tangent structures. Remove four (4) existing double-circuit steel tangent structures. | 2019-11-09 | 2020-05-02 | 2020-05-02 | 1193327.68 | 1193327.68 |  |  | 100 | 138 | na | 1.1239 | 1033.5 kcmil ACSR | Steel Poles | 140 | 0.56193 | na | na | 25.101(c)(5)(F)
18T61033 0PT37604 | TxDOT Relocation, Liggett-Hackberry 138 kV Line | City of Irving, Dallas County | Install new double-circuit, steel tangent structures. Remove four (4) existing double-circuit steel tangent structures. | 2019-10-15 | 2019-12-20 | 2019-12-20 | 1193327.68 | 1193327.68 |  |  | 100 | 138 | na | 1.1239 | 1033.5 kcmil ACSR | Steel Poles | 140 | 0.56193 | na | na | 25.101(c)(5)(F)
17T61078 | AEP Lotebush - Blake Draw 138 kV Line | City of Coyanosa, Pecos County | Install new single-circuit, steel dead end structures. Remove existing single-circuit temporary wood pole structures. | 2019-01-26 | 2019-06-20 | 2019-06-20 | 400000 | 400000 | 857355.67 | 114.3% | 100 | 138 | na | 0.11856 | 959.6 kcmil ACSS/TW | Steel Monopole Structures | Varies | 0.11856 | na | na | 25.101(c)(5)(B) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to access and project coordination issues.
18T61039 | TxDOT Relocation, Kirkland Park-Centerville Sw. 138 kV Line | City of Garland, Dallas County | Install new double-circuit, steel tangent structures. Remove nine (9) existing double-circuit steel tangent structures. | 2018-12-08 | 2019-11-24 | 2019-11-24 | 1755049.01 | 3445119 |  |  | 100 | 138 | na | 2.0958 | 1033.5 kcmil ACSR | Steel Monopole Structures | Varies | 1.0479 | na | na | 25.101(c)(5)(F)
0PT37508 | IH 635 Lake Hubbard-Centerville 138 kV Relocation, Lake Hubbard-Centerville 138 kV Line | City of Dallas, Dallas County | Relocation with new single-circuit, steel monopole dead end and tangent structures and remove existing single-circuit, steel lattice tower dead end and tangent structures. | 2018-12-11 | 2019-06-11 | 2019-06-11 | 858655 | 1186735 | 2482407 | 109.2% | 100 | 138 | na | 1.1833 | 1926 ACSS/TW Cumberland (Non-Bundled) & 1431 ACSR Plover (Non-Bundled) | Steel Monopole Structures | Varies | 0.59167 | na | na | 25.101(c)(5)(F) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope and unexpected weather conditions.
15T64031 | Corsicana - Mildred 69 kV Line Rebuild to 138 kV Line | Navarro County | This project is to rebuild the Corsicana - Mildred 69 kV line to a 138 kV line. | 2019-01-22 | 2019-06-28 | 2019-06-28 | 11854408.55 | 14093244 |  |  | 100 | 69 | 138 | 9.5 | 959.6 kcmil ACSS/TW | Steel Poles | 50 | 9.5 | na | na | 25.101(c)(5)(B)
18T61038 | TxDOT Relocation, Judd Court 138 kV Tap Line | City of Garland, Dallas County | Install new single-circuit, steel dead end and tangent structures. Remove four (4) existing single-circuit steel tangent structures. | 2019-01-08 | 2019-06-05 | 2019-06-05 | 875226.27 | 875226.27 | 1654810.44 | 89.07% | 100 | 138 | na | 0.47386 | 336.4 kcmil ACSR and 959.6 kcmil ACSS/TW | Steel Monopole Structures | na | na | na | na | 25.101(c)(5)(F) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope and unexpected weather conditions.
0PT37510 | IH 635 Royal Relocation, Hackberry/Northlake-Grapevine Ball St. 138 kV Line | City of Dallas, Dallas County | Relocation with new double-circuit, steel monopole dead end and tangent structures and remove existing double-circuit, steel monopole dead end and tangent structures. | 2018-11-26 | 2019-06-11 | 2019-06-11 | 1974592 | 1565355 | 2627107.92 | 67.83% | 100 | 138 | na | 0.55871 | 1926 ACSS/TW Cumberland (Non-Bundled) | Steel Monopole Structures | Varies | 0.55871 | na | na | 25.101(c)(5)(F) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
0PT04371 | Wink Sw. Sta. – Yukon Sw. Sta. 138 kV adding 2nd Circuit | Winkler County/Odessa County | The scope of the work entails adding the second circuit of the newly constructed Yukon Sw. Sta. to Wink Sw. Sta. | 2019-01-03 | 2019-06-30 | 2019-06-30 | 6500000 | 10421193 | 13357189.9 | 28.17% | 100 | 138 | 138 | 36 | 1926.9 ACSS/TW | Steel Monopoles | 50 | 36 | na | na | 25.101(c)(5)(C) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
0PT37335 | Blackland Sw. - RCEC Blackland Sub 138 kV Line | City of Fate, Rockwall County | Connect the new Blackland Switch to the new RCEC Blackland Substation. | 2019-01-30 | 2019-06-26 | 2019-06-26 | 411416 | 411416 | 509269.92 | 23.78% | 100 | 138 | 138 | 0.1 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(A) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to increase in material cost and unexpected weather conditions.
17T62069 0PT38781 | Everman Switch - Cedar Hill Switch 345 kV Line (Courtland-Cedar Hill Section): HT Upgrade | City of Arlington, Tarrant County | Upgrade the Courtland - Cedar Hill Switch section of Everman Switch - Cedar Hill Switch 345 kV Line. | 2018-08-20 | 2020-05-14 | 2020-05-14 | 4455604 | 4800000 |  |  | 100 | 345 | na | 20.66 | 795 kcmil ACSR | Steel Lattice | 150 | 11.3 | na | na | 25.101(c)(5)(B) | WA split from Courtland - Cedar Hill, WA 17T62069
0PT37192 | Rivercrest Switch - Sulphur Springs East Tap 138 kV Line : CMPC Line Hardening | City of Sulphur Springs, Hopkins County | This is a CMPC Project that covers the cost to rebuild a section of the Rivercrest Switch - Sulphur Springs East Tap 138 kV Line in Hopkins County. The section is 0.1 miles of single-circuit wood H-Frames. | 2020-07-13 | 2020-07-23 | 2020-07-23 | 681893 | 681893 |  |  | 100 | 138 | na | 0.1 | 336.4 kcmil ACSR | Steel H-Frames | 100 | na | na | na | 25.101(c)(5)(B)
17T63206 | Eskota SW. - Sweetwater Creek NO. 2 : 69 kV CMPC Line Hardening | City of Sweetwater, County of Nolan | Relocate and replace 6 structures across Interstate 20 for CMPC System Hardening | 2019-02-14 | 2020-02-17 | 2020-02-17 | 588652.67 | 706000 |  |  | 100 | 69 | na | 0.1 | ACSR 4/0 | Steel Monopole, Wood Monopole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT37196 | Eskota Switch - Sweetwater Creek POI 69 kV Line | City of Sweetwater, County of Nolan | Relocate and replace 4 structures across Interstate 20 for CMPC System Hardening | 2020-08-24 | 2020-09-30 |  | 708375.72 | 1323460 |  |  | 0 | 69 | na | 0.1 | ACSR 4/0 | Concrete Monopole, Wood Monopole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
17T63211 | Sweetwater Downtown Tap 138 kV Line: CMPC System Hardening | City of Sweetwater, County of Nolan | Rebuild a section of the Eskota Switch – Morgan Creek Switch Downtown Tap 138 kV Line in Nolan County. The section is 0.1 miles of single-circuit wood monopoles with single post insulators. | 2019-11-11 | 2019-12-09 | 2019-12-09 | 483277 | 300000 |  |  | 100 | 138 | na | 0.24 | 336.4 kcmil ACSR | Concrete Monopole | 50 | 0.24 | na | na | 25.101c(5)(B)
17T63207 | Colorado City - China Grove Sw. 69 kV Line: CMPC System Hardening | City of Colorado City, Mitchell County | Relocate and replace 3 structures across I-20 for CMPC System Hardening | 2019-09-03 | 2019-09-19 | 2019-09-19 | 524709 | 524709 |  |  | 100 | 69 | na | 0.3 | 4/0 ACSR | Concrete Poles | 50 | 0.3 | na | na | 25.101(c)(5)(B)
0PT37296 | Forest Grove Switch - Canton Switch 138 kV Line : CMPC System Hardening | City of Canton, Van Zandt County | Relocate and replace 2 structures across I-20 for CMPC Hardening. | 2019-05-06 | 2019-06-07 | 2019-06-07 | 629033.47 | 629033 |  |  | 100 | 138 | na | 0.1 | 336.4 kcmil ACSR | Concrete H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
17T63209 | Eskota SW. - Flintkote -U.S. Gypsum 69 kV Line: CMPC Line Hardening | City of Sweetwater, Nolan County | This Work Authorization (WA) covers the cost to rebuild a section of the Eskota Sw. - Flintkote - U.S. Gypsum 69 kV line in Nolan County. | 2019-07-08 | 2019-08-06 | 2019-08-06 | 1040085 | 1040085 |  |  | 100 | 69 | 69 | 0.6 | 1/0 ACSR | Steel Poles & Concrete Poles | 50 | na | Varies | na | 25.101(c)(5)(B) | Replacing wood structures with Steel & Concrete as part of CMPC hardening project
0PT37441 | Burkburnett - Sheppard AFB 69 kV Tap: Line Relocation | City of Wichita Falls, Wichita County | Relocate a section of this line to accommodate new base entrance construction onto Sheppard AFB. | 2019-07-10 | 2019-12-10 | 2019-12-10 | 500000 | 500000 |  |  | 100 | 69 | na | 0.32 | 4/0 ACSR | Wood Poles | na | na | na | na | 25.101(c)(5)(D) | Relocation is at the request of Sheppard Air Force Base and is 100% reimbursable by the United States Air Force.
0PT37271 | Big Spring Switch - Buzzard Draw Switch 69 kV Line: Knott Sub Line Work | Howard County | This cut in will be located in the Big Spring Sw - Buzzard Draw line section. This work will support the establishment of the new Knott substation. | 2019-01-30 | 2019-06-28 | 2019-06-28 | 550000 | 550000 | 678878.93 | 23.43% | 100 | 69 | na | 0.4 | 4/0 ACSR and 959.6 ACSS/TW | Steel Monopole | 50 | 0.4 | na | na | 25.101(c)(5)(A) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to material issues.
0PT37509 | IH 635 Parkdale-Lake Hubbard 138 kV Relocation, Parkdale-Lake Hubbard 138 kV Line | City of Dallas, Dallas County | Relocation with new single-circuit, steel monopole dead end and tangent structures and remove existing single-circuit, steel lattice tower dead end and tangent structures. | 2019-01-22 | 2019-06-05 | 2019-06-05 | 853205 | 1267433 | 1545485.38 | 21.94% | 100 | 138 | na | 1.1951 | 1926 ACSS/TW Cumberland (Non-Bundled) & 1431 ACSR Plover (Non-Bundled) | Steel Monopole Structures | Varies | 0.59754 | na | na | 25.101(c)(5)(F) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to unexpected weather conditions and ROW access issues.
0PT37389 | DFW D West - DFW E East UG Fiber Installation | Tarrant County | Install 1.4 mile of UG fiber from DFW D West to DFW E East on the Liggett - Euless 138 kV Line. | 2018-12-03 | 2020-12-30 |  | 565552 | 565552 |  |  | 99 | 0 | 0 | 1.4 | ADSS Fiber | UG | na | 1.1 | 30 | 0.31 | 25.101(c)(5)(B)
16T65090 16T65186 | Northaven Switching Station - Preston Road North 138 kV Line Rebuild | City of Dallas, Dallas County | Upgrade the 6.1 mile Northaven Switching Station - Preston Road North double-circuit line. Upgrade the 138 kV terminal equipment to meet or exceed 2000 A. | 2018-03-05 | 2019-06-24 | 2019-06-24 | 11705282 | 13705282 | 16548335 | 20.74% | 100 | 138 | 138 | 12.2 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | Varies | 6.1 | Varies | na | 25.101(c)(5)(B) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to specialized construction requirements.
0PT04156 | Hutto Sw. - Gilleland Creek Sw. 138 kV Line: Bird Nest Sub Line Work | City of Pflugerville, County of Travis | Modify Hutto Switch - Gilleland Creek 138 kV line to accommodate construction of the new Bird Nest Substation. | 2019-09-03 | 2019-11-23 | 2019-11-23 | 883029 | 1200000 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW/HS | Steel, Monopole | 70 | 0.4 | na | na | 25.101(c)(5)(A) | This line work is to support the establishment of Bird Nest substation in Pflugerville, TX.
16T65165 0PT39960 | Crown Road - Norwood Switching Station 138 kV Line Rebuild | City of Dallas, Dallas County | Upgrade the 9.1 mile Crown Road - Norwood Switching Station double-circuit line. Upgrade the 138 kV terminal equipment to meet or exceed 2000 A. | 2018-12-17 | 2020-04-29 | 2020-04-29 | 12229402 | 16300813 |  |  | 100 | 138 | 138 | 18.2 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | Varies | 9.1 | Varies | na | 25.101(c)(5)(B)
0PT37338 | Wichita Falls - Burkburnett 69 kV: Rebuild from Wichita Falls North to 2/5 | Wichita Falls, Wichita County | Rebuild and upgrade the Wichita Falls - Burkburnett 69 kV line. | 2019-01-23 | 2019-06-28 | 2019-06-28 | 2644756 | 2950000 | 3336000.09 | 13.08% | 100 | 69 | na | 1.58 | 959.6 MCM ACSS/TW | Steel Poles | 50 | 1.58 | na | na | 25.101(c)(5)(B) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to unexpected weather conditions.
0PT38376 | McDonald Road Switch - Spraberry Switch 138 kV Line: Retermination | City of Big Springs & City of Garden City, Glasscock County | Convert the McDonald Road Switch - Spraberry Switch 69 kV Line to 138 kV and reterminate the line into McDonald Road Switch. | 2019-09-25 | 2019-11-01 | 2019-11-01 | 1808351.15 | 1440116 |  |  | 100 | 69 | 138 | 0.3 | 959.6 kcmil ACSS/TW | Steel Monopoles | 50 | 0.3 | na | na | 25.101(c)(5)(B)
0PT37659 | Garden City Sub - Midkiff Switch 69 kV Line: Rebuild | City of Garden City, Glasscock County & Regan County | Rebuild the 16 mile existing 69 kV line to double-circuit 69 kV on one side and 138 kV on the other to connect the 138 kV Shipwreck Substation. | 2019-08-01 | 2019-11-01 | 2019-11-01 | 20611032.06 | 20064430 |  |  | 100 | 69 | 138 | 16 | 959.6 kcmil ACSS/TW | Steel Monopoles | 50 | 15 | na | na | 25.101(c)(5)(A) | This line work supports the establishment of Shipwreck Sub 138 kiva in Big Springs, TX.
0PT04278 | Anna Switch - McKinney Sub 138 kV line: Cut-In to Weston Sub | City of McKinney, Collin County | Relocating Structure associated with establishing Weston Substation | 2020-04-08 | 2020-05-07 | 2020-05-07 | 146533 | 270000 |  |  | 100 | 138 | na | 0.1 | 1233.6 ACSS/TW | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
17T65218 | Northaven - Kirkland Park 138 kV Line: Northaven Line Work | City of Dallas, Dallas County | Reterminate the Northaven-Kirkland Park 138 kV Transmission Line at the Northaven Switch Station. | 2018-09-06 | 2018-12-27 | 2018-12-27 | 832746.33 | 759106.64 | 796536.19 | 4.931% | 100 | 138 | 138 | 0.1 | 959 ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B) | Final Actual Costs Reported. Project will be removed on next month's report.
19T64005 | Round Rock - Round Rock South 138 kV Line: Round Rock Sw. Station Line Work | City of Round Rock, Williamson County | Reconfigure line work associated with Round Rock Switch Station. | 2019-04-19 | 2019-06-10 | 2019-06-10 | 350000 | 455000 | 442727.62 | -2.697% | 100 | 138 | 138 | 0.02 | 959.6 kcmil ACSS/TW Bundled 795 ACSR Bundled 1590 KCMIL ACSR | Steel Pole | 400 | 0.08 | na | na | 25.101(c)(5)(B) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT37439 | Waco West Switch - Lake Creek Switch 138 kV Line: Line work to connect the Du Puy Sub | Waco/McLennan County | This cut in will be located in the Waco West Sw. - Lake Creek Sw. section. This work will support the establishment of the new Du Puy substation. | 2019-10-28 | 2019-12-02 | 2019-12-02 | 350000 | 450000 |  |  | 100 | 138 | na | 0.01 | 1926.9 ACSS/TW | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT37666 | Andrews County South - Littman 138 kV Line: Jumbo Hills Wind Interconnect | City of Andrews, Andrews County | Establish a generator interconnection by building a .4 mile looping in and out of Nelson Switch. | 2019-10-05 | 2019-12-02 | 2019-12-02 | 1602400 | 1602400 |  |  | 100 | 138 | na | 70 | 959.6 kcmil ACSS/TW | Steel Poles | 200 | na | 0.4 | 0.4 | 25.101(c)(5)(A)
0PT37467 | IH 635 Lake Hubbard-Centerville 345kV LA Prada Relocation, Lake Hubbard-Centerville 345kV Line | City of Dallas, Dallas County | Relocation with new single-circuit, steel monopole dead end and tangent structures and remove existing single-circuit, steel monopole dead end and tangent structures. | 2019-01-09 | 2019-06-11 | 2019-06-11 | 1042688 | 1286451 | 1241993.39 | -3.456% | 100 | 345 | na | 0.46212 | 2 - 959 ACSS/TW Suwannee | Steel Monopole Structures | Varies | 0.46212 | na | na | 25.101(c)(5)(F) | Final Actual Costs Reported. Project will be removed on next month's report. Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
16T62099 0PT41013 | Structure 4/5 - North Main Switch (West) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the structure 4/5 - North Main Switch (West Ckt) section of the Saginaw - Denton Ave - North Main Switch 138 kV line. The project consists of rebuilding the West circuit of the 2.1 mile line from structure 4/5 - Heritage. The rebuilt line will support 959.6 kcmil ACSS/TW conductor on double-circuit steel monopole structures. | 2019-02-04 | 2020-12-15 |  | 3840000 | 3840000 |  |  | 91 | 69/138 | 138 | 2.1 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 2.1 | na | na | 25.101(c)(5)(B)
18T62003 | Structure 4/5 - North Main Switch (East) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the structure 4/5 - North Main Switch (East Ckt) section of the North Main Switch - Richland Hills 138 kV line. The project consists of rebuilding the West circuit of the 2.1 mile line from structure 4/5 - North Main Switch. The rebuilt line will support 959.6 kcmil ACSS/TW conductor on double-circuit steel monopole structures. | 2019-02-04 | 2020-06-10 | 2020-06-10 | 1040000 | 1040000 |  |  | 100 | 69/138 | 138 | 2.1 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 2.1 | na | na | 25.101(c)(5)(B)
0PT04048 | Jewett Switch - Crockett Switch 138 kV Line: Rebuild Grapeland Magnolia 138 kV Tap | Houston County | Install a new 138 kV tap point for the existing Grapeland Magnolia 138 kV Substation on the Jewett Switch - Crockett Switch 138 kV Line. Install three line sectionalizing switches. | 2019-04-10 | 2019-06-24 | 2019-06-24 | 440000 | 760000 | 605395.28 | -20.34% | 100 | 138 | na | 1.4 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 1.4 | na | na | 25.101(c)(5)(A) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT04280 | Grandview Tap 138 kV Line: Parks Bell Ranch Sub Line Work | Ector County | This cut in will be located in the Grandview Tap line section of the Moss Switch - Midland County Northwest 138 kV Line. This work will support the establishment of the new Parks Bell Ranch substation. | 2019-03-30 | 2019-06-12 | 2019-06-12 | 1400000 | 1400000 | 944807.12 | -32.51% | 100 | 138 | na | 0.5 | 1926.9 ACSS/TW | Steel Monopole | 175 | 0.4 | na | na | 25.101(c)(5)(A) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT37514 | SH 121 Collin County Outer Loop 138 kV Relocation, Payne-Royce 138 kV Line | City of Anna, Collin County | Relocation with new single-circuit, concrete H-frame tangent structures and remove existing single-circuit, wood H-frame tangent structures. | 2019-03-25 | 2019-04-11 | 2019-04-11 | 305413 | 252413 | 160245.77 | -36.51% | 100 | 138 | na | 0.30436 | 795 ACSR Drake | Concrete H-frame Structures | 70 | 0.30436 | na | na | 25.101(c)(5)(F) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT37714 | Build Horseshoe Springs Switch – Horseshoe Draw STATCOM 138 kV Line | Culberson County | Build the Horseshoe Springs Switch – Horseshoe Draw STATCOM 138 kV Line. | 2019-03-19 | 2019-06-24 | 2019-06-24 | 340000 | 450000 | 275196.27 | -38.85% | 100 | 138 | na | 0.13 | 1926.9 ACSS/TW/HS | Steel Poles | 50 | na | na | na | 25.101(c)(5)(A) | Final Actual Costs Reported. Project will be removed on next month's report.
18T64007 | Jim English (Berea) 138 kV POI | Houston County | Install a new 138 kV point of interconnection for Houston County Electric (HCEC) to their existing Berea 138 kV Substation on the Lufkin Switch - Crockett 138 kV Line. HCEC has requested to switch grids. They are currently in SPP and wish to switch to ERCOT. Install three line sectionalizing switches. | 2018-04-24 | 2018-06-01 | 2018-06-01 | 800000 | 900000 | 214308 | -76.19% | 100 | 138 | na | 0.06 | 795 kcmil ACSR | Steel Poles | 100 | na | 100 | 0.06 | 25.101(c)(5)(A) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT04374 0PT38764 0PT40259 | Wink - Notrees Sw 138 kV Line: Rebuild | City of Wink, Winkler County | Rebuild the 27.8-mile Wink Sw. Sta. - No Trees Sw. Sta. 138 kV Line using a conductor rated 2569 A or greater. Use double-circuit 138 kV structures with one circuit in place. Upgrade all line terminal and associated equipment to meet or exceed 2000 A and removal conductor and structures. | 2019-05-03 | 2020-09-01 |  | 36645152 | 37500000 |  |  | 66 | 138 | na | 27.8 | 1926.9 ACSS/TW/HS | Steel Poles | 50 | 27.8 | na | na | 25.101(c)(5)(B)
19T65004 | Tri Corner Switch - Watermill Switch 345 kV Line: Reconductor | Cities of Lancaster and Seagoville, Dallas County | Reconductor 11.5 miles from Tri Corner Switch – Watermill Switch 345 kV South circuit. | 2019-02-04 | 2020-06-30 | 2020-06-30 | 10189806.17 | 10189806.17 |  |  | 100 | 345 | na | 11.5 | (2) 959.6 kcmil ACSS/TW - Bundle Suwannee | Steel Towers | 165 | 11.5 | na | na | 25.101(c)(5)(B)
0PT38079 | China Grove - Radium 138 kV Line: Sunoco POD | Colorado City, Mitchell County | Build a 0.6 mile line extension in the China Grove Switch - Radium 138 kV Line to serve the Sunoco Pipeline facilities. | 2019-06-24 | 2019-09-06 | 2019-09-06 | 2600000 | 2600000 |  |  | 100 | 138 | na | 0.6 | 959.6 ACSS/TW | Steel Poles | na | na | 75 | 0.6 | 25.101(c)(5)(A)
19T62002 | Sherry Switch Station - General Motors Substation 138 kV: Reconductor | City of Arlington, Tarrant County | Reconductor the west circuit of the Sherry Switch Station - General Motors Substation 138 kV Line. | 2019-02-16 | 2019-12-11 | 2019-12-11 | 2353682.32 | 3809556 |  |  | 100 | 138 | 138 | 2.35 | 1926.9 kcmil ACSS/TW | Steel Poles | Varies | 2.35 | na | na | 25.101(c)(5)(B)
0PT37248 | Benbrook Junction - Rocky Creek Sw HT Upgrade | City of Benbrook, Tarrant County | Upgrade the 8 miles, Benbrook Junction to Rocky Creek portion of the Mitchell Bend - Rocky Creek 345 kV Line for High Temperature operation. | 2019-09-03 | 2020-12-15 |  | 13662232 | 13662232 |  |  | 86 | 345 | 345 | 8 | (2) 1590 kcmil ACSS | Steel Poles | 100 | 8 | na | na | 25.101(c)(5)(B)
0PT37557 | Spraberry Switch - Garden City Sub 69 kV Line: Rebuild | City of Garden City, Glasscock County | Rebuild the 0.2 mile existing Spraberry Switch to Garden City Sub 69 kV Line in order to convert the 69 kV circuit to 138 kV and reterminate into McDonald Road Switch. | 2019-10-08 | 2019-11-01 | 2019-11-01 | 799293 | 775165 |  |  | 100 | 69 | 138 | 0.2 | 959.6 kcmil ACSS/TW | Steel Monopoles | 50 | 0.2 | na | na | 25.101(c)(5)(A) | This line work supports the establishment of Shipwreck Sub 138 kV in Big Springs, TX and the retermination into McDonald Road Switch. Project to be energized 10/15/19.
0PT37318 | Venus Switch - Sardis Switch 138 kV Line: Establish New Kemp Ranch Switch Station | City of Venus, Ellis County | Reterminate the two circuits of the Venus Switch - Sardis Switch 138 kV Line to the newly constructed Kemp Ranch Switch Station. This line will no longer connect at Venus Switch Station. | 2019-06-24 | 2019-11-18 | 2019-11-18 | 2340759 | 2340792 |  |  | 100 | 138 | na | 0.4 | (2) 959.6 kcmil ACSS/TW/E3X | Lattice Towers and Steel Poles | 100 | 0.1 | 100 | 0.4 | 25.101(c)(5)(A)
0PT38090 | Kemp Ranch Switch - Genus #1 138 kV Line | City of Venus , Ellis County | Build a new line connecting the newly constructed Kemp Ranch Switch Station and the newly constructed Genus Substation. | 2019-06-24 | 2020-01-13 | 2020-01-13 | 839798 | 839798 |  |  | 100 | 138 | na | 0.2 | 959.6 kcmil ACSS/TW/E3X | Steel Poles | na | na | 100 | 0.2 | 25.101(c)(5)(A)
0PT38091 | Kemp Ranch Switch - Genus #2 138 kV Line | City of Venus, Ellis County | Build a new line connecting the newly constructed Kemp Ranch Switch Station and the newly constructed Genus Substation. | 2019-06-24 | 2020-01-13 | 2020-01-13 | 754553 | 754553 |  |  | 100 | 138 | na | 0.3 | 959.6 kcmil ACSS/TW/E3X | Steel Poles | na | na | 100 | 0.3 | 25.101(c)(5)(A)
0PT38077 | Venus Switch - Kemp Ranch Switch 138 kV Line: Establish Kemp Ranch Switch Station | City of Venus, Ellis County | Build a new line connecting the existing Venus Switch Station and the new constructed Kemp Ranch Switch Station. | 2019-06-17 | 2019-12-02 | 2019-12-02 | 1643551 | 1643551 |  |  | 100 | 138 | na | 0.5 | (2) 959.6 kcmil ACSS/TW/E3X | Steel Poles | na | na | 75 | 0.5 | 25.101(c)(5)(A)
0PT38076 | Alvarado - Venus - Kemp Ranch Switch Station 138 kV Line: Establish Kemp Ranch Switch Station | City of Venus, Ellis County | Build a new line connecting the existing Venus Switch Station and the new constructed Kemp Ranch Switch Station. | 2019-06-13 | 2019-11-21 | 2019-11-21 | 1634409 | 1634409 |  |  | 100 | 138 | na | 0.4 | (2) 959.6 kcmil ACSS/TW/E3X | Steel Poles | na | na | 75 | 0.4 | 25.101(c)(5)(B)
0PT38703 | Yucca drive - Crane switch 69 kV Line | Odessa and Crane County | Replace a pole required to accommodate a new auto transformer at Barnsley Substation. | 2019-04-29 | 2019-09-25 | 2019-09-25 | 300000 | 300000 |  |  | 100 | 69 | 69 | 0.1 | 959.6 kcmil ACSS | Steel Pole | na | na |  | 0.1 | 25.101(c)(5)(A)
0PT38369 | Roanoke Switch - Euless Switch 138 kV Line | Forth Worth and Tarrant County | Install a single-circuit steel monopole on the Roanoke Switch - Euless Switch 138 kV double-circuit line. | 2019-08-06 | 2019-12-16 | 2019-12-16 | 175852.21 | 180000 |  |  | 100 | 138 | 138 | 0.1 | 1033.5 ACSS | Steel Pole | na | na |  | 0.1 | 25.101(c)(5)(B)
0PT38572 | Graham Switch - Morgan Creek Switch 345 kV Line: 345 kV Lattice Hardening | Sweetwater City and Jones County | Harden a section of the Graham – Morgan Creek Switch 345 kV Line in Jones County. | 2019-09-16 | 2019-10-11 | 2019-10-11 | 709609.37 | 800000 |  |  | 100 | 345 | 345 | 0.2 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | 140 | 0.2 | 140 | 0.2 | 25.101(c)(5)(B)
0PT38584 | Graham Switch - Morgan Creek Switch 345 kV Line: 345 kV Lattice Hardening | Sweetwater City and Fisher County | Harden a section of the Graham – Morgan Creek 345 kV Line in Fisher County. | 2019-09-16 | 2019-10-11 | 2019-10-11 | 733491.13 | 920000 |  |  | 100 | 345 | 345 | 0.2 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | 140 | 0.2 | 140 | 0.2 | 25.101(c)(5)(B)
18T62004 | Structure 4/5 - Springdale (North) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the structure 4/5 - Springdale (North Ckt) section of the Saginaw - Springdale - Richland Hills 138 kV line. The project consists of rebuilding the North circuit of the 2.6 mile line from structure 4/5 - Springdale. | 2019-02-18 | 2019-06-30 | 2019-06-30 | 2335000 | 2335000 |  |  | 100 | 69/138 | 138 | 2.6 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 2.6 | na | na | 25.101(c)(5)(B)
18T62005 | Structure 4/5 - Springdale (South) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the structure 4/5 - Springdale (South Ckt) section of the North Main Switch - Richland Hills 138 kV line. The project consists of rebuilding the South circuit of the 2.6 mile line from structure 4/5 - Springdale. | 2019-02-18 | 2020-06-10 | 2020-06-10 | 690000 | 690000 |  |  | 100 | 69/138 | 138 | 2.6 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 2.6 | na | na | 25.101(c)(5)(B)
0PT38583 0PT39653 | Spraberry-Garden City East Sub 138 kV Line: Re-establish 69 kV Line South circuit and Cut-In to 138 kV line North Circuit | City of Midland/Midland County | Replacing (1) structure with a monopole, removing (3) structures, and a cut-In to the new station in support of establishing the new 138 kV Tex-Harvey Substation and the decommissioning of the existing 69 kV Tex-Harvey Substation | 2019-04-01 | 2019-12-02 | 2019-12-02 | 538549 | 538549 |  |  | 100 | 69/138 | na | 0.02 | 959.6 kcmil ACSS/TW | Steel Poles | 400 | 0.1 | na | na | 25.101(c)(5)(A) | South Circuit is 69 kV and North Circuit is 138 kV
18T63112 | AEP Lotebush-Coyanosa NW 138 kV Installation, Lotebush-Coyanosa NW 138kV Line | City of Coyanosa, Pecos County | Installation of new double-circuit, steel monopole dead end structures and concrete tangent structures. The installation is at the request of the Oncor. | 2019-07-22 | 2019-11-15 | 2019-11-15 | 2902452 | 2500000 |  |  | 100 | na | 138 | 1.817 | 959 kcmil ACSS/TW Suwannee | Steel and Concrete Monopole Structures | na | 0 | 80 | 0.90852 | 25.101(c)(5)(A)
0PT37574 | Norwood - E Levee 138 kV Line: Establish Knights Branch POD for UT Southwestern Medical Center | City of Dallas, Dallas County | Establish a point of delivery to Knights Branch sub on Norwood - E Levee 138 kV transmission line. The point of delivery will be located approximately 360 feet east of existing UTSWMC POD | 2019-04-06 | 2019-09-11 | 2019-09-11 | 1527554 | 1527554 |  |  | 100 | 138 | 138 | 0.5 | 1926 kcmil ACSS/TW | Steel Poles | 100 | 0.5 | na | na | 25.101(c)(5)(A)
0PT37679 | Trinidad Switch - Long Lake 138 kV Line: Holly Ervin 138 kV POD | City of Palestine, Anderson County | Build a point of interconnection for Atmos Pipeline. | 2019-09-09 | 2019-10-07 | 2019-10-07 | 852139.22 | 1200661.92 |  |  | 100 | 138 | na | 0.6 | 795 kcmil ACSR/Drake | Steel H-Frame Switch/ H-Frame Tangents | 100 | na | na | na | 25.101(c)(5)(A)
16T62072 | Saginaw - North Main 138 kV Line: Cut in to new North Main Sub | City of Fort Worth, Tarrant County | Build a cut in to Oncor North Main Sub on the Saginaw - North Main 138 kV Line. The Interconnect will be between the existing Heritage Sub and the new North Main Sub. | 2019-03-19 | 2020-12-15 |  | 697036.76 | 697037 |  |  | 56 | 138 | na | 0.1 | 959.6 kcmil ACSS/TW | Steel Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A)
16T62077 | Connect North Main Sub To North Main Switch | City of Fort Worth, Tarrant County | Connect the North Main Sub to North Main Switch on the Randol Mill - North Main 138 kV Line. The initial line will be between the existing North Main Switch and the new North Main Sub. | 2019-03-19 | 2020-06-29 | 2020-06-29 | 659044.01 | 1057827 |  |  | 100 | 138 | na | 0.3 | 959.6 kcmil ACSS/TW | Steel Poles | 50 | 0.3 | na | na | 25.101(c)(5)(A)
0PT37277 | Temple - Minerva 69 kV Line: Relocation | City of Temple, Bell County | Relocate approximately 0.75 miles of the Temple - Minerva 69 kV Line in order to accommodate Waste Management's proposed landfill. | 2019-07-10 | 2019-11-15 | 2019-11-15 | 931000 | 1141647 |  |  | 100 | 69 | na | 0.6 | 959.6 kcmil ACSS/TW | Steel/Concrete Poles | 100 | 0.75 | 100 | 0.6 | 25.101(c)(5)(D)
0PT37364 | Liggett Sw - Norwood Sw 138 kV Line: Norwood Retermination | City of Dallas, Dallas County | Reterminate the Liggett - Norwood Sw (North Circuit) and install one (1) SCSP inline dead-end between Str 7/2 and the proposed H-Frame station dead-end on the North Circuit. | 2019-04-25 | 2019-11-11 | 2019-11-11 | 351000 | 351000 |  |  | 100 | 138 | na | 0.1 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | na | na | na | 25.101(c)(5)(B)
0PT38413 | Battalion POD 138 kV Loop Line | City of Killeen, Bell County | Construct a 138 kV loop line off the Killeen Park St. 138 kV Line to aide in establishing the Battalion POD. | 2019-05-30 | 2019-09-17 | 2019-09-17 | 2500000 | 2700000 |  |  | 100 | na | 138 | 0.8 | 1-959.6 ACSS/TW/HS | Steel Poles | na | na | 70 | 0.8 | 25.101(c)(5)(A)
0PT38341 | Killeen Park Street 138 kV Line: Modifications to Serve Battalion POD | City of Killeen, Bell County | Add a second circuit to the existing Killeen Park St. 138 kV Tap Line from structure 2C/6 A to structure 1/5 A. | 2019-06-03 | 2020-12-15 |  | 1800000 | 1950000 |  |  | 55 | 138 | 138 | 1.2 | 1-959.6 ACSS/TW/HS | Steel Poles | N/A | 0.5 | N/A | 0.5 | 25.101(c)(5)(C)
0PT38070 | Wink - Culberson 138 kV Line: Modify for Riverton - Sand Lake 345 kV Line | Reeves County | Modify the Wink - Culberson 138 kV transmission line due to the new construction of the Riverton – Sand Lake 345 kV line | 2019-11-04 | 2020-05-01 | 2020-05-01 | 1300000 | 1600000 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW/HS | Steel Poles | 50 | na | 160 | 0.26 | 25.101(c)(5)(D)
0PT37287 | Valley Switch - Paris Switch 345 kV Line: Relocate for the Lower Bois d'Arc Creek Reservoir | Fannin County | Rebuild and raise the Valley – Paris 345 kV line at the request of the North Texas Municipal Water District in order to accommodate the proposed Lower Bois d’Arc Creek Reservoir. | 2019-09-25 | 2020-06-15 | 2020-06-15 | 18300000 | 20500000 |  |  | 100 | 345 | na | 12.8 | (2) 1926.9 ACSS/TW/HS Bundled | Steel Poles | 150 | 6.4 | na | na | 25.101(c)(5)(E)
0PT37288 | Valley Switch - Paris Switch 138 kV Line: Relocate for the Lower Bois d'Arc Creek Reservoir | Fannin County | Rebuild and raise the Valley – Paris 138 kV line at the request of the North Texas Municipal Water District in order to accommodate the proposed Lower Bois d’Arc Creek Reservoir. | 2019-09-18 | 2020-07-01 | 2020-07-01 | 7200000 | 8750000 |  |  | 100 | 138 | na | 6.62 | 1926.9 ACSS/TW/HS | Steel Poles | 100 | 6.62 | na | na | 25.101(c)(5)(E)
0PT04089 | Wink Switch - Culberson Switch 138 kV Line: Cut In Quarry Field Switch | Culberson County | This cut in will be located in the Elmar - Mason line section. This work will support the establishment of the new Quarry Field Switch. | 2019-09-04 | 2019-10-14 | 2019-10-14 | 2650000 | 2900000 |  |  | 100 | 138 | na | 0.96 | 1926.9 ACSS/TW/HS | Steel Poles | 50 | na | 70 | 0.96 | 25.101(c)(5)(A)
0PT37680 | Build Quarry Field Switch – Rondo STATCOM 138 kV Line | Culberson County | Build the Quarry Field Switch – Rondo STATCOM 138 kV Line. | 2019-09-13 | 2019-12-12 | 2019-12-12 | 420000 | 500000 |  |  | 100 | 138 | na | 0.18 | 1926.9 ACSS/TW/HS | Steel Poles | 50 | na | 70 | 0.18 | 25.101(c)(5)(A)
0PT38473 | Rebuild Screwbean Tap - Screwbean Sub 138 kV Line | Culberson County | Rebuild 0.2 miles of the Screwbean Tap - Screwbean Sub Line to accommodate the new transformer being installed in the Screwbean Sub, utilizing 1926.9 ACSS/TW "Cumberland". | 2019-11-18 | 2019-12-31 | 2019-12-31 | 740000 | 900000 |  |  | 100 | 138 | na | 0.23 | 1926.9 ACSS/TW/HS | Steel Poles | na | na | 150/100 | 0.23 | 25.101(c)(5)(B)
0PT37752 | Wink - Culberson 138 kV Line: Boulder POD for Anadarko Haley | Loving County | Install three motor operated 138 kV 3200 A line sectionalizing switches as a part of installing a 138 kV point-of-interconnection (POD) for Anadarko's Petroleum Corporation on the north circuit of the Wink – Culberson 138 kV Double-circuit Line. The POD will be located 1.4 miles west of the Loving Substation | 2019-10-07 | 2019-11-19 | 2019-11-19 | 1700000 | 1850000 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW/HS | Steel Poles/ H-frame | 50 | na | 70 | 0.25 | 25.101(c)(5)(A)
0PT04154 | Arco (DME) Switch - Collin Switch 138 kV Line: Establish Blagg Sub | City of Denton, Denton County | Cut-in approximately 0.7 miles of the Arco (DME) Switch - Collin Switch 138 kV line to establish Blagg Sub. | 2020-10-15 | 2020-12-31 |  | 2117860.39 | 514856 |  |  | 0 | 138 | 138 | 0.2 | 1926.9 ACSS/TW | Steel Monopoles | 70 | 0.1 | na | na | 25.101(c)(5)(A)
0PT38669 | Relocate Martin Marietta, Chico-Jacksboro 69 kV Line | City of Chico, Wise County | Relocate structures 13/2 through 14/1 on Chico-Jacksboro 69 kV Line at the request of Martin Marietta. | 2019-08-05 | 2019-12-20 | 2019-12-20 | 1686384.95 | 1546139 |  |  | 100 | 69 | na | 1.3 | 795 ACSR | Steel Monopole Structures | 100 | 1.078 | 100 | 1.3 | 25.101(c)(5)(D) | This project is 100% reimbursable by Martin Marietta. Relocation results in existing line being .2 miles longer in length.
0PT38670 | Relocate Martin Marietta, Bridgeport-Chico 138 kV Line | City of Chico, Wise County | Relocate structures 4/9 through 6/5 on Bridgeport - Chico 138 kV Line at the request of Martin Marietta. | 2019-08-23 | 2019-11-15 | 2019-11-15 | 1686384.95 | 1546159 |  |  | 100 | 138 | na | 1.3 | 795 ACSR | Steel Monopole Structures | 100 | 1.078 | 100 | 1.3 | 25.101(c)(5)(D) | This project is 100% reimbursable by Martin Marietta. Relocation results in existing line being .2 miles longer in length.
18T64092 | Jewett Switch - Crockett 138 kV Line: Rebuild Pleasant Springs to Grapeland Magnolia Tap | Crockett and Houston/Leon Counties | Rebuild the 14.0 mile section from Pleasant Springs to Grapeland Magnolia Tap of the Jewett - Crockett 138 kV Line using double-circuit monopole construction with only one circuit installed. | 2019-08-14 | 2019-12-18 | 2019-12-18 | 13000000 | 17500000 |  |  | 100 | 138 | 138 | 14 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 14 | na | na | 25.101(c)(5)(B)
0PT38731 | Falcon Seaboard Switch-Midland East Sub 345 kV Line: Hardening 44/5 & 44/4 | City of Big Springs, Howard County | Rebuild a section from Falcon Seaboard Switch to Midland East Substation 345 kV Line by replacing two lattice H frames with two dead-end towers. | 2020-02-22 | 2020-10-30 |  | 813755 | 1300000 |  |  | 33 | 345 | na | 0.2 | (2) 795 ACSR | Steel Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38350 | Valley Switch - Payne Switch #3 138 kV Line: CMPC Line Hardening | Fannin County | Rebuild approximately 0.6 miles of the Valley Switch - Payne Switch #3 138 kV Line. | 2019-09-16 | 2020-01-24 | 2020-01-24 | 720654 | 735488 |  |  | 100 | 138 | 138 | 0.6 | 959.6 ACSS/TW/HS | Steel Poles | 100 | 0.6 | na | na | 25.101(c)(5)(B)
0PT37464 | Valley Switch - Payne Switch #4 138 kV Line: CMPC Line Hardening | Fannin County | Rebuild approximately 0.6 miles of the Valley Switch - Payne Switch #4 138 kV Line. | 2019-09-23 | 2019-12-23 | 2019-12-23 | 845310 | 863514 |  |  | 100 | 138 | 138 | 0.6 | 959.6 ACSS/TW/HS | Steel Poles | 100 | 0.6 | na | na | 25.101(c)(5)(B)
0PT37395 | Rivercrest Switch - Sulphur Springs 138 kV Line : Monticello Sw. Tap (CMPC) | City of Mount Vernon, Franklin County | Relocate and replace structures 4/3 and 4/4 on the Rivercrest - Sulphur Springs 138 kV line: Monticello Sw. Tap. | 2019-08-05 | 2019-08-10 | 2019-08-10 | 394204.53 | 394204.53 |  |  | 100 | 138 | na | 0.3 | 959 ACSS | Wood H-Frame | 90 | na | na | na | 25.101(c)(5)(B)
17T64107 | Mankin Switch Station - TRWD Station 138 kV Line | City of Trinidad, Henderson County | Build the Mankin Switch Station – Tarrant Regional Water District (TRWD) Station 138 kV line section to the TRWD point of delivery | 2019-04-01 | 2019-12-03 | 2019-12-03 | 900000 | 1100000 |  |  | 100 | na | 138 | 0.6 | 959.6 ACSS/TW/HS | Steel Poles | na | na | 70 | 0.6 | 25.101(c)(5)(A)
0PT38605 | Forest Grove Sw - Canton Sw 138 kV Ln: Rebuild Forest Grove Sw - Eustace | City of Athens, Henderson County | Rebuild 4.47 miles of existing wood H-frame and 3-pole structures with new double-circuit capable steel monopoles utilizing | 2019-06-17 | 2020-01-10 | 2020-01-10 | 4605058 | 6400000 |  |  | 100 | 138 | na | 4.5 | 1926.9 kcmil ACSS/TW | Steel Poles | 160 | 4.47 | na | na | 25.101(c)(5)(B)
19T63003 | Cowden North - Odessa North 69 kV Line: 138 kV Rebuild | City of Odessa, Ector County | Rebuild the 10.3-mile Cowden North – Odessa North Sw. Sta. 69 kV Line section using a conductor rated 1649 A or greater. | 2019-06-10 | 2019-12-02 | 2019-12-02 | 8891636 | 8891636 |  |  | 100 | 69 | 138 | 12.3 | 959.6 kcmil ACSS/TW | Steel Poles | 50 | 12.3 | na | na | 25.101(c)(5)(B)
0PT38389 | Fisher Road Switch - Oklaunion Tie 345 kV Line : Hardening 14/6 & 15/1 | City of Wichita Falls, Wichita County | Rebuild a section of the Fisher Road Switch - Oklaunion Tie 345 kV Line in Wichita County. Replace two (2) H-frame lattice structures (14/6 & 15/1) | 2019-10-21 | 2019-11-27 | 2019-11-27 | 782557 | 968532 |  |  | 100 | 345 | 345 | 0.2 | 2 - 795 MCM ACSR Drake | Lattice Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38654 | Fisher Road Switch - Oklaunion Tie 345 kV Line : Hardening 2/2 & 2/3 | City of Wichita Falls, Wichita County | Rebuild a section of the Fisher Road Switch - Oklaunion Tie 345 kV Line in Wichita County. Replace two (2) H-frame lattice structures (2/2 & 2/3) | 2019-09-26 | 2019-11-27 | 2019-11-27 | 792887 | 945824 |  |  | 100 | 345 | 345 | 0.2 | 2 - 795 MCM ACSR Drake | Lattice Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38698 | Fisher Road Switch - Oklaunion Tie 345 kV Line : Hardening 1/1 | City of Wichita Falls, Wichita County | Rebuild a section of the Fisher Road Switch - Oklaunion Tie 345 kV Line in Wichita County. Replace one (1) H-frame lattice structure (1/1) | 2018-11-16 | 2019-11-27 | 2019-11-27 | 359954 | 509118 |  |  | 100 | 345 | 345 | 0.2 | 2 - 795 MCM ACSR Drake | Lattice Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38726 | Forest Grove Switch - Canton Switch 138 kV Line : Rebuild Mabank Tap - Eustace SE Switch | City of Eustace, Henderson County | Rebuild the Mabank Tap - Eustace SE Switch section of the Forest Grove Switch – Canton Switch 138 kV Line to allow the integration of RCEC. | 2019-06-17 | 2020-02-01 | 2020-02-01 | 7000000 | 9798629 |  |  | 100 | 138 | 138 | 6 | 1926.9 MCM ACSS/TW/HS “Cumberland” | Steel Pole, Steel 3 - Pole | 100 | 6 | na | na | 25.101(c)(5)(B)
0PT38720 | Elkton Switch - Palestine South Switch 138 kV Line : Blackburn Switch (Apollo) 138 kV POI | City of Cuney, Cherokee County | Establish a 138 kV point of interconnection for the Blackburn 138 kV Sw. Sta. located in the Elkton Sw. Sta. – Palestine South Sw. Sta. 138 kV Line. Install 4 monopoles to install the Blackburn 138 kV point of interconnection, which will accommodate the RCEC integration. | 2019-11-04 | 2019-12-02 | 2019-12-02 | 953860 | 971502 |  |  | 100 | 138 | 138 | 0.4 | 2 - 795 MCM ACSR Drake and 959 MCM ACSS/TW Suwannee | Steel and Concrete Monopole | 100 | 0.4 | na | na | 25.101(c)(5)(A)
0PT38080 | Enterprise Pipeline 138 kV POD: Construct two 138 kV lines from Quarry Field 138 kV Switch to Enterprise GC LLC | City of Mentone, Loving County | Install two 138 kV point-of-deliveries (PODs) for Enterprise GC LLC out of Quarry Field 138 kV Switch. Install two 3200 A, 138 kV circuit breakers at Quarry Field Switch. The PODs will be located approximately 1 mile east from Quarry Field Switch. | 2019-11-13 | 2019-12-20 | 2019-12-20 | 2636926.73 | 2636927 |  |  | 100 | na | 138 | 1 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | 70 | 1 | 25.101(c)(5)(A)
0PT38393 | Falcon Seaboard Switch-Midland East Sub 345 kV Line: Hardening 55/2 | City of Stanton, Martin County | Replace structure 55/2 with a dead-end structure to harden the line. | 2020-01-25 | 2020-05-01 | 2020-05-01 | 488000 | 613018 |  |  | 100 | 345 | 345 | 0.4 | 2 - 795 MCM ACSR Drake | Lattice Towers | 150 | 0.4 | na | na | 25.101(c)(5)(B)
0PT38728 0PT40695 | Palestine Switch - Palestine South Switch 138 kV Line: Reconductor and Hardening | City of Palestine, Anderson County | Reconductor the 1.4-mile and hardening Palestine South Switch - Palestine 138 kV Line | 2019-09-30 | 2019-11-04 | 2019-11-04 | 597383 | 722000 |  |  | 100 | 138 | na | 1.4 | 795 ACSR Drake | Steel monopoles | 70 | 1.4 | na | na | 25.101(c)(5)(B)
0PT38872 | Minerva Sub - Robertson Switch 138 kV Line : Structure Relocation | City of Milano, Milam County | This is a CMPC project to relocate structure 32/2 due to erosion by the Little River on the Minerva Sub - Robertson Switch 138kV line. | 2019-09-10 | 2019-10-16 | 2019-10-16 | 665094 | 222000 |  |  | 100 | 138 | na | 0.4 | 795 ACSR Drake | Steel monopoles | 70 | 0.4 | na | na | 25.101(c)(5)(B)
0PT38582 | Falcon Seaboard Switch - Midland East Sub 345 kV Line : Hardening 63/1 & 63/2 | City of Midland, County of Midland | Rebuild a section of the Falcon Seaboard Switch - Midland East Sub 345 kV Line in Midland County. Replace two (2) H-frame lattice structures (63/1 & 63/2) adjacent to I-20 with dead-end towers. | 2020-02-21 | 2020-04-07 | 2020-04-07 | 800172 | 1035000 |  |  | 100 | 345 | na | 0.2 | 2 - 795 ACSR Drake | Lattice Steel Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38587 | Falcon Seaboard Switch - Midland East Sub 345 kV Line: Hardening 35/4 & 35/5 | City of Big Spring, County of Howard | Rebuild a section of the Falcon Seaboard Switch - Midland East Sub 345 kV Line in Howard County. | 2019-04-02 | 2020-04-07 | 2020-04-07 | 776453 | 1111000 |  |  | 100 | 345 | na | 0.2 | 2 - 795 ACSR Drake | Lattice Steel Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT04019 | Village Creek Tap - Bowen 138 kV Line: Rebuild | City of Arlington, Tarrant County | Rebuild the Village Creek Tap – Bowen 138 kV Line as a double-circuit line. | 2019-07-01 | 2019-09-30 | 2019-09-30 | 5111631.35 | 5111631 |  |  | 100 | 138 | 138 | 2.4 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 1.2 | na | na | 25.101(c)(5)(B)
0PT38496 | Bowen East 138 kV Tap Line: Conductor Removal | City of Arlington, Tarrant County | Remove the Bowen East 138 kV Tap Line. | 2020-04-14 | 2020-04-30 | 2020-04-30 | 224817.55 | 224818 |  |  | 100 | 138 | na | 1.7 | na | na | na | na | na | na | 25.101(c)(5)(B)
18T62093 0PT39362 | Lake Wichita SW. STA. - Holliday 69 kV Line Conversion to 138 kV | Archer County | Convert the 10.8-mile Lake Wichita Sw. Sta. – Holliday 69 kV Line to 138 kV and terminate at Bowman. Move and raise tower 3/6 to provide necessary horizontal and vertical clearance for the upgraded Lake Wichita to Holliday 138 kV line. | 2019-07-29 | 2019-12-29 | 2019-12-29 | 17106248 | 17950000 |  |  | 100 | 69 | 138 | 10.1 | 959.6 ACSS/TW/HS | Steel monopoles | 50 | 10.1 | na | na | 25.101(c)(5)(B)
0PT39015 | Holliday Sub - Archer City Sub 69 kV Line : Reterminate at Holliday | Archer County | Reterminate line at Holliday Sub in association with Holliday Station expansion to allow room for new 138 kV yard. | 2019-07-01 | 2019-12-17 | 2019-12-17 | 541775 | 585000 |  |  | 100 | 69 | na | 0.1 | 336 ACSR | Wood and steel poles | 50 | 0.1 | na | na | 25.101(c)(5)(E)
0PT04050 | Pleasant Springs 138 kV POI | Leon County | Install a new 138 kV point of interconnection for Houston County Electric (HCEC) to their existing Pleasant Springs 138 kV Substation on the Jewett Switch - Crockett Switch 138 kV Line. | 2019-08-19 | 2019-12-18 | 2019-12-18 | 200000 | 315000 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT38456 17T65128 0PT38387 | TI-Schroeder 138 kV UG Line: Increase double-circuit Section Ampacity | City of Dallas, Dallas County | Rebuild to increase the ampacity of the 0.5 mile double-circuit TI - Schroeder 138 kV UG Line section. | 2019-05-01 | 2020-05-22 | 2020-05-22 | 29613898 | 30000000 |  |  | 100 | 138 | 138 | 0.5 | 3-3500 kcmil Cu HPFF, 2-6000 kcmil Cu XLPE | Underground Transmission Line | 100 | 0.45 | na | na | 25.101(c)(5)(B)
0PT38808 | Sandow Switch - Temple Switch 138 kV Line: Storm Restoration | City of Buckholts, Milam County | Rebuild approximately 0.2 miles of the Sandow Switch - Temple Switch 138 kV Line due to Storm Damage. | 2018-12-09 | 2019-11-26 | 2019-11-26 | 298835.06 | 1882456.31 |  |  | 100 | 138 | na | 0.2 | 2-1926.9 kcmil ACSS/TW | Steel Poles | 50 | 0.2 | na | na | 25.101(c)(3) | Emergency Storm Restoration
0PT38959 | Yucca Drive Sw-Culberson Sw 138 kV Line: Cut-In to Barstow Northwest Sub | City of Pecos, Ward County | Reconfigure line to accommodate the expansion of Barstow Northwest Substation by utilizing one new dead-end monopoles | 2019-12-09 | 2019-12-22 | 2019-12-22 | 295580 | 330000 |  |  | 100 | 138 | na | 0.04 | 1926.9 Cumberland | Steel Poles | 80 | 0.1 | na | na | 25.101(c)(5)(A)
0PT37683 | Lake Creek Switch - Tradinghouse Switch (East Ckt) 345 kV Line: Lake Hall Sw. Line Work | City of Hallsburg, McLennan County | Cut in the Lake Hall Switch (Prairie Hill Wind Interconnect) into the Lake Creek Sw. - Tradinghouse Sw. (East) 345 kV Line. | 2019-11-21 | 2020-08-17 |  | 849108 | 1008746 |  |  | 99 | 345 | na | 0.1 | 959.6 kcmil ACSS/TW/HS | Lattice Steel Towers | 170 | 0.1 | na | na | 25.101(c)(5)(A)
0PT04399 | Thorntonville Sub: Line work associated with establishing Thorntonville Sub | City of Monahans, Ward County | Relocate and install structures to cut in the Permian Basin - Crane 69 kV Line to establish the new Thorntonville Sub. | 2019-09-03 | 2019-11-01 | 2019-11-01 | 913304 | 1421935.69 |  |  | 100 | 69 | 69 | 0.5 | 959.6 MCM ACSS/TW/HS Suwannee | Steel poles | 50 | na | 50 | na | 25.101(c)(5)(A)
0PT39236 | Navy Lake POD 69kV Line | Archer County | This project is to construct the tap from the Cotton Wood Rd Switch - Navy Kickapoo Switch 69kV line to Navy Kickapoo Switch - Navy Kickapoo 69 kV line to serve Texas Express Pipe Line at Navy Kickapoo POD. | 2019-07-22 | 2019-10-10 | 2019-10-10 | 1000000 | 850000 |  |  | 100 | 69 | 69 | 0.1 | 4/0 kcmil ACSR | Woods or Concrete Poles | Varies | na | Varies | 0.1 | 25.101(c)(5)(A)
0PT38586 | Buzzard Draw Switch - Gunsight Switch 138 kV Line: Howden (Surge Operating) POD | City of Big Spring, Howard County | Install a new 138 kV point of delivery for Surge Energy's new 138 kV substation on the Buzzard Draw Switch - Gunsight Switch 138 kV Line. | 2019-10-18 | 2019-12-20 | 2019-12-20 | 974000 | 974000 |  |  | 100 | 138 | na | 0.1 | 336 MCM ACSR | Steel/ Wood Poles | 75 | na | na | na | 25.101(c)(5)(A)
0PT38532 | Yucca Switch - Moss Switch 138 kV Line: Shin Oak POD for Blackbeard Operating, LLC | Winkler County | Install a new 138 kV point of delivery (POD) for Blackbeard Operating, LLC on the Yucca Switch - Moss Switch 138 kV Line | 2019-09-03 | 2019-12-16 | 2019-12-16 | 1200000 | 1200000 |  |  | 100 | 138 | 138 | 0.4 | 795 ACSR | Steel Poles | 75 | 0.2 | 75 | 0.2 | 25.101(c)(5)(A)
18T62143 | Hackberry - Grapevine Ball St 138 kV Line: Cut-In at Vineyard Switch | City of Grapevine, Tarrant County | Separate and terminate the Northlake - Grapevine Ball Street 138 kV Line to establish the new Vineyard Switch. | 2019-11-16 | 2019-12-19 | 2019-12-19 | 918748 | 1905000 |  |  | 100 | 138 | 138 | 0.33 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.33 | Varies | na | 25.101(c)(5)(B)
18T62144 | Southlake - Euless 138 kV Line: Cut-In at Vineyard Switch | City of Grapevine, Tarrant County | Separate and terminate the Roanoke Switch - Euless 138 kV Line to establish the new Vineyard Switch. | 2019-10-07 | 2019-12-19 | 2019-12-19 | 1510549 | 2713000 |  |  | 100 | 138 | 138 | 0.85 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.85 | Varies | na | 25.101(c)(5)(B)
0PT04098 | Roanoke to Coppell (BEC) 138 kV Line: Cut-In at Vineyard Switch (West) | City of Grapevine, Tarrant County | Separate and terminate the Roanoke Switch - Euless 138 kV Line to establish the new Vineyard Switch. | 2020-09-14 | 2020-12-15 |  | 400262 | 907000 |  |  | 0 | 138 | 138 | 0.13 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.13 | Varies | na | 25.101(c)(5)(B)
0PT39498 | Andrews Co South Switch - Littman Sub 138 kV Line : Lower 1/3 to 1/5 | City of Andrews, Andrews County | Lower structures 1/3 to 1/5 to accommodate the new Clearfork - Doghouse 345 kV Line. | 2019-10-14 | 2019-11-01 | 2019-11-01 | 495649.35 | 535000 |  |  | 100 | 138 | 138 | 0.45 | 1926.9 ACSS/TW | Concrete Poles | 80 | 0.45 | 80 | na | 25.101(c)(5)(B)
0PT37564 | Horseshoe Springs Sw - Owl Hills 138 kV Line: Cut-in to Est Alligator Draw | Orla City Reeves County | Cut in the new Alligator Draw Station utilizing the new structures on the Horseshoe Springs - Chimney Wells POD 138 kV Line. | 2019-10-18 | 2019-12-31 | 2019-12-31 | 1600000 | 1373310 |  |  | 100 | na | 138 | 18.7 | 1926.9 kcmil ACSS/TW | Steel Poles | na | na | 70 | 0.3 | 25.101(c)(5)(A)
18T64117 | Tyler - Tyler West 69kV to 138kV Rebuild | Tyler, Smith County | Rebuild the Tyler- Tyler West 69kV Line to 138kV designed to operate at 90C and 897 Amps. | 2019-06-17 | 2019-08-30 | 2019-08-30 | 2924331.77 | 3750952 |  |  | 100 | 69 | 138 | 1.9 | 795 kcmil 26/7 ACSR Drake | Steel Monopoles | Varies | na | Varies | na | 25.101(c)(5)(B)
0PT38852 | Wink Switch - Notrees Switch 138 kV Line : Railside POD (Exxon) | City of Wink, Winkler County | This project is to provide two point of deliveries for Exxon Mobil Pipeline Company on the Wink - Notrees 138 kV Line. | 2019-12-09 | 2019-12-23 | 2019-12-23 | 700000 | 700000 |  |  | 100 | na | 138 | 0.1 | 1926.9 kcmil ACSS/TW/HS | Steel Poles | na | na | 100 | 0.1 | 25.101(c)(5)(A)
0PT37221 | Means - Fullerton Switch 138 kV Line: Cut-In to Establish Blackbird Switch | City of Andrews, Andrews County | This project is to provide a point of interconnection for the customer's generator (Lapetus Energy Project, LLC) at Blackbird Sw | 2019-09-30 | 2019-11-11 | 2019-11-11 | 1317334 | 1317334 |  |  | 100 | na | 138 | 0.48 | 959.6 ACSS/TW/HS | Steel Poles | na | na | 160 | 0.48 | 25.101(c)(5)(A)
0PT38849 | Decatur Sub - Bowie Sub 69 kV Line: Bennett Road Switch Retermination | City of Decatur, Wise County | Install one dead-end structure to reterminate the Decatur - Bowie 69 kV Line into Bennett Road Switch | 2019-10-22 | 2019-12-24 | 2019-12-24 | 270280 | 317827 |  |  | 100 | 69 | 69 | 0.03 | 959 MCM ACSS/TW Suwannee | Steel Poles | 50 | 0.11 | na | na | 25.101(c)(5)(A) | Work being done on Oncor Substation Property.
0PT39007 | Decatur Sub - Oran Sub 69 kV Line: Bennett Road Switch Retermination | City of Decatur, Wise County | Install one dead-end structure to reterminate the Decatur - West Chico - Oran 69 kV Line into Bennett Road Switch | 2019-10-21 | 2019-12-24 | 2019-12-24 | 235794 | 265931 |  |  | 100 | 69 | 69 | 0.03 | 959 MCM ACSS/TW Suwannee | Steel Poles | 50 | 0.11 | na | na | 25.101(c)(5)(A) | Work being done on Oncor Substation Property.
0PT38088 | Wolf Switch - Moss Switch 138 kV Line: Establish Red Lakes Switch for Oberon Solar Interconnect | Ector County | Install four steel monopole structures to loop into new Red Lakes Switch for Oberon Solar Interconnect. | 2019-10-30 | 2019-12-02 | 2019-12-02 | 1065942 | 1200000 |  |  | 100 | 138 | 138 | 0.15 | 1926.9 MCM ACSS/TW Cumberland | Steel Poles | Centerline | 0.11 | 150 | 0.04 | 25.101(c)(5)(A)
0PT38352 | Graham Switch - Tonkawa Switch 345 kV Line: CMPC Hardening 133/3 &133/4 | Scurry County | Replace structures 133/3 & 133/4 with dead-end structures to harden the line. | 2019-09-10 | 2019-10-11 | 2019-10-11 | 795443 | 380000 |  |  | 100 | 345 | 345 | 0.2 | 2 - 795 MCM ACSR “Drake | Lattice Towers | 190 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38380 | Tyler West Sub - Tyler Switch 138kV Line: Upgrade | Tyler, Smith County | The Tyler West - Tyler Switch 138 kV line will be upgraded and hardened to prepare the idle line to be energized. | 2019-09-16 | 2020-12-31 |  | 1243914 | 2139599 |  |  | 99 | 138 | 138 | 5.3 | 795 kcmil 26/7 ACSR Drake | Steel Towers, Wood H-Frames, Concrete H-Frames, and Steel Monopoles | varies | na | varies | na | 25.101(c)(5)(B)
0PT38081 0PT40571 | No Trees Switch - Andrews County South Switch 138 kV Line: Rebuild | City of Wink, Winkler County | Rebuild the 8.8 miles of single-circuit wood h-frames. The final build will utilize double-circuit steel monopoles. Re-terminate the line going to Andrews North on the first rung and terminate the new line going to the second autotransformer on the second rung. | 2019-03-29 | 2020-05-14 | 2020-05-14 | 17005546.49 | 19000000 |  |  | 100 | 138 | 138 | 8.8 | 1926 kcmil ACSS/TW | Steel and Concrete Poles | 50-125 | 8.8 | na | na | 25.101(c)(5)(B)
0PT04329 | Installation for Canyon Wind POI, Scurry County South Switch-Canyon Wind 138 kV Line | City of Dunn, Scurry County | Installation with new single-circuit, steel monopole dead end structures. The installation is at the request of the Canyon Wind. | 2021-04-06 | 2021-05-15 |  | 1412751.89 |  |  |  | 0 | na | 138 | 0.28049 | 959 ACSS/TW Suwannee | Steel Monopole Structures | na | na | na | na | 25.101(c)(5)(A) | Structure installation is at the request of Canyon Wind.
0PT39809 | 2019 CMPC Odessa District, Paint Creek-China Grove 138 kV Line | City of Snyder, Scurry County | Modify highway crossing to improve the system reliability. | 2019-09-20 | 2019-11-04 | 2019-11-04 | 606394.78 | 250400 |  |  | 100 | 138 | na | 0.27633 | 636 ACSR Grosbeak | Concrete H-frame Structures | 100 | 0.27633 | 100 | na | 25.101(c)(5)(B)
0PT39804 | Yucca - Holt 138 kV Line: Raise Structure 10/1 | Winkler County | Raise structure 10/1 to aide in establishing the Shin Oak POD for Blackbeard Operating, LLC. | 2019-09-23 | 2019-12-16 | 2019-12-16 | 173157 | 175000 |  |  | 100 | 138 | 138 | 0.01 | 795 ACSR | Steel Poles | 75 | 0.1 | na | na | 25.101(c)(5)(B)
0PT39953 | Athens Sub - Jacksonville Switch 69 kV Line: Reterm Jacksonville Switch | City of Jacksonville, Cherokee County | Determinate and reconfigure Athens Sub - Jacksonville Switch 69 kV transmission line into the rebuilt Jacksonville Switch Station. | 2019-10-15 | 2019-12-18 | 2019-12-18 | 450000 | 450000 |  |  | 100 | 69 | na | 0.1 | 795 kcmil ACSR | Steel or Concrete Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A) | Work is being done on Oncor property.
0PT39956 | Jacksonville Plant Sub - Jacksonville Switch 69 kV Line: Reterm | City of Jacksonville, Cherokee County | Reterminate the Jacksonville Plant - Jacksonville Tap - Jacksonville Switch 69 kV Line for the rebuild of the Jacksonville Switch Station. | 2019-10-15 | 2019-12-18 | 2019-12-18 | 240000 | 240000 |  |  | 100 | 69 | na | 0.1 | 795 kcmil ACSR | Steel or Concrete Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A) | Work is being done on Oncor property.
0PT39963 | Jacksonville Plant South-Jacksonville Sw 69 kV Line: Reterm Jacksonville Switch | City of Jacksonville, Cherokee County | Reterminate the Jacksonville Plant - Beaumont Street Tap- Jacksonville Switch 69 kV Line for the rebuild of the Jacksonville Switch Station. | 2019-10-15 | 2019-11-13 | 2019-11-13 | 138748 | 138748 |  |  | 100 | 69 | na | 0.1 | 795 kcmil ACSR | Steel or Concrete Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A) | Work is being done on Oncor property.
17T65086 | Collin Sw - Payne Sw 138 kV Line: (Redbud) Prolina POI Reroute | City of Prosper, Grayson County | Build a Point of Interconnect to Brazos Electric's 'Redbud Substation' on the Collin Switch - Stone Creek Switch 138 kV Line. | 2019-09-23 | 2019-11-15 | 2019-11-15 | 905000 | 905000 |  |  | 100 | 138 | na | 0.2 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | 100 | 0.2 | na | na | 25.101(c)(5)(A)
0PT38421 | Central Bluff Sw. - Holstein Solar I Sw. 345 kV Line: Construct transmission line for connection Holstein Solar | City of Sweetwater, Nolan County | Install a 345 kV point-of-interconnection (POI) for customer's generator ( Holstein Solar I) at Central Bluff Switch. | 2019-09-23 | 2019-12-02 | 2019-12-02 | 580000 | 650000 |  |  | 100 | 345 | na | 0.2 | 795 kcmil ASCR | Steel or Concrete Poles | 150 | 0.1 | na | na | 25.101(c)(5)(A) | Work is being done on Oncor property.
0PT37440 | Jacksonville Switch- Troup 69 kV Line: Reterminate and Reconfigure for Jacksonville Switch Rebuild | City of Jacksonville, Cherokee County | Utilize the existing Jacksonville Sw. Sta. – Structure 50/9 69 kV double-circuit line section to operate the Jacksonville Sw. Sta. – Athens 69 kV Line and Jacksonville Sw. Sta. – Troup 69 kV Line as a continuous circuit. Disconnect the Jacksonville Tap – Structure 50/9 69 kV line section and establish a Jacksonville Sw. Sta. – Carey Lake Tap – Jacksonville SES 69 kV Line. Reterminate the transmission line into the rebuilt Jacksonville Switch Station. Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | 2019-10-15 | 2019-11-13 | 2019-11-13 | 405000 | 425000 |  |  | 100 | 69 | na | 0.2 | 795 kcmil ASCR | Steel or Concrete Poles | 50 | 0.2 | na | na | 25.101(c)(5)(A) | Work is being done on Oncor property.
0PT38450 | Kirkland Park Sub - Ti Sub 138 kV Line: Replace 3/8 Edhs Shield Wire | City of Dallas, Dallas County | Replace the 3/8" EHS shield wire with OPGW on the Kirkland Park - Schroeder Road section of the Kirkland Park Sub - TI Sub 138 kV Line. | 2020-11-09 | 2020-11-30 |  | 514856.41 | 514856 |  |  | 0 | 138 | na | 2.1 | OPGW | Steel Monopoles | 100 | 2.1 | na | na | 25.101(c)(5)(A)
0PT39714 | Northaven Switch-Renner Switch 138 kV: Rebuild Alpha Rd. - Knoll Trail. | City of Dallas, Dallas County | Rebuild the 2.25 mile Alpha Road-Knoll Trail 138 kV double-circuit line using a conductor rated for 2569A or greater. | 2019-04-15 | 2020-05-25 | 2020-05-25 | 6606401.32 | 6850000 |  |  | 100 | 138 | 138 | 4.5 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 2.25 | na | na | 25.101(c)(5)(B) | The original project was Northaven-Renner (16T65090), and it was split so that we now have Northaven-Alpha Road & Knoll Trail-Preston Road North (16T65186), Preston Road North-Renner (16T65090), and Alpha Road-Knoll Trail (0PT39714). The WA that should now be associated with this project on the PUC Report is 0PT39714.
0PT39736 | Cedar Hill Switch - Camp Wisdom 138 kV Line: Replace Str T-1005 | City of Dallas, Dallas County | Repair structure T-1005 on the Camp Wisdom Road – Cedar Hill Switch 138 kV line. The damaged structure will be repaired using a field welded steel support sleeve. | 2019-07-30 | 2019-08-30 | 2019-08-30 | 87945 | 34664 |  |  | 100 | 138 | 138 | 0.1 | 972 kcmil ACAR | Steel Pole | na | na | na | na | 25.101(c)(5)(B) | Original project was to replace structure T-1005. Updated scope is to repair the structure using a field welded steel support sleeve.
0PT37559 | Polk St Terminal - Polk St 138 kV Line : Terminations Replacement | City of Dallas, Dallas County | Replace existing terminations at Polk St Sub and Polk Terminal. | 2019-10-14 | 2019-11-18 | 2019-11-18 | 690000 | 690000 |  |  | 100 | 138 | na | na | 600 kcmil Cu Phelps Dodge Cable | Underground Transmission Line | na | na | na | na | 25.101(c)(5)(B)
0PT38283 | Edgemere Sub - Bandera Sub 138 kV Line : Terminations Replacement | City of Dallas, Dallas County | Replace existing terminations at Edgemere Terminal and Bandera Sub. | 2019-10-28 | 2019-11-11 | 2019-11-11 | 690000 | 690000 |  |  | 100 | 138 | na | na | 900 kcmil Alu Okonite Cable | Underground Transmission Line | na | na | na | na | 25.101(c)(5)(B)
0PT40192 | Dog House - Prospero Solar 345 kV Line | Andrews County | Install one monopole and one span of wire to connect the customer line to Doghouse Switch. | 2020-01-06 | 2020-04-16 | 2020-04-16 | 590033 | 450000 |  |  | 100 | na | 345 | 0.3 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(A)
0PT38448 | Krum Tap Switch - Gainesville Sub 138 kV Line: Rippey Solar Interconnect | City of Gainesville, Cooke County | This project interconnects the Rippey Solar on the Krum Tap Sw - Gainesville Sub 138 kV Line at the Ray Roberts Switch. | 2020-10-12 | 2020-11-13 |  | 1015306 |  |  |  | 0 | 138 | 138 | 0.3 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT37229 | Roanoke Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (Roanoke/Euless) 138 kV line connecting to new Deen Sw. | 2020-05-14 | 2020-12-15 |  | 958557.96 | 958558 |  |  | 50 | 138 | 138 | 0.1 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B) | Below grade construction to start 10/1/2019, above grade construction to start 1/3/2020
0PT37237 | Handley Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (Handley) 138 kV line connecting to new Deen Sw. | 2020-05-07 | 2020-12-15 |  | 943604.37 | 943604 |  |  | 49 | 138 | 138 | 0.1 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B) | Below grade construction to start 10/1/2019, above grade construction to start 1/3/2020
0PT37236 | Hicks Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (Hicks) 138 kV line connecting to new Deen Sw. | 2020-04-10 | 2020-12-15 |  | 1387626.12 | 1387627 |  |  | 50 | 138 | 138 | 0.3 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B) | Below grade construction to start 10/1/2019, above grade construction to start 1/3/2020
0PT37238 | Eagle Mountain Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (Eagle Mtn.) 138 kV line connecting to new Deen Sw. | 2020-05-05 | 2020-12-15 |  | 1387626.12 | 1387627 |  |  | 46 | 138 | 138 | 0.3 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B) | Below grade construction to start 10/1/2019, above grade construction to start 1/3/2020
0PT37235 | North Main Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (N. Main) 138 kV line connecting to new Deen Sw. | 2020-04-10 | 2020-12-15 |  | 810689.33 | 810689 |  |  | 49 | 138 | 138 | 0.2 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B)
0PT38778 | Monticello Switch - Paris Switch 345 kV Line: Establish Woodard Switch | Lamar County | Establish a point of interconnection to the Impact Solar LLC generating facility by establishing Woodard Switch on the Monticello - Paris 345 kV transmission line. | 2020-04-16 | 2020-05-15 | 2020-05-15 |  | 2000776 |  |  | 100 | 345 | 345 | 0.25 | 2-959.6 kcmil ACSS/TW | Steel Towers | 170 | na | 370 | 0.25 | 25.101(c)(5)(A)
0PT38200 | Carrollton East - Renner/Northaven 138 kV Line: Rebuild Farmers Branch Gillis - Structure T308A | City of Farmers Branch, Dallas County | Rebuild the 1.3 mile section of the Carrollton East - Renner Sw/Northaven Sw 138 kV Line from Farmers Branch Gillis – Structure T308A using conductor greater than 1928A. Rebuild will end at structure T308A which is where the two circuits split to Renner and Northaven respectively. | 2019-11-25 | 2020-04-03 | 2020-04-03 |  | 5500000 |  |  | 100 | 138 | na | 1.3 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 1.3 | na | na | 25.101(c)(5)(B)
0PT38236 | Lake Creek Switch - Waco East Switch 138 kV Line: Rebuild Lake Creek Switch - Waco LaSalle Sub | City of Waco, McLennan County | Rebuild of 7.6 mile 138 kV Line of single-circuit wooden h-frame structures to steel monopoles | 2020-01-21 | 2020-05-21 | 2020-05-21 | 12773383 | 12773383 |  |  | 100 | 138 | 138 | 7.6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 7.6 | na | na | 25.101(c)(5)(B) | Early start in November for foundations
0PT40107 | Lake Creek Switch - Waco East Switch 138 kV Line: Rebuild Waco LaSalle Sub - Structure 1/9 section | City of Waco, McLennan County | Rebuild of 2.2 mile 138 kV Line of single-circuit wooden h-frame structures to steel monopoles | 2020-09-23 | 2020-12-31 |  |  | 4450342 |  |  | 0 | 138 | 138 | 2.2 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 2.2 | na | na | 25.101(c)(5)(B)
0PT38347 | Stephenville Switch - Comanche Switch 138 kV Line : MCPc H-frame Replacement | City of Comanche, Comanche County | This is a potential 2019 CMPC Corrosion and Erosion project. Background: A seasonal creek has eroded approx. 5' of soil around one of the legs of the wooden h-frame 10/2 to where it is now exposed significantly. This scope and estimate includes the cost of replacing the wooden h-frame with a more durable h-frame and contains a lot of access dollars due to its location. | 2019-10-08 | 2019-10-16 | 2019-10-16 |  | 521762 |  |  | 100 | 138 | 138 | 0.2 | 636 ACSR | Steel Poles | 100 | 0.2 | na | na | 25.101(c)(3) | Emergency work to replace structure near Walnut Creek due to severe erosion.
0PT38497 | Lake Creek (east) Switch - Tradinghouse Switch 345 kV Line : MCPc Erosion Control | City of Waco, McLennan County | This is a CMPC Erosion project to be completed in 2019. Tower foundations on either side of the crossing have been eroded and exposed. We will be reinforcing tower foundations to ensure a safe crossing. | 2020-11-02 | 2020-12-31 |  |  | 1000000 |  |  | 0 | 345 | 345 | 0.5 | 795 kcmil ACSR | DC Tangent Lattice | 100 | 0.5 | na | na | 25.101(c)(5)(B) | Project is being canceled and charges will be moved to Substation WA 0PT41753
0PT39397 | Wink Switch - Culberson Switch 138 kV Line: Long Pasture POD for BPX Energy Keystone | Reeves County | Establish a point of delivery to BPX Energy’s Keystone on the Wink - Culberson 138 kV transmission line. The point of delivery will be located in the Mason - Screwbean line section. | 2020-01-20 | 2020-02-14 | 2020-02-14 |  | 1574155 |  |  | 100 | 138 | na | 0.35 | 959.6 ACSS/TW | Steel Poles/ H-frame Switch | 50 | na | 70 | 0.32 | 25.101(c)(5)(A)
0PT39077 | Valley Switch - Paris Switch 138 kV Line: Allens Creek POI for Rayburn Lower Bois d'Arc Water Pump Station | Fannin County | Establish a point of interconnection to Rayburn Country Electric Cooperative’s Lower Bois d’Arc Creek Water Pump Station on the Valley - Paris 138 kV transmission line. | 2020-01-31 | 2020-02-07 | 2020-02-07 |  | 1271785 |  |  | 100 | 138 | na | 0.4 | 959.6 ACSS/TW | Steel Poles/ H-frame Switch | 100 | na | 75 | 0.04 | 25.101(c)(5)(A)
0PT39500 | Seagoville Switch - Crandall Sub 138 kV Line : MCPc Erosion Relocation | City of Seagoville, Dallas County | This project is a 2019 CMPC Corrosion/Erosion project. Structure 12/6 is a hybrid pole no located in the Trinity River due to severe erosion. | 2019-11-04 | 2019-11-18 | 2019-11-18 |  | 1011727 |  |  | 100 | 138 | 138 | 0.2 | 795 ACSR | Steel Poles | 100 | 0.2 | 100 | 0.2 | 25.101(c)(5)(B) | Emergency work to replace two structures near the Trinity due to severe erosion, increased access charges.
18T62019 | Springdale - Richland Hills (North Ckt) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the Springdale - Richland Hills (North Ckt) section of the Saginaw - Springdale - Richland Hills 138 kV line. The project consists of rebuilding the North circuit of the 3.7 mile line from Springdale - Str 7/3 N. | 2020-06-16 | 2020-12-15 |  |  | 5750000 |  |  | 90 | 69/138 | 138 | 3.7 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 3.7 | na | na | 25.101(c)(5)(B)
18T62020 | Springdale - Richland HiIls (South Ckt) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the Springdale - Richland Hills (South Ckt) section of the North Main Switch - Richland Hills 138 kV line. The project consists of rebuilding the South circuit of the 3.7 mile line from Str 3/5 S - 7/3 S. | 2020-06-16 | 2020-12-15 |  |  | 1040000 |  |  | 96 | 69/138 | 138 | 3.7 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 3.7 | na | na | 25.101(c)(5)(B)
0PT40145 | Wolf Switch - Moss Switch 138 kV line: High Temp Upgrade | Ector & Ward County | Upgrade the Moss Switch – Wolf Switch 138 kV line for 120°C and 1146A, high temperature operation. | 2019-12-12 | 2019-12-21 | 2019-12-21 |  | 1007917 |  |  | 100 | 138 | 138 | 2 | 795 kcmil ACSR | Wood H-Frames | 50 | 2 | na | na | 25.101(c)(5)(B)
0PT40963 | Handley Switch - Denton Avenue Sub 69 kV Line : CMPC System Hardening (Str. 3/5 & 3/6) | Tarrant County | Replace Structures 3/5 & 3/6 adjacent to I-30 in Arlington, TX consisting of existing single-circuit wooden H-frames with concrete H-frames. | 2018-12-13 | 2019-12-27 | 2019-12-27 |  | 275000 |  |  | 100 | 69 | na | 0.1 | 300 kcmil ACSR | Concrete H-Frames | Varies | na | na | na | 25.101(c)(5)(B)
0PT38115 | Lewisville Switch (Brazos) - Lakepoint Switch (TNMP) Sub. 138 kV Line: Reconductor | City of Lewisville, Denton County | Upgrade 5.3 miles of the Lewisville Switch (BEC) – Lakepoint (TNMP) 138 kV Line using conductor 959.6 MCM ACSS "Suwanee” with E3X coating designed to operate at 1996 Amps and 200C. The existing 3/8" EHS shield wire will be replaced with 0.546" OD 48 count OPGW. Upgrade all line terminal and associated equipment to meet or exceed 1996 A. | 2020-02-10 | 2020-04-02 | 2020-04-02 |  | 4645000 |  |  | 100 | 138 | na | 5.3 | 959.6 kcmil ACSS/TW | Steel Towers | Varies | 5.3 | na | na | 25.101(c)(5)(A)
0PT39974 0PT40949 | SL Pemkiff - Ringo 138kV Line: Slager Lake POD | Reagan County | Provide a 138 kV point-of-delivery (POD) for Sherrod on the Pemkiff - Ringo 138 kV line. The POD will be located approximately 1.8 miles east of the Pemkiff substation. In addition the cost to remove 1 existing concrete pole along the Pemkiff – Ringo 138 kV transmission line. This removal is required to accommodate the new Slager Lake POD for XTO Sherrod Substation. | 2020-03-13 | 2020-05-19 | 2020-05-19 |  | 1100000 |  |  | 100 | 138 | na | 0.9 | 959.6 ACSS/TW | Steel Poles | na | na | 105 | 0.5 | 25.101(c)(5)(A)
0PT39620 | Spraberry Switch - Midland East 138 kV Line : Cloverdale POD | City of Midland, Midland County | Provide a 138 kV point-of-delivery (POD) on the Spraberry Switch - Midland East 138 kV line. The POD will be located approximately 2.0 miles southeast of the Midland East Substation. | 2020-04-17 | 2020-06-24 | 2020-06-24 |  | 2436280 |  |  | 100 | 138 | na | 0.9 | 1926.9 ACSS/TW | Steel Poles | na | na | 70 | 0.9 | 25.101(c)(5)(A)
0PT40458 | Ringgold Magnolia Tap – Beaver Creek Tap 69 kV Line: Install Barrel Springs (Oneok) POI | Clay County | Provide a 138 kV point-of-interconnect (POI) for TNMP's Oneok on the Ringgold Magnolia Tap - Beaver Creek Tap 69 kV line. The POI will be located approximately 2.6 circuit-miles from Beaver Creek Tap. | 2020-02-13 | 2020-04-16 | 2020-04-16 |  | 1050000 |  |  | 100 | 69 | na | 0.5 | 1/0 ACSR, 959.6 ACSS/TW | Steel Poles | na | na | 100 | 0.5 | 25.101(c)(5)(A)
0PT39894 | McKenzie Draw Switch - Midland County Northwest/Midland East Switch 138 kV Line: Kelton Windmill POD | Martin County | Establish a point of delivery on the eastern circuit of the McKenzie Draw Switch - Midland County Northwest/Midland East Switch 138 kV transmission line. | 2020-01-27 | 2020-03-09 | 2020-03-09 |  | 2100000 |  |  | 100 | 138 | na | 0.29 | 1926.9 ACSS/TW/HS | Steel Poles/ H-frame Switch | 75 | na | 70 | 0.29 | 25.101(c)(5)(A)
0PT40457 0PT40948 | Brown - Grady 138 kV Line: Lenorah POD | Martin County | Establish a point of delivery by establishing Lenorah Switch on the Brown - Grady 138 kV transmission line. Remove concrete poles on the Brown - Grady 138 kV Line to accommodate the new Lenorah POD. | 2020-04-02 | 2020-06-08 | 2020-06-08 |  | 1950000 |  |  | 100 | 138 | 138 | 0.3 | 1-1926.9 kcmil ACSS/TW | Steel Monopoles | 70 | na | 70 | 0.3 | 25.101(c)(5)(A)
0PT39509 | Venus Switch-Sardis Switch 138 kV Line: Structure Replacement for Midlothian Hospital | City of Midlothian, Ellis County | Replace wood H-frame to a concrete H-frame for Midlothian Hospital | 2019-12-19 | 2019-12-21 | 2019-12-21 |  | 300000 |  |  | 100 | 138 | na | 0.02 | 795 kcmil ACSR | Concrete H-Frame | 50 | 0.02 | na | na | 25.101(c)(5)(D) | This is a 100% reimbursable project by Methodist Hospital of Dallas
0PT39916 | McDonald Road-Big Spring Switch 138 kV Line: Loop into Hill Crest Sub | City of Big Spring, Howard County | Reconfigure McDonald Road-Big Springs Switch 138 kV line to loop into new Hill Crest Sub | 2020-01-05 | 2020-03-09 | 2020-03-09 |  | 1000000 |  |  | 100 | 138 | na | 0.02 | 1926.9 ACSS/TW | Steel DE Monopoles | 100 | 0.5 | na | na | 25.101(c)(5)(A)
0PT40226 | Big Spring Switch-Chalk 69 kV line: Modify Line for Hill Crest Sub | City of Big Spring, Howard County | Reconfigure Big Spring Switch-Chalk 69 kV Line to support the establishment of the new Hill Crest | 2020-01-02 | 2020-03-09 | 2020-03-09 |  | 1500000 |  |  | 100 | 69 | na | 0.02 | 1926.9 ACSS/TW | Steel DE 3-poles | 100 | 0.5 | na | na | 25.101(c)(5)(A)
0PT39135 | Yucca Drive Switch-Holt Switch 138 kV Line: Loop into Turnbaugh Corner Switch | City of Goldsmith, Ector County | Looping the Holt Sw-Yucca Drive Sw 138 kV Line into the Turnbaugh Corner Switching Station | 2020-02-18 | 2020-06-15 | 2020-06-15 |  | 1800000 |  |  | 100 | 138 | na | 1 | 1926.9 ACSS/TW | Steel Monopoles | 75 | 1 | na | na | 25.101(c)(5)(A)
0PT39137 | Turnbaugh Corner Switch-Holt Switch 138 kV Line: Loop into Turnbaugh Corner Switch | City of Goldsmith, Ector County | Establish a new transmission line from Turnbaugh Corner Switch to the customer owned Oxy Goldsmith Substation | 2020-02-13 | 2020-06-01 | 2020-06-01 |  | 800000 |  |  | 100 | 138 | na | 0.2 | 795 ACSR | Steel Monopoles | 75 | 0.2 | na | na | 25.101(c)(5)(A)
0PT40144 0PT41448 | Wink Switch - Notrees Switch 138 kV Line : Install Second Circuit | City of Wink, Winkler County | Install second circuit to the newly rebuilt 29 miles Wink - Notrees 138 kV Line. | 2019-12-17 | 2020-05-11 | 2020-05-11 |  | 15021928 |  |  | 100 | 138 | na | 28 | 1926.9 ACSS/TW | Steel Poles | 50 | 29 | na | na | 25.101(c)(5)(C)
0PT41051 | Eskota Switch - Morgan Creek Switch 138 kV Line : Structure Replacements | City of Sweetwater, County of Nolan | Replace 2 H-Frame structures and remove 1 H-Frame structure. | 2020-09-12 | 2020-10-19 |  |  | 450000 |  |  | 0 | 138 | na | 0.1 | 795 ACSR | Steel, Monopoles | 70 | 0.1 | na | na | 25.101(c)(5)(B)
0PT40946 | Comanche Switch - Corn Trail Switch 345 kV Line: CMPC Insulator Replacement | Comanche/ Comanche County | Replace insulators on the Comanche - Corn Trail 345 kV Line. | 2020-03-10 | 2020-06-23 | 2020-06-23 |  | 467396 |  |  | 100 | 345 | 345 | 7.7 | 2 - 1590 kcmil ACSR Falcon | Steel Lattice Towers | 160 | 7.7 | na | na | 25.101(c)(5)(B)
0PT41067 | Benbrook South Tap Rebuild | City of Benbrook, Tarrant County | Upgrade the conductor on the 0.2 mile Benbrook South Tap 138 kV Line. | 2020-02-04 | 2020-03-15 | 2020-03-15 |  | 550000 |  |  | 100 | 138 | na | 0.2 | 795 ACSR | Concrete/Steel Poles | 75 | na | na | na | 25.101(c)(5)(B)
0PT39277 | Royse Switch - Oates (TMPA) 138 kV Line: Fate Sub Cut-in | City of Fate, Rockwall County | Separate and terminate the Royse Switch - Oates (TMPA) 138 kV Line to establish the new Fate Substation. | 2020-03-23 | 2020-05-04 | 2020-05-04 |  | 1147948 |  |  | 100 | 138 | 138 | 0.2 | BUNDLED (2X) 959.6 kcmil ACSS/TW | Steel Poles | Varies | 0.2 | Varies | na | 25.101(c)(5)(A)
18T64093 | Jewett Switch - Crockett 138 kV Line: Rebuild Centerville Sub to Pleasant Springs | Leon County | Rebuild the 7.6 mile section from Centerville to Pleasant Springs of the Jewett - Crockett 138 kV Line using double-circuit monopole construction with only one circuit installed. | 2020-01-06 | 2020-05-05 | 2020-05-05 |  | 6891179 |  |  | 100 | 138 | 138 | 7.6 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 7.6 | na | na | 25.101(c)(5)(B)
0PT04097 | Vineyard Switch - Flower Mound 138kV Line: Disconnect and Rebuild Vineyard Switch to McKamy Tap | City of Grapevine, Tarrant County | Extend the McKamy Tap line section into the new Vineyard Switch | 2020-09-14 | 2020-12-15 |  |  | 2067425 |  |  | 0 | 138 | 138 | 1.5 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.5 | Varies | 0.97 | 25.101(c)(5)(A)
0PT04105 | Vineyard Switch - Coppell 138kV Line: Disconnect and Rebuild Vineyard Switch to McKamy Tap | City of Grapevine, Tarrant County | Disconnect the Grapevine Junction - Coppell line section and extend to the new Vineyard Switch | 2020-09-14 | 2020-12-15 |  |  | 6648486 |  |  | 0 | 138 | 138 | 1.5 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.5 | Varies | 0.97 | 25.101(c)(5)(A)
0PT04103 | Roanoke to Coppell (BEC) 138 kV Line: Cut-In at Vineyard Switch (East) | City of Grapevine, Tarrant County | Disconnect the Grapevine Junction - Coppell line section and extend to the new Vineyard Switch | 2020-09-14 | 2020-12-15 |  |  | 1395620 |  |  | 0 | 138 | 138 | 1.5 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.5 | Varies | 0.97 | 25.101(c)(5)(A)
0PT40370 0PT40913 | Vealmoor - Brown 138 kV Line: Vealmoor Retermination | Borden County | The scope of this project is to reterminate the Vealmoor - Brown 138 kV Line at its new terminal location at Vealmoor. This retermination will be 275 feet, utilizing one (1) new single circuit monopole dead-end. Existing dead-end structure 1/1 will be reused to route the line north. | 2020-02-23 | 2020-03-01 | 2020-03-01 |  | 303000 |  |  | 100 | 138 | 138 | 0.05 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 0.05 | Varies | na | 25.101(c)(5)(A)
0PT40690 0PT40914 | Luther - Vealmoor 138 kV Line: Vealmoor Retermination | Borden County | The scope of this project is to reterminate the Vealmoor - Luther 138 kV Line at its new terminal location at Vealmoor. This retermination will be 300 feet, utilizing only new conductor and shield wire. No new structures will be installed as a part of this project. | 2020-02-24 | 2020-03-01 | 2020-03-01 |  | 59000 |  |  | 100 | 138 | 138 | 0.06 | 795 MCM ACSR Drake | Steel Poles | Varies | 0.06 | Varies | 0 | 25.101(c)(5)(A)
0PT40691 0PT40915 | Longdraw - Vealmoor 345 kV Line: Vealmoor Retermination | Borden County | The scope of this project is to reterminate the Longdraw - Vealmoor 345 kV Line at its new terminal location at Vealmoor. | 2020-01-26 | 2020-03-01 | 2020-03-01 |  | 355700 |  |  | 100 | 138 | 138 | 0.09 | 2 - 795 MCM ACSR Drake | Steel Poles | Varies | 0.09 | Varies | 0 | 25.101(c)(5)(A)
0PT40102 | TxDOT Relocation I30 Crossing Forney-Mesquite 138kV Line | City of Mesquite, Dallas County | Relocation with new double circuit, steel monopole dead end and tangent structures. | 2020-02-05 | 2020-04-28 | 2020-04-28 |  | 909704 |  |  | 100 | 138 | na | 0.6 | 795 ACSR Drake | Steel Monopole Structures | 100 | 0.3 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT40112 | TxDOT Relocation I635 Crossing Forney-Mesquite 138kV Line | City of Mesquite, Dallas County | Relocation with new double circuit, steel monopole dead end and tangent structures. | 2020-02-06 | 2020-04-28 | 2020-04-28 |  | 1164170 |  |  | 100 | 138 | na | 1.3121 | 795 ACSR Drake | Steel Monopole Structures | 100 | 0.65606 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
14T61006 | Relocation for Skyline Landfill, Waxahachie-Ferris-Trinity Hts. 69kV Line | City of Ferris, Dallas County | Relocation with new single circuit, steel monopole dead end structures. | 2020-03-09 | 2020-05-15 | 2020-05-15 |  | 2053820 |  |  | 100 | 69 | na | 1.1945 | 959 ACSS/TW Suwannee | Steel Monopole Structures | 100 | 1.1945 | 100 | 0.71496 | 25.101(c)(5)(D) | Structure relocation is at the request of Waste Management of Texas Inc. and is 100% reimbursable by Waste Management of Texas Inc..
0PT39936 | Relocation for Bremond Mine, Lake Creek-Jewett-Twin Oak 345kV Line | City of Bremond, Robertson County | Relocation with new double circuit, steel lattice tower dead end and tangent structures. | 2020-09-14 | 2020-10-31 |  |  | 1050259 |  |  | 0 | 345 | na | 0.79186 | 1590 ACSR Falcon (Bundled) | Steel Lattice Structures | 230 | 0.79186 | 230 | 0.40341 | 25.101(c)(5)(D) | Structure relocation is at the request of Luminant and is 100% reimbursable by Luminant.
0PT40495 | TxDOT Relocation US 59 Lufkin-Diboll East Loop 138kV Line | City of Diboll, Angelina County | Relocation with new single circuit, concrete H-frame tangent structures. | 2020-03-23 | 2020-04-28 | 2020-04-28 |  | 747185 |  |  | 100 | 138 | na | 0.54129 | 336 ACSR Linnet (Non-Bundled) | Concrete H-frame Structures | 100 | 0.54129 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT40403 | Commerce – Bonham 138 kV Line: Loring POI for Rayburn Lower Bois d’Arc Water Treatment Plant | Fannin County | Establish the point of interconnection to Rayburn Electric Cooperative’s Vinson substation for the Lower Bois d’Arc Creek Water Treatment Plant on the Commerce - Bonham 138 kV transmission line. | 2020-04-01 | 2020-06-22 | 2020-06-22 |  | 1100000 |  |  | 100 | 138 | na | 0.27 | 795 ACSR | Steel Poles/ H-frame Switch | 100 | 0.27 | 120 | na | 25.101(c)(5)(A)
0PT40198 | Greenville Ave SW - Matilda Sub 138 kV Line : Pumping Plant Replacement | City of Dallas, Dallas County | Replace the two existing 1000 gallon pumping plants at Greenville Ave SW with newer refurbished Schroeder 4500 gallon pumping plant. | 2020-02-28 | 2020-06-23 | 2020-06-23 |  | 663176 |  |  | 100 | 138 | na | na | 600 CU HPFF | Underground Transmission Line | na | na | na | na | 25.101(c)(5)(B)
0PT40216 | Polk St. Sub - Polk Terminal 138 kV Line: Replace Terminations | City of Dallas, Dallas County | Replace the 138 kV Underground Transmission Terminations at Polk ST. SUB and Polk Terminal SUB | 2020-10-19 | 2020-12-31 | [5 empty] | 0 | 138 | na | na | 600 CU HPFF | Underground Transmission Line | na | na | na | na | 25.101(c)(5)(B)
0PT40602 | Canton Switch - Canton Sub 138 kV Line : Replace STR's 1/1 - 1/3 | Van Zandt County | This is a CMPC project to replace STR's 1/1, 1/2, and 1/3 with (1) one steel dead-end pole and (1) one steel or concrete tangent pole. | 2020-04-20 | 2020-06-01 | 2020-06-01 |  | 325000 |  |  | 100 | 138 | na | 0.25 | 336 kcmil ACSR | Steel Poles | 100 | na | na | na | 25.101(c)(5)(B)
0PT40610 | Edgemere Sub - Bandera Sub 138 kV Line : Terminations Replacement | City of Dallas, Dallas County | Replace existing terminations at Edgemere Terminal and Bandera Sub. | 2020-10-05 | 2020-12-31 | [5 empty] | 0 | 138 | na | na | 900 kcmil Alu Okonite Cable | Underground Transmission Line | na | na | na | na | 25.101(c)(5)(B)
0PT39279 | Jack Rabbit 138 kV Station: Cut-In | City of Odessa, Ector County | Line work and structure relocations to cut-in the Odessa – Midessa South Switch 138 kV Line to the new Jack Rabbit 138 kV Substation. | 2020-03-23 | 2020-05-12 | 2020-05-12 |  | 2000000 |  |  | 100 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Steel Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT39796 | Everman - Cedar Hill 345 kV line | City of Kennedale, Tarrant | The 0.8 mile re-route will remove 6 steel tower structures. The new build will utilize six (7) dead-end steel monopole structures and three (2) double circuit tangent monopole structures. The existing 2-795 ASCR "Drake" conductor and shield wires will remain. | 2020-02-10 | 2020-05-11 | 2020-05-11 |  | 3557262 |  |  | 100 | 345 | na | 0.8 | 795 kcmil ACSR | Steel Poles | 100 | 0.8 | na | na | 25.101(c)(5)(B)
0PT39783 | Everman - Mansfield 138 kV line | City of Kennedale, Tarrant County | To build the 0.8 mile 138 kV line extension in the Everman Switch - Mansfield 138 kV line from existing structure 2/7 to the new Kennedale 138 kV terminals. This line will utilize steel monopole construction, seven (7) dead-end structures and four (4) tangent structures with anchor bolted foundations. | 2019-05-07 | 2020-06-19 | 2020-06-19 |  | 2368188 |  |  | 100 | 138 | na | 0.8 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 0.8 | na | na | 25.101(c)(5)(A)
0PT40082 | Bulldog - Coyote 138 kV Line: CMPC Pole Raise/Replace | City of Big Spring, Howard County | Replace 2 poles to meet clearance on Bulldog-Coyote 138kV Line | 2020-03-16 | 2020-04-09 | 2020-04-09 |  | 350000 |  |  | 100 | 138 | na | 0.1 | 795 ACSR | Concrete Monopole | 70 | 0.1 | na | na | 25.101(c)(5)(B) | Legacy Sharyland Project
0PT39270 | China Lake Sub - Sandstone SW (TNMP) 138 kV Line: Establishing China Lake Sub | Ward County | Line work associated with establish China Lake Substation | 2020-04-08 | 2020-06-23 | 2020-06-23 |  | 1200000 |  |  | 100 | 138 | na | 0.3 | 959.6 kcmil ACSS/TW Suwannee | Steel Monopoles | na | na | 100 | 0.3 | 25.101(c)(5)(A)
0PT40957 | Norwood - E Levee 138 kV Line: Harry Hines Sub Cut In | City of Dallas, Dallas County | This project is associated with establishing Harry Hines Substation by connecting the Norwood - East Levee 138 kV Line. | 2020-09-16 | 2020-12-31 |  |  | 1329601 |  |  | 0 | 138 | na | 0.25 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 50 | 0.25 | 100 | 0.2 | 25.101(c)(5)(A)
0PT39986 | Spraberry Switch - Odessa EHV Switch 138 kV Line : Camp Pasture (Concho Parks) POD | Ector County | The scope of this project is to build a POD to COG Operating LLC's Concho Parks Substation on the Spraberry Switch - Odessa EHV Switch 138 kV Line. | 2020-02-17 | 2020-03-01 | 2020-03-01 |  | 1280536 |  |  | 100 | 138 | na | 0.2 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT40413 | Carrollton East – Renner/Northaven 138kV Line: Rebuild Carrollton East – Farmers Branch Gillis | City of Farmers Branch, Dallas County | Rebuild the 2.9 mile section of the Carrollton East - Renner Sw/Northaven Sw 138 kV Line from Carrollton East – Farmers Branch Gillis using conductor greater than 1928A. | 2020-03-29 | 2020-12-15 |  |  | 11739544 |  |  | 22 | 138 | na | 2.9 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 100 | 2.9 | na | na | 25.101(c)(5)(B)
0PT40246 | Eagle Mountain Switch - Weatherford Switch 138 kV Line : Reconfigure Azle Sub Termination Point | City of Fort Worth, Tarrant County | Reterminate the Eagle Mountain - Weatherford Switch 138 kV line at its new terminal location at Azle sub | 2020-04-09 | 2020-06-20 | 2020-06-20 |  | 805440.55 |  |  | 100 | 138 | na | 0.05 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 150 | 0.15 | na | na | 25.101(c)(5)(A)
0PT39965 | Corsicana Sub - Hillsboro Sub 69 kV Line : CMPC Line Hardening (Str. 3/13 & 3/14) | City of Hillsboro, Hill County | Relocate and replace 2 structures across I-35 for CMPC System Hardening | 2020-05-18 | 2020-06-01 | 2020-06-01 |  | 450000 |  |  | 100 | 69 | na | 0.05 | 3/0 ACSR Pigeon | Steel Poles | 50 | 0.15 | na | na | 25.101(c)(5)(B)
0PT40209 | Sherry Switch - Fish Creek Switch 138 kV Line: Lakecrest Sub Cut-In | City of Grand Prairie, Dallas County | Line work associated to connecting the Lakecrest 138 kV Substation adjacent to the Fish Creek 138/69 kV Switch. | 2020-09-21 | 2020-12-01 |  |  | 650000 |  |  | 10 | 138 | na | 0.2 | 2 - 959.6 kcmil ACSS/TW/HS Suwannee | Steel Poles | 150 | 0.2 | na | na | 25.101(c)(5)(A)
17T62174 | Hilltop-White Settlement 69 kV Line: Sylvan 69 kV POI (BEC) | City of Weatherford, Parker County | Install a 69 kV POI for the Sylvan (BEC) Substation located in the Hilltop – White Settlement 69 kV Line. | 2020-04-20 | 2020-06-01 | 2020-06-01 |  | 1200000 |  |  | 100 | 69 | na | 1.29 | 2 - 4/0 ACSR Penguin | Steel and Concrete Poles | 175 | 1.29 | na | na | 25.101(c)(5)(A)
0PT39822 0PT39909 0PT39910 | Chisholm Grid - Hicks Switch 138 kV Line: Provide a 138 kV POI for Chisholm Grid LLC Merchant Plant (MP) | City of Fort Worth, Tarrant County | Provide a 138 kV Interconnection for Chisholm Grid LLC Merchant Plant (MP). | 2020-02-18 | 2020-09-01 |  |  | 910100 |  |  | 99 | 138 | na | 0.2 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Poles | na | na | 70 | 0.2 | 25.101(c)(5)(A)
0PT41139 | Crown Rd - Las Colinas 138 kV Line: CMPC Erosion Control | City of Dallas, Dallas County | This is an erosion control project that will mitigate the damage caused to Las Colinas Sub and structure 2/3 by a catastrophic slope failure. The project will entail installing a seacant pile wall to prevent future movement of the soil and re-grading to control the surface erosion. | 2020-07-24 | 2020-09-25 |  |  | 2078756 |  |  | 25 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
18T64121 | Athens Switch - Tyler West 69 kV Line: Retermination at Tyler Switch | City of Tyler, Smith County | Reterminate the Athens Switch - Tyler West 69 kV Line into Tyler Switch utilizing one new single circuit three pole structure. Also construct a bypass around Tyler Switch in order to construct the new Tyler Switch. | 2020-02-21 | 2020-12-15 |  |  | 852000 |  |  | 34 | 69 | na | 0.1 | 4/0 ACSR and 2/0 ACSR Penguin | Steel Monopoles | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT40117 | Odessa EHV Switch - Wolf Switch 138 kV Line : Rebuild Section | City of Monahans, Ward County | Rebuild a 2.3 mile section of the Odessa EHV - Monahans - Wolf Switch 138 kV Line to accommodate the Odessa EHV/Moss-Wolf section of the Odessa EHV/Moss - Riverton 345 kV Line. | 2020-03-09 | 2020-07-23 | 2020-07-23 |  | 2000000 |  |  | 100 | 138 | na | 2.3 | 2 - 1926.9 kcmil ACSS/TW/HS Cumberland | Steel Poles | 75 | 2.3 | na | na | 25.101(c)(5)(B)
0PT39784 | W. Plano Sub - Allen Switch 138 kV Line : Line Relocation | City of Plano, Collin County | Reroute a 0.55 mile portion of the W. Plano Sub – Allen Switch 138 kV line. | 2020-03-16 | 2020-12-15 |  |  | 1857561 |  |  | 17 | 138 | na | 0.55 | 1926.9 kcmil ACSS/TW/HS Cumberland | Steel Monopoles | 100 | 0.55 | na | na | 25.101(c)(5)(D)
18T64118 | Tyler - Swan #1 69 kV Line: Upgrade Black Fork Switch - Tyler Sub Section to 138 kV | City of Tyler, Smith County | Convert the Black Fork Switch – Tyler Sub Section from 69 kV to 138 kV by utilizing four single circuit steel monopole structures | 2020-03-14 | 2020-05-21 | 2020-05-21 |  | 1400000 |  |  | 100 | 69 | 138 | 0.3 | 2 - 795 kcmil ACSR Drake | Steel Monopoles | 100 | 0.3 | na | na | 25.101(c)(5)(B)
0PT39398 | Leon Switch - Dublin Switch 69 kV Line : Magellan Pod | Comanche County | Line work to establish Magellan POD | 2020-04-10 | 2020-05-18 | 2020-05-18 |  | 210000 |  |  | 100 | 69 | na | 0.1 | 1/0 ACSR Raven | Steel Poles/ H-frame Switch | 75 | 4 | na | na | 25.101(c)(5)(A)
0PT40534 | Morgan Creek Switch - Cosden Sub 138 kV Line : Line Work To Establish Brelyn Sub | City of Cahoma, Howard County | Cut in to existing Morgan Creek - Cosden 138kV Line in order to establish new Brelyn Substation | 2020-03-18 | 2020-04-16 | 2020-04-16 |  | 481000 |  |  | 100 | 138 | na | 0.1 | 959 kcmil ACSS Suwannee | Concrete H-Frame | 100 | na | na | na | 25.101(c)(5)(A)
0PT40552 | Taylor Sub - Hutto Switch 138 kV Line : Relocation At Request Of City Of Hutto | City of Hutto, Williamson County | Relocate structures to accommodate future land development for the City of Hutto | 2020-09-28 | 2020-12-15 |  |  | 2020834 |  |  | 0 | 138 | na | 0.8 | 1926.9 kcmil ACSS Cumberland | Steel Monopole | 100 | na | 80 | na | 25.101(c)(5)(F)
0PT40715 | Austin Ranch Sub - Josey Sub (BEPC): Construct Line | City of The Colony, Denton County | Construct a 138 kV line from Austin Ranch Substation to establish Josey Substation | 2021-04-12 | 2021-06-01 | [5 empty] | 0 | 138 | na | 0.1 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Dead ends | na | na | 100 | 0.1 | 25.101(c)(5)(A)
0PT40707 | Yucca Drive Switch - Wink Sub 69 kV Line : Dooley Sub Cut-in | City of Monahans, Ward County | Cut-in the Yucca Drive Switch - Wink Sub 69 kV Line to establish the new Dooley Substation | 2020-04-20 | 2020-06-30 | 2020-06-30 |  | 191378 |  |  | 100 | 69 | na | 0.4 | BUNDLED (2X) 4/0 Penguin | Wood H-Frames | 50 | 0.4 | 50 | 0.4 | 25.101(c)(5)(A)
0PT41116 0PT04037 0PT41115 0PT41143 0PT41149 | Hood - DeCordova 138 kV Line | City of Granbury, Hood County | Reterminate the existing Hood - DeCordova, Benbrook - DeCordova, Everman - DeCordova, Cleburne - DeCordova, Comanche Peak - DeCordova from the existing DeCordova Sw. Sta. to the new Carmichael Bend Sw. Sta. | 2020-03-22 | 2020-12-31 |  |  | 5184792 |  |  | 20 | 138/345 | na | 2.5 | 959.6 kcmil ACSS/TW Suwannee & 1926.9 ACSS/TW Cumberland | Steel Towers and Poles | 600 | 3.5 | na | na | 25.101(c)(5)(A)
0PT41151 0PT41155 0PT41144 | Carmichael - DeCordova 138 kV Line | City of Granbury, Hood County | Connect the new Carmichael Bend Sw. Sta. to the DeCordova Sw. Station and reterminate the Mitchell Bend - DeCordova line from the existing DeCordova Sw. Sta. to the new Carmichael Bend Sw. Sta. | 2020-09-14 | 2020-12-31 |  |  | 3515606 |  |  | 0 | 345 | 138 | 2.5 | 1590 kcmil ACSR 54/19 Falcon 959.6 kcmil ACSS/TW Suwannee | Steel Towers and Poles | 600 | 2.5 | na | na | 25.101(c)(5)(A)
0PT41215 | Screwbean Tap - Screwbean Sub 138 kV Line: Rebuild 1/1 to 1/5 | Culberson County | Rebuild a portion of the Screwbean Tap - Screwbean Sub 138 kV line | 2020-10-26 | 2020-12-15 |  |  | 1234000 |  |  | 0 | 138 | na | 0.8 | 1926.9 kcmil ACSS/TW/HS Cumberland | Steel Poles | na | na | 150/ 100 | 0.8 | 25.101(c)(5)(B)
0PT41240 | Whinstone Sub - Sandow Switch 138 kV Line: Install Whinstone POD | City of Rockdale, Milam County | This project is associated with establishing new POD from Sandow Switch to Whinstone US, Inc. | 2020-02-18 | 2020-04-08 | 2020-04-08 |  | 460000 |  |  | 100 | 138 | na | 0.08 | (2) 959 ACSS/TW Suwannee | Steel Poles | 100 | 0.08 | na | na | 25.101(c)(5)(A)
0PT39419 | Valley Switch – Commerce Switch 138 kV Line: Connect Gober 138 kV Switch | Wolfe City, Fannin County | Connect the Gober 138 kV Switch to the Bonham – Wolf City 138 kV line section of the Valley Switch – Commerce Switch 138 kV Line approximately 3.5 circuit miles from Wolfe City to establish a 138 kV point-of-interconnection (POI) for Coniglio Solar Generator. | 2020-10-12 | 2020-12-17 | [5 empty] | 0 | 138 | na | 0.1 | 795 MCM ACSR | Steel poles | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT39806 | Stone Creek Switch - Denison Tap 138 kV Line: CMPC Line Hardening (Str 11/11 & 11/12) | City of Denison Grayson County | Replace Structures 11/11 and 11/12 adjacent to US-75 in Denison, TX with concrete monopole structures | 2020-04-16 | 2020-05-04 | 2020-05-04 |  | 504900 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR Drake | Concrete Monopole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT39807 | Stone Creek Switch - Denison Tap 138 kV Line: CMPC Line Hardening (Str 17/4 & 17/5) | City of Denison Grayson County | Replace Structures 17/4 and 17/5 adjacent to US-75 in Denison, TX with steel H-Frame structures | 2020-04-07 | 2020-05-04 | 2020-05-04 |  | 639755 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR Drake | Steel H- Frame | 70 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41178 | Barber Lake Switch - Morgan Creek Switch 138 kV Line: CMPC Line Hardening Str. 5/1 & 5/2 (West Circuit) | Mitchell County | Replace wood H Frame structures 5/1 and 5/2 on the West circuit of the Barber Lake Switch - Morgan Creek Switch 138 kV Line crossing the Union Pacific Railroad west of Colorado City, TX with concrete H Frame structures. | 2020-04-27 | 2020-05-08 | 2020-05-08 |  | 307607 |  |  | 100 | 138 | na | 0.1 | 636 ACSR Grosbeak | Concrete H- Frame | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41180 | Barber Lake Switch - Morgan Creek Switch 138 kV Line: CMPC Line Hardening Str. 5/1 & 5/2 (East Circuit) | Mitchell County | Replace wood H Frame structures 5/1 and 5/2 on the East circuit of the Barber Lake Switch - Morgan Creek Switch 138 kV Line crossing the Union Pacific Railroad west of Colorado City, TX with concrete H Frame structures. | 2020-04-24 | 2020-05-04 | 2020-05-04 |  | 304905 |  |  | 100 | 138 | na | 0.1 | 636 ACSR Grosbeak | Concrete H- Frame | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41198 | Stanton East Switch - Big Spring Switch 138 kV Line: Cut in Beals Creek Sub | Howard County | Cut in the Stanton East - Big Spring 138 kV line to establish the new Beals Creek Sub | 2020-04-19 | 2020-05-04 | 2020-05-04 |  | 214764 |  |  | 100 | 138 | na | 0.2 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Monopole | 50 | 0.2 | na | na | 25.101(c)(5)(A)
0PT38203 | Shipwreck Sub - Midkiff Sw 138 kV Rebuild | Reagan County Upton County | Rebuild the 69 kV transmission line from Shipwreck Sub to Midkiff SW as a double circuit 138 kV transmission line on steel structures. | 2020-05-29 | 2020-12-25 |  |  | 13605088 |  |  | 60 | 69 | 138 | 20.6 | 959.6 kcmil ACSS Suwannee | Steel Monopoles | 50 | 10.3 | na | na | 25.101(c)(5)(B)
0PT03963 | Canton Switch - Elkton Switch 138 kV: Retermination at Tyler Switch | City of Tyler, Smith County | Connect the new Tyler Switch station to the 138 kV Elkton Switch and Canton Switch stations. | 2020-10-05 | 2020-12-15 | [5 empty] | 0 | 138 | na | 0.1 | 795 kcmil 26/7 ACSR Drake | Steel Poles | 100 | na | na | na | 25.101(c)(5)(A)
0PT41322 | Tyler - Tyler West 138 kV: Retermination at Substations | City of Tyler, Smith County | Connect the new Tyler 138 kV substation to the Tyler West Substation. | 2020-09-14 | 2020-10-30 |  |  | 980278 |  |  | 0 | 69 | 138 | 0.25 | 795 kcmil 26/7 ACSR Drake | Steel Poles | varies | na | na | na | 25.101(c)(5)(A)
0PT39802 | Denison Dam Tap - Valley Switch 138 kV Line: CMPC Line Hardening | City of Denison, Grayson County | Relocate and replace 3 structures across US-75 for CMPC System Hardening | 2020-03-05 | 2020-04-20 | 2020-04-20 |  | 576138 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR Drake | Concrete & Wood H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT39805 | Stone Creek Switch - Denison Tap 138 kV Line: CMPC Line Hardening | City of Sherman, Grayson County | Relocate and replace 2 structures across US-75 for CMPC System Hardening | 2020-03-26 | 2020-04-20 | 2020-04-20 |  | 616768 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR Drake | Concrete H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41092 | Corn Trail Switch - Brown Switch 345 kV Line: CMPC Insulator Replacement | Comanche/ Comanche County | Replace insulators on the Corn Trail - Brown 345 kV Line. | 2020-03-25 | 2020-12-31 |  |  | 2635498 |  |  | 68 | 345 | 345 | 45.1 | 2 - 1590 kcmil ACSR Falcon | Steel Lattice Towers | 160 | 45.1 | na | na | 25.101(c)(5)(B)
0PT41134 | DART Cotton Belt Relocation Northaven Sw. Sta.-Renner Sw. Sta. 138kV Line | City of Addison, Dallas County | Relocation with new double circuit, steel monopole dead end and tangent structures. | 2021-02-01 | 2021-03-31 | [5 empty] | 0 | 138 | na | 1.0833 | 1926 ACSS/TW Cumberland (Non-Bundled) | Steel Monopole Structures | varies | 0.54167 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Dallas Area Rapid Transit (DART) and is 100% reimbursable by the Dallas Area Rapid Transit (DART).
0PT41225 | TxDOT NTE 3C Relocation I-35 Crossing Eagle Mtn-Roanoke 345kV (Alliance Substation Tap) Line | City of Keller, Tarrant County | Relocation with new double circuit, steel lattice tangent structures. | 2020-03-23 | 2020-04-28 | 2020-04-28 |  | 516263 |  |  | 100 | 345 | na | 1.0227 | 1590 ACSR Falcon (Bundled) | Steel Lattice Structures | 150 | 0.51136 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41470 | TxDOT US 59 Nacogdoches Relocation Nacogdoches-Loop South Section 138kV Line | City of Nacogdoches, Nacogdoches County | Relocation with new single circuit, concrete H-frame tangent structures. | 2020-03-09 | 2020-04-28 | 2020-04-28 |  | 656236 |  |  | 100 | 138 | na | 0.33049 | 336 ACSR Linnet (Bundled) | Concrete H-frame Structures | 100 | 0.33049 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT40515 | Gainesville North Switch - Spring 138 kV Line : System Hardening (str. 41/9 & 42/1) | City of Gainesville, Cooke County | Replace Structures 41/9 & 42/1 adjacent to I-35 in Gainesville, TX consisting of existing single-circuit wooden H-frames with concrete H-frames. | 2021-05-01 | 2021-06-30 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR | Concrete H-Frame | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38167 | Plano West Sub-Richardson East Sub 138 kV Line: Retermination line at Plano Switch | City of Richardson, Collin County | Retermination Line work on the Plano West Sub - Richardson East Sub 138 kV line. | 2020-03-26 | 2020-12-15 |  |  | 455000 |  |  | 99 | 138 | na | 0.25 | 2-959.6 kcmil ACSS/TW | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A) | This is a 100% reimbursable project by Texas Instruments
0PT41602 | Allen Switch- Plano West Switch 138 kV Line: Establish POD | City of Richardson, Collin County | Retermination Line work on the Allen Switch - Plano West Switch 138 kV line. | 2020-03-26 | 2020-12-15 |  |  | 556000 |  |  | 99 | 138 | na | 0.25 | 2-959.6 kcmil ACSS/TW | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A) | This is a 100% reimbursable project by Texas Instruments
0PT40559 | Wink Switch – Culberson Switch 138 kV Line: Cut In Willow Wells Substation | City of Odessa, Winkler County | Establish the new Willow Wells Substation as a Point of Delivery for Oasis petroleum out of the Willow Wells substation. | 2020-04-20 | 2020-05-15 | 2020-05-15 |  | 1150000 |  |  | 100 | 138 | na | 0.1 | 1926 ACSS/TW Cumberland (Non-Bundled) | Steel Monopole Structures | 50 | 0.1 | na | na | 25.101(c)(5)(A) | The new transmission line is going to reside on Oncor fee owned property.
0PT40577 | Stone Creek Switch - Gainesville Sub 69 kV Line : Camp Howze Tap MCPc Line Hardening (str. 4/6 & 4/7) | City of Gainesville, Cooke County | Replace Structures 4/6 & 4/7 adjacent to I-35 in Gainesville, TX consisting of existing single-circuit wooden H-frames with concrete H-frames. | 2020-10-01 | 2021-06-30 | [5 empty] | 0 | 69 | na | 0.3 | 1/0 ACSR | Concrete H-Frame | 147 | 0.3 | na | na | 25.101(c)(5)(B)
0PT40814 0PT40883 | Saint Lawrence - East Stiles 138 kV Line: Blissard Retermination | Glasscock County | Reterminate the Saint Lawrence - East Stiles 138 kV line at a new terminal location in Blissard Sub. The new Blissard Sub will be located immediately east of the existing Saint Lawrence Sub. | 2020-04-06 | 2020-05-15 | 2020-05-15 |  | 380000 |  |  | 100 | 138 | 138 | 0.1 | 1926.9 ACSS/TW | Steel Poles | 90 | 0.1 | 90 | 0.07 | 25.101(c)(5)(A)
0PT41233 | Roanoke Switch - Euless 138 kV Line: OPGW Replacement | City of Grapevine, Tarrant County | Replace the existing shield wire on the 7/8 - Grapevine Ball Street section (1.8 miles) of the Roanoke Switch - Euless 138 kV Line with 0.546” OD 48 count OPGW. Additionally, Grapevine Junction will be reconfigured by re-terminating the conductor from structure 15/10W to 15/10E. | 2020-09-16 | 2020-10-15 |  |  | 495463 |  |  | 0 | 138 | 138 | 1.8 | 1926.9 ACSS/TW | Steel Poles | Varies | 1.8 | na | na | 25.101(c)(5)(A)
0PT41264 | Canton Switch - Elkton Switch 138 kV Line : Replace Str's 36/8 & 36/8a | Van Zandt County | Replace existing wood 4-Poles with new wood 3-Poles for structures 36/8A and 36/8. Replace Floating Deadends and Jumpers to Wave Trap. | 2020-04-22 | 2020-05-01 | 2020-05-01 |  | 155000 |  |  | 100 | 138 | 138 | 0.1 | 636 ACSR | Wood Poles | 100 | 0.1 | na | na | 25.101(c)(5)(B)
17T65200 | West Levee - Norwood 345 kV: Install OPGW | City of Dallas, Dallas County | Replace 3/8" shield wire with OPGW to the West Levee - Norwood 345 kV 0.1 miles 2 spans | 2020-05-02 | 2020-12-15 |  |  | 105489 |  |  | 99 | 345 | 345 | 0.1 | OPGW | Steel Poles | 150 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41453 | Sandow SES (Tie #3) - Sandow Switch 138kV Line: Relocate Sandow Sw Terminal | City of Rockdale, Milam County | Relocation of Sandow Switching Station - Alcoa Switching Station 138 kV Line #3 to the position in Sandow Switching Station served by 138 kV breakers No. 9300 and 9305 to establish POD. | 2020-03-19 | 2020-04-08 | 2020-04-08 |  | 360000 |  |  | 100 | 138 | na | 0.1 | 2-959 ACSS/TW Suwannee | Steel Poles | 100 | 0.1 | 100 | 0.1 | 25.101(c)(5)(A)
0PT37449 | Cedar Hill Sw - Sorcey Road Sub - Cedar Hill Sub 138kV Line Rebuild (Phase 1) | City of Cedar Hill, Dallas County | Upgrade the 2.6-mile Sorcey Road Sub to Cedar Hill Sw 138 kV line. | 2020-11-30 | 2021-05-15 | [5 empty] | 0 | 138 | na | 2.6 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 250 | 2.6 | na | na | 25.101(c)(5)(B)
0PT03990 | Cedar Hill Sw - Sorcey Road Sub - Cedar Hill Sub 138kV Line Rebuild (Phase 2) | City of Cedar Hill, Dallas County | Upgrade the 1.7-mile Cedar Hill Sub to Sorcey Road Sub 138 kV line. | 2021-09-15 | 2021-12-15 | [5 empty] | 0 | 138 | na | 1.7 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 250 | 1.7 | na | na | 25.101(c)(5)(B)
0PT03996 | Cedar Hill Sw - Sorcey Road Sub - Cedar Hill Sub 138kV Line Rebuild (Phase 3) | City of Cedar Hill, Dallas County | Upgrade the 0.8-mile Duncanville South Loop 138 kV line. | 2021-09-13 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.8 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 75 | 0.8 | na | na | 25.101(c)(5)(B)
0PT41582 | Krum West Switch - Anna Switch 345 kV Line: Connect Cedar Elm 345 kV Switch | City of Era, Cook County | Line work associated with connecting the 345 kV Cedar Elm Switch | 2020-10-12 | 2020-11-12 | [5 empty] | 0 | 345 | na | 0.2 | 2-1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 100 | 0.1 | 100 | 0.1 | 25.101(c)(5)(A)
0PT39030 | Temple Elm Creek Sub - Belton Sub 138 kV Line : Relocation for BNSF | City of Tyler, Bell County | Relocation of structure 33/16 on the North Temple - Belton 138 kV Line for BNSF Railway to accommodate railroad modifications. The existing structure is a 150' DCSP tangent. | 2020-08-31 | 2020-11-01 |  |  | 600000 |  |  | 0 | 138 | na | 0.01 | 2- 1590 ACSR Falcon | Steel Monopoles | 100 | 0.01 | na | na | 25.101(c)(5)(E)
0PT41445 | Eagle Mountain Switch - Weatherford Switch 138 kV Line: Raise Structure 61/8 | Azle, Parker County | Raise and replace structure 61/8 with a taller wood H-Frame to accommodate BEPC's new distribution bay. | 2020-03-30 | 2020-04-01 | 2020-04-01 | 100 | 36323 |  |  | 100 | 138 | 138 | 1.2 | 636 ACSR | Wood H-Frame | 50 | 1.2 | na | na | 25.101(c)(5)(B)
0PT40459 | Riverton Switch - Tunstill POD 138 kV Line: Install Roadrunner POD for BP's Aspen | Reeves County | Establish the point of delivery to BPX Energy’s Aspen substation on the Riverton Switch – Tunstill POD 138 kV transmission line. | 2020-08-17 | 2020-11-15 |  |  | 1900000 |  |  | 36 | 138 | na | 0.19 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Poles & H-Frame Switch | 70 | na | 70 | 0.19 | 25.101(c)(5)(A)
0PT39453 | Midessa South Switch - Midland Airport Sub 138 kV Line: Install Nobles POD for Diamondback's Spanish Trails Sub | , Midland County | Establish the point of delivery to Diamondback’s Spanish Trails substation on the Midessa South Switch – Midland Airport 138 kV transmission line. | 2020-09-21 | 2020-11-15 |  |  | 505000 |  |  | 0 | 138 | na | na | 1590 kcmil ACSR Falcon | Steel Poles & H-Frame Switch | 75 | na | na | na | 25.101(c)(5)(A)
0PT39979 0PT41106 | SL Brown - Grady 138 kV Line: Oceanic POD for Endeavor's Olympus Sub | Martin County | Establish the point of delivery to Endeavor Energy’s Olympus substation on the Brown - Grady 138 kV transmission line. | 2020-08-31 | 2020-10-31 |  |  | 2053000 |  |  | 0 | 138 | na | 0.22 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles & H-Frame Switch | 70 | na | 100 | 0.22 | 25.101(c)(5)(A)
0PT40386 | SL Brown - Grady 138 kV Line : Install Red Salt POD For Diamondback Cobra | Martin County | Establish the point of delivery to Diamondback’s Cobra substation on the Brown - Grady 138 kV transmission line. | 2020-09-07 | 2020-11-15 |  |  | 2545000 |  |  | 0 | 138 | na | 0.38 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles & H-Frame Switch | 70 | na | 100 | 0.38 | 25.101(c)(5)(A)
0PT39402 | Spraberry Switch - Midland East Sub 138 kV Line: Fairgrounds POD for Centurion's Midland Tank Farm | Midland County | Establish a point of delivery to Centurion Pipeline, LLC on the Spraberry - Midland East 138 kV line. | 2020-09-08 | 2020-11-15 |  |  | 1733385 |  |  | 0 | 138 | na | 0.15 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles & H-Frame Switch | 50 | na | 100 | 0.15 | 25.101(c)(5)(A)
0PT39833 | LCRA Crane – Crane East 138 kV Line : Manning (Hazel) POD for Concho Chickadee Neal via LCRA Motorman Switch | Upton County | Establish the point of delivery from LCRA’s Motorman Switch to Concho’s Chickadee Neal on the Crane – Crane East 138 kV (LCRA) transmission line. | 2020-11-02 | 2020-12-31 | [5 empty] | 0 | 138 | na | 0.11 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles & H-Frame Switch | na | na | 100 | 0.11 | 25.101(c)(5)(A)
18T64017 | Salado - Round Rock 138 kV Line: cut-in to establish Salado South Substation | Bell County | This project will cover the cost to cut-in the Salado - Round Rock 138 kV line to establish the new Salado South Substation. | 2020-09-08 | 2020-12-01 |  |  | 949748 |  |  | 0 | 69/138 | 138 | 0.2 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 100 | 0.2 | na | na | 25.101(c)(5)(A)
18T64094 | Jewett Switch - Crockett 138 kV Line: Rebuild Jewett Switch to Centerville Sub | City of Jewett Vicinity, Jewett County | Rebuild the 7.2 mile section from Jewett Switch to Centerville Substation of the Jewett - Crockett 138 kV Line, using double-circuit structures with one circuit in place. | 2020-06-08 | 2020-12-31 |  |  | 15383867 |  |  | 31 | 138 | 138 | 7.2 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 7.2 | na | na | 25.101(c)(5)(B)
0PT39859 | Hillsboro Sub - Elm Mott Sub 69 kV Line : Tower Replacement | Hill County | Replace damaged tower 107 on the Hillsboro - Elm Mott 69 kV line. | 2020-04-28 | 2020-06-01 | 2020-06-01 |  | 119314 |  |  | 100 | 69 | 69 | 0.1 | 1/0 MCM Cu | Steel Lattice Tower | 70 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42028 | Stryker Creek Switch - Tyler Grande Switch 138 kV Line: Structure 4/6 to 4/8 Insulator Failure | City of Tyler, Cherokee County | Replaced damaged insulators due to storm damage | 2020-03-04 | 2020-03-06 | 2020-03-06 |  | 430000 |  |  | 100 | 138 | 138 | 0.2 | 1233.6 kcmil ACSS/TW Yukon | Concrete Poles | 100 | 0.2 | na | na | 25.101(c)(3) | Emergency Storm Restoration
0PT41539 | Owl Hills Sub - Tunstill POD 138 kV Line : Install Second Circuit | Culberson and Reeves Counties | Install second circuit to the Owl Hills - Tunstill POD 138 kV Line. | 2021-03-01 | 2021-05-15 | [5 empty] | 0 | 138 | na | 18.5 | 1926.9 kcmil ACSS/TW | Steel Poles | 70 | 18.5 | na | na | 25.101(c)(5)(C) | Second circuit to the 48582 Owl Hills - Tunstill POD 138 kV Line CCN.
0PT41577 | Saginaw Switch - Roanoke Switch 138 kV Line : Tower Replacement | Haltom City, Tarrant County | Damaged leg extension on structure 03/04 on the Saginaw Switch - Roanoke Switch 138 kV line. The scope entails replacing the existing structure with a double circuit concrete tangent pole. | 2020-11-01 | 2020-12-31 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Concrete Pole | 125 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38110 | Everman Switch - Venus Switch 345 kV Line : Reterminate at Timberview Switch | City of Everman, Tarrant County | Reterminate the Everman Switch - Venus Switch 345 kV Line from Everman Switch to new Timberview Switch. | 2021-01-01 | 2021-05-15 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38112 | Benbrook Switch - Everman Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Reterminate the Benbrook Switch - Everman Switch 345 kV Line from the Everman Switch to new Timberview Switch. | 2021-01-01 | 2021-05-15 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38113 | Everman Switch - Cedar Hill Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Reterminate the Everman Switch - Cedar Hill Switch 345 kV Line from the Everman Switch to new Timberview Switch | 2021-01-01 | 2021-05-15 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38114 | Everman Switch - DeCordova Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Retermination the Everman Switch - DeCordova Switch 345 kV Line from Everman Switch to new Timberview Switch | 2021-01-01 | 2021-05-15 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT41761 | Navarro Switch - Watermill Switch 345 kV Line : Line modification to connect Elrod Switch | City of Corsicana, Navarro County | Line work associated with connecting the 345 kV Elrod Switch | 2021-01-04 | 2021-04-21 | [5 empty] | 0 | 345 | na | 0.1 | 2-1590 kcmil ACSR Falcon | Steel Tower | 160 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41810 | Allen Sw - Monticello Sw 345kV Line: Stouts Creek Cut In | City of Sulphur Springs, Hopkins County | Line work associated with connecting the 345 kV Stouts Creek Switch | 2021-09-21 | 2021-11-01 | [6 empty] | 345 | na | 35 | 2-795 kcmil ACSR Drake | Steel Tower | 170 | 35 | na | na | 25.101(c)(5)(A)
0PT42027 | Jewett Switch - Big Brown Switch 345 kV Line : Structure 28/4 Insulator Failure | City of Palestine, Freestone County | This Work Authorization is for the material and labor associated with replacing damaged insulator at Structure 28/4 due to storm damage on the Jewett Switch - Big Brown Switch 345 kV Line. | 2020-03-04 | 2020-03-13 | 2020-03-13 |  | 459000 |  |  | 100 | 345 | 345 | 32.91 | 795 ACSR "Drake" | Steel Lattice | 160 | 32.91 | na | na | 25.101(c)(3) | Emergency Storm Restoration
17T65237 | Simpson Stuart - Camp Wisdom 138 kV Line: Rebuild | City of Dallas, Dallas County | Upgrade the 3.7 mile Simpson Stuart - Camp Wisdom Road 138 kV Line section of the Cedar Hill - Watermill 138 kV Line. | 2020-11-09 | 2021-05-15 | [5 empty] | 0 | 138 | 138 | 3.7 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 3.7 | Varies | na | 25.101(c)(5)(B)
19T63004 | Ennis Creek Sw. Sta. - Bec Salt Creek Sw. Sta. 69 kV: Rebuild To 138 kV (eng) | City of Snyder, Scurry County | Rebuild the existing 9.0 mile single circuit wood pole Ennis Creek – Cogdell 69 kV line as the Ennis Creek – Rough Creek 138 kV Line utilizing 138 kV double circuit steel poles with one circuit in place. | 2020-08-31 | 2020-12-18 |  |  | 11387254 |  |  | 0 | 69 | 138 | 9 | 959.6 kcmil ACSS/TW | Steel Poles | 50 | 9 | 70 | 0.8 | 25.101(c)(5)(B)
0PT42274 0PT42275 | Wolf - Aroya 138kV Line: Reterminate Aroya End at Yucca to establish Wolf - Yucca #2 Circuit 138 kV Line Wink - Yucca 138kV Line: Reterminate Yucca End at Aroya Switch to establish Wink - Aroya 138 kV Line | City of Monahans, Ward County | Disconnect the existing Yucca Drive Switch – Wink Switch 138 kV Line and Aroya Switch – Wolf Switch 138 kV Lines where the two lines intersect. Connect the lines in the new configuration to create the new Yucca Drive Switch – Wolf Switch 138 kV Line. Connect the lines in the new configuration to create the new Aroya Switch – Wink Switch 138 kV Line. | 2020-04-23 | 2021-05-15 |  |  | 730000 |  |  | 85 | 138 | na | 0.2 | 959 kcmil ACSS/TW Suwannee & 2-959 kcmil ACSS/TW Suwannee | Steel Poles & Wood Poles | 75 | 0.2 | na | na | 25.101(c)(5)(B) | This project is planned to reconfigure two existing circuits to reduce operational constraints in the area due to continued load growth. In order to complete this reconfiguration prior to the summer clearance moratorium, Oncor is unable to list this project in compliance with 16 Tex. Admin Code § 25.83(c)(1), but is instead providing 20 days’ pre-construction notice with today’s filing.
0PT37565 | Horseshoe Springs Switch - Owl Hills Sub 138 kV Line : Chimney Well POD | Culberson County | Build a Point of Delivery (POD) to Chevron USA Inc.'s Chimney Well POD on the new Horseshoe Springs Switch - Owl Hills Sub 138 kV Line. | 2019-06-01 | 2019-12-31 | 2019-12-31 |  | 952291 |  |  | 100 | na | 138 | 0.1 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | 90 | 0.1 | 25.101(c)(5)(A) | This was added to CCN section inadvertently and should have been in the exempt section.
0PT04031 | Dermott Switch - Golden Switch 138 kV Line: Ennis Creek Switch Station Retermination | City of Snyder, Scurry County | This project is to reterminate the Dermott Switch - Golden Switch 138 kV Line at its new terminal following the rebuild of the Ennis Creek Switch Station. | 2020-09-15 | 2020-12-01 |  |  | 841896 |  |  | 0 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Steel Poles | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42070 | Odessa North - Odessa Basin Switch - Odessa Basin 69 kV Line: Retermination | Odessa County | Reterminate the Odessa North - Odessa Basin Switch - Odessa Basin 69 kV Line to aid in the demolition of Odessa Basin Switch station by installing one single-circuit steel pole. | 2020-09-21 | 2020-11-15 |  |  | 450000 |  |  | 0 | 69 | 69 | 0.1 | 959.6 kcmil ACSS/TW | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41677 | Texas Instruments Sub - Beltline Sub 138 kV Line- Structure replacement | City of Richardson, Dallas County | Replace existing tower T-448 on the Texas Instruments Sub- Beltline Sub 138kV and install a new double circuit span into the rebuilt Richardson Spring Valley Sub. | 2020-10-05 | 2020-12-31 | [5 empty] | 0 | 138 | 138 | 0.1 | 1926.9 kcmil ACSS/TW | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41191 | TxDOT I-20 at CR 1250 Relocation Midessa 138kV tap line | City of Midland, Midland County | Relocation of structure on Midessa 138 kV tap line. | 2020-09-21 | 2020-12-31 |  |  | 1087902 |  |  | 0 | 138 | na | 1.036 | 1926 ACSS Cumberland | Steel Monopole Structures | 75 | 0.51799 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41129 | 2020 CMPC Big Spring District, Morgan Creek Switch-Falcon Seaboard Sub. 345 kV Line Str. 19/5 | City of Big Spring, Howard County | Rebuild the section of the Morgan Creek-Midland East 345 kV Line that crosses South Farm to Market (FM) 821 in Howard County | 2020-10-12 | 2020-12-31 | [5 empty] | 0 | 345 | na | 0.33 | 2-795 ACSR Drake | Lattice Tower Structure | 150 | 0.33 | na | na | 25.101(c)(5)(B)
0PT41131 | 2020 CMPC Odessa District, Falcon Seaboard Sub.-Midland East Sub. 345 kV Line, Str. 68/2 | City of Midland, Midland County | Rebuild the section of the Morgan Creek-Midland East 345 kV Line that crosses N. County Rd. 1135 in Midland County | 2020-09-08 | 2020-12-31 |  |  | 675424 |  |  | 0 | 345 | na | 0.38 | 2-95 ACSR Drake | Lattice Tower Structure | 150 | 0.38 | na | na | 25.101(c)(5)(B)
0PT41118 | 2020 CMPC Sweetwater District, Morgan Creek Switch-Falcon Seaboard Sub. 345 kV Line, Str. 12/5 | City of Colorado City, Mitchell County | Rebuild the section of the Morgan Creek-Midland East 345 kV Line that crosses N. County Rd. 1135 in Midland County. | 2020-10-08 | 2020-12-31 | [5 empty] | 0 | 345 | na | 0.35 | 2-795 ACSR Drake | Lattice Tower Structure | 150 | 0.35 | na | na | 25.101(c)(5)(B)
0PT39676 | Carrollton East Switch - Northaven Switch 138 kV Line: Farmers Branch Retermination | City of Addison, Dallas County | Reterminate the existing Carrollton East Switch - Northaven Switch 138 kV Line at Farmers Branch Substation to a new structure. | 2020-09-14 | 2020-12-01 |  |  | 369671 |  |  | 0 | 138 | na | 0.1 | 795 ACSR Drake | Steel Poles | 70 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41977 | Sweetwater No.2 Sub - Colorado City Sub 69 kV Line: Line work associated with Loraine Sub Decommission | City of Loraine, Mitchell County | Line work associated with the decommission of Loraine Sub. | 2020-11-09 | 2020-12-15 | [5 empty] | 0 | 69 | na | 0.1 | 4/0 ACSR Penguin | Wood Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41189 0PT40230 | SL Clearfork Switch - Telephone Road Switch 345 kV Line: Line work to establish Gardendale 345 kV Switch NTUSU Clearfork Switch - Telephone Road Switch 345 kV Line: Retirements and Modifications Only | City of Andrews, Andrews County | Line work to cut into Clearfork Switch - Telephone Road Switch 345 kV Line to establish Gardendale 345 kV Switch. | 2020-09-21 | 2020-10-23 |  |  | 1462757 |  |  | 0 | 345 | na | 0.1 | 2-1926.9 kcmil ACSS/TW Cumberland | Steel Towers | 135 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41505 | Yucca Drive Switch - Sand Lake Switch 138 kV Line: Modify for Sand Lake - Solstice 345 kV Line | Ward County | Modifying the existing Yucca Drive Switch - Sand Lake Switch 138 kV Line by lowering it from Structure 35/3 to Structure 35/5 for new the Sand Lake - Solstice 345 kV Line to fly over the existing 138 kV line. | 2020-09-14 | 2020-10-31 |  |  | 950000 |  |  | 0 | 138 | 138 | 0.4 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Poles | 70 | 0.2 | na | na | 25.101(c)(5)(B)
0PT41108 | Eagle Mountain Ses - Wichita Falls 138 kV Line: Hb 4150 Lake Arrowhead Crossing | City of Henrietta, Clay County | Rebuild 0.1 mile section of the Eagle Mountain SES - Wichita Falls 138 kV line which crosses Lake Arrowhead. | 2020-09-21 | 2020-12-31 |  |  | 212670 |  |  | 0 | 138 | na | 0.2 | 636 km ASCR | Steel Poles | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT41701 | Eskota Switch - Morgan Creek Switch 138 kV Line : Erosion Control | City of Colorado, Mitchel County | Build a erosion control guards around tower 131/18 on the Eskota - Morgan Creek 138 kV line. A series of culverts will be installed on both sides of the tower to divert the water around the tower and protect the structure from future erosion. A retaining wall will also be installed and filled with selective backfill in the eroded area to ensure structural integrity in the soil. | 2020-11-15 | 2020-12-31 | [5 empty] | 0 | 138 | na | na | 636 ACSR Grosbeak & 795 ACSR Drake | Steel Lattice Tower | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41738 | Forest Grove Switch - Eustace SE Switch 138 kV Line : Retirement Only | Henderson County | This project is to retire 3.8 miles of the old Forest Grove Switch - Eustace SE 138 kV Line. | 2020-07-28 | 2020-08-21 | 2020-08-21 |  | 230000 |  |  | 100 | 138 | 0 | 3.8 | 1033 ACSR Curlew | Wood H-Frames | 160 | 3.8 | na | na | 25.101(c)(5)(B)
0PT41912 | Sulphur Springs Switch - Canton Switch 138 kV Line : Hb 4150 Lake Tawakoni Crossing | City of Willis Point, Hunt County | This is to rebuild a 0.1 mile section of the Sulphur Springs – Canton Switch 138 kV Line. | 2020-09-23 | 2020-12-31 |  |  | 512793 |  |  | 0 | 138 | na | 0.15 | 795 ACSR Drake | Steel Poles | 100 | 0.15 | na | na | 25.101(c)(5)(B)
0PT41983 | Double Mountain Switch - Dunbar Switch 345 kV Line : Station Tie Line Build | City of Lubbock, Lubbock County | This project includes constructing two single circuit 345 kV lines between Double Mountain Switch (Oncor owned) and Dunbar Switch (LP&L owned) to connect the two stations. Conductor will be bundled 959 ACSS/TW. | 2020-11-23 | 2021-03-14 | [5 empty] | 0 | na | 138 | 0.1 | 2-959.6 ACSS/TW | Steel Pole | na | na | na | 0.1 | 25.101(c)(5)(B) | Project to be moved under corresponding CCN project. This line item will be removed on next month's report.
17T62074 | Paris Switch-Rivercrest/Tenaska 138 kV Line (Lamar Jct-Reno Tap Section):Rebuild | City of Paris, Lamar County | Rebuild the Lamar Tap - Reno Tap line section of the Paris Switch - Rivercrest - Tenaska 138 kV Line. | 2020-10-05 | 2020-12-15 |  |  | 14100000 |  |  | 0 | 138 | na | 5.3 | 2-959.6 MCM ACSS/TW/HS Suwannee | Steel Poles | 100 | 5.3 | 100 | na | 25.101(c)(5)(B)
0PT42509 | Oakland Avenue Tap - Oakland Avenue Sub 138 kV Line : Install OPGW | City of Dallas, Dallas County | Reconductor the Oakland Avenue Tap – Oakland Avenue Substation 138 kV line section | 2020-10-12 | 2020-12-15 | [5 empty] | 0 | 138 | na | 0.64 | 927.2 MCM ACAR | Steel Towers | 100 | 0.64 | na | na | 25.101(c)(5)(B)
0PT39227 | Valley Switch - Commerce Switch 138 kV Line : Establish Copperhead Switch (Phoenix/GSE 1) | City of Bonham, Fannin County | Build 0.6 mile double-circuit tap to establish Copperhead Switch to pick-up merchant plant station, Phoenix (GSE 1). | 2020-10-05 | 2021-03-01 |  |  | 3086380 |  |  | 0 | na | 138 | 0.64 | 959.6 ACSS/TW | Steel Poles | na | na | 100 | 0.6 | 25.101(c)(5)(A)
0PT42291 | Dermott Switch - Scurry South Switch 345 kV Line: Replace Str. 7/1 | City of Snyder, Scurry County | Replace structure 7/1 on the Dermott - Scurry South 345 kV line to provide additional clearance for the Ennis Creek - Rough Creek 138 kV Line Rebuild utilizing a new 345 kV tower. | 2020-11-14 | 2020-12-31 | [5 empty] | 0 | 345 | na | 0.1 | 2-1926.9 kcmil ACSS/TW | Steel Tower | 160 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38084 | Norwood Switch - Denton Drive Switch 138 kV Line: Reconductor | City of Dallas, Dallas County | Reconductor the Norwood Switch - Denton Drive Switch 138 kV Line. | 2020-09-16 | 2021-05-15 |  |  | 2865516 |  |  | 0 | 138 | na | 3.9 | 959.6 kcmil ACSS/TW (Bundled) | Steel Poles | 100 | 3.9 | na | na | 25.101(c)(5)(B)
0PT41981 | Yucca Drive Switch - Northern Natural Gas 69 kV Line: Coyanosa Substation Retermination | City of Coyanosa, Pecos County | Reterminate the Coyanosa Station in the Yucca Drive Switch - Northern Natural Gas 69 kV Line. | 2020-10-26 | 2020-12-15 | [5 empty] | 0 | 69 | na | 0.5 | 4/0 ACSR Penguin | Steel Poles | 50-75 | 0.5 | 65-90 | 0.3 | 25.101(c)(5)(A)
0PT41002 | McDonald Road Sw. – Spraberry Sw. 138 kV Line: Thirtysix Draw POD for CrownQuest Operating Wrage Sub | City of Midland, Glasscock County | Establish the point of delivery to CrownQuest Operating’s Wrage on the McDonald Road Sw. – Spraberry Sw. 138 kV transmission line. | 2020-11-02 | 2021-03-30 | [5 empty] | 0 | 138 | na | 0.22 | 959 ACSS/TW | Steel Poles/ H-frame Switch | 50 | 0.22 | 90 | na | 25.101(c)(5)(A)
0PT39834 | Andrews North - McKenzie Draw Switch 138 kV Line: Install Dillon POD for Diamondback's Cats POD | City of Andrews, Martin County | Establish the point of delivery to Diamondback’s Cats substation on the Andrews North – McKenzie Draw 138 kV transmission line. | 2020-11-04 | 2021-03-26 | [5 empty] | 0 | 138 | na | 0.17 | 1926 ACSS/TW | Steel Poles/ H-frame Switch | 70 | na | 100 | 0.17 | 25.101(c)(5)(A)
0PT42244 | Stone Creek Switch - Anna Switch 138 kV Line: Spirit POI for Rayburn's East Fork Sub | City of Anna, Collin County | Establish the point of delivery to Rayburn Country Electric Cooperative’s East Fork substation on the Stone Creek Switch – Anna Switch 138 kV transmission line. | 2021-01-18 | 2021-05-10 | [5 empty] | 0 | 138 | na | 0.19 | 2- 959 ACSS/TW | Steel Poles/ H-frame Switch | 70 | 0.19 | 100 | na | 25.101(c)(5)(A)
18T65206 | Renner Switch- Allen Switch/Plano Tennyson Switch 138 kV Line: Rebuild STR 11/4D - Plano Tennyson | City of Plano, Collin County | Rebuild the existing Renner - Allen/Plano Tennyson 138 kV line with double circuit, bundled conductor | 2021-06-04 | 2021-12-15 | [5 empty] | 0 | 138 | na | 1.7 | 2-959.6 ACSS/TW/HS Suwannee | Steel Poles | 100 | 1.7 | na | 100 | 25.101(c)(5)(B)
0PT42436 | Tyler Northwest Switch - Tyler Northeast Sub 138 kV: Reterminate to Tyler Northwest Switch | City of Tyler, Smith County | Reterminate the existing 138 kV line from Shamburger - Black fork into the Tyler Northwest station | 2021-04-16 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 959.6 ACSS/TW/HS Suwannee | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT40854 | Tyler Switch - Elkton Switch 138kV Line Rebuild | City of Tyler, Smith County | Rebuild the 5.3 mile Tyler Switch - Elkton Switch 138kV Line, using 138kV double-circuit structures with one circuit in place using a conductor rated 2071 A or greater. | 2021-01-04 | 2021-05-15 | [5 empty] | 0 | 138 | na | 5.3 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 5.3 | na | na | 25.101(c)(5)(B)
0PT41578 | SL AEE – White River 345kV: Retermination at Blackwater Draw | City of Lubbock, Lubbock County | Reterminate the two circuits currently coming into Abernathy station into their newly constructed terminal locations at Blackwater Draw which is located on same property roughly 800' north. | 2021-01-15 | 2021-04-20 | [5 empty] | 0 | 345 | na | 1.4 | 2-959.6 ACSS/TW | Steel Poles | 100 | 0.45 | 100 | 0.95 | 25.101(c)(5)(A)
0PT42077 | Edgewood Switch - Terrell Switch 69 kV Line: HB 4150 Lake Tawakoni Crossing | City of Wills Point, Hunt County | Rebuild section of the Edgewood - Iron Bridge-Terrell Switch 69kV line which crosses Lake Tawakoni. | 2020-10-08 | 2020-12-31 | [5 empty] | 0 | 69 | na | 0.15 | 4/0 ACSR Penguin | Steel Poles | 100 | 0.15 | na | na | 25.101(c)(5)(B)
0PT39373 | Anna Switch to Anna Tap 138 kV Line: Rebuild | City of Melissa, Collin County | Rebuild the Anna Switch - Anna Tap 138-kV Line. | 2020-12-01 | 2021-05-15 | [5 empty] | 0 | 138 | na | 16.4 | 2-959.6 kcmil ACSS/TW | Steel Poles | Varies | 8.2 | na | na | 25.101(c)(5)(B)
0PT40827 | Eagle Mountain Switch - Deen Switch 138 kV Line: Rebuild Eagle Mountain Switch - Rosen Heights Tap | City of Saginaw, Tarrant County | Rebuild the Eagle Mountain Switch to Rosen Heights Tap section of the Eagle Mountain Switch - Deen Switch 138 kV line. | 2020-11-02 | 2021-05-15 | [5 empty] | 0 | 138 | na | 20 | 2-959.6 kcmil ACSS/TW | Steel Poles | Varies | 10 | na | na | 25.101(c)(5)(B)
0PT38119 | Lufkin Sw. - Herty Sw. 138 kV Line | City of Angelina, Lufkin County | Rebuild of Herty North Switch (Renamed Redland Switch) will require the retermination of the single circuit Herty North Sw. – Lufkin Sw. 138 kV line. | 2021-02-08 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.3 | 1926 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(B)
0PT41976 | Nacogdoches Southeast Switch - Herty North Switch 138 kV Line | City of Angelina, Lufkin County | Retermination of the single circuit Nacogdoches Southeast Sw. – Herty North Sw. 138 kV line. | 2021-02-06 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.3 | 1926 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT41975 | Herty North Sw. - Huntington Sw. 138 kV Line | Angelina/ Lufkin | Retermination of the double circuit Herty North Sw. – Huntington/Lufkin East 138 kV line. | 2021-02-06 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.3 | 1926 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT38602 | Morgan Creek Switch - Falcon Seaboard 345kV Line: 345kV Lattice Hardening (6/5) | Mitchell County | Rebuild a section of the Morgan Creek switch – Falcon Seaboard Switch 345 kV Line in Mitchell County. | 2020-11-02 | 2020-12-01 | [5 empty] | 0 | 345 | na | 0.1 | 2-795 ACSR Drake | Steel Tower | 100 | 1 | na | na | 25.101(c)(5)(B)
0PT42248 | Brown Switch - Killeen Switch 345 kV Line: Establish Buckhorn Switch | Mills County | Build a cut in the Brown Switch - Killeen Switch 345 kV Line to establish the new Buckhorn Switching Station. | 2020-09-28 | 2021-05-14 |  |  | 1490000 |  |  | 0 | 345 | na | 0.4 | 2 -1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole, Steel Tower | 160 | 0.2 | na | 0.2 | 25.101(c)(5)(A)
0PT42088 0PT42233 | SL South Midland Switch-Pronghorn Switch 138 kV Line: Loop in and out the Cottonfield 138 Substation | City of Midland/Midland County | Loop in and out the SL South Midland Switch - Pronghorn Switch 138 kV Line to establish the new Cottonfield 138 kV substation. | 2020-11-09 | 2020-12-15 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR/959 ACSS | Steel Poles | 70 | 0.1 | na | na | 25.101(c)(5)(A)
0PT39788 | Everman Switch-Cleburne Switch 138 kV Line: Terminate the line at the new Burleson Switch | City of Burleson/Tarrant County | Reterminate the Everman Switch-Cleburne Switch 138 kV line at Burleson Switch | 2020-11-09 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.3 | 1926 ACSS/TW | Steel Poles | 200 | 0.3 | na | na | 25.101(c)(5)(A)
0PT39797 | Marrs Switch-Bourland Sub 138 kV Line: Terminate line at the Burleson Switch | City of Burleson/Tarrant County | Reterminate the Marrs Switch-Bourland Sub 138 kV Line at Burleson Switch | 2020-11-02 | 2021-05-20 | [5 empty] | 0 | 138 | na | 0.3 | 1926 ACSS/TW | Steel Poles | 90 | 0.3 | na | na | 25.101(c)(5)(A)
0PT41854 0PT42038 | Martin Lake Switch - Stryker Creek Switch 345 kV Line: HB 4150 Martin Lake Crossing | Rusk County | Rebuild a section of the Martin Lake Switch - Stryker Creek Switch 345 kV Line that crosses Lake Martin. | 2020-10-05 | 2020-12-18 | [5 empty] | 0 | 345 | na | 0.2 | 2-1590 ACSR Falcon | Steel Lattice Tower | 300 | 0.1 | na | na | 25.101(c)(5)(B)
0PT39517 | Forney Switch - Tri-Corner Switch 345 kV Line: CMPC Erosion Control -- STR #25/1 | Seagoville City, Dallas County | Scope entails replacing tower with a double circuit steel pole and relocating structure away from the river. | 2020-10-28 | 2020-12-31 | [5 empty] | 0 | 345 | na | 0.1 | 2-795 ACSR | Steel Pole | 150 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42284 | Trinidad Switch - Hillsboro Switch 138 kV Line: HB 4150 Richland Chambers Lake Crossing | Navarro County | Rebuild a section of the Trinidad Switch - Hillsboro Switch 138 kV Line that crosses Richland Chambers Reservoir. | 2020-10-26 | 2020-12-31 | [5 empty] | 0 | 138 | na | 0.2 | 959.6 ACSS/TW | Concrete H-Frame | 175 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41920 | Long Lake Tap - Big Brown Sub 138 kV Line: HB 4150 Lake Fairfield Crossing | City of Fairfield, Freestone County | Rebuild a section of the Long Lake Tap - Big Brown Sub 138 kV Line. | 2020-10-12 | 2020-12-31 | [5 empty] | 0 | 138 | na | 0.3 | 795 ACSR Drake | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(B)
0PT42574 | China Grove Switch - Radium - Paint Creek 138 kV Line: HB 4150 Lake Stamford Crossings | City of Haskell, Haskell County | Rebuild a section of the China Grove - Radium - Paint Creek 138 kV Line. | 2021-04-01 | 2021-05-31 | [5 empty] | 0 | 138 | na | 1 | 636 ACSR Grosbeak | Steel Poles | 50 | 1 | na | na | 25.101(c)(5)(B)
0PT40858 | Jacksboro Switch - Krum West Switch 345 kV Line: Failed Dead End Replacements | City of Decatur, Wise County | Replace line dead-end terminals and insulator assemblies on the Jacksboro - Krum West 345 kV line. | 2020-10-15 | 2020-12-31 | [5 empty] | 0 | 345 | na | 0.1 | 1590 kcmil ACSR | Steel Towers | 100 | 0.1 | na | na | 25.101(c)(5)(B)
17T65032 | Royse City - Commerce 69kV Line: Scatter Branch Sub Line Work | City of Neylandville, County of Hunt | Line work associated with establishing the new Scatter Branch Substation | 2020-10-12 | 2020-12-01 | [5 empty] | 0 | 69 | na | 0.75 | 1926.9 kcmil ACSS/TW | Steel Poles | 75 | 0.75 | na | na | 25.101(c)(5)(A)
17T65244 | Renner TPL - Allen / Plano Tennyson 138 kV Line: Rebuild Renner TPL - STR 11/4D | City of Plano, Collin County | Rebuild Renner - Structure 11/4D section of the Renner TPL - Allen / Plano Tennyson 138 kV Line. | 2020-11-09 | 2021-05-15 | [5 empty] | 0 | 138 | na | 3.6 | 2-959.6 kcmil Suwannee ACSS/TW | Steel Poles | varies | 3.6 | na | na | 25.101(c)(5)(B)
0PT42555 | NTUSU AJ Swope Sub - Alibates Sub 345 kV Line : Galloping Device Installation | City of Amarillo, Potter County | Install galloping devices on several spans of the AJ Swope - Alibates 345 kV Line. | 2020-10-05 | 2020-11-15 | [5 empty] | 0 | 345 | na | 0.19 | 2-1926 ACSS/TW | Steel Towers | 175 | 0.19 | na | na | 25.83(a)(3)
0PT42557 | NTUSU Ogallala - Tule Canyon 345 kV Line: Galloping Device Installation | City of Tulia, Swisher & Carson County | Install galloping devices on several spans of the Ogallala - Tule Canyon 345 kV Line. | 2020-10-19 | 2020-11-15 | [5 empty] | 0 | 345 | na | 1.57 | 2-1926 ACSS/TW | Steel Towers | 175 | 1.57 | na | na | 25.83(a)(3)
0PT42670 | NTUSU Abernathy Switch - White River Switch 345 kV Line : Galloping Device Installation | City of Hale Center, Hale County | Install galloping devices on several spans of the Abernathy Sw - White River Sw 345 kV Line. | 2020-10-26 | 2020-11-16 | [5 empty] | 0 | 345 | na | 9.43 | 2-1926 ACSS/TW | Steel Poles, Towers | 175 | 9.43 | na | na | 25.83(a)(3)
0PT41579 | Argyle Sub - Krum Tap Switch 138 kV Line : Structure Replacement | City of Denton, Denton County | Relocate 3 H-frame structures to avoid future impact of nearby river. | 2020-10-06 | 2020-12-31 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR | Concrete and Wood H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42858 | Jewett Switch - Wortham Gulf Pump Sub 69 kV Line: Line Work due to Decommissioning of Simsboro Magnolia 69 kV Sub | City of Teague/ Freestone County | Respan from structure 27/13 to 27/14 on the Jewett Switch-Wortham Gulf Pump Sub 69 kV line | 2020-10-05 | 2020-12-15 | [5 empty] | 0 | 69 | na | 0.01 | 4/0 Penguin | Wood | 50 | 0.01 | na | na | 25.101(c)(5)(B) | Project cancelled. Project will be removed from next month's report.
0PT42686 | Royse Switch-Terrell Switch: Establish Quinlan Tap 138/69 kV Autotransformer | Royse City/Rockwall County | Rebuild a section on the Royse Switching Station - Terrell Substation 69 kV Line for the installation of the Quinlan Tap 138/69 kV Autotransformer. | 2021-02-15 | 2021-05-15 | [5 empty] | 0 | 138/69 | 138 | 0.15 | 1590 ACSR Falcon | Steel Poles, H-frame Switch | 100 | 0.15 | na | na | 25.101(c)(5)(A)
0PT42236 | Waxahachie Sub - Ennis South Sub 138 kV Line: Reterminate section from Ennis West Switch to Sterrett Switch into Ennis West Switch | City of Ennis, Ellis County | Reterminate the Waxahachie Sub - Ennis South Sub 138 kV Line section from Ennis West Switch - Sterrett Switch into its new bay position at Ennis West Switching Station. | 2021-02-15 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW | Steel Monopoles | 100 | 0.2 | na | na | 25.101(c)(5)(A)
0PT42526 | Waxahachie Sub - Ennis South Sub 138 kV: Reterminate into Ennis West Switch | City of Ennis, Ellis County | Reterminate the Waxahachie Sub - Ennis South Sub 138 kV Line section from Ennis West Switch - Ennis South Sub into its new bay position at Ennis West Switching Station | 2021-02-08 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW | Steel Monopoles | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT42531 | Sweetwater Downtown Tap - Sweetwater Downtown Substation 138 kV Line: Replace Structures 101/1 & 1/1 | City of Sweetwater, Nolan County | Replace tap structure (101/1) with a new Heavy Duty H-Frame Switch structure and replace two line sectionalizing switches and install an additional switch and replace existing structure (1/1) with a SC wood pole. | 2020-10-26 | 2020-12-15 | [5 empty] | 0 | 138 | na | 0.1 | 336 ACSR Linnett | Steel H-Frame Switch & Wood monopole | 25 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42618 | Eskota Switch - Morgan Creek Switch 138 kV Line: Replace Structures 100/10 & 101/2 | City of Sweetwater, Nolan County | Replace structures (100/10) & (101/2) with wood H-Frames with steel crossarms and double insulators. A temporary bypass will be utilized for this project. | 2020-10-26 | 2020-12-31 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR Drake | Wood H-Frames | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38743 | Oran Sub - Mineral Wells Sub 138 kV Line : Erosion Control | City of Mineral Wells/Palo Pinto County | Install erosion control guards around structures 02/08 on the Oran Sub - Mineral Wells Sub 138 kV line. | 2020-10-28 | 2020-12-31 | [5 empty] | 0 | 138 | na | 0.1 | 1590 ACSR | Wood H-frame | 100 | 0.1 | na | na | 25.101 (c)(5)(B)
0PT41580 | Tyler Grande Sub - Overton Sub 138 kV Line : Structure Replacement | City of Arp, Smith County | Relocate structure 61/02 on the Tyler Grande Sub – Overton Sub 138 kV line. | 2020-11-12 | 2020-12-31 | [5 empty] | 0 | 138 | na | 0.3 | 4/0 CU | Wood H-frame | 100 | 0.3 | na | na | 25.101 (c)(5)(B)
0PT43075 | Rosen Heights Tap No 1 (West) : Rebuild Tap Point | City of Fort Worth, Tarrant County | Reconfigure the existing Rosen Heights Tap (west circuit) from a hard tap to 3-way switch configuration. | 2020-10-01 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 2-959.6 kcmil ACSS/TW | Steel Poles | 75 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43076 | Rosen Heights Tap No 2 (East) : Rebuild Tap Point | City of Fort Worth, Tarrant County | Reconfigure the existing Rosen Heights Tap (east circuit) from a hard tap to 3-way switch configuration. | 2020-10-01 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 2-959.6 kcmil ACSS/TW | Steel Poles | 75 | 0.1 | na | na | 25.101(c)(5)(B)
17T62191 | Handley SES - Sherry 138 kV Line: Rebuild Handley SES - Pantego Sub Section (Phase 1) | City of Arlington, Tarrant County | Rebuild the Handley SES - Pantego Sub Section (Phase 1) of the Handley SES - Sherry 138 kV Line. | 2020-11-01 | 2021-05-15 | [6 empty] | 138 | na | 3.8 | 1926.9 kcmil ACSS/TW | Steel Poles | Varies | 3.8 | na | na | 25.101(c)(5)(B)
0PT41855 | Jewett Switch - Rattlesnake Road Switch 345 kV Line : HB 4150 Lake Limestone Crossing | City of Groesbeck, Limestone County | Rebuilding a section of the Jewett Switch - Rattlesnake Road Switch 345 kV Line | 2021-01-25 | 2021-05-15 | [5 empty] | 0 | 345 | na | 1.4 | 795 ACSR & 1590 ACSR Falcon | Steel Lattice Tower | 125 | 0.7 | na | na | 25.101(c)(5)(B)
0PT42279 | Lake Creek Switch - Jewett Switch 138 kV Line : HB 4150 Lake Limestone Crossing | City of Groesbeck, Limestone County | Rebuild a section of the Lake Creek Switch - Jewett Switch 138 kV Line that crosses Lake Limestone in Limestone County in order to increase vertical clearance over the flood plan area. | 2021-01-19 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.2 | 795 ACSR | Wood H-Frame | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43066 | Liggett Switch - Euless 138kV Line: Reterminate at Irving Valley View Sub | City of Irving, Dallas County | Reterminate Liggett Switch - Euless 138kV Line at Irving Valley View Substation. | 2021-02-08 | 2021-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 2-1033.5 ACSR Curlew | Steel Poles | 140 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41254 | NTUSU Brown Switch - Killeen Switch 345 kV Line : Retirement Only | Mills County | Retire assets for the new Buckhorn Switch Station | 2021-01-05 | 2021-05-14 | [5 empty] | 0 | 345 | na | 0.4 | 2 -1926.9 MCM ACSS/TW/HS Cumberland | Steel Tower | 160 | 0.2 | na | 0.2 | 25.101(c)(5)(A) | Project scope adjusted and no longer meets reporting criteria. Project will be removed on next month's report.
0PT40191 | Elm Mott - Bosque (BEC) 138kV Line: Rebuild Elm Mott Switch - Rogers Hill Sub (BEC) | City of Elm Mott, McLennan County | Rebuild the Elm Mott Switch - Rogers Hill Sub (BEC) section of the Elm Mott Switch to Bosque Switch (BEC) 138 kV Line. | 2021-01-11 | 2021-05-15 | [5 empty] | 0 | 138 | na | 5.6 | 2 - 959.6 MCM ACSS/TW/HS “Suwannee” | Steel Poles | 100 | 5.6 | na | na | 25.101(c)(5)(B)
0PT42346 | Hutto - Round Rock - Gabriel 138 kV Line: Midnight Sub Cut- In | City of Round Rock, Williamson County | Line work associated with establishing Midnight Substation. This work is occurring on the Hutto Switch - Round Rock - Gabriel 138kV line. | 2021-03-15 | 2021-05-15 | [6 empty] | 138 | na | 0.4 | 795 ACSR | Wood H-Frames | 100 | 0.4 | na | na | 25.101(c)(5)(A)
0PT41461 | Farmersville Switch - Monticello Switch 345 kV Line : Delilah Solar Generator Interconnect | Franklin County | Establish a 345 kV point-of-interconnection (POI) for Delilah Solar Generator at Thorn Tree 345 kV Switch. | 2021-03-01 | 2021-05-31 | [5 empty] | 0 | 345 | na | 0.2 | 2-1926.9 ACSS/TW Cumberland | Steel Poles and Towers | 170 | 0.2 | na | na | 25.101(c)(5)(A)
18T65207 | Northaven Switch - Morrison Lane Switch 138 kV Double Circuit Line Section: Rebuild Northaven - Welch Road - Marsh Lane | City of Dallas, Dallas County | Rebuild 2.9 mile section of Northaven Switch - Morrison Lane Switch 138 kV Double Circuit Line from Northaven to Marsh Lane Sub. | 2021-02-15 | 2021-05-15 | [5 empty] | 0 | 138 | na | 5.8 | 1926.9 ACSS/TW | Steel Poles | 100 | 2.9 | na | na | 25.101(c)(5)(B)
0PT38695 | Waco West Switch – Waco East Switch 138kV Line: Rebuild Waco West Switch - Structure 1/8 Line Section | City of Waco, McLennan County | Rebuild the 10.6-mile Waco West Switch - Structure 1/8 138 kV line section of the Waco West Switch – Waco East Switch 138 kV Line. | 2021-08-16 | 2021-12-15 | [5 empty] | 0 | 138 | na | 10.6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 10.6 | na | na | 25.101(c)(5)(B)
0PT41773 | Navarro Switch - Watermill Switch 345 kV Line: Establish Big Onion Switch | City of Ennis, Ellis County | Establish a point of interconnection to the Solar Strategic Energy generating facility by establishing Big Onion Switch on the Navarro - Watermill 345 kV transmission line. | 2021-01-04 | 2021-04-21 | [5 empty] | 0 | 345 | na | 0.1 | 2-1926.9 kcmil ACSS/TW | Steel Towers | 160 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43220 | Navy Kickapoo Switch - Holliday 69 kV Line: Storm Damage (TSP20017) | City of Archer, Archer County | Replace 8 wood pole structures, including 24 insulators, and 3 cross arms Holliday Sub - Navy Kickapoo Sub 69 kV Line. | 2020-08-17 | 2020-08-22 | 2020-08-22 |  | 185007.21 |  |  | 100 | 69 | NA | 0.57 | 4/0 ACSR | Wood Monopoles | 50 | 0.57 | na | na | 25.101(c)(3) | Storm Damage Restoration
0PT43218 | Holliday - Seymour 69 kV Line: Storm Damage (TSP20017) | City of Wichita Falls, Wichita County | Replace 4 wood pole structures and 21 insulator assemblies Holliday Sub - Seymour Sub 69 kV Line. | 2020-08-17 | 2020-08-22 | 2020-08-22 |  | 89072.43 |  |  | 100 | 69 | NA | 0.8 | 4/0 ACSR | Wood Monopoles | 50 | 0.8 | na | na | 25.101(c)(3) | Storm Damage Restoration
0PT43219 | Holliday - Electra 69 kV Line: Storm Damage (TSP20017) | City of Electra, Wichita County | Replace 1 cross arms on the Holliday - Electra 69 kV Line. | 2020-08-17 | 2020-08-21 | 2020-08-21 |  | 16609.62 |  |  | 100 | 69 | NA | 0.01 | 4/0 ACSR | Wood H-frames | 50 | 0.01 | na | na | 25.101(c)(3) | Storm Damage Restoration
0PT43229 | NTUSU Driver - Hadacol Corner 138 kV Line: Damage | City of Midland, Midland County | Replace 4 spans of conductor, OPGW, and 5 structures worth of insulators as the result of fire damage. | 2020-08-18 | 2020-08-20 |  |  | 290783.85 |  |  | 99 | 138 | NA | 0.63 | 959 ACSS/TW | Steel Deadends, Concrete Tangents | 75 | 0.63 | na | na | 25.101(c)(3) | Emergency Project
0PT43288 | NTUSU Driver - SkyWest 138 kV Line: OPGW Damage | City of Midland, Midland County | Replace 3 spans of OPGW as the result of fire damage. | 2020-08-20 | 2020-09-04 |  |  | 57042.42 |  |  | 99 | 138 | NA | 0.36 | 959 ACSS/TW | Steel Deadends, Concrete Tangents | 75 | 0.36 | na | na | 25.101(c)(3) | Emergency Project
0PT43237 | Sherry Switch - Fish Creek Switch 138 kV Line (South Circuit): Damage Restoration | City of Grand Prairie, Dallas County | Replace 2 lattice towers with 2 steel monopoles and replace conductor and shield wire on the Sherry Sw - Fish Creek Sw 138 kV Line. | 2020-08-19 | 2020-09-01 |  |  | 520049 |  |  | 99 | 138 | na | 0.97 | 795 ACSR, Drake, Single | Steel Monopoles | Variable | 5150 | na | na | 25.101(c)(3) | Emergency Project
0PT43249 | Sherry Switch - Fish Creek Switch 138 kV Line (North Circuit) : Damage Restoration | City of Grand Prairie, Dallas County | Replace conductor and install 2 steel monopoles on the Sherry Sw - Fish Creek Sw 138 kV Line. | 2020-08-19 | 2020-08-28 |  |  | 520049 |  |  | 99 | 138 | na | 0.97 | 795 ACSR, Drake, Single | Steel Monopoles | Variable | 5150 | na | na | 25.101(c)(3) | Emergency Project
0PT42445 | Willow Creek Switch - Hicks Switch 345 kV | Wise County | The scope of this project involves relocating an existing TE 69190 Tower (24/05) on the Willow Creek Switch - Hicks Switch 345 kV Line. | 2020-11-10 | 2020-12-31 | [5 empty] | 0 | 345 | na | 23.99 | 1926 ACSS/TW | Lattice Tower | 160 | 24 | na | na | 25.101(c)(5)(B)
0PT42438 | Commerce Switch - Sulphur Springs Switch 138 kV Line : Erosion Control | Commerce City | Structure 06/01 concrete H-frame on the edge of the creek bed experiencing high levels of exposure. This project entails relocating the structure experiencing the erosion issues. | 2020-11-10 | 2020-12-31 | [5 empty] | 0 | 138 | na | 35 | 795 ACSR | H-Frame | 100 | 35 | na | na | 25.101(c)(5)(B)
0PT41581 | Valley Switch - Commerce Switch 138 kV Line : Erosion Control | Fannin County | Installing erosion control guards around structures 01/06 - 01/07 on the Valley Switch - Commerce Switch 138 kV line. | 2020-10-30 | 2020-12-31 | [5 empty] | 0 | 138 | na | 25.9 | 795 ACSR | Lattice Tower | 100 | 25.9 | na | na | 25.101(c)(5)(B)
0PT41709 | Shamburger Switch - Martin Lake Switch 345 kV Line : Erosion Control | Overton City | Large degrees of erosion around structure 24/05 on the Shamburger - Martin Lake 345kV line. Scope entails installing erosion control guards. | 2020-11-02 | 2020-12-31 | [5 empty] | 0 | 345 | na | 43.4 | 1590 ACSR | Lattice Tower | 160 | 43.4 | na | na | 25.101(c)(5)(B)
STATIONS
0PT03998 | Plano Tennyson Switch: Upgrade line terminal and associated equipment to meet or exceed 3200 A | City of Plano, Denton County | Upgrade line terminal and associated equipment to meet or exceed 3200 A as a part of upgrading the Renner TPL Plano Tennyson 138 kV Line | 2021-11-01 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03999 | Renner Switch: Upgrade line terminal and associated equipment to meet or exceed 3200 A | City of Plano, Denton County | Upgrade line terminal and associated equipment to meet or exceed 3200 A as a part of upgrading the Renner Switch - Allen Switch/Plano Tennyson Switch 138 kV | 2020-11-02 | 2021-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03981 | Sherry Switch: Two Line Terminal Upgrade | City of Arlington, Tarrant County | Upgrade line terminal and associated equipment to meet as a part of upgrading the Handley Sherry 138 kV Double-circuit Line | 2021-05-16 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40632 | Ogallala Switch : Install Terminal for Nazareth Solar | City of Nazareth, Castro County | Install one 345 kV, 3200 A circuit breaker at Install a 345 kV (POI) for customer's generator (TX Nazareth Solar, LLC). | 2021-07-16 | 2021-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65069 | Camp Wisdom Sub: Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | City of Dallas, Dallas County | Install three 138 kV sectionalizing switches and upgrade all line terminal and associated equipment to meet or exceed 2000 A as apart of upgrading the 11.5-mile Watermill Sw. Sta. - Camp Wisdom Road 138 kV line. | 2020-09-24 | 2020-12-15 |  |  | 995282 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41211 | Elm Fork Pump Sub : Install one transformer and a feeder breaker | City of Carrollton, Denton County | Install one transformer and a feeder breaker | 2020-05-20 | 2020-11-15 |  |  | 2294139 |  |  | 46 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40492 | Parkdale Switch : Replace circuit breakers | City of Dallas, Dallas County | Replace three circuit breakers | 2020-11-02 | 2020-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41077 | Richardson Spring Valley Sub : Rebuild Substation by relocating both transformers inside the station | City of Richardson, Dallas County | Rebuild Substation by relocating both transformers inside the station | 2020-06-12 | 2020-12-15 |  |  | 4610004 |  |  | 10 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40485 | Snyder Switch : Replace two circuit breakers | City of Snyder, Scurry County | Replace one 69 kV circuit breaker and one 138 kV circuit breaker | 2020-09-14 | 2020-12-15 |  |  | 246340 |  |  | 0 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41498 | Willow Wells Sub : Install 2nd transformer and two feeder breakers | City of Odessa, Winker County | Install second transformer and two feeder breakers. | 2020-02-02 | 2020-12-15 |  |  | 2109618 |  |  | 4 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41490 | Witt Rd Sub: Install second transformer with three feeder breakers | City of Lancaster, Dallas County | Install second transformer with three feeder breakers | 2020-03-30 | 2020-12-15 |  |  | 2021287 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39073 | Allens Creek POI: Establish 138 kV Point of Interconnection | Fannin County | Allens Creek POI: Establish 138 kV Point of Interconnection for Rayburn Interconnect, located in the Valley-Paris Sw. line. | 2019-12-10 | 2020-06-24 | 2020-06-24 |  | 644190 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37562 | Alligator Draw Sub : Establish station with two transformers and two feeder breakers. | City of Orla, Culberson County | Alligator Draw Sub : Establish station with two transformers and two feeder breakers on the new Horseshoe Springs Sw. Sta. Owl Hills 138 kV Line | 2019-09-17 | 2020-02-17 | 2020-02-17 |  | 5725089 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40140 | Andrews County South Switch : Install Auto #2 and establish the new Wink Switch terminal. Upgrade No Trees Switch line terminal for the existing Wink circuit. | City of Andrews, Andrews County | Install Auto #2 Install and establish the new Wink Switch terminal. Upgrade all line terminal and associated equipment for the existing No Trees – Wink line as a part of rebuilding the 8.8-mile No Trees Sw. Sta. - Andrews County South Sw. Sta. 138 kV Line. | 2019-09-03 | 2020-03-27 | 2020-03-27 |  | 4699579 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT01033 | Azle Sub: Install the third transformer with one feeder breaker | City of Azle, Tarrant County | Azle Sub: Install the third transformer with one feeder breaker | 2020-02-26 | 2020-06-26 | 2020-06-26 |  | 3988592 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37352 | Barstow Northwest Sub : Install Transformer #3 w/ two 21.6 kV feeder breakers and three feeder ties | City of Odessa, Ector County | Install Transformer with two feeder breakers and three feeder ties. | 2019-07-23 | 2019-12-28 | 2019-12-28 |  | 2989092 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38971 | Benbrook Sub : Create a loop in loop out, install FID's and install new Sub IV protection for transformer #1 and #2 | City of Fort Worth, Tarrant County | Create a loop in loop out, install FID's and install new protection for transformer #1 and #2 | 2019-09-16 | 2019-12-31 | 2019-12-31 |  | 2399766 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37383 | Bennett Road Switch: Establish 69 kV ring bus | City of Decatur, Wise County | Relocate the 138/69 kV from Decatur Switch by establishing a 69 kV yard at Bennett Road Switch. Install two (2) Circuit Breakers to Bowie and Oran. Expand the three Circuit Breaker 138 kV ring bus arrangement to a four Circuit Breaker ring bus arrangement. | 2019-06-10 | 2019-12-20 | 2019-12-20 |  | 2192033.7 | 2276002.04 | 3.831% | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT04157 | Bird Nest Sub formerly (Pflugerville South Substation) | City of Pflugerville, Travis County | Establish Substation with one Transformer and Two Feeder Breakers | 2019-03-12 | 2019-12-21 | 2019-12-21 |  | 3943117 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37341 | Blackbird Switch: Establish Station | City of Odessa, Andrews County | Establish station with a 3-breaker 138 kV ring bus arrangement to install a 138 kV point-of-interconnection (POI) for customer's generator. The POI will be located on the Andrews North Sw. Sta. - Fullerton Sw. Sta. 138 kV Line | 2019-08-12 | 2019-12-18 | 2019-12-18 |  | 4169055 | 3359364.55 | -19.42% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT38719 | Blackburn Switch: Establish station for a 138 kV point of interconnection | City of Jacksonville, Cherokee County | Establish a switching station in a 3-breaker 138 kV ring bus arrangement located in the Elkton Switch - Palestine South Switch 138 kV Line, approximately 17.2 miles south of Elkton Switch | 2019-07-22 | 2019-12-22 | 2019-12-22 |  | 3510836 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37445 | Blackland POD: Station Demolition | City of Fate, Rockwall County | Remove Oncor owned equipment and structures from the Blackland POD. | 2020-02-13 | 2020-04-14 | 2020-04-14 |  | 253048 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65108 | Blackland Switch: Establish 138 kV station | City of Fate, Rockwall County | Install a 138 kV point of interconnection with a 3-breaker 138 kV ring bus arrangement on the Royse Sw. Sta. - Terrell Sw. Sta. 138 kV Line. | 2018-10-11 | 2019-12-20 | 2019-12-20 |  | 5527820 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04155 | Blagg Sub: Establish Substation with one Transf. and Two Feeder Breakers: | City of Denton, Denton County | Establish Substation with one Transf. and Two Feeder Breakers | 2020-07-28 | 2020-12-31 |  |  | 4763870 |  |  | 10 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38284 | Boulder POD : 138 kV Point of Delivery | City of Odessa | Establish Boulder a 138kV point of delivery for customer owned station on the south circuit of the Wink – Culberson 138 kV Double-circuit Line. | 2019-11-26 | 2020-06-10 | 2020-06-10 |  | 1268563 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04108 | Bowman Switch: 138 kV Line Terminal Additions | City of Wichita Falls, Tarrant County | Install two circuit breakers. Move the existing Bowman - Lake Wichita 138 kV Line termination at Bowman from bus B to bus A. | 2019-06-30 | 2019-12-31 | 2019-12-31 |  | 2088435 | 2152550.73 | 3.07% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT40126 | Brelyn Sub: (Coahoma West Sub) Establish substation | City of Coahoma, Howard County | Establish Substation with a one transformer with two Feeder Breakers | 2020-02-13 | 2020-06-16 | 2020-06-16 |  | 4040613 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38723 | Canton Tap Switch: Canton Tap 138 kV Switching Station. Point of Interconnection | City of Canton, Van Zandt County | Establish a line terminal to connect Glenn Pine 138 kV Line. Upgrade and reconfigure all line terminal and associated equipment at Canton Tap Sw. Sta. to provide a 138 kV point of interconnection. | 2019-09-03 | 2019-12-27 | 2019-12-27 |  | 500458 | 918120.42 | 83.46% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
0PT03966 | Canton Tap Switch: Modify Tyler Switch Line Relaying | City of Forney, Kaufman County | Modify relaying for ring bus terminal at Tyler Switch | 2020-11-02 | 2020-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39750 | Carrollton Frankford Rd Sub : Convert Station One and Two to 125 VDC and Replace Breakers | City of Carrollton, Denton County | Update protection, convert station one and two to 125 VDC and replace breakers | 2019-10-31 | 2020-06-24 | 2020-06-24 |  | 597449 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65033 | Carrollton NW Sub: Upgrade 138 kV Norwood & Lakepoint Lines | City of Carrollton, Denton County | Upgrade all terminal and associated equipment as a part of upgrading the NW Carrollton – Norwood Sw. Sta. 138 kV Double-circuit line. | 2018-11-15 | 2020-06-23 | 2020-06-23 |  | 435226 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65029 | Cedar Crest Switch: Upgrade industrial line and replace bus diff panels | City of Dallas, Dallas County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | 2018-12-03 | 2019-12-26 | 2019-12-26 |  | 407403 | 356286.41 | -12.55% | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
18T65018 | Centerville Switch: Upgrade line, auto and bus relaying | City of Dallas, Dallas County | Upgrade line, auto and bus relaying at Centerville Switch. | 2019-09-09 | 2020-06-26 | 2020-06-26 |  | 1678074 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38420 | Central Bluff Switch : Install 345 kV breaker to provide Generator with one Point of Interconnection from a 345 kV breaker-and-a-half arrangement. | City of Blackwell, Nolan County | Install 345 kV breaker to provide Generator with one Point of Interconnection from a 345 kV breaker-and-a-half arrangement. | 2019-09-23 | 2019-12-23 | 2019-12-23 |  | 1771933 | 1719701.3 | -2.948% | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT37566 | Chimney Well POD : Provide a 138 kV point-of-delivery (POD) | City of Odessa, Ector County | Establish Chimney Well POD for customer owned station, a 138 kV on the Horseshoe Springs Sw - Owl Hills 138kV line. | 2019-10-21 | 2020-05-01 | 2020-05-01 |  | 921244.66 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04158 | China Springs Substation: Install one Transf. #2 and 1-25 kV Feeder and install Distribution Automation on Feeders 2401 and 2403 | City of China Spring, McLennan County | Install Bank #2 with one Transformer and One Feeder Breaker. Includes installation of Distribution Automation on Feeders 2401 and 2403. | 2019-07-12 | 2019-12-01 | 2019-12-01 |  | 1243074 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04000 | Collin Sw. Station 345/138 kV autotransformer #2 series reactor | City of Frisco, Collin County | Install a series reactor in series with the 345/138 kV autotransformer #2. | 2020-01-30 | 2020-06-16 | 2020-06-16 |  | 1135739 |  |  | 100 | 345/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39490 | Comanche Peak 345 kV Switch : Upgrade Mitchell Bend to Double Breaker Double Bus | Glen Rose County | Upgrade Mitchell Bend line terminal to Double Breaker Double Bus | 2020-01-31 | 2020-05-21 | 2020-05-21 |  | 1212265 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38434 | Comanche Peak 345 kV: Upgrade Everman to double breaker double bus | City of Glen Rose, Somervell County | Install a new 345 kV breaker and breaker disconnect switch for the Everman line to make the bay double breaker, double bus. | 2019-12-04 | 2020-04-28 | 2020-04-28 |  | 1340588.81 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
17T65036 | Crown Road Sub: Upgrade 138 kV line terminals | City of Dallas, Dallas County | Upgrade all terminal and associated equipment as a part of upgrading the NW Carrollton Norwood Switch 138 kV double-circuit line. | 2019-12-02 | 2019-12-29 | 2019-12-29 |  | 264870 | 318975.42 | 20.43% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
0PT04086 | Deen Switch: Establish Station to Replace Saginaw 138 kV Switch | City of Fort Worth, Tarrant County | Establish Deen Switch station by installing sixteen 138 kV circuit breakers in a breaker-and-a-half arrangement. | 2019-10-07 | 2020-12-15 |  |  | 15912850 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39812 | Dollarhide Sub: Modify bus to loop 138kV line in and out of station | City of Odessa, Winkler County | Modify bus to loop line in and out of station as a part of rebuilding the No Trees Switch - Andrews County South Switch 138 kV line. | 2020-03-02 | 2020-04-29 | 2020-04-29 |  | 1127694 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37283 | Du Puy (Waco West) Sub : Replace Transformer by Rebuilding the Existing Substation | City of Waco, McLennan County | Establish Du Puy Substation with three transformers and ten feeder breakers. | 2019-09-16 | 2020-04-01 | 2020-04-01 |  | 5906786 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38578 | Dunn POD : Provide a 138 kV point-of-delivery (POD) | City of Colorado City, Mitchell County | Establish Dunn POD for customer owned stations for a 138 kV point of delivery, on the China Grove Radium 138 kV Line | 2019-08-12 | 2019-10-28 | 2019-10-28 |  | 551660 | 646344.2 | 17.16% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
0PT04035 | Ennis Creek Switch: 138 kV Station Rebuild | City of Snyder, Scurry County | Rebuild the 138 kV Ennis Creek Switch with a 3-breaker 138 kV ring bus arrangement. | 2020-05-20 | 2020-10-17 |  |  | 4204788 |  |  | 90 | 138/69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39276 | Fate Sub: Establish Substation with one transformer and two feeder breakers | City of Fate, Rockwall County | Establish Substation with one transformer and two feeder breakers | 2020-04-06 | 2020-06-26 | 2020-06-26 |  | 4424090 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38216 | Fisher Road Switch : Replace 138 kV circuit breaker | City of Wichita Falls, Tarrant County | Replace 138 kV circuit breaker | 2019-10-17 | 2019-12-20 | 2019-12-20 |  | 216982 | 203356.71 | -6.279% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT38725 | Forest Grove Switch : Terminal Upgrade | City of Malakoff, Henderson County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | 2019-11-09 | 2020-02-12 | 2020-02-12 |  | 344369 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03958 | Goddard Sub: Upgrade Line Terminal to 2000 A and Install FIDs on transformer #1 and #2 | City of Odessa, Midland County | Upgrade line terminal and associated equipment as part of the upgrade of Midland County Northwest Sw. Sta. - Midland East Sw. Sta. 138 kV Double-circuit Line. Install FIDs on transformer #1 and #2. | 2019-10-28 | 2020-02-28 | 2020-02-28 |  | 1444304 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39341 | Heritage Sub : Convert transformer #1 to 138 kV and upgrade protection on CB | City of Fort Worth, Tarrant County | Convert Transformer #1 to 138 kV and upgrade line protection on circuit breaker. | 2020-04-06 | 2020-12-25 |  |  | 187469 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39386 | Hicks Switch: Modification for interconnect and convert line communication for line to fiber | City of Fort Worth, Tarrant County | Modifications for interconnect and convert the line communication for line to fiber. | 2019-04-01 | 2020-12-15 |  |  | 1857917 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04057 | Hicks Switch: 13.8 kV Reactor Installation | City of Fort Worth, Tarrant County | Install 13.8 kV tertiary shunt reactors on Autotransformer #2 and installation of AC service to the new microwave center. | 2019-02-28 | 2019-11-27 | 2019-11-27 |  | 1016416 | 741967.72 | -27% | 100 | 13.8 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT04106 | Holliday Sub: 69 kV Terminal Upgrade to 138 kV | City of Holliday, Archer County | Upgrade the 69 kV Lake Wichita line terminal to 138 kV. | 2019-06-03 | 2019-12-31 | 2019-12-31 |  | 3456242 | 3894510.53 | 12.68% | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope and access issues.
0PT38362 | Holly Ervin POD : Establish a 138 kV Point of Interconnection | City of Palestine, Anderson County | Establish Holly Ervin POD for customer owned station, 138kV point of delivery on the Big Brown Tap - Long Lake 138kV line. | 2019-07-22 | 2019-12-20 | 2019-12-20 |  | 1477517.87 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37618 | Horsehead Draw Sub (formerly Mentone Southwest Sub) : Establish one Substation Transformer and three feeder breakers | City of Odessa, Ector County | Establish station with one Transformer and three feeder breakers | 2019-03-18 | 2019-12-20 | 2019-12-20 |  | 4043063 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
19T62005 | International Airport Sub: Replace 12.5 kV Substation | City of Fort Worth, Tarrant County | Rebuild the existing 138/12.5 kV Substation by replacing the existing 12.5 kV distribution switchgear with outdoor air insulated distribution circuit breakers at Stations 1 and 2. | 2019-06-05 | 2019-12-30 | 2019-12-30 |  | 5421782 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Legacy Sharyland Project
0PT37436 | Jacksonville Switch : Upgrade and reconfigure the existing station in a 5-breaker 69 kV single-bus arrangement | City of Jacksonville, Cherokee County | Upgrade and reconfigure the existing station by installing five, 69 kV circuit breakers in single-bus arrangement. Remove the Single Phase Auto Transformers. | 2019-06-25 | 2019-12-23 | 2019-12-23 |  | 5034419 |  |  | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37311 | Kemp Ranch Switch (Venus Switch) : Install two 138 kV point of interconnections by constructing a 138 kV switching station in a breaker-and-a-half bus arrangement. | City of Midlothian, Ellis County | Install two 138 kV POD for customer owned stations by constructing a 138 kV Kemp Ranch Switching station in a breaker-and-a-half bus arrangement. | 2019-03-04 | 2019-12-02 | 2019-12-02 |  | 11506348 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38411 | Killeen Park Street Sub : Install three sectionalizing switches to loop line | City of Killeen, Tarrant County | Install three sectionalizing switches and loop line into station to as a part of establishing a 138 kV point of interconnection (POI). | 2020-11-15 | 2020-12-31 |  |  | 191, 851 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38360 | Lake Hall Switch : Establish 345 kV Switching Station to Provide POI | City of Waco, McLennan County | Establish 345 kV switching station by installing two 345 kV transmission line exits and provide one interconnection point from a 345 kV three breaker ring bus arrangement. | 2019-09-16 | 2020-08-17 |  |  | 7196857 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04107 | Lake Wichita Switch: 69 kV Line Terminal Upgrade to 138 kV | City of Wichita Falls, Tarrant County | Install one 138 kV circuit breaker on the 138 kV bus. Remove 69 kV bus and associated equipment. | 2019-08-26 | 2019-12-31 | 2019-12-31 |  | 1140802 | 1418872.71 | 24.38% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
18T65010 | Las Colinas Sub: Upgrade 138 kV line terminals | City of Dallas, Dallas County | Upgrade all terminal and associated equipment to meet or exceed 2000 A as a part of upgrading the NW Carrollton- Norwood Switch 138 kV Double-circuit line. | 2020-02-14 | 2020-05-14 | 2020-05-14 |  | 485166 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38367 | Latigo (McPherson (BEC)) POI : Install a new 138 kV point of interconnection for the McPherson (BEC) 138 kV Substation | City of Fort Worth, Tarrant County | Establish a new 138 kV point of interconnection for the McPherson (BEC) 138 kV Substation located in the Roanoke Sw. Euless Sw. 138 kV Line. | 2019-07-22 | 2020-10-01 |  |  | 860751 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
17T65009 | Liggett Switch: 138 kV Cedar Hill Terminal upgrade, 345 kV protective relay upgrades and replace the Norwood switch transfer trip panel | City of Irving, Dallas County | Upgrade all terminal and associated equipment as a part of upgrading the Cedar Hill Sw. Sta. Liggett 138 kV line. | 2018-01-10 | 2020-03-11 | 2020-03-11 |  | 1630734 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04389 | Mankin Switch: Establish Station for POI | City of Trinidad City, Henderson County | Establish a 138 kV Point of Interconnection located in the Trinidad Sw. Sta. Kaufman Northwest 138 kV line by constructing the Mankin 138 kV POI with a 3-breaker 138 kV ring bus arrangement. | 2019-04-01 | 2019-12-19 | 2019-12-19 |  | 4840466.13 | 3681765.38 | -23.94% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Final Estimated Cost adjusted due to error on initial report.
0PT38220 | Montfort Switch: Replace 138 kV circuit breaker | City of Corsicana, Navarro County | Replace three 138 kV circuit breakers | 2019-09-16 | 2020-02-28 | 2020-02-28 |  | 699414 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38134 | McDonald Road Switch : Establish line terminal | City of Big Springs, Howard County | Install one 3200 A, 138 kV circuit breaker in a ring bus arrangement as a part of converting the McDonald Road Switch - Garden City Substation 69 kV Line Section to 138 kV operation. | 2019-07-20 | 2019-11-01 | 2019-11-01 |  | 1097713.5 | 1128162 | 2.774% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT38218 | Navarro Sub : Replace two 138 kV circuit breakers | City of Corsicana, Navarro County | Replace two 138 kV circuit breakers | 2019-09-23 | 2019-12-23 | 2019-12-23 |  | 310041 | 456755.9 | 47.32% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
0PT37587 | Nelson Switch : Install a 138 kV POI | City of Odessa, Andrews County | Install a 138 kV POI on the Andrews County South Sw. Sta. Fullerton Sw. Sta. 138 kV Line by installing three 138 kV circuit breakers in a ring bus configuration. | 2019-09-09 | 2019-12-20 | 2019-12-20 |  | 4329713 | 3512376.79 | -18.88% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
16T62037 | North Main Switch: Install two 138 kV, 2000 A circuit breakers with provisions for an additional 138 kV circuit. | City of Fort Worth, Tarrant County | Install two 138 kV, 2000 A circuit breakers with provisions for an additional 138 kV circuit. | 2019-12-22 | 2020-12-31 |  |  | 3730993 |  |  | 44 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT01788 | Norwood Substation: Upgrade 138 kV NW Carrollton Line Terminals | City of Irving, Dallas County | Upgrade all terminal and associated equipment as a part of upgrading the NW Carrollton Norwood Sw. Sta. 138 kV double-circuit line. | 2019-03-23 | 2020-06-10 | 2020-06-10 |  | 286343 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65027 | Norwood Substation: 345 kV Bus Auto #1 & 138 kV yard relay upgrade | City of Irving, Dallas County | Upgrade protective relaying within the 345 kV and 138 kV switchyards at Norwood Substation | 2019-02-25 | 2020-06-11 | 2020-06-11 |  | 2500000 |  |  | 100 | 345/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65039 | Norwood Switch: Modify 345/138 auto #1 relay protection | City of Irving, Dallas County | Modify 345/138 auto #1 relay protection | 2019-03-07 | 2019-12-02 | 2019-12-02 |  | 295008 | 961541.19 | 225.9% | 100 | 345 /138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
0PT37340 | Odessa EHV Switch : Install security measures | City of Odessa, Midland County | Install security measures at switching station. | 2020-02-03 | 2020-12-15 |  |  | 2102168 |  |  | 10 | 345/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04005 | Odessa North Switch: Remove 69 kV terminal and re-terminate the new Cowden North - Odessa North 138 kV Line | City of Odessa, Ector County | Remove 69 kV terminal and re-terminate the new Cowden North - Odessa North 138 kV Line. | 2019-08-05 | 2020-04-01 | 2020-04-01 |  | 518029 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39370 | Palestine Sub : Modify relaying for the new Blackburn Switch terminal. | City of Palestine, Anderson County | Modify relaying for the new Blackburn Switch terminal by adding a transfer trip receiver | 2019-09-15 | 2020-02-28 | 2020-02-28 |  | 116126 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
16T62052 | Panther Island Sub | City of Fort Worth, Tarrant County | Remove and rebuild the North Main Substation to the south of Heritage Sub and North Main Switch as Panther Island Sub consisting of two transformers and eight feeder breakers | 2019-12-02 | 2020-06-29 | 2020-06-29 |  | 6029913 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65075 | Parkdale Switch: Replace two 138 kV bus differentials and replace 138 kV | City of Dallas, Dallas County | Upgrade 138 kV bus protection to provide redundancy for three phase faults and replace 138 kV circuit breaker. | 2019-11-13 | 2019-12-13 | 2019-12-13 |  | 678303 | 872779.61 | 28.67% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope.
18T65175 | Prolina (Redbud) 138 kV POI | City of Prosper, Collin County | Install three motor operated SCADA control 138 kV line sectionalizing switches. | 2019-09-18 | 2020-06-01 | 2020-06-01 |  | 1226517.76 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38606 | Railside Switch : Establish POD by installing four 138 kV circuit breakers in a ring-bus arrangement | City of Odessa, Wink County | Provide two 138 kV PODs for customer owned stations on the Wink Switch No Trees Switch 138 kV Line by establishing four 138 kV circuit breakers in a ring-bus arrangement. | 2019-09-03 | 2019-12-30 | 2019-12-30 |  | 4469729 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04062 | Ranger Sub: 69 kV emergency capacitors | City of Ranger, Eastland County | Install one bank of 69 kV transmission capacitors and associated terminal equipment. | 2019-02-28 | 2019-11-19 | 2019-11-19 |  | 2077310 | 2428280.15 | 16.9% | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report. Variance due to change in scope and unexpected weather conditions.
0PT38072 | Red Lakes Switch : Establish station a 3-breaker 138 kV ring bus arrangement | City of Odessa, Ector County | Establish station with a 3-breaker 138 kV ring bus arrangement for interconnection generation interconnection. | 2019-08-07 | 2019-12-02 | 2019-12-02 |  | 4213265 | 3644535.56 | -13.5% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT39224 | Richardson Spring Creek-Install 4th Transformer and Two Feeder Breakers | City of Dallas, Dallas County | Install 4th Transformer and Two Feeder Breakers | 2019-10-25 | 2020-06-17 | 2020-06-17 |  | 2073664 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37647 | Rondo STATCOM | Odessa County | Install one +250/-250 Mvar Dynamic Reactive Device and one 138 kV circuit breaker at Quarry Field 138 kV Sw. Station | 2019-09-15 | 2019-12-19 | 2019-12-19 |  | 33058594 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04026 | Rough Creek Sub: Establish 138-12.5 kV Station | Scurry County | Convert the station to operate at 138 kV by replace the existing substation with a two transformer station. | 2020-02-15 | 2020-06-15 | 2020-06-15 |  | 4960354 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT01720 | Royse Switch: 138 kV Forney line terminal upgrade | City of Royce City, Rockwall County | Upgrade all terminal and associated equipment as a part of upgrading the Forney Switching Station Royse Switching Station 138 kV Line. | 2019-02-25 | 2019-12-23 | 2019-12-23 |  | 527217 | 571589.55 | 8.416% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT04308 | Screwbean Sub: Install Second Transformer and Two Feeders | City of Salt Flat, Hudspeth County | Install Screwbean Substation Transformer #2, one transformer and two feeder breakers | 2019-05-06 | 2019-12-18 | 2019-12-18 |  | 3504267 | 3842599.75 | 9.655% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
18T65019 | Seagoville Switch: Replace Seagoville Switch: Replace 345 kV bus and 138 kV bus protective relaying | City of Seagoville, Dallas County | Upgrade protective relaying at 345 kV and 138 kV Switching Stations. Replace failed Reactor on Reactor Bank #1 | 2019-04-08 | 2019-12-01 | 2019-12-01 |  | 1600000 | 1306389.08 | -18.35% | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
0PT38854 | Shin Oak 138 kV POD : Establish Point of Delivery | City of Wink, Winkler County | Establish a 138 kV POD for customer owned station on the Yucca Switch Moss Switch 138 kV Line. | 2019-11-04 | 2019-12-27 | 2019-12-27 |  | 614379 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04142 | Shipwreck Sub : Establish Substation with two Transformers and five Feeder Breakers | City of Odessa, Ector County | Establish Substation with two Transformers and five Feeder Breakers. Connect the Shipwreck 138 kV Substation to the McDonald Road Switch - Shipwreck Substation 138 kV Line, approximately 14 miles southwest of Garden City 69 kV Substation, and install three 138 kV sectionalizing switches | 2019-05-06 | 2019-12-31 | 2019-12-31 |  | 4600000 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T62062 | Springdale Sub - Upgrade bus and switches to 2000 A | City of Fort Worth, Tarrant County | Upgrade all line terminal and associated equipment. | 2019-01-07 | 2020-06-24 | 2020-06-24 |  | 412200 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04398 | Thorntonville Sub: Install one transformer and two Feeder | City of Monahans, Ward County | Establish substation by installing Transformer #1,one transformer, and two feeder breakers | 2019-08-05 | 2019-12-30 | 2019-12-30 |  | 4083202 | 3742189.25 | -8.352% | 100 | 138/69 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Final Actual Costs Reported. Project will be removed on next month's report.
18T65002 | TI Dallas Sub: Terminal upgrade for Coit Road line, (West Circuit) | City of Dallas, Dallas County | Upgrade all terminal and associated equipment as a part of upgrading the TI Dallas - Schroeder Road 138 kV double-circuit underground line section by replacing the existing HPFF underground conductor with two new XLPE underground conductors. | 2019-09-09 | 2020-04-22 | 2020-04-22 |  | 946042 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37764 | TI Dallas Sub : Terminal upgrade for Kirkland park line, (East Circuit) | City of Dallas, Dallas County | Upgrade all terminal and associated equipment as a part of upgrading the TI Dallas – Schroeder Road 138 kV double-circuit underground line section by adding two additional HPFF underground conductors. | 2020-01-30 | 2020-04-28 | 2020-04-28 |  | 605480 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04051 | Tri Corner Switch: 345 kV rung 4 addition | City of Seagoville, Dallas County | Install three 345 kV, 3200 A circuit breakers to create the Watermill Sw. Sta. to Trinidad 345 kV Line Terminal as a part of the reconductor of Tri Corner Switching Station. Watermill Switching Station. 345 kV line | 2019-01-30 | 2020-02-19 | 2020-02-19 |  | 2186397.78 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04054 | Trinidad Switch: Terminal upgrade | City of Trinidad, Henderson County | Upgrade line terminal as a part of the Tri Corner Switching Station. Watermill Switching Station. 345 kV line upgrade to 3200 A. and modify relaying for the new Tri Corner Sw Line terminal. | 2019-02-11 | 2020-02-14 | 2020-02-14 |  | 367680.82 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38928 | Turnbaugh Corner Switch: Establish 138 kV switching station | Odessa County | Establish a switching station with a 3-breaker 138 kV ring bus arrangement for a 138 kV POI for customers generator. | 2019-10-14 | 2020-05-16 | 2020-05-16 |  | 4172459 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03971 | Tyler Substation: Rebuild to 138 kV | City of Tyler, Smith County | Convert Tyler Sub to 138kV by replacing two transformers with two transformers and install one feeder breaker. | 2020-01-09 | 2020-06-26 | 2020-06-26 |  | 7116396 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
18T65023 | Venus Switch: Bus and auto relay upgrades | City of Venus, Ellis County | Upgrade North and South 345 kV bus protection and add three 345 kV circuit breakers. | 2019-08-21 | 2019-12-30 | 2019-12-30 |  | 2808705 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04099 | Vineyard (formerly Grapevine) Switch: Establish 138 kV Station | City of Grapevine, Tarrant County | Establish the Vineyard 138 kV Switch approximately 0.2 miles south of McKamy Tap by installing twelve 3200 A, 138 kV circuit breakers in a breaker-and-a-half arrangement. | 2019-08-29 | 2019-12-20 | 2019-12-20 |  | 10349114 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04053 | Watermill Switch: Line Terminal Upgrade and Replace 138 kV circuit breaker | City of Lancaster, Dallas County | Upgrade line terminal as a part of the reconductor of Tri Corner Switching Station -Watermill Switching Station 345 kV. Replace 138 kV circuit breaker. | 2019-02-11 | 2020-02-19 | 2020-02-19 |  | 720044 |  |  | 100 | 345/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39201 | West Network Sub-Rebuild station adjacent to existing station | City of Dallas, Dallas County | Rebuilding of West Network Substation includes replacing switchgear containing twelve feeder breakers and three transformers. | 2020-05-20 | 2021-04-01 |  |  | 16333958 |  |  | 24 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04289 | Weston Substation: Establish one substation transformer and two feeder breakers | City of McKinney, Dallas County | Establish one substation transformer and two feeder breakers | 2020-02-20 | 2020-12-01 |  |  | 4667449 |  |  | 90 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39591 | Willow Wells Sub: Install one transformer and two feeder breakers | Odessa County | Install one transformer and two feeder breakers | 2020-02-19 | 2020-06-16 | 2020-06-16 |  | 4096977 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38773 | Wolf Switch: Establish 345 kV three rung breaker and a half | City of Monahans, Ward County | Establish switching station by installing nine 345 kV circuit breakers in a three rung breaker and a half arrangement with two autotransformers and three 138 kV circuit breakers. | 2019-11-21 | 2020-07-02 | 2020-07-02 |  | 20150000 |  |  | 100 | 138 | 345/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38646 | Ray Roberts Switch : Establish Station for POI | City of Gainesville, Cooke County | Install a 138 kV (POI) Connect the Ray Roberts 138 kV Switch to the Gainesville Switch – Spring Switch (BEC) and install three circuit breakers | 2020-06-12 | 2020-11-13 |  |  | 4222333 |  |  | 78 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39579 | Hill Crest: Rebuild station to replace existing station with one transformer & three feeder breakers | City of Big Springs, Howard County | Rebuild station to replace the existing station with one transformer and three feeder breakers | 2020-01-15 | 2020-06-16 | 2020-06-16 |  | 2794508 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39819 | Dog House Switch : Establish 345kV Switching Station | City of Andrews, Andrews County | Establish the Dog House Switch that will provide a POI in Andrews County and the existing Clear Fork 345 kV Switch. | 2019-12-11 | 2020-06-01 | 2020-06-01 |  | 4929127 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38704 | Handley Switch : Bus Protection Upgrade | City of Fort Worth, Tarrant County | Replace 138 kV bus protection and install new 138 kV breaker and associated switches/CCVT's. | 2020-06-22 | 2020-12-15 |  |  | 1597389 |  |  | 40 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38948 | Ntusu Clearfork Switch : Establish 345 kV Line Terminal To Dog House | City of Andrews, Andrews County | Establish one 345 kV, 3000A circuit breaker at Clearfork Switch and all terminal and associated equipment. | 2019-10-31 | 2020-04-22 | 2020-04-22 |  | 2721164 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39269 | China Lake Sub : Establish Substation with one transformer and two feeder breakers | City of Pyote, Ward County | Establish substation with one transformer and two feeder breakers | 2020-02-26 | 2020-06-26 | 2020-06-26 |  | 4275296 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39945 | Decatur Switch : Demo 69 kV Station | City of Decatur, Wise County | Demolition of the 69 kV yard at Decatur. | 2019-09-09 | 2020-02-14 | 2020-02-14 |  | 449459 |  |  | 100 | 138/69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38585 | Howden POD : Provide A 138 kV (POD) | City of Big Springs, Howard County | Install motor operated SCADA control on three 138 kV 3200 A line sectionalizing switches and provide customer revenue metering as a part of installing a 138 kV (POD) on the Buzzard Draw – Gunsight 138 kV Line. | 2019-10-28 | 2019-12-27 | 2019-12-27 |  | 563897 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39746 | Allen Switch : Security Updates | City of Plano, Denton County | Security Updates | 2020-11-02 | 2020-12-15 |  |  | 1856896 |  |  | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39900 | Camp Pasture POD | City of Odessa, Ector County | Provide a 138 kV (POD) on the south circuit of the Spraberry Switch – Midessa South Switch/Odessa EHV Switch 138 kV Double-Circuit Line. Install motor operated SCADA control on three 138 kV 3200 A line sectionalizing switches, provide customer revenue metering. | 2020-04-04 | 2020-06-26 | 2020-06-26 |  | 580615 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39273 | Cedar Hill Sub: Install one transformer | City of Cedar Hill, Dallas County | Add second transformer, transformer #4, convert the distribution load and move away from transformer #1 and #2. | 2020-02-03 | 2020-06-29 | 2020-06-29 |  | 2161780 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04046 | Centerville I45 Sub: 138 kV Line Terminal Upgrade | City of Buffalo, Leon County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A as a part of the rebuild of the Crockett Switching Station - Jewett Switching Station 138 kV Line. | 2020-01-31 | 2020-05-28 | 2020-05-28 |  | 334820 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39416 | Cloverdale POD: Provide a (POD) | City of Midland, Midland County | Provide a 138 kV POD on the Midland East Spraberry Switch 138 kV Line. Install motor operated SCADA control on three 138 kV 2000 A line sectionalizing switches, and provide customer revenue metering. | 2020-05-07 | 2020-06-01 | 2020-06-01 |  | 800000 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
17T65011 | Dalworth Substation 138 kV line terminal upgrade | City of Arlington, Tarrant County | Upgrade all terminal and as a part of upgrading the Cedar Hill Sw. Sta. Liggett 138 kV line. Includes replacing high side switches on both transformers and adding FIDs to both transformers. | 2020-10-05 | 2020-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39275 | Dooley Sub : Replace one transformer | City of Monahans, Ward County | Rebuild existing Northward Sub with one transformer and establish new Dooley Sub with one transformer | 2020-04-05 | 2020-06-30 | 2020-06-30 |  | 3392399 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39272 | Edgecliff Sub : Install Second Transformer #4 with Two Feeder Breakers | City of Fort Worth, Tarrant County | Install Transformer #4 with two feeder breakers, rebuild the bus, upgrade station #3 bus to standard and relaying to Suburban IV. | 2020-09-15 | 2020-12-01 |  |  | 3949536 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39911 0PT40872 | Elbow Sub : Replace Transformer #1 with one transformer | City of Big Springs, Howard County | Replace Transformer #1 with one transformer | 2020-05-12 | 2020-06-29 | 2020-06-29 |  | 1462792 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Legacy Sharyland Project
0PT39466 | Gober Switch: Establish a switching station for a 138 kV POI | City of Gober, Fannin County | Install three 138 kV, 3200 A circuit breakers in a ring bus arrangement to establish a 138 kV (POI). Connect this switching station to the Bonham Wolf City 138 kV line section of the Valley Switch. | 2020-07-09 | 2020-12-17 |  |  | 4029773 |  |  | 44 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39759 | Hutto Switch : 345/138kV autotransformer #2 | City of Hutto, Williamson County | Install a new autotransformer, one 345 kV, 3200 A circuit breaker and two 138 kV, 3200 A circuit breakers at Hutto Switch. Install two 37.5 MVAR reactors on the tertiary of the new autotransformer. | 2020-01-16 | 2020-06-19 | 2020-06-19 |  | 4716132 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
17T65187 | Industrial Blvd Switching Station: 138 kV Cedar Crest Line Terminal Upgrade | City of Dallas, Dallas County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | 2018-05-07 | 2020-05-13 | 2020-05-13 |  | 277462 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39278 | Jack Rabbit Sub : Establish Substation with one Transformer, and three feeder Breakers | City of Odessa, Ector County | Establish Substation with one Transformer, and three feeder Breakers | 2019-12-12 | 2020-06-18 | 2020-06-18 |  | 3907085 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39895 | Kelton Windmill POD: Establish POD | City of Odessa, Ector County | Provide a 138 kV (POD) on the east circuit of the McKenzie Draw Switch – Midland County Northwest/Midland East Switch 138 kV Double-Circuit Line. Install motor operated SCADA control on three 138 kV 3200 A line sectionalizing switches, provide customer revenue metering. | 2020-03-30 | 2020-06-26 | 2020-06-26 |  | 535682 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39748 | Kennedale Sub : Establish substation with two transformers | City of Kennedale, Tarrant County | Establish substation by installing Bank #3 and Bank #4 with two transformers and four feeder breakers. This will be done by looping the Everman – Cleburne 138 kV Line into station. | 2020-04-08 | 2020-06-29 | 2020-06-29 |  | 4194465 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39486 | Lakecrest Sub (Fish Creek) : Establish Substation with one Transformer and Three Feeder Breaker | City of Grand Prairie, Dallas County | Establish Substation with one transformer and three feeder breakers | 2020-05-08 | 2020-12-01 |  |  | 4390668 |  |  | 69 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40696 | Lakewood Sub : Replace transformer #1 and #2 | City of Fort Worth, Tarrant County | Replace transformer #1 and #2 with Delta-Wye transformers due to transformer #2 failing and requiring replacement. | 2019-10-07 | 2020-04-14 | 2020-04-14 |  | 1393478 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39742 | Long Pasture POD | Not in City Limits, Ward County | Install motor operate Scada control on three 138 kV 3200A line sectionalizing switches, a 138kV circuit breaker for UVLS, and provide customer revenue metering as a part of installing a as a part of installing a 138 kV (POD) on the north circuit of the Wink Switch - Riverton Switch 138 kV Double-Circuit Line. | 2020-03-16 | 2020-04-20 | 2020-04-20 |  | 1053183 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40652 | Loring POI : Establish 138 kV POI | Clay County, TX | Install motor operated Scada control on three 138 kV 2000 A line sectionalizing switches as a part of installing a 138 kV POI located in the Commerce Sw. - Bonham Sw. 138kV line. | 2020-04-05 | 2020-09-30 |  |  | 527263 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04282 | Pauline Substation: Install one Transf. #2 and one 25kV Feeder | City of Mabank, Henderson County | Install one transformer #2 and One Feeder Breaker | 2020-08-26 | 2020-12-01 |  |  | 1968298 |  |  | 40 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT01087 | Salado South Substation: Establish Salado South Substation with one transformer and two feeder breakers | City of Salado, Bell County | Establish Salado South Substation with one transformer and two feeder breakers | 2020-04-27 | 2020-12-01 |  |  | 2665327 |  |  | 30 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT01906 | Scatter Branch Substation: Establish New Substation with One Transformer and Two 25 kV Feeder Breakers | City of Greenville, Hunt County | Establish New Substation with one transformer and Two 25 kV Feeder Breakers | 2020-06-12 | 2020-12-01 |  |  | 4173587 |  |  | 99 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40274 | Slager Lake POD : Provide a 138 kV (POD) | Reagan County | Install motor operate Scada control on three 138 kV 2000 A line sectionalizing switches as a part of installing a 138 kV POD on the Pemkiff-Ringo 138 kV Line. | 2020-04-13 | 2020-06-29 | 2020-06-29 |  | 588,514 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39694 | Vealmoor Switching Station: Install second autotransformer | City of Big Springs, Howard County | Upgrade the switch by installing a second auto transformer and re-configuring the switching station. Install a 4-breaker ring bus arrangement with four 345 kV, 3200 A circuit breakers. | 2019-10-01 | 2020-06-15 | 2020-06-15 |  | 25000000 |  |  | 100 | 345/138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | NTSU project
0PT40162 | Wink Switch : Install 138 kV circuit breaker | City of Wink, Winkler County | Install one 3200 A, 138 kV circuit breaker and reterminate the Wink Switch – Yucca Drive Switch 138 kV Line onto the fifth rung and terminate the new Wink Switch – Andrews County South Switch 138 kV Line on the fourth rung. | 2020-01-29 | 2020-06-16 | 2020-06-16 |  | 620365 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38701 | Woodard Switch : Establish Station for (POI) | City of Deport, Lamar County | Install a 345 kV (POI) at Woodard 345 kV Switch. Connect the Woodard 345 kV Switch to the Monticello Switch Paris Switch 345 kV line section. Install three 345 kV, 3200 A circuit breakers at Woodard 345 kV Switch. | 2020-02-12 | 2020-06-01 | 2020-06-01 |  | 7029097 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40476 | Adobe Meadows Sub : Replace oil circuit breaker (BZO) with FID | City of Midland, Midland County | Replace oil circuit breaker (BZO) with FID and install retrofit transformer protection panels. | 2020-09-21 | 2020-12-15 |  |  | 413082 |  |  | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04036 | Carmichael Bend Switch: Rebuild the existing Decordova Switching Station in a breaker-and-a-half bus arrangement. | City of Granbury, Hood County | Rebuild the existing Decordova 345/138 kV Sw. Sta. with a 12-breaker, 138 kV breaker-and-a-half bus arrangement, and a 5-breaker 345 kV breaker-and-a-half bus arrangement. | 2020-06-05 | 2020-12-31 |  |  | 23315000 |  |  | 11 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40694 | Comanche Peak Switch 138 kV: Replace relaying on Decordova terminal to Carmichael Bend | City of Glen Rose, Somervell County | Replace Relaying in the 138 kV Comanche Peak Control house for the Decordova bay to work with the new Carmichael Bend Switchyard. | 2020-09-21 | 2020-12-15 |  |  | 318031 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40227 | Gardendale Switch : Install a 345 kV point-of-interconnection (POI) | City of Andrews, Andrews County | Establish a three 345 kV, 3200 A circuit breakers ring bus to install a 345 kV(POI). The POI will be located on the Clearfork Switch Telephone Road Switch 345 kV Line. | 2020-04-23 | 2020-10-23 |  |  | 6166150 |  |  | 68 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40490 | Killeen Switch : Replace 138 kV circuit breakers | City of Killeen, Tarrant County | Replace 138 kV circuit breakers | 2020-01-10 | 2020-05-15 | 2020-05-15 |  | 433754 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40659 | Lenorah POD : Establish 138 kV POD | City of Lenorah, Martin County | Install Scada control on three 138 kV 2000 A line switches, two 138 kV 2000A isolation switches and one set of 138 kV revenue metering with associated structures and equipment as a part of establishing a 138 kV (POD) on the Grady Switch Brown Switch 138 kV Line. | 2020-04-07 | 2020-07-15 | 2020-07-15 |  | 1292715 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38868 | Monument Draw Sub: Establish substation with one transformer and two feeder breakers | City of Andrews, Andrews County | Establish substation with one transformer, two feeder breakers | 2020-03-27 | 2020-09-01 |  |  | 4227699 |  |  | 89 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04287 | Morris Dido Substation: Install one Transformer #2 and two Feeder Breakers | City of Fort Worth, Tarrant County | Install one transformer #2 with two Feeder Breakers | 2020-07-08 | 2020-12-01 |  |  | 1786931 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40871 0PT39915 | Blissard Sub: Establish one substation next to the existing Saint Lawrence Sub | City of Garden City, Glasscock County | Blissard Sub: Establish one substation next to the existing Saint Lawrence Sub. | 2020-03-19 | 2020-06-23 | 2020-06-23 |  | 3257919 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Legacy Sharyland Project
0PT40918 | Odessa EHV CREZ Switch : Security system installed | City of Odessa, Midland County | Security system installed | 2020-09-14 | 2020-12-15 |  |  | 1044061 |  |  | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40703 | Royse Switch: Replace the existing 138 kV fuseless capacitor banks with 110.4 Mvar | City of Royce City, Rockwall County | Remove capacitor Bank #1 that's connected to the North 138 kV Bus. Replace the existing 138 kV fuseless capacitor banks with 110.4 Mvar, 138 kV supervisory-controlled transmission capacitor banks on 138 kV south bus. Install three new FIDS for switching capacitors. | 2020-02-27 | 2020-06-01 | 2020-06-01 |  | 958638 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40357 | Sandow Switch : Install one bank of three 36.8 MVAR stages | City of Rockdale, Milam County | Install 110.4 Mvar of 138 kV capacitors consisting of three 36.8 MVAR stages that are voltage and supervisory controlled emergency. | 2020-03-03 | 2020-06-01 | 2020-06-01 |  | 1825926 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40874 | Grady Sub : Install one Transformer #2 with two Feeder Breakers | City of Lenorah, Martin County | Install one Transformer #2 with two Feeder Breakers. | 2020-02-19 | 2020-06-10 | 2020-06-10 |  | 1885509 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Legacy Sharyland Project
0PT40876 0PT39914 | Triangle Sub : Install one Transformer on #2 | City of Stanton, Martin County | Install a second transformer and remove transformers #1 and #2 at Stanton Substation. Complete installation of fiber for line protection, modify 138 kV bus protection to provide redundancy. | 2022-03-16 | 2022-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40943 | Stryker Creek Switch : Replace tertiary reactor on 345/138 kV Auto #1 | City of Lufkin, Angelina County | Replace tertiary reactor on 345/138 kV Auto #1 | 2020-01-15 | 2020-06-22 | 2020-06-22 |  | 702508 |  |  | 100 | 345/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39281 | Sulphur Springs East Sub : Install Second Transformer and Two Feeder Breakers | City of Sulphur Springs, Hopkins County | Install Second transformer with Two Feeder Breakers | 2020-08-07 | 2020-12-31 |  |  | 2643132 |  |  | 13 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04125 | Tri Corner Switch: Install three 345 kV, 3200 A circuit breakers to establish the Forney Switch - Elkton 345 kV Line Termination at Tri Corner Switch | City of Seagoville, Dallas County | Install three 345 kV, 3200 A circuit breakers and terminate the Forney Switch - Elkton Switch 345 kV Line at Tri Corner 345 kV Switch. | 2020-03-12 | 2020-05-22 | 2020-05-22 |  | 2727080 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40418 | Tunstill POD : Install SCADA controlled motor operators on existing switches | Reeves County | Install SCADA controlled motor operators on existing 138 kV line switches for Tunstill POD. | 2020-03-10 | 2020-05-14 | 2020-05-14 |  | 782247 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37353 | Tyler Northwest Sub: Remove the 138-69 kV Auto and demo the 138 kV bus at Tyler NW | City of Tyler, Smith County | Remove the 138/69kV Auto, remove the 69 kV Circuit Breaker, remove the associated relay panels and demo the 138kV bus at Tyler NW. Relocate the 138/69 kV auto to Tyler Switch. | 2020-09-01 | 2020-12-15 |  |  | 210000 |  |  | 0 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39292 | Tyler Southwest Sub : Install 2nd Transformer and two Feeder Breakers | City of Tyler, Smith County | Install second Transformer and two Feeder Breakers | 2020-07-27 | 2020-12-01 |  |  | 1238958 |  |  | 40 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03968 | Tyler Switch: Rebuild to a four(4) breaker 138 kV ring bus | City of Tyler, Smith County | Upgrade the existing station by installing four 2000 A or greater, 138 kV circuit breakers and associated equipment in a 4-breaker ring bus arrangement. Install one autotransformer and associated equipment. | 2020-06-01 | 2020-12-15 |  |  | 5592300 |  |  | 15 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03969 | Tyler West Sub: Retire 69 kV | City of Tyler, Smith County | After the completion of R6071 (Black Fork Sw. Sta. Tyler West Tyler Sw. Sta. 69 kV Line Conversion to 138 kV) and R6073 (Tyler Sw. Sta.) projects remove station. | 2020-08-20 | 2020-12-15 |  |  | 1017891 |  |  | 28 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39289 | Waxahachie Sub : Replace two Transformers with one upgraded Transformer and add 2 Feeder Breakers | City Azle, Tarrant County | Replace two Transformers with one upgraded Transformer and add 2 Feeder Breakers | [7 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40344 | Beals Creek (formerly Andrews Highway) Sub : Establish two transformers and three feeder breakers | City of Big Spring, Howard County | Establish substation with two transformers and three feeder breakers. | 2019-02-18 | 2020-06-29 | 2020-06-29 |  | 5919478 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39744 | Celeste Sub : Install FID and new control center for separation of the POI from TMPA | City of Sulphur Springs, Hopkins County | Install a FID and new control center complete with relaying protection for all Oncor owned equipment to establish plant separation at Celeste substation | 2020-03-24 | 2020-11-02 |  |  | 897899 |  |  | 40 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40489 | Comanche Switch : Replace 138 kV circuit breakers | City of Comanche, Comanche County | Replace two 138 kV circuit breakers | 2020-03-10 | 2020-06-12 | 2020-06-12 |  | 518143 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40487 | Elkton Switch : Replace 138 kV circuit breakers | City of Tyler, Smith County | Replace four 138 kV circuit breakers | 2020-03-01 | 2020-05-21 | 2020-05-21 |  | 814735 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03967 | Elkton Switch: Modify relaying for ring bus terminal at Tyler Switch | City of Tyler, Smith County | Modify relaying for ring bus terminal at Tyler Switch. | 2020-09-13 | 2020-12-15 |  |  | 79487 |  |  | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40497 | Graham 69 Switch : Replace 69 kV circuit breakers | City of Graham, Young County | Replace two 69 kV circuit breakers | 2020-03-25 | 2020-05-12 | 2020-05-12 |  | 267228 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40597 0PT40870 | Luther Sub : Install a second transformer and feeder breakers | City of Big Spring, Howard County | Install a second transformer and feeder breakers. Complete installation of fiber for line protection, modify 138 kV bus protection and add second battery | 2020-02-18 | 2020-05-29 | 2020-05-29 |  | 2350324 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40615 | Nelson Switch : Establish a 138 kV POI for Rodeo Solar Generator | City of Odessa, Ector County | Establish a 138 kV (POI) for Rodeo Solar Generator by installing one 138 kV, 3200 A circuit breaker in existing ring-bus. | 2020-09-02 | 2020-11-13 |  |  | 1240255 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40488 | Palestine South Switch : Replace 138 kV circuit breaker | City of Palestine, Anderson County | Replace 138 kV circuit breaker. | 2020-09-28 | 2020-12-15 |  |  | 253406 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40647 | Red Salt POD : Establish 138 kV POD | City of Big Spring, Howard County | Install three motor operated 138 kV 2000 A line sectionalizing switches as part of installing a 138 kV (POD) substation on the Brown - Grady 138 kV transmission line. | 2020-08-17 | 2020-11-15 |  |  | 752389 |  |  | 10 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40493 | Richardson East Sub: Replace 138 kV circuit breaker | City of Richardson, Dallas County | Replace two 138 kV circuit breaker . | 2020-09-14 | 2020-12-15 |  |  | 392583 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40926 | Sargent Road Switch : Install second transformer | City of Dallas, Dallas County | Install second autotransformer, one 3200 A circuit breakers. | 2020-03-13 | 2020-05-14 | 2020-05-14 |  | 2035196 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40484 | Temple Switch: Replace 69 kV and 138 kV circuit breakers | City of Temple, Bell County | Replace 69 kV and 138 kV circuit breakers. | 2020-09-09 | 2020-10-26 |  |  | 619777 |  |  | 0 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39045 | Arbala 138 kV Switch : Establish station for 138 kV POI for Solemio Solar Generator | City of Sulphur Springs, Hopkins County | Install a 138 kV POI for Solemio Solar Generator at Arbala 138 kV switch. Connect the Arbala 138 kV switch to the Sulphur Springs Switch- Commerce Switch 138 kV line section. | 2021-01-04 | 2021-05-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40335 | Cedar Elm Switch : Establish a 345 kV switching station for Era Wind Generator | City of Sanger, Fresno County | Establish switching station by installing three 345 kV, 5000 A circuit breakers in a ring bus arrangement for a 345 kV (POI) for the Era wind Wildcat Creek Wind Farm facility. | 2020-06-15 | 2020-11-13 |  |  | 7478024 |  |  | 14 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38349 | Copperhead Switch: Establish Station for (POI) for Phoenix Solar | City of Bonham, Fannin County | Install a 138 kV (POI) for Phoenix Solar Generator at Copperhead 138 kV Switch. Connect the Copperhead 138 kV Switch to the Bonham -Wolf City 138 kV line section of the Valley Switch-Commerce Switch 138 kV line. | 2020-07-01 | 2021-03-01 |  |  | 4209664 |  |  | 35 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41008 | Fairgrounds POD : Establish 138 B567 kV POD | City of Midland, Midland County | Install three motor operated Scada controlled 138 kV 3200 A line sectionalizing switches as part of installing two 138 kV (POD) | 2020-09-25 | 2020-11-14 |  |  | 822820 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40938 | Harry Hines Sub : Establish Substation with one transformer and a switchgear building with twelve circuit breakers for eight feeders | City of Dallas, Dallas County | Establish Substation with one transformer and a switchgear building with twelve circuit breakers for eight feeders. | 2020-08-28 | 2020-12-15 |  |  | 5583889 |  |  | 25 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41001 | Oceanic POD : Establish 138 kV POD | City of Big Springs, Howard County | Install three motor operated 138 kV 2000 A line sectionalizing switches as part of installing a 138 kV (POD) substation on the Brown - Grady 138 kV transmission line. | 2020-08-01 | 2020-10-31 |  |  | 742147 |  |  | 10 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40655 | Roadrunner (formerly Aspen) POD : Establish 138 kV Point of Interconnection | City of Odessa, Ector County | Install motor operate Scada control on three 138 kV 3200 A line sectionalizing switches, a 138 kV circuit breaker, and provide customer revenue metering as a part of installing a as a part of installing a 138 kV (POD). | 2020-08-31 | 2020-11-15 |  |  | 1347704 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41462 | Alkali Lake Sub : Replace transformers #1 & #2 | City of Stanton, Martin County | Replace transformers #1 & #2 | 2020-09-21 | 2020-12-15 |  |  | 2443568 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40614 | Culberson Switch : Install a new 3200 A, 138 kV circuit breaker in an existing ring bus for a POI for LCRA | City of Odessa, Ector County | Install a new 3200 A, 138 kV circuit breaker in an existing ring bus for a POI for LCRA. | 2020-08-28 | 2020-10-16 |  |  | 671330 |  |  | 28 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04152 | Farmers Branch Substation: Install bank #4 with one transformer and one circuit breaker | City of Dallas, Dallas County | Install bank #4 with one transformer and one circuit breaker. | 2020-02-22 | 2020-12-01 |  |  | 3326427 |  |  | 52 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41196 | Las Colinas Sub : Installation of piers for the stabilization of the station | City of Irving, Dallas County | Installation of piers for the stabilization of the station. | 2020-07-24 | 2020-12-01 |  |  | 750105 |  |  | 10 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40650 | Manning POD: Establish a 138 kV POD | City of Odessa, Ector County | Establish a 138 kV POD on the LCRA Crane East - Crane 138 kV line. | 2020-10-05 | 2021-03-08 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40412 | Nobles POD : Provide a 138 kV POD | City of Midland, Midland County | Establish Nobles POD for customer owned station, a 138 kV POD on the Midessa South - Midland Airport 138 kV line. | 2020-08-15 | 2020-11-15 |  |  | 857254.49 |  |  | 21 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41600 | Plano Texas Instrument Switch : Establish POD | City of Richardson, Dallas County | Install two 138 kV circuit breakers to establish a 138 kV POD on the Plano West Switch – Allen Switch and Plano West Switch – Richardson East Switch 138 kV lines. | 2020-04-05 | 2020-12-15 |  |  | 6129808 |  |  | 75 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41239 | Sandow Switch : Establish POD | City of Rockdale, Milam County | Disconnect circuit #3 from two breakers and reroute circuit #3 to two future breakers at Sandow 138 kV Switch. Terminate the Whinstone 138 kV point of interconnection. | 2020-02-25 | 2020-06-01 | 2020-06-01 |  | 480698 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
19T63016 | Scurry County South Switch: Add 138 kV line terminal for Canyon Wind | City of Snyder, Scurry County | Install a new 138 kV bay with two 138 kV, 3200 A circuit breakers and associated equipment to install a 138 kV POI for customer's generator. | 2021-03-25 | 2021-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41232 | Venus Switch : Dismantle and remove all out-of-service 138 kV switch-yard facilities due to establishment of Kemp Ranch Switch | City of Dallas, Dallas County | Dismantle and remove all out-of-service 138 kV switch-yard facilities due to establishment of Kemp Ranch Switch. | 2020-06-11 | 2020-08-31 |  |  | 692000 |  |  | 91 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39790 | Burleson Sub: Establish substation with a 4-breaker ring bus arrangement | City of Burleson, Tarrant County | Establish substation with a 4-breaker ring bus arrangement and remove the existing 138 kV capacitor bank from Burleson Substation. | 2020-10-26 | 2021-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41089 | Decordova Switch : Reconfigure the station to connect new 138 kV lines from Carmichael Bend Switch | Hood County | Reconfigure the station to connect new 138 kV lines from Carmichael Bend Switch to two circuit breakers. Auto will be stored in place and remove all other 138 kV breakers in the yard. | 2020-10-01 | 2020-12-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38516 | Fullerton Switch: Construct the third breaker-and-a-half rung of 138 kV circuit breakers | City of Andrews, Andrews County | Construct the third breaker-and-a-half rung of 138 kV circuit breakers. Terminal equipment minimum capability of 2000 A or greater. Remove the Fullerton 69 kV Substation. | 2020-09-15 | 2021-05-15 |  |  | 2400000 |  |  | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41110 | Horsehead Draw Sub : Add second transformer with two feeder breakers | City of Odessa, Ector County | Add second transformer with two feeder breakers | 2020-07-06 | 2020-11-01 |  |  | 2096238 |  |  | 67 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41497 | Jack Rabbit Sub : Install 2nd transformer with two feeder breakers | City of Odessa, Ector County | Install second transformer with two feeder breakers. | 2020-01-06 | 2020-12-15 |  |  | 2079653 |  |  | 86 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41542 | Midkiff Switch : Remove Midkiff 69 kV switch | City of Odessa, Upton County | Remove Midkiff 69 kV Switch | 2020-06-17 | 2020-08-28 |  |  | 505820 |  |  | 38 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38205 | Midkiff Switch: Install 138 kV circuit breaker | City of Odessa, Ector County | Install one 3200 A, 138 kV circuit breaker and close the normally open switch at Shipwreck Substation. | 2020-08-21 | 2020-12-15 |  |  | 1269711 |  |  | 10 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41509 | Renner Switch : Replace SVC 1 and SVC 2 Controls | City of Plano, Collin County | Upgrading control system. | 2020-03-16 | 2021-05-15 |  |  | 7983373 |  |  | 40 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41551 | Stanton Sub : Install a fourth transformer at Stanton Substation with a one transformer, remove transformers #1 and #2 at Stanton Substation and demo 69 kV wood structure | City of Stanton, Martin County | Install a fourth transformer at Stanton Substation with a one transformer, remove transformers #1 and #2 at Stanton Substation and demo 69 kV wood structure. | 2020-08-28 | 2020-12-15 |  |  | 2143550 |  |  | 28 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41988 | Shipwreck Sub : Terminate line from Midkiff | Reagan County | Terminate line from Midkiff. | 2020-08-23 | 2020-12-25 |  |  | 318217 |  |  | 65 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39282 | Poolville Sub : Establish Substation with one transformer and two feeder breakers | City of Weatherford, Parker County | Establish Substation with one transformer and two feeder breakers. | 2020-09-01 | 2020-12-01 |  |  | 4099718 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39502 | Elrod 345 kV Switch : Establish station with a 345 kV, 3 breaker ring bus station for POI | City of Corsicana, Navarro County | Establish station with a 345 kV, 3 breaker ring bus station for POI. | 2020-10-05 | 2021-04-21 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41313 | Quinlan Tap : Establish a radial line terminal by installing a one autotransformer with a 69 kV breaker | City of Royce City, Rockwall County | Establish a radial line terminal by installing a one autotransformer with a 69 kV breaker. | 2020-07-21 | 2021-05-15 |  |  | 2308995 |  |  | 10 | na | 138-69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40390 | Big Onion Switch : Establish station with 3-breaker, 345 kV ring-bus arrangement for POI | City of Ennis, Ellis County | Establish station with 3-breaker, 345 kV ring-bus arrangement for POI. | 2020-10-05 | 2021-04-21 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41798 | Double Mountain Switch : Install one 75 MVAR reactor | Lubbock County | Install one 75 MVAR reactor | 2021-03-15 | 2021-06-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41685 | Cottonfield Sub : Establish substation with transformer and two 25 kV feeder breakers | City of Stanton, Martin County | Establish substation with transformer and two 25 kV feeder breakers. | 2020-06-12 | 2020-12-31 |  |  | 4490269 |  |  | 35 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41537 | Valley 345 kV Switch : Replace 345 kV DFR | City of Savoy, Fannin | Replace 345 kV DFR | 2020-11-02 | 2020-11-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41799 | Fiddlewood Switch : Install one 75 MVAR reactor on the 345 kV south bus | Lubbock County | Install one 75 MVAR reactor on the 345 kV south bus | 2020-06-16 | 2021-06-15 |  |  | 2848009 |  |  | 16 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41309 | Wall Street Sub : Remove station #4 transformer and switchgear and install UG distribution bays for Station #3, and reconfigure 138 kV bus | City of Dallas, Dallas County | Remove station #4 transformer and switchgear and install UG distribution bays for Station #3, and reconfigure 138 kV bus. | 2020-08-31 | 2020-12-15 |  |  | 2000000 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40937 | Coyanosa Sub : Replace transformer #1 | City of Pecos, Reeves County | Replace transformer #1 | 2021-01-18 | 2021-05-15 |  |  | 3281351 |  |  | 0 | na | 138-69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41528 | TI Dallas Sub: Replace CB #012 | City of Dallas, Dallas County | Replace CB #012 | 2020-11-16 | 2020-12-30 | [5 empty] | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40479 | Armstrong Sub: Replace flash bus | City of Dallas, Dallas County | Replacing flash bus by installing three FIDS and retrofit transformer protection panels on three transformers. | 2020-11-01 | 2020-12-15 | [5 empty] | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41831 | China Grove Switch : Upgrade 138 kV bus protection and 138 kV/69 kV auto protection relaying | Mitchell County | China Grove Switch : Upgrade 138 kV bus protection and 138 kV/69 kV auto protection relaying | 2020-09-10 | 2020-12-15 |  |  | 2017975 |  |  | 0 | 69138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40648 | Dillon POD : Establish 138 kV POD | Martin County | Provide a 138 kV (POD) on the Andrews North McKenzie Draw 138 kV line by installing three138 kV 3200 A motor operated sectionalizing switches and low-voltage metering. | 2021-01-04 | 2021-03-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41776 | Dog House Switch: Install two 345 kV, 3200 A circuit breakers, POI | City of Andrews, Andrews County | Install two 345 kV, 3200 A circuit breakers POI, ensure all terminal and associated equipment meets or exceeds 3200 A. | 2021-01-11 | 2021-03-31 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40611 | Graham 345 kV Switch: Auto protection upgrade | Young County | Upgrade 138 kV/345 kV auto protection panels (2 panels total) and (1) Tertiary reactor panel. Modify 345 kV DC system to allow fully redundant DC sources. Add 345 kV bus CCVT's C & D buses. Replace 345 kV C&D house battery chargers with 35A. | 2020-10-14 | 2021-06-15 | [5 empty] | 0 | 138, 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40543 | Graham Plant Switch : Bus protection upgrade scope | Young County | Modify relaying to include installing two gen interconnection/separation schemes, and upgrade 138 kV Bus A&B protection. Add 138 kV bus CCVT's on A & B buses to provide backup for single-breaker line protection. | 2020-10-14 | 2021-06-15 | [5 empty] | 0 | 138, 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39271 | LTV Sub : Install breaker to relieve overloaded Grand Prairie feeders | City of Dallas, Dallas County | Install breaker to relieve overloaded Grand Prairie feeders. | 2020-06-29 | 2020-12-01 |  |  | 2536057.82 |  |  | 10 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40475 | North Breckenridge Sub : Replace FID | City of Breckenridge, Stephens County | Replace FID with new 1200A, 40kA S&C circuit switcher | 2020-09-14 | 2020-12-15 |  |  | 263417 |  |  | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41312 | Renner Sub: Replace one 138 kV cap bank relay panel | City of Plano, Denton County | Replace one 138 kV cap bank relay panel. | 2020-09-21 | 2020-12-15 |  |  | 338767 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41311 | Renner Switch : Replace two 138 kV cap bank relay panels | City of Plano, Denton County | Replace two 138 kV cap bank relay panels on two circuit breakers. | 2020-09-21 | 2020-12-15 |  |  | 573201 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41627 | Stouts Creek Switch : Establish Station for (POI) | Hopkins County | Establish station by installing three 345 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement for a (POI). Station will connect to the Allen Switch- Monticello Switch 345 kV line. | 2021-05-17 | 2021-11-01 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41535 | Temple Pecan Creek Switch : Replace the 138 kV and 345 kV DFR | City of Temple, Bell County | Replace the 138 kV and 345 kV DFR | 2020-11-01 | 2020-11-15 | [5 empty] | 0 | 138, 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41908 | Thirtysix Draw POD: Establish 138 kV POD | Glasscock County | Provide a 138 kV (POD) on the Spraberry Switch - McDonald Road Switch 138 kV line by installing three 138 kV 2000 A motor operated sectionalizing switches and low-voltage metering. | 2020-11-02 | 2021-03-30 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42420 | Tyler Grande Switch : Replace one failed circuit breaker | City of Tyler, Smith County | Replace one failed circuit breaker | 2020-05-04 | 2020-06-29 | 2020-06-29 |  | 479573 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(d) | Emergency Project
0PT39848 | Waco West Sub : Demo and retire station | City of Waco, McLennan County | Demo and retire station as part of rebuilding station at new location called Du Puy Substation | 2020-06-15 | 2020-10-15 |  |  | 391310 |  |  | 72 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41084 | Buckhorn Switch: Establish a 345 kV switching station for POI | City of Goldthwaite, Mills County | Establish switching station with a 3-Breaker ring bus. The POI will be located within Oncor's Brown Switch - Killeen Switch 345 kV double-circuit line. | 2020-10-12 | 2021-05-14 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41795 | Byrd Road 345 kV Switch: Establish 345 kV switch station in a 3-Breaker ring bus switchyard for POI | City of Electra, Wichita County | Establish a 345 kV switching station POI by installing three 345 kV, 3200 A circuit breakers in a ring bus. | 2021-01-04 | 2021-05-21 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41218 | Ennis West Switch: Install 138 kV circuit breakers | City of Ennis, Ellis County | Install 138 kV circuit breakers and re-terminate Oncor line terminals | 2021-01-05 | 2021-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40478 | Fairmont Sub : Replace flash bus by installing four FIDS and retrofit transformer protection panels | City of Dallas, Dallas County | Replace flash bus by installing four FIDS and retrofit transformer protection panels on all transformers | 2020-10-01 | 2020-12-15 | [5 empty] | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40687 | Loraine Sub: Decommission Substation | City of Sweetwater, Nolan County | Decommission substation | 2020-09-08 | 2020-12-15 |  |  | 313505 |  |  | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40995 | Quarry Field Switch: Establish 345 kV switching station | Loving County | Establish switching station with a 345 kV four rung breaker-and-a-half configuration with 5000 A two 345/138 kV autotransformers, four 138 kV circuit breakers and four 13.8 kV reactors. | 2020-07-01 | 2021-05-15 |  |  | 20740520 |  |  | 10 | na | 138, 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38759 | Redland Switch: Rebuild Herty North Switch with a 6-breaker 138 kV breaker-and-a-half bus arrangement | City of Lufkin, Angelina County | Rebuild Herty North Switch with a 6-breaker 138 kV breaker-and-a-half bus arrangement. | 2020-08-25 | 2021-05-15 |  |  | 8859445 |  |  | 3 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03989 | Welch Road Sub: Upgrade all line terminal and associated equipment to meet or exceed 3000 A | City of Dallas, Dallas County | Welch Road Sub: Upgrade all line terminal and associated equipment to meet or exceed 3000 A | 2021-03-08 | 2021-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39691 | Andrews North Sub: Establish a new 138 kV line terminal at Andrews North Substation | Andrews County | Establish a new 138 kV line terminal at Andrews North Substation as apart of converting the Fullerton Switch - Andrews North Line (East) to operate at 138 kV. | 2020-11-02 | 2021-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42588 | Burnett Switch Replace failed autotransformer #2 with a 138-69 kV autotransformer | City of Wichita Falls, Sedgwick County | Replace failed autotransformer #2 with a 138-69 kV autotransformer. | 2020-12-07 | 2021-05-14 | [5 empty] | 0 | na | 138-69 | na | na | na | na | na | na | na | 25.83(d) | Emergency project
0PT42130 | Irving Valley View Sub : Install transformer #4 with one transformer and two feeder breakers | City of Irving, Dallas County | Install transformer #4 with one 138/25 kV transformer and two feeder breakers. | 2020-11-02 | 2021-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42611 | Italy Sub : Replace the single-phase transformer with one three phase transformer and install 1 additional feeder breaker | City of Italy, Ellis County | Replace the single-phase transformer with one three phase transformer and install 1 additional feeder breaker. | 2020-10-05 | 2020-12-01 | [5 empty] | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42127 | John Day Sub : Install transformer #2 with a 138-25 kV | City of Fort Worth, Tarrant County | Install transformer #2 with a 138-12 kV. | 2020-11-02 | 2021-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41597 | Keller Wall Price 138 kV Sub: Replace the two existing capacitor banks | City of Keller, Tarrant County | Replace the two existing capacitor banks with two supervisory-controlled transmission capacitor banks. | 2021-01-18 | 2021-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38749 | Norwood Switch: Upgrade two 138 kV circuit breakers | City of Irving, Dallas County | Upgrade two 138 kV circuit breakers. | 2021-01-25 | 2021-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42333 | Saginaw Switch : Dismantle and retire station | City of Fort Worth, Tarrant County | Dismantle and retire station as a part of establishing Deen Switch station. | 2020-08-29 | 2021-05-15 |  |  | 844750 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42621 | Southlake Sub : Replace failed transformer #1 | City of Fort Worth, Tarrant County | Replace failed transformer #1, with spare transformer removed from Round Rock South. | 2020-06-06 | 2020-08-04 | 2020-08-04 |  | 1375866 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d) | Emergency project
0PT41249 | Thorn Tree Switch : Establish switching station to install a 345 kV for POI | City of Mount Vernon, Franklin County | Establish switch station in a 9-breaker 345 kV breaker-and-a-half arrangement. | 2020-11-16 | 2021-05-31 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42530 | Sweetwater Tap: Install motor operate Scada control on three 138 kV line sectionalizing switches | City of Sweetwater, Nolan County | Install motor operate Scada control on three 138 kV line sectionalizing switches and install trans-closure to replace the existing control house. | 2020-10-16 | 2020-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39690 | Means Sub: Convert the station from 69 kV to 138 kV | City of Andrews, Andrews County | Convert the station from 69 kV to 138 kV and connect to the Fullerton Switch - North Andrews 138 kV line (East). | 2020-11-02 | 2021-05-15 | [6 empty] | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42368 | Keystone Sub : Establish station by installing a one transformer with two feeder breakers | City of Odessa, Winkler County | Establish station by installing one transformer with two feeder breakers. | 2020-10-26 | 2021-04-01 | [6 empty] | na | 69/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03991 | Sorcey Road Sub: Upgrade line terminal and associated equipment | City of Dallas, Dallas County | Upgrade line terminal and associated equipment as a part of upgrading the Cedar Hill Sw. Sta. – Sorcey Road – Cedar Hill 138 kV line. | 2020-11-02 | 2021-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03992 | Cedar Hill Switch Sub: Upgrade line terminal and associated equipment | City of Cedar Hill, Dallas County | Upgrade line terminal and associated equipment as a part of upgrading the Cedar Hill Sw. Sta. – Sorcey Road – Cedar Hill 138 kV. | 2020-11-02 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42207 | Alcatraz Sub : Establish substation with two transformers and four feeder breakers | Loving County | Establish substation with two transformers and four OH feeder breakers. | 2021-01-04 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41719 | Elkton Switch: Upgrade all line terminal and associated equipment | City of Tyler, Smith County | Upgrade all line terminal and associated equipment as a part of rebuilding the 5.3-mile Tyler Switch - Elkton Switch 138 kV line | 2021-01-11 | 2021-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42121 | Midland West Sub : Install transformer #4 by adding one transformer and one feeder breaker with UG exit | City of Odessa, Midland County | Install transformer #4 by adding one transformer and one feeder breaker with UG exit. | 2021-02-01 | 2021-06-30 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42838 | Watermill Switch : Replace one overdutied 345 kV CB | City of Lancaster, Dallas County | Replace one overdutied 345 kV CB | 2021-03-01 | 2021-05-15 | [6 empty] | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41624 | Pebble Creek Switch: Establish 138 kV switching station | City of Red Oak, Ellis County | Establish 138 kV switching station for (POD) | 2021-01-25 | 2021-11-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42129 | Midnight Sub (Round Rock North): Establish two transformers and three 25 kV UG feeder breakers | City of Temple, Bell County | Establish two transformers and three feeder breakers. | 2020-11-02 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42134 | Loving Sub : Replace transformer #1 & #2 with two transformers and four feeder breakers with UG feeder exits | Loving County | Replace transformer #1 & #2 with two transformers and four feeder breakers with UG feeder exits. | 2021-01-18 | 2021-06-30 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39692 | Frankel City Sub : Convert station from 69 kV to 138 kV | City of Andrews, Andrews County | Convert station from 69 kV to 138 kV | 2021-03-15 | 2021-05-15 | [6 empty] | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42665 | Austin Ranch Sub : Establish a POI 138 kV for Brazos | City of The Colony, Denton County | Establish a 138 kV POI at Austin Ranch. Install two LS switches | 2021-04-05 | 2021-06-01 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42794 | Plano Shiloh Road Sub : Install a third transformer at Plano Shiloh Rd and three breakers | City of Plano, Collin County | Install a third transformer at Plano Shiloh Rd and three breakers | 2021-03-15 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42143 | Driver Sub : Install transformer #4 with one transformer and two feeders | City of Odessa, Midland County | Install transformer #2 with one transformer and two UG feeder breakers | 2021-01-04 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04147 | Riverview Sub : Establish one transformer and two feeder breakers | Ward County | Establish one transformer and two feeder breakers. | 2021-01-06 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03997 | Plano Coit Road Sub: Upgrade line terminal and associated equipment | City of Plano, Collin County | Upgrade line terminal and associated equipment as a part of upgrading the Renner Switch - Allen Switch/Plano Tennyson Switch 138 kV | 2021-03-08 | 2021-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03986 | Marsh Lane Switch: Upgrade all line terminal and associated equipment | City of Dallas, Dallas County | Upgrade all line terminal and associated equipment as a part of the rebuilding the Northaven Sw. Station - Morrison Lane Sw. Station 138 kV double-circuit line | 2021-04-12 | 2021-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42155 | Bulldog Sub : Install transformer #2 with one transformer and three feeder breakers | City of Big Springs, Howard County | Install transformer #2 with one transformer and three feeder breakers | 2021-01-18 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41447 | Toco Switch: Add a single line terminal to establish POI | City of Toco, Lamar County | Add a single line terminal to the existing ring-bus for the POI. | 2021-03-22 | 2021-05-20 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42145 | Canal Road Sub : Install transformer #2 with one transformer and two feeder breakers | City of Odessa, Winkler County | Install transformer #2 with one transformer and two feeder breakers | 2021-01-18 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42133 | Screwbean Sub : Replace transformer #1 with one transformer and two feeder breakers with UG feeder exits | City of Salt Flat, Hudspeth County | Replace transformer #1 with one transformer and two feeder breakers with UG feeder exits. | 2021-01-18 | 2021-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42240 | Thorntonville Sub : Install transformer #2 with one transformer with two feeder breakers | City of Monahans, Ward County | Install transformer #2 with one transformer with two feeder breakers. | 2021-02-01 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39291 | Frisco West Sub : Install transformer #2 with one transformer and two feeder breakers | City of Frisco, Collin County | Install transformer #2 with one transformer and two feeder breakers | 2021-01-18 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41783 | Andrews Switch : Remove & retire station as a part of Fullerton Switch - North Andrews Switch 138 kV Conversion East | Andrews County | Remove & retire station as a part of Fullerton Switch - North Andrews Switch 138 kV Conversion East | 2021-04-05 | 2021-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42139 | Celina Southeast Sub : Install transformer #2 with one transformer and two UG feeder breakers | City of Celina, Collin County | Install transformer #2 with one transformer and two 25 kV feeder breakers. | 2021-04-05 | 2021-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
CCN APPLICATIONS - APPROVED
13T80013 16T80061 | New Bethel 345 kV Loop Line | Anderson, Freestone, Navarro and Henderson Counties | This project is to construct the new double-circuit New Bethel 345 kV Line connecting the proposed New Bethel Switching station to a connection along one of four existing 345 kV transmission line segments in the region. | 2020-12-31 | 2022-12-31 |  | 26,499,000 (t-line) 7,232,000 (stations) |  |  |  | 0 | na | 345 | 27 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | na | na | 160 | 13.5 | 44672 | 13T80013 has been Canceled. Application Filed 7/10/2015. Administrative Approval received on 09/25/2015.
16T80079 0PT38665 0PT04007 0PT04008 0PT01664 | Riverton - Sand Lake 345 kV Line (Operating at 138 kV) | Reeves, Ward, and Loving Counties | Construct the new double-circuit capable Riverton - Sand Lake 345 kV Line connecting the proposed Riverton Switching Station to the proposed Sand Lake Switching Station. Initially, one circuit will be installed and operated at 138 kV. | 2019-01-17 | 2019-12-30 | 2019-12-30 | 47,483,000 (t-line) 8,750,000 (stations) | Line: 62,908,903 Station: 10,584,293 |  |  | 100 | na | 138 | 39.7 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | na | na | 160 | 39.7 | 47368 | Application Filed 7/21/2017. Final Order issued on 5/11/2018.
17T80077 0PT38181 0PT38182 0PT38179 0PT38178 0PT38426 19T63008 0PT38517 0PT38518 | Odessa EHV - Riverton and Moss - Riverton 345 kV Line | Crane, Ector, Loving, Reeves, Ward, and Winkler Counties | This project is to construct the new double-circuit 345 kV line connecting the Odessa EHV Switching Station and the Moss Switching Station to the Riverton Switching Station. | 2019-03-06 | 2020-12-30 |  | 199,729,000 (t-line) 23,832,000 (stations) | Line: 248,571,042 Station 18,840,070 |  |  | 80 | 345 | 345 | 216.7 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | 150 | 15.9 | 160 | 100.4 | 48095 | 17T80077 is a ROW Project Only and status is Proposed Cancel. Application Filed 3/16/2018. Final Order issued on 9/17/2018.
18T80036 0PT04001 0PT38840 0PT04013 (Portion) 0PT04138 (50%) | Horseshoe Springs - Owl Hills 138 kV Line | Culberson County | Construct the new single-circuit 138 kV line connecting the Horseshoe Springs Switching Station to Owl Hills Substation. | 2019-10-01 | 2020-02-11 | 2020-02-11 | 34,033,000 (t-line) 2,868,000 (stations) | Line: 39,923,135 Station 4,485,331 |  |  | 100 | na | 138 | 29.9 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 29.9 | 48544 | Application Filed 8/31/2018. Administrative Approval received on 11/20/2018.
0PT37302 0PT38601 0PT04138 (50%) | Owl Hills - Tunstill POD 138 kV Line | Culberson and Reeves Counties | Construct the new single-circuit 138 kV line connecting the proposed Owl Hills Substation to the Tunstill POD. | 2019-05-04 | 2020-09-30 |  | 20,628,000 (t-line) 1,847,000 (stations) | Line: 26,705,050 Station 3,100,331 |  |  | 86 | na | 138 | 18.7 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 18.7 | 48582 | OPT37302 - ROW Project Only. Application Filed 8/31/2018. Administrative Approval received on 11/20/2018.
17T80032 0PT04024 | Cogdell - Clairemont 138 kV Line | Kent and Scurry Counties | This project is to construct the new double-circuit 138 kV line connecting the Oncor existing Cogdell Substation to the Brazos Electric existing Clairemont Substation. One circuit will be installed initially. | 2019-04-17 | 2020-12-15 |  | 10,197,500 (t-line) na (stations) (Oncor Portion) | Line: 17,800,000 Station: na |  |  | 99 | na | 138 | 11.9 (Oncor Portion) | 959.6 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 11.9 (Oncor Portion) | 47808 | 17T80032 is a ROW Project Only. This is a joint project with Brazos Electric Power - only Oncor associated project costs are being reported. Application Filed 12/11/2017. Final Order issued on 1/18/2019.
0PT39679 0PT39819 0PT38948 | Clearfork - Dog House 345 kV Line | Andrews County | Construct the new 345 kV transmission line connecting the existing Clearfork Switchyard to the proposed Dog House Switchyard. | 2019-10-23 | 2020-06-01 | 2020-06-01 | 14,304,695 (t-line) 6,995,400 (stations) | Line: 14,104,673 Station 8,282,514 |  |  | 100 | na | 345 | 10.3 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | 175 | 10.3 | 48861 | Application Filed 11/28/2018. Administrative Approval received 2/6/2019. This is a NTU project.
NA | Stiles - Coates 138 kV Line | Reagan County | Construct the new 138 kV transmission line connecting the existing Stiles station to the proposed Coates station. | 2021-12-31 | 2023-12-31 |  | 9682000 |  |  |  | 0 | na | 138 | 8 | 959.6 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 100 | 8 | 46726 | Application Filed 1/17/2017. Final Order issued on 9/29/2017. This is a NTU project. No project number has been assigned yet.
0PT37182 0PT40453 0PT38505 0PT38427 | Sand Lake - Solstice 345 kV Line | Pecos, Reeves, and Ward Counties | This project is to construct the new double-circuit 345 kV line connecting the Oncor Sand Lake Switch to the AEP Texas Solstice Switch. | 2019-06-21 | 2020-12-15 |  | 49,110,000 (t-line) 17,600,000 (stations) (Oncor Portion) | Line: 68,869,754 Station: 22,523,721 |  |  | 34 | na | 345 | 89 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | na | na | 160 | 44.5 | 48785 | This is a joint project with AEP Texas - only Oncor associated project costs are being reported. Application Filed 11/7/2018. Final Order issued on 6/26/2019.
0PT38174 0PT40267 0PT04144 (50%) | Riverton - Kyle Ranch 138 kV Line | Loving and Reeves Counties | Construct the new single-circuit 138 kV line connecting the Riverton Switch station to the Kyle Ranch Substation. | 2020-06-08 | 2020-12-31 |  | 19,207,000 (t-line) 3,040,000 (stations) | Line: 20,690,623 Station: 3,106,711 |  |  | 35 | na | 138 | 15.2 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 15.2 | 49304 | Application Filed 3/28/2019. Administrative Approval received on 7/17/2019.
0PT38573 0PT38506 0PT38427 0PT38426 | Riverton - Sand Lake 345 kV Line Circuit Addition (Phase 2) | Reeves and Ward Counties | Add the second circuit on the vacant circuit position of the Riverton - Sand Lake 345 kV Line that will be operated at 345 kV. | 2019-06-21 | 2020-12-15 |  | 29,200,000 (t-line) 1,185,000 (station) | Line: 24,561,647 Station: 1,454,167 |  |  | 72 | 138 | 345 | 39.9 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | 160 | 39.9 | na | na | 49723 | Application Filed 7/19/2019. Administrative Approval received on 10/7/2019.
0PT38176 0PT04088 0PT04087 0PT04144 (50%) | Kyle Ranch - Quarry Field 138 kV Line | Loving County | Construct the new single-circuit 138 kV line connecting the Kyle Ranch Substation to the Quarry Field Switch station. | 2019-03-18 | 2021-05-15 |  | 16,832,000 (t-line) 15,855,000 (stations) | Line: Cost not available, line construction has not begun Station: 16,677,507 |  |  | 70 | na | 138 | 12.4 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 12.4 | 49302 | Application Filed 3/28/2019. Final Order issued on 3/2/2020.
18T65163 0PT38449 0PT04020 0PT04021 | Sargent Road - Oakland Ave. Tap 138 kV Line | Dallas County | Construct the new single-circuit 138 kV line connecting Sargent Road Switch to Oakland Avenue Tap installed completely within Oncor fee-owned property. | 2019-07-10 | 2020-12-15 |  | 4,940,000 (t-line) 1,375,000 (stations) | Line: 4,460,100 Station: 1,424,358 |  |  | 7 | na | 138 | 2.5 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 2.5 | na | 2.5 | 50217 | Application Filed 11/21/2019. Notice of approval issued on 3/4/2020.
0PT41156 0PT42396 0PT40679 0PT41331 0PT41511 0PT42120 | Johnson Draw POD - Salt Flat Road 138 kV Line | Midland County | Construct the new single-circuit 138 kV line connecting the Salt Flat Road Switch to the proposed Johnson Draw POD. | 11/30/2020 12/7/2020 11/2/2020 1/18/2021 | 3/1/2021 3/1/3021 3/1/2021 5/15/2021 |  | 5,257,000 (t-line) 1,461,000 (stations) |  |  |  | 0 | na | 138 | 2.8 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 2.8 | 50560 | Application Filed 3/5/2020.
CCN APPLICATIONS - PENDING
0PT39531 | Bearkat - Longshore 345 kV Line | Glasscock and Howard Counties | Construct the new single-circuit 345 kV line connecting the WETT Bearkat Switch to the Oncor Longshore Switch. | 2021-01-14 | 2022-03-31 |  | 29,339,500 (t-line) 1,700,000 (station) (Oncor Portion) |  |  |  | 0 | na | 345 | 30.8 | 1926.9 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 160 | 30.8 | 50410 | Application Filed 1/14/2020.
CCN APPLICATIONS - Oncor / LP&L: The following projects are being reported on behalf of Oncor and the City of Lubbock, by and through Lubbock Power & Light
0PT39835 0PT39844 0PT39623 0PT39631 0PT39632 (56.2%) | Ogallala - Abernathy 345 kV Line | Castro, Hale and Swisher Counties | Construct the new single-circuit 345 kV line connecting the existing Ogallala station to the existing Abernathy station. This project is part of the LP&L integration into the ERCOT system. | 1/15/2020 | 2021-06-15 |  | 87,876,048 (t-line) 8,304,600 (stations) | Line: 88,807,431 Station: 9,122,137 |  |  | 26 | na | 345 | 57.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 57.9 | 48625 | Application Filed 9/6/2018. Final Order issued on 9/26/2019. Originally filed under the NTU predecessor report.
0PT39896 0PT40341 0PT39625 0PT41983 0PT39632 (25.7%) 0PT39633 (55.3%) | Abernathy - Wadsworth 345 kV Line | Hale and Lubbock Counties | Construct the new single-circuit 345 kV line connecting the existing Abernathy station to the existing Wadsworth station. This project is part of the LP&L integration into the ERCOT system. | 1/15/2020 | 6/15/2021 |  | 56,736,759 (t-line) 9,403,700 (stations) | Line: 56,702,358 Station: 9,557,334 |  |  | 46 | na | 345 | 32.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 32.9 | 48668 | Application Filed 9/20/2018. Final Order issued on 10/14/19. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39845 0PT41440 0PT41442 0PT39634 0PT39635 0PT39628 0PT39626 0PT41832 0PT39633 (44.7%) | Wadsworth - New Oliver - Farmland 345 kV Line (WNF) | Lubbock and Lynn Counties | Construct the new single-circuit 345 kV line connecting the existing Wadsworth station to the existing Farmland station, routed through one of two options for the proposed New Oliver station. This project is part of the LP&L integration into the ERCOT system. | 2020-03-24 | 2021-06-15 |  | 67,769,000 (t-line) 20,638,000 (stations) | Line: 77,538,361 Station: 23,403,675 |  |  | 23 | na | 345 | 41.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 41.9 | 48909 | Application Filed 12/19/2018. Originally filed under the NTU predecessor report. Final Order issued on 1/23/20. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39845 0PT41452 0PT39732 0PT39967 0PT39629 0PT39630 | Southeast - New Oliver - Oliver 115 kV Line (SNO) | Lubbock County | Construct the new single-circuit 115 kV line connecting the existing Southeast station to the existing Oliver station, routed through one of two options for the proposed New Oliver station. This project is part of the LP&L integration into the ERCOT system. | 2020-05-27 | 2021-06-15 |  | 20,688,000 (t-line) 31,248,000 (stations) | Line: 21,452,317 Station: 27,949,110 |  |  | 3 | na | 115 | 17.8 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | 60 | 17.8 |  | Application Filed 12/19/2018. Originally filed under the NTU predecessor report. Final Order issued on 1/23/20. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39846 0PT41891 0PT39637 0PT39968 0PT39636 0PT41986 0PT39632 (18.1%) | Abernathy - North - North Loop 345/115 kV Line | Hale and Lubbock Counties | Construct the new transmission line connecting the existing Abernathy station to the northern portion of LP&L's planned 115 kV loop line, routed through one of three options for the proposed North station. Depending on which North station is used, this line will be either a single-circuit 345 kV line or a combination of single-circuit 345 kV and double-circuit 115 kV line. This project is part of the LP&L integration into the ERCOT system. | 2020-01-15 | 2021-06-15 |  | 39,782,000 (t-line) 33,367,000 (stations) | Line: 44,361,677 Station: 20,274,578 |  |  | 33 | na | 345/115 | 34.3 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers (345 kV) Steel Poles (115 kV) | na | na | 175 (345 kV) 60 (115 kV) | 24.6 | 49151 | Application Filed 2/19/2019. Final Order issued on 3/12/2020. Originally filed under the NTU predecessor report.

## EntryInstructions
General Instructions for Entering Information
1. Please use "na" whenever appropriate to reduce ambiguity, except in the "Costs," "Percent Complete," and "Percent Variance" columns. 2. Any new or revised entry must be entered using a red font and highlighted in yellow. In the month following the red font entry, change the previous month's red entries back to black and make any new entries for the new month in red. This aids PUCT staff in quickly identifying any changes from the previous month's report. 3. On the final monthly report on an existing line in which one of the attributes as listed in the attribute spreadsheets below has changed, enter that data in a bolded green font.
Utility's Project Number | Enter the Utility's Project Number. No duplicate numbers are allowed in this column.
Project Name | Enter the name of the project. If possible, use the same name as was reported to ERCOT in any reports.
Location (City/County) | Enter the names of the counties where the project is located. Also enter the names of cities, if appropriate. Please delineate all county and city names with commas only. (e.g., Liberty, Chambers, Anahuac, etc.)
Description | Describe the project in enough detail to allow the Commission to ensure that the work does not require a CCN, if the utility does not intend to apply for a CCN. Include any significant or relevant detail not being reported in other columns. Do not include Point of Delivery and add periods to all sentences.
Estimated (or Actual) Start Date | Enter the estimated project starting date. When construction begins, please replace the estimated date with the actual date of the start of construction
Finish Date (Construction Complete) | Enter the date (mm/dd/yy) when the construction related to the project has been completed.
Date Energized (If Applicable) | Enter the date (mm/dd/yy) the project was energized or restored to service (if applicable).
Initial Estimated Project Cost | CCN Projects Only: Enter the estimated cost from the CCN application. When reporting both T-Line and Substation Costs, enter them separately in the same cell. (e.g., "$3,946,000 T-Line; $1,768,000 Substation") This number shall not be changed in future months unless the Application is amended. Please DO NOT use links to other sheets within the workbook. Non-CCN Projects Only: No entry is needed; Enter the estimated cost in the
Final Estimated Project Cost | CCN Projects: Enter the latest available estimated cost for the month that construction starts. This number shall not be changed after construction begins. and a cost variance explanation is not required unless requested by PUC Staff For Non-CCN Projects: Enter the initial estimated cost. Estimate revisions are not necessary
Final Actual Project Cost | Enter the actual, final project cost after the project has been energized and all costs have been recorded. Omit the project from all following reports.
% Variance | The cells contain a formula for calculating the percent variance of the final actual cost with respect to the final estimated cost. This is essentially a calculation of the percent of the cost over-run or under-run. Please do not change these cells.
Percent Complete | State the construction progress of the project as a percent. Please use only an integer and do not write"%." Do not report the percent of money spent.
Existing Voltage | Enter the nominal system existing voltage, if any. In the event of a voltage upgrade, this will be the "before" voltage. If the project is for a new line, enter "na." For projects involving multiple voltages, please delineate the voltages by a comma, (e.g., "69,138"). Please do not write "volts."
Upgraded or New Voltage | Enter the nominal system voltage after upgrading or if new line construction is involved. Please use the same practices described in the "Existing Voltage" column. Please do not write "volts."
Circuit Length (Miles) | Enter the total circuit length. Example: For a new double-circuit line using 10 miles of new ROW, the circuit length would be 20 miles. Please enter only a number, if possible. Please do not write "miles."
Conductor Type & Size & Bundling | Describe the conductor characteristics, including whether double or single circuit or mixed. Lengthy explanations shall be made in the Project Description column. (Format should be Quantity - Conductor Size and Type). Do not include quotations for supplier given code words or the word bundled.
Structure Type(s) | Describe structure types and materials used.
Existing ROW Width (Feet) | Enter width of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Entries such as "60,80,100" or "60 - 100" or "centerline" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
Existing ROW Length (Miles) | Enter length of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Make detailed explanations, if needed, elsewhere. Please do not write "miles."
New ROW Width (Feet) | Enter width of new ROW. The entry type is unrestricted. Entries such as "60,80,100" or "60 - 100" or "centerline" or "railroad" or "street" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
New ROW Length (Miles) | Enter new (additional) ROW length, in miles. Please do not write "miles."
Rule Section or PUC Control Number | Enter the PUC Substantive Rule 25.101 section(s) which are applicable. For multiple section applicability, please delineate by commas, e.g., "25.101(c)(5)(A), 25.101(c)(5)(B)" for a project incorporating a line extension (A) and a voltage upgrade on the existing line which is being extended (B). If the project involves a CCN Application, enter ONLY the .5-digit control number. Please do not write "docket," "CCN" or other text, except when needed in citing Rule 25.101. Should the project include work done under both CCN and 25.101(c)(5), follow the same practices and delineate with commas.
Comments | Enter information not included elsewhere, including reimbursed costs. A cost variance explanation is no longer required for non-CCN projects. However, utilities will be required to submit a Cost Analysis only for CCN Projects. See Note below.
139510
0PT39030 SB |  | City of Tyler, Bell County

## 16T80061 & 16T64136
Project No. 16T80061 & 16T64136 - New Bethel 345 kV Loop Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1963) | Estimated cost once a route is approved and CCN granted (Route 1963) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2952000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 601000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 2959000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8324000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 11663000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 26499000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 26499000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | N/A | N/A
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 499000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3341000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 338000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2467000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 6645000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 587000 | Costs not yet available | Costs not yet available
Estimated Project Total | 7232000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 33731000
139510
0PT39030 SB |  | City of Tyler, Bell County

## 16T80079 & 0PT04007
Project No. 16T80079 & 0PT04007 & 0PT38665- Riverton - Sand Lake 345 kV Line - Transmission Line Project (Operating at 138 kV)
| Estimated cost included in CCN Application (Route 56) | Estimated cost once a route is approved and CCN granted (Route 54) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4781000 | 8230416 | Costs not yet available
Engineering and Design (Utility) | 1773000 | 976563 | Costs not yet available
Engineering and Design (Contract) | 1987000 | 1621845 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 14486000 | 20013049 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 24456000 | 32067030 | Costs not yet available
Estimated Total Cost | 47483000 | 62908903 | Costs not yet available
Other (all costs not included in the above categories) |  | 0 | Costs not yet available
Estimated Project Total | 47483000 | 62908903 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 500000 | 501523 | Costs not yet available | USE
Procurement of Material & Equipment (including Stores) | 4000000 | 3521325 | Costs not yet available
Construction of Facilities (Utility) | 100000 | 323791 | Costs not yet available
Construction of Facilities (Contract) | 4150000 | 2888255 | Costs not yet available
Estimated Total Cost |  |  | Costs not yet available
Other (all costs not included in the above categories) | 0 | 3349399 | Costs not yet available
Estimated Project Total | 8750000 | 10584293 | Costs not yet available
Reported on Monthly Construction Report | 56233000 | 73493196
139510
0PT39030 SB |  | City of Tyler, Bell County

## 17T80077
Project No. 17T80077, 0PT38181, 0PT38182, 0PT38179, 0PT38178, 0PT38426, 19T63008, 0PT38517, 0PT38518 - Odessa EHV - Riverton and Moss - Riverton 345 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1180) | Estimated cost once a route is approved and CCN granted (Route 1180) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 21540000 | 29205738 | Costs not yet available
Engineering and Design (Utility) | 5322000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2269000 | 2877377 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 74495000 | 76498142 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 96103000 | 103610002 | Costs not yet available
Estimated Total Cost | 199729000 | 212191259 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 36379783 | Costs not yet available
Estimated Project Total | 199729000 | 248571042 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 245000 | 166800 | Costs not yet available
Engineering and Design (Contract) | 922857 | 908706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 15969607 | 9781320 | Costs not yet available
Construction of Facilities (Utility) | 2270494 | 479109 | Costs not yet available
Construction of Facilities (Contract) | 4424042 | 5436125 | Costs not yet available
Estimated Total Cost | 23832000 | 0 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 2068010 | Costs not yet available
Estimated Project Total | 23832000 | 18840070 | Costs not yet available
Reported on Monthly Construction Report | 223561000 | 267411112
139510
0PT39030 SB |  | City of Tyler, Bell County

## 18T80036
Project No. 18T80036, 0PT04001, 0PT38840, 0PT0413 (Portion of WA),0PT04138 (50% of WA) - Horseshoe Springs - Owl Hills 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 508) | Estimated cost once a route is approved and CCN granted (Route 508) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2827000 | 3272874 | Costs not yet available
Engineering and Design (Utility) | 970000 | 2474576 | Costs not yet available
Engineering and Design (Contract) | 1402000 | 2739308 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 9019000 | 13818723 | Costs not yet available
Construction of Facilities (Utility) | 0 | 34819 | Costs not yet available
Construction of Facilities (Contract) | 19815000 | 17582835 | Costs not yet available
Estimated Total Cost | 34033000 | 39923135 | Costs not yet available
Other (all costs not included in the above categories) |  |  | Costs not yet available
Estimated Project Total | 34033000 | 39923135 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 90000 | 0 | Costs not yet available
Engineering and Design (Contract) | 80000 | 94300.66 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1752000 | 2464654.45 | Costs not yet available
Construction of Facilities (Utility) | 226500 | 403438.41 | Costs not yet available
Construction of Facilities (Contract) | 602000 | 1368937.48 | Costs not yet available
Estimated Total Cost | 2750500 | 4331331 | Costs not yet available
Other (all costs not included in the above categories) | 117500 | 154000 | Costs not yet available
Estimated Project Total | 2868000 | 4485331 | Costs not yet available
Reported on Monthly Construction Report | 36901000 | 44408466
139510
0PT39030 SB |  | City of Tyler, Bell County

## 17T80032
Project No. 17T80032 & 0PT04024 - Cogdell - Clairemont 138 kV Line - Transmission Line Project
*THIS IS A JOINT PROJECT WITH BRAZOS ELECTRIC POWER - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 125) | Estimated cost once a route is approved and CCN granted (Route 39) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1226000 | 1400000 | Costs not yet available
Engineering and Design (Utility) | 378500 | 900000 | Costs not yet available
Engineering and Design (Contract) | 438000 | 900000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2930000 | 3925000 | Costs not yet available
Construction of Facilities (Utility) | 0 | 1685000 | Costs not yet available
Construction of Facilities (Contract) | 5225000 | 8990000 | Costs not yet available
Estimated Total Cost | 10197500 | 17800000 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 10197500 | 17800000 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | N/A | N/A | N/A
Engineering and Design (Utility) | N/A | N/A | N/A
Engineering and Design (Contract) | N/A | N/A | N/A
Procurement of Material & Equipment (including Stores) | N/A | N/A | N/A
Construction of Facilities (Utility) | N/A | N/A | N/A
Construction of Facilities (Contract) | N/A | N/A | N/A
Estimated Total Cost | N/A | N/A | N/A
Other (all costs not included in the above categories) | N/A | N/A | N/A
Estimated Project Total | N/A | N/A | N/A
Reported on Monthly Construction Report | 10197500 | 17800000
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37302
Project No. OPT37302, 0PT38601 - Owl Hills - Tunstill POD 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 15) | Estimated cost once a route is approved and CCN granted (Route 15) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1769000 | 3498658 | Costs not yet available
Engineering and Design (Utility) | 607000 | 0 | Costs not yet available
Engineering and Design (Contract) | 830000 | 3505474 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5734000 | 8210994 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 11688000 | 11489924 | Costs not yet available
Estimated Total Cost | 20628000 | 26705050 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 20628000 | 26705050 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | N/A | N/A
Engineering and Design (Utility) | 90000 | 0 | Costs not yet available
Engineering and Design (Contract) | 0 | 14301 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1250000 | 1862654.45 | Costs not yet available
Construction of Facilities (Utility) | 155000 | 309438.41 | Costs not yet available
Construction of Facilities (Contract) | 352000 | 913937.48 | Costs not yet available
Estimated Total Cost | 1847000 | 3100331.34 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 1847000 | 3100331.34 | Costs not yet available
Reported on Monthly Construction Report | 22475000 | 29805381.34
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37182
Project No. 0PT37182, 0PT40453, OPT38505, 0PT38427- Sand Lake - Solstice 345 kV Line - Transmission Line Project
*THIS IS A JOINT PROJECT WITH AEP TEXAS - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 320) | Estimated cost once a route is approved and CCN granted (Route XX) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4561500 | 10686669 | Costs not yet available
Engineering and Design (Utility) | 1058500 | 694256 | Costs not yet available
Engineering and Design (Contract) | 1348000 | 1105909 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 16793500 | 13285278 | Costs not yet available
Construction of Facilities (Utility) | 500 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25348000 | 38847631 | Costs not yet available
Estimated Total Cost | 49110000 | 64619743 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 4250011 | Costs not yet available
Estimated Project Total | 49110000 | 68869754 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 400000 | 444635 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13200000 | 17005560 | Costs not yet available
Construction of Facilities (Utility) | 1210000 | 1065160 | Costs not yet available
Construction of Facilities (Contract) | 2026000 | 4008366 | Costs not yet available
Estimated Total Cost | 16836000 | 22523721 | Costs not yet available
Other (all costs not included in the above categories) | 764000 | 0 | Costs not yet available
Estimated Project Total | 17600000 | 22523721 | Costs not yet available
Reported on Monthly Construction Report | 66710000 | 91393475
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT38174
Project No. 0PT38174 ,0PT40267 & 0PT04144 - Riverton - Kyle Ranch 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 7) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1694000 | 1852123 | Costs not yet available
Engineering and Design (Utility) | 517000 | 1258500 | Costs not yet available
Engineering and Design (Contract) | 876000 | 1300000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4866000 | 7416500 | Costs not yet available
Construction of Facilities (Utility) | 0 | 708500 | Costs not yet available
Construction of Facilities (Contract) | 11254000 | 8155000 | Costs not yet available
Estimated Total Cost | 19207000 | 20690623 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 19207000 | 20690623 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 70000 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 115906.71 | Costs not yet available
Engineering and Design (Contract) | 200000 | 13288.25 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1900000 | 1852954.57 | Costs not yet available
Construction of Facilities (Utility) | 120000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 750000 | 1124561.47 | Costs not yet available
Estimated Total Cost | 3040000 | 3106711 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 3040000 | 3106711 | Costs not yet available
Reported on Monthly Construction Report | 22247000 | 23797334
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT38176
Project No. 0PT38176, 0PT04088, 0PT04087, 0PT04144 - Kyle Ranch - Quarry Field 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 11) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1382000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 422000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 834000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4424000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 9770000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 16832000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 16832000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 2270000 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 300000 | Costs not yet available
Engineering and Design (Contract) | 500000 | 390782 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 7700000 | 7837492 | Costs not yet available
Construction of Facilities (Utility) | 585000 | 2363273 | Costs not yet available
Construction of Facilities (Contract) | 4800000 | 5766660 | Costs not yet available
Estimated Total Cost | 15855000 | 16658207 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 19300 | Costs not yet available
Estimated Project Total | 15855000 | 16677507 | Costs not yet available
Reported on Monthly Construction Report | 32687000 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39679
Project No. 0PT39679, 0PT39819, 0PT38948 - Clear Fork - Dog House Line - NTU Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost once a route is approved and CCN granted | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1051381 | 1051381 | Costs not yet available
Engineering and Design (Utility) | 32509 | 0 | Costs not yet available
Engineering and Design (Contract) | 632401 | 641000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 7237942 | 5723710 | Costs not yet available
Construction of Facilities (Utility) | 97793 |  | Costs not yet available
Construction of Facilities (Contract) | 5169697 | 5618865 | Costs not yet available
Estimated Total Cost | 14221723 | 13034956 | Costs not yet available
Other (all costs not included in the above categories) | 82972 | 1069717 | Costs not yet available
Estimated Project Total | 14304695 | 14104673 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 10400 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 3195 | Costs not yet available
Engineering and Design (Contract) | 724600 | 132129 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3217100 | 685666 | Costs not yet available
Construction of Facilities (Utility) | 0 | 3364336 | Costs not yet available
Construction of Facilities (Contract) | 3043300 | 3413805 | Costs not yet available
Estimated Total Cost | 6995400 | 7599131 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 683383 | Costs not yet available
Estimated Project Total | 6995400 | 8282514 | Costs not yet available
Reported on Monthly Construction Report | 21300095 | 22387187
139510
0PT39030 SB |  | City of Tyler, Bell County

## NA
Project No. NA - Stiles - Coates 138 kV Line - NTU Transmission Line Project
| Estimated cost included in CCN Application (Route B4) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3347000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 249000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 733000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2070000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 222000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2915000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 9536000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 146000 | Costs not yet available | Costs not yet available
Estimated Project Total | 9682000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 161000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 84000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 893000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4376000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 432000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2780000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 8726000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 8726000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 18408000 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39835
Project No. 0PT39835, 0PT39623, 0PT39631, 0PT39632 - Ogallala - Abernathy 345 kV Line - NTU Transmission Line Project (Dkt. 48625)
| Estimated cost included in CCN Application (Route 4) | Estimated cost once a route is approved and CCN granted (Route 4a) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 13575702 | 14502458.3192 | Costs not yet available
Engineering and Design (Utility) | 165760 | 186171.1163 | Costs not yet available
Engineering and Design (Contract) | 3430680 | 3126596.9787 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 35371142 | 33506760.9081 | Costs not yet available
Construction of Facilities (Utility) | 356601 | 0 | Costs not yet available
Construction of Facilities (Contract) | 34795274 | 37485443.6777 | Costs not yet available
Estimated Total Cost | 87695159 | 88807431 | Costs not yet available
Other (all costs not included in the above categories) | 180889 | 0 | Costs not yet available
Estimated Project Total | 87876048 | 88807431 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 507200 | 441197.96 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4883800 | 4431568.67 | Costs not yet available
Construction of Facilities (Utility) | 0 | 302334.32 | Costs not yet available
Construction of Facilities (Contract) | 2913600 | 3947036.33 | Costs not yet available
Estimated Total Cost | 8304600 | 9122137.28 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 8304600 | 9122137.28 | Costs not yet available
Reported on Monthly Construction Report | 96180648 | 97929568.28
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39896
Project No. 0PT39896 - Abernathy - Wadsworth 345 kV Line - NTU Transmission Line Project (Dkt. 48668)
| Estimated cost included in CCN Application (Route 1) | Estimated cost once a route is approved and CCN granted (Route 1) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 7979470 | 9543014.7112 | Costs not yet available
Engineering and Design (Utility) | 110471 | 150723.6435 | Costs not yet available
Engineering and Design (Contract) | 1917538 | 1785293.9269 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 21275928 | 19474125.3795 | Costs not yet available
Construction of Facilities (Utility) | 202943 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25127504 | 25749200.3389 | Costs not yet available
Estimated Total Cost | 56613854 | 56702358 | Costs not yet available
Other (all costs not included in the above categories) | 122905 | 0 | Costs not yet available
Estimated Project Total | 56736759 | 56702358 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 605500 | 359797 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5266900 | 4710275.06 | Costs not yet available
Construction of Facilities (Utility) | 0 | 236755.19 | Costs not yet available
Construction of Facilities (Contract) | 3531300 | 4250506.42 | Costs not yet available
Estimated Total Cost | 9403700 | 9557333.67 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 9403700 | 9557333.67 | Costs not yet available
Reported on Monthly Construction Report | 66140459 | 66259691.67

## 0PT39845
Project No. 0PT39845 - Wadsworth - New Oliver - Farmland 345 kV Line (WNF) and Southeast - New Oliver - Oliver 115 kV Line (SNO) - NTU Transmission Line Projects (Dkt. 48909)
| Wadworth - New Oliver - Farmland 345 kV Line |  |  |  | Southeast - New Oliver - Oliver 115 kV Line
| Estimated cost included in CCN Application (Route 20) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete |  | Estimated cost included in CCN Application (Route 9) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs: |  | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 8257000 | 11775886.9771 | Costs not yet available | Right-of-Way and Land Acquisition | 4471000 | 5164970.0609 | Costs not yet available
Engineering and Design (Utility) | 117000 | 178363.3316 | Costs not yet available | Engineering and Design (Utility) | 120000 | 62760.5556 | Costs not yet available
Engineering and Design (Contract) | 2794000 | 3791870.5499 | Costs not yet available | Engineering and Design (Contract) | 1530000 | 1649065.0706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 27393000 | 27464811.7198 | Costs not yet available | Procurement of Material & Equipment (including Stores) | 4298000 | 5126788.2332
Construction of Facilities (Utility) | 314000 | 0 | Costs not yet available | Construction of Facilities (Utility) | 216000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 28726000 | 34327428.4216 | Costs not yet available | Construction of Facilities (Contract) | 9921000 | 9448733.0797 | Costs not yet available
Estimated Total Cost | 67601000 | 77538361 | Costs not yet available | Estimated Total Cost | 20556000 | 21452317 | Costs not yet available
Other (all costs not included in the above categories) | 168000 | 0 | Costs not yet available | Other (all costs not included in the above categories) | 132000 | 0 | Costs not yet available
Estimated Project Total | 67769000 | 77538361 | Costs not yet available | Estimated Project Total | 20688000 | 21452317 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities |  | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 564000 | 611576.8 | Costs not yet available | Right-of-Way and Land Acquisition | 0 | 152894.2 | Costs not yet available
Engineering and Design (Utility) | 0 | 21830.19 | Costs not yet available | Engineering and Design (Utility) | 105000 | 27328.31 | Costs not yet available
Engineering and Design (Contract) | 1617000 | 1000798.39 | Costs not yet available | Engineering and Design (Contract) | 1075000 | 635862.34 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 10517000 | 10394558.73 | Costs not yet available | Procurement of Material & Equipment (including Stores) | 25465000 | 21705484.59 | Costs not yet available
Construction of Facilities (Utility) | 0 | 497613.72 | Costs not yet available | Construction of Facilities (Utility) | 170000 | 523401.98 | Costs not yet available
Construction of Facilities (Contract) | 7940000 | 10877297.09 | Costs not yet available | Construction of Facilities (Contract) | 4433000 | 4904138.78 | Costs not yet available
Estimated Total Cost | 20638000 | 23403674.92 | Costs not yet available | Estimated Total Cost | 31248000 | 27949110.2 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 20638000 | 23403674.92 | Costs not yet available | Estimated Project Total | 31248000 | 27949110.2 | Costs not yet available
Reported on Monthly Construction Report | 88407000 | 100942035.92 | Costs not yet available | Reported on Monthly Construction Report | 51936000 | 49401427.2 | Costs not yet available

## 0PT39846
Project No. 0PT39846 - Abernathy - North - North Loop 345/115 kV Line - NTU Transmission Line Project (Dkt. 49151)
| Estimated cost included in CCN Application (Route 25) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4871000 | 8342781.3539 | Costs not yet available
Engineering and Design (Utility) | 237000 | 95753.4343 | Costs not yet available
Engineering and Design (Contract) | 2720000 | 1799694.4634 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13414000 | 14554335.7083 | Costs not yet available
Construction of Facilities (Utility) | 230000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 18124000 | 19569112.0401 | Costs not yet available
Estimated Total Cost | 39596000 | 44361677 | Costs not yet available
Other (all costs not included in the above categories) | 186000 | 0 | Costs not yet available
Estimated Project Total | 39782000 | 44361677 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 300000 | Costs not yet available
Engineering and Design (Utility) | 115000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2141000 | 610437.2 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 21621000 | 13689359.68 | Costs not yet available
Construction of Facilities (Utility) | 150000 | 506821.26 | Costs not yet available
Construction of Facilities (Contract) | 9340000 | 5167959.8 | Costs not yet available
Estimated Total Cost | 33367000 | 20274577.94 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 33367000 | 20274577.94 | Costs not yet available
Reported on Monthly Construction Report | 73149000 | 64636254.94

## 0PT38573
Project No. 0PT38573, 0PT38506, 0PT38427, 0PT38426 - Riverton - Sand Lake 345 kV Line Circuit Addition - Transmission Line Project (Phase 2)
| Estimated cost included in CCN Application | Estimated cost once a route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 0 | 648304 | Costs not yet available
Engineering and Design (Utility) | 1400000 | 281000 | Costs not yet available
Engineering and Design (Contract) | 1900000 | 485000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 12500000 | 11332089 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 13400000 | 11815254 | Costs not yet available
Estimated Total Cost | 29200000 | 24561647 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 29200000 | 24561647 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 155000 | 82677 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 665000 | 785964 | Costs not yet available
Construction of Facilities (Utility) | 78000 | 140876 | Costs not yet available
Construction of Facilities (Contract) | 287000 | 414784 | Costs not yet available
Estimated Total Cost |  | 1424301 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 29866 | Costs not yet available
Estimated Project Total | 1185000 | 1454167 | Costs not yet available
Reported on Monthly Construction Report | 30385000 | 26015814 | Costs not yet available

## 18T65163
Project No. 18T65163, 0PT04021, 0PT38449, 0PT04020 - Sargent Road - Oakland Ave. Tap 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 0 | 35000 | Costs not yet available
Engineering and Design (Utility) | 80000 | 100000 | Costs not yet available
Engineering and Design (Contract) | 440000 | 270000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 750000 | 670100 | Costs not yet available
Construction of Facilities (Utility) | 170000 | 220000 | Costs not yet available
Construction of Facilities (Contract) | 3500000 | 3165000 | Costs not yet available
Estimated Total Cost | 4940000 | 4460100 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 4940000 | 4460100 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 120000 | 0 | Costs not yet available
Engineering and Design (Contract) | 195000 | 331882 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 610000 | 595572 | Costs not yet available
Construction of Facilities (Utility) | 130000 | 153277 | Costs not yet available
Construction of Facilities (Contract) | 320000 | 343627 | Costs not yet available
Estimated Total Cost | 1375000 | 1424358 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 1375000 | 1424358 | Costs not yet available
Reported on Monthly Construction Report | 6315000 | 5884458

## 0PT39531
Project No. 0PT39531 - Bearkat (WETT) - Longshore 345 kV Line Transmission Line Project
*THIS IS A JOINT PROJECT WITH WETT - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 102) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3125500 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 771500 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1170000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8803500 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 15469000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 29339500 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 29339500 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | Costs not yet available | N/A
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 150000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 810000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 60000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 390000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 1410000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 290000 | Costs not yet available | Costs not yet available
Estimated Project Total | 1700000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 31039500 | Costs not yet available | Costs not yet available

## 0PT41156
Project No. 0PT41156 - Johnson Draw POD - Salt Flat Road Switch 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 62000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 50000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 795000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1600000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 150000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2600000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 5257000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 5257000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 1000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 210000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 610000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 170000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 470000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 1461000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 1461000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 6718000 | Costs not yet available