## MCPR Nov. 2020
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | MCPR Row Number | Project Manager
1010656 | Blumenthal TL Addition (CCN) | Gillespie, Kendall, Blanco | Construct a new 138-kV transmission line connecting the new Blumenthal (CTEC) Substation to a tap point on the Kendall - Mountain Top 138-kV transmission line (T342). | 2017-10-02 08:00 | 2018-05-18 | 2018-05-18 | T-Line $18.9 - 32.9M; Substation $3.3 - 4.2M; Tap Point $1.4 - 3.2M |  |  |  | 100 | 0 | 138 | 14.4 | 3x1-795 ACSR "Drake" | Poles & H-Frames | 0 | 0 | 100 | 14.4 | 43599 | 12/4/15 PUC Approved Route 16; approved route cost estimate in CCN application for transmission line $21.5M; substation 3.9M; tap-point $1.6M | 2 | Bo Beauregard
1015208 | Zorn - Marion TL Addition (CCN) | Guadalupe | Construct a new 345-kV transmission line to provide a transmission point of interconnection between Central Texas and San Antonio area. | 2018-06-01 08:00 | 2019-05-30 | 2019-05-30 | T-Line $46.8 - 62M; existing substation work $7.9M |  |  |  | 100 | 0 | 345 | 20.33 | 3x2-959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7-11 | Varies; 40 - 200 | 20.34 | 45601 | 9/15/16 PUC Approved Route 10M; approved route cost estimate in CCN application for transmission line $46.8M. | 4 | Thuanny Anderson
1014910 | TXDOT US 83 Relief Route Rio Grande City-La Grulla (T485) | Starr | Modify existing transmission line (T485), Rio Grande City-La Grulla, to accommodate road expansion by TXDOT. | 2018-11-09 | 2018-11-30 | 2018-11-30 |  | 266000 |  |  | 100 | 138 | 138 | 31.66 | 3x1-795 ACSR/AW "Drake/AW" | Steel Poles | Varies | 31.6 | n/a | n/a | 25.101 (C)(5)(B) |  | 5 | Ellie Ross
1014352 | Leander - Round Rock TL Addition (CCN) | Williamson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to two load-serving substations | 2019-01-02 | 2020-06-04 | 2020-06-04 | T-Line $49 - 81.6M; Substations $ 7M - 10.1M |  |  |  | 100 | 0 | 138 | 14.22 | 3x2- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 60 - 100 | 11-22 | 45866 | 6/6/17 PUC Approved Route LHO-1; approved route cost estimate in CCN application for transmission line $57.6M; substation 1 - $9M; substation 2 - $7M | 7 | Michael Griswold
1017026 | Manor - Cedar Hills TL Addition (T495) Phase 1 (Flood Remediation Substation Upgrade – 1016539) | Travis | Remove (structure #112) concrete pole and replace with two concrete poles. | 2017-07-05 | 2017-10-28 | 2017-10-19 |  | 215000 | 214250 | -0.3488% | 100 | 138 | 138 | 8.21 | 3x1-795 ACSR "Drake" | Concrete Poles, Steel Poles & Lattice Tower | 100 | 8.21 | n/a | n/a | 25.101(C)(5)(B) |  | 16 | Brian Good
1017998 | Hamilton Road - Uvalde Fiber Addition (T570), (T624) & (T464) | Val Verde, Kinney, Uvalde | Replace 25 structures to support new OPGW | 2018-01-29 | 2019-03-10 | 2019-03-10 |  | 10792000 |  |  | 100 | 138 | 138 | 70.6 | 3x1-ACSS "Drake" | Steel Poles | Varies | 70.6 | n/a | n/a | 25.101 (C)(5)(B) |  | 27 | Brian Good
1017838 | Kendall - Fredericksburg TL Fiber Build Out (T120) | Kendall, Gillespie | Replace static arm on 70 H-frame structures, install 1 new steel dead-end pole, and install 2 new guyed wood h-frames to support new OPGW | 2018-04-16 08:00 | 2018-06-28 17:00 | 2018-06-19 |  | 1334000 | 1338292.86 | 0.3218% | 100 | 138 | 138 | 20.55 | 3x1- 795 ACSR "Drake" | Wood H-Frames, Single Pole Wood DE | Centerline | 20.55 | n/a | n/a | 25.101 (C)(5)(B) |  | 28 | Tony Rhodes
1015116 | Henne - Comal TL Upgrade (T235) | Comal | Rebuild the existing 138kV transmission line (T235) with new structures and conductor. | 2018-01-10 | 2019-05-15 | 2019-05-15 |  | 15417000 | 13775549.11 | -10.65% | 100 | 138 | 138 | 7.51 | 3x1- 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 7.51 | n/a | n/a | 25.101 (C)(5)(B) |  | 33 | Bo Beauregard
1017347 | Mendoza - Colton-Elroy (T397) | Caldwell, Travis | Add circuit breakers at Colton Substation. Add OPGW to (T397) Mendoza - Colton - Elroy. Replace structures that are currently not capable of supporting OPGW. | 2018-02-08 17:00 | 2018-05-18 | 2018-05-18 |  | 10285000 | 9874071.83 | -3.995% | 100 | 138 | 138 | 12.9 | 3x1- 795 ACSR "Drake" | Concrete Poles, Steel Poles and Wood H-frames | Varies | 12.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 34 | Bo Beauregard
1017387 | Harwood - Luling Double Circuit TL OH Phase 1(T145)(173) ; Luling - Waelder TL Add Phase 2 (T145) | Caldwell, Gonzales | Replace 45 double-circuit lattice tower structures with double circuit steel Poles and add OPGW on (T145/T173) Harwood-Luling and Luling-Waelder | 2018-02-26 | 2019-05-14 | Phase 1: 6/29/2018 Phase 2: 5/14/2019 |  | 9951000 | 9311536.68 | -6.426% | 100 | 138 | 138 | Phase 1 -12.9; Phase 2 - 21.85 | Phase 1 - 3x2- 795 ACSR "Drake"; Phase 2 Drake 795 ACSR & 26/7 & Single | Concrete Poles, Steel Poles & Wood H-frames | 100; Centerline | Phase 1-19.4 ; Phase 2 - 21.85 | n/a | n/a | 25.101 (C)(5)(B) |  | 35 | Brian Good
1017859 | Clear Springs - Marion TL Addition (419) | Guadalupe | Replace 3 double-circuit lattice tower structures with 3 CREZ F5 lattice dead-end tower structures, Install OPGW, Repair 1 cage/arm member at Structure #88, Install new bundled Drake between new spans between A-Frames and new Towers and between #108A & #108B. | 2018-02-15 08:00 | 2018-11-18 | 2018-11-18 |  | 3206000 | 3210184.39 | 0.1305% | 100 | 345 | 345 | 8.5 | 3x2- 795 ACSR "Drake" | Steel Lattice | 100; Centerline | 8.5 | n/a | n/a | 25.101(C)(5)(B) |  | 37 | Tony Rhodes
1017856 | San Marcos - Kyle Fiber Build-Out (T322) | Hays | Add OPGW from San Marcos to Canyon | 2018-03-19 | 2018-05-18 | 2018-05-18 |  | 1153000 | 1155618.98 | 0.2271% | 100 | 138 | 138 | 3.46 | 2x1- 795 ACSR "Drake" | Steel Poles, Concrete Poles | Varies | 3.46 | n/a | n/a | 25.101 (C)(5)(B) |  | 42 | Tony Rhodes
1017403 | Sim Gideon - Smithville TL Storm Hardening - (T150) | Bastrop | Increase the reliability of transmission facilities on the Sim Gideon – Smithville 13.8-le 138-kV transmission line (T150). | 2018-07-17 | 2019-03-18 | 2019-03-18 |  | 3845000 | 3220637.44 | -16.24% | 100 | 138 | 138 | 13.8 | 795 ACSR Drake | Steel Poles & Hybrid Poles | 80 | 13.8 | n/a | n/a | 25.101 (C)(5)(B) |  | 46 | Vicki O'Connor
1017854 | Fairland - Lago Vista TL Addition (T414) | Travis, Burnett | OPGW add and Tower replacements | 7/15/18 | 2019-03-27 | 2019-03-27 |  | 7756000 | 7805151.64 | 0.6337% | 100 | 138 | 138 | 21.38 | 795 CONDOR ACSR/SD | Lattice Towers & Steel Poles | 100; Centerline | 21.38 | n/a | n/a | 25.101 (C)(5)(B) |  | 47 | Tony Rhodes
1017348 | Cooks Point TL Addition (CCN) | Burleson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2020-07-01 | 2021-05-06 |  | T-Line $ 26.5 - 34.1M; Substation $ 6.1 - 6.7M |  |  |  | 10 | 0 | 138 | 17-23 | 2x1- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 80 | 17-23 | 45838 | 6/17/19 - PUC Approved Route 12; approved route cost estimate in CCN application for transmission line $29M; substation $6.2M | 48 | Manny Garcia
1016356 | Bellville S - Glidden TL Addition (T113) (Bellville S-Glidden TL Storm Hardening - 1016355) | Austin County/Colorado | Replace 11 lattice tangent tower structures with steel pole structures to meet storm hardening requirements; the existing rating of the transmission circuit will be maintained at 110 MVA. | 2018-08-23 | 2019-09-20 | 2019-09-20 |  | 10029000 |  |  | 100 | 69 | 69 | 31.24 | Existing: (1)795 ACSR “Drake” New: Bellville-Str 26 (1)959 ACSS “Suwannee” and Str.27-Glidden (1)795 ACSR “Drake” | Bellville-Str.26 Concrete H-Frame and Steel DE Str. 27-Glidden Steel DE, Lattice Towers, and concrete tangents | 120 | 31.24 | 120 | 31.24 | 25.101 (C)(5)(B) |  | 49 | Thuanny Anderson
1017847 | Coronado - Fairland TL Addition (T110) (LCRA TSC Fiber Build-Out FY18-1017418) | Burnet/Llano | OPGW is being installed and multiple structures are being replaced or repaired to support the added fiber as part of the FY18 Fiber Build Out program. | 2018-08-29 | 2019-05-24 | 2019-05-24 |  | 5769000 | 5622926.76 | -2.532% | 100 | 138 | 138 | 12.41 | 795 ACSR CONDOR, 795 ACSR Drake, 72 CT OPGW | Steel lattice, & steel Poles | Varies | 12.41 | n/a | n/a | 25.101 (C)(5)(B) |  | 50 | Tony Rhodes
1017842 | Gillespie - Horseshoe Bay TL Addition (T448) (LCRA TSC Fiber Build-Out FY18-1017418) | Gillespie/Llano | OPGW is being installed and multiple structures are being replaced or repaired to support the added fiber as part of the FY18 Fiber Build Out program. | 2018-08-01 | 2019-11-30 | 2019-05-13 |  | 8660000 | 8661662.13 | 0.01919% | 100 | 138 | 138 | 36.43 | 795 ACSR Drake, 72 Ct OPGW | Steel lattice | Varies | 36.43 | n/a | n/a | 25.101 (C)(5)(B) |  | 51 | Tony Rhodes
1017658 | Burnet - Wirtz TL Overhaul (T218) (Burnet-Wirtz TL Overhaul - 1017657) | Burnet | Structure replacement and add OPGW | 2019-01-04 | 2019-12-20 | 2019-12-20 |  | 4526000 | 4717157.26 | 4.224% | 100 | 138 | 138 | 16.4 | 795 ACSR Drake | Steel & Wood Poles | Varies | 16.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 52 | Christopher Grimes
1016322 | Bellville South - Waller TL Storm Hardening (T213) (Bellville South - Waller TL Storm Hardening - 1016321) | Austin/Waller | Increase reliability and capacity of transmission facilities on Bellville South to Waller | 2018-09-04 | 2019-06-21 | 2019-06-28 |  | 32129000 |  |  | 100 | 138 | 138 | 15.77 | 795 ACSR Drake | Concrete & steel Poles | Varies; 85 | 15.77 | n/a | n/a | 25.101 (C)(5)(B) |  | 53 | Alfred Mackey
1018931 | Flatonia - Moulton South TL Addition (T134) (Shiner Circuit Breaker Addition - 1017402) | Lavaca | Increase transmission service reliability to the Shiner Substation | 2018-10-09 | 2019-02-11 | 2019-02-11 |  | 80000 | 95297.94 | 19.12% | 100 | 138 | 138 | 11.1 | 795 ACSR Drake | Concrete/Steel Poles | 30; 40; 45; 60; 100 | 11.1 | n/a | n/a | 25.101 (C)(5)(A) |  | 55 | Vaibhav Pitale
1017830 | North McCamey – LCRA Crane TL Addition (T455) [King Mountain Circuit Breaker Addition 1017391] | Upton | Install three circuit breakers, provide real-time monitoring at King Mountain Substation. | 2018-10-01 | 2019-06-28 | 2019-05-10 |  | 847000 |  |  | 100 | 138 | 138 | 23.08 | (2) 795 kcl ACSR "Drake" | Concrete & steel monopoles | Centerline; 80 | 23.08 | n/a | n/a | 25.101 (C)(5)(A) |  | 56 | Dave Ilges
1017513 | Airline - Naval Base TL Addition (T475) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-09-24 | 2019-09-30 | 2019-09-30 |  | 993000 |  |  | 100 | 69 | 138 | 6.39 | (1) 795kcl ACSR/AW "Drake" | Steel Monopole | Centerline; 16' | 6.39 | n/a | n/a | 25.101 (C)(5)(D) |  | 57 | Ellie Ross
1017515 | Airline - Naval Base TL Addition (T476) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-03-28 | 2019-04-16 | 2019-04-16 |  | 331000 |  |  | 100 | 69 | 138 | 7.98 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 7.98 | n/a | n/a | 25.101 (C)(5)(D) |  | 58 | Ellie Ross
1018756 | Heines - Naval Base TL Addition (T685) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. (Once Heines Substation Addition is complete, the transmission assets on (T476) will be renumbered to T685 Heines - Naval Base) | 2018-10-03 | 2020-05-07 | 2020-05-07 |  | 894000 |  |  | 100 | 69 | 138 | 5.3 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 5.3 | n/a | n/a | 25.101 (C)(5)(A) |  | 59 | Josh Bollich
1018755 | Airline - Heines TL Addition (T476) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. | 2018-10-11 | 2020-05-07 | 2020-05-07 |  | 994000 |  |  | 100 | 69 | 138 | 2.57 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 2.57 | n/a | n/a | 25.101 (C)(5)(A) |  | 60 | Josh Bollich
1018663 | RioPecos - HorseCrossing TL Addition (T451/ future T682) | Crane | Provide transmission service to a generator. (This circuit will be added to the open position on the structures on the (T451) Rio Pecos - Crane, after the project is complete the transmission line will be numbered T682 Rio Pecos - Horse Crossing) | 2021-01-08 17:00 | 2021-03-09 17:00 |  |  | 1038000 |  |  | 0 | 0 | 138 | 0.76 | (2) 795 ACSR Drake | Steel/Concrete Monopoles | 80; Centerline | 0.76 | n/a | n/a | 25.101 (C)(5)(C) |  | 61 | Josh Bollich
1019260 | Winchester - Salem T170 TL Addition (T170) (Winchester Autotransformer Addition - 1017413) | Fayette | Install new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-03-25 | 2020-03-25 17:00 |  | 2287000 |  |  | 100 | 138 | 138 | 37.28 | (1) 795 kcl ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100; Centerline | 37.16 | n/a | n/a | 25.101 (C)(5)(A) |  | 62 | Jack Sandel
1017777 | Winchester - Fayetteville TL Addition (T165) (Winchester Autotransformer Addition - 1017413) | Fayette | Install new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-03-26 17:00 | 2020-03-26 17:00 |  | 2535000 |  |  | 100 | 138 | 138 | 18.92 | (1) 795 kcl ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100; Centerline | 18.75 | n/a | n/a | 25.101 (C)(5)(A) |  | 63 | Jack Sandel
1017495 | Brenham North - Waller TL Addition (T232) (Flood Mitigation - FY2018 System Upgrade 1017378) | Waller, Washington | Reduce flood risk and potential damage to substation equipment | 2019-09-23 | 2019-11-07 | 2019-11-07 |  | 4076000 | 3565494 | -12.52% | 100 | 138 | 138 | 12.94 | 795 Drake ACSR & 630.0 TYPE 21 ACCS/TW/C7 (BETWEEN #17/1 TO #18/1) | Concrete Poles, Wood H-frame, Steel H-frame | 75 @ single circuit; 85 @ double circuit | 12.94 | 75 @ single circuit; 85 @ double circuit | 12.94 | 25.101 (C)(5)(B) |  | 65 | Brian Good
1019038 | Plum - La Grange TL Addition (T208) (Riverside Circuit Breaker Addition - 1018925) | Fayette | Increase the reliability of substation equipment at the Riverside Substation. | 2019-01-28 | 2020-12-30 | 2020-10-20 |  | 1873000 |  |  | 99 | 138 | 138 | 8.39 | 795 ACSR. GA2 Drake. 3/8 EHS. OPGW | Wood H-frame | Undefined Centerline | 5.58 | Undefined Centerline | 5.58 | 25.101 (C)(5)(B) |  | 66 | Tyreeta Young
1019276 | Harwood - Gonzales (T542) (Gonzales - Harwood TL Overhaul - 1018965) | Gonzales | Increase the reliability and capability of circuit (T542) on Cuero – Luling 53.9-les of 69-kV transmission line for the 10 les between City of Gonzales (S31) & Harwood Station (S397). | 2019-04-01 | 2019-10-31 | 2019-10-25 |  | 7029000 |  |  | 100 | 69 | 69 (138kV Capable) | 9.97 | Single 795 ACSR "Drake" | Concrete & Steel Pole | Blanket, Centerline | 9.97 | n/a | n/a | 25.101 (C)(5)(B) |  | 67 | Amir Toor
1017695 | North McCamey - Robbins SW TL Addition (T456) (Robbins Switch Circuit Breaker Addition 1017400) | Upton | Provide transmission service to a generator by constructing substation for interconnection. | 2018-10-31 | 2019-05-10 | 2019-05-10 |  | 750000 | 771491.32 | 2.866% | 100 | 138 | 138 | 5.68 | 2x 795 Drake ACSR | Concrete Poles | 80 | 5.68 | n/a | n/a | 25.101 (C)(5)(A) |  | 68 | Manny Garcia
1017510 | Tunas Creek - Mesa View TL Addition (T620) (FourMile Circuit Breaker Addition 1017380) | Pecos | Increase transmission service reliability to the FourMile Substation (formerly Indian Mesa/Orion/NWP Tap). | 2018-11-27 | 2019-10-13 | 2019-10-13 |  | 883000 | 0 |  | 100 | 138 | 138 | 11.68 | 3x2, 795 kcl "Drake" | Steel & Concrete Poles | 80 | 11.68 | n/a | n/a | 25.101 (C)(5)(B) | Costs were moved to Project Fourmile Substation Addition 1017505 | 69 | Josh Bollich
1017588 | Tunas Creek - Mesa View SW TL Addition (T620) (Desert Mesa Circuit Breaker Addition 1017353) | Pecos | Increase transmission service reliability to the Desert Mesa Substation (formerly Desert Sky Tap #1). Provide real-time monitoring facilities at the Desert Mesa Substation. Increase the reliability of transmission facilities on the T620 Tunas Creek – Mesa View transmission line. | 2018-10-31 | 2019-05-15 | 2019-05-15 |  | 1073000 | 0 |  | 100 | 138 | 138 | 18.40 | 3x2, 795 kcl "Drake" | Steel & Concrete Poles | 80 | 18.4 | n/a | n/a | 25.101 (C)(5)(A) | Costs were moved to Desert Mesa Substation Addition Project 1017582 | 70 | Josh Bollich
1019213 | Round Rock TL Relocation (T527, T378) | Williamson | Increase the transmission service reliability to the Round Rock substation and to support the expansion of the substation by Oncor. | 2019-01-07 | 2019-05-07 | 2019-05-07 |  | 1662000 | 1240990.62 | -25.33% | 100 | 138 | 138 | 5.1 | (1) 795 ACSR "Drake" | Steel Lattice, Steel H-Frame | 100 | 5.1 | n/a | n/a | 25.101 (C)(5)(B) |  | 71 | Lindsay Mijares
1016702 | Altair - Nada TL Addition (T545) (Glidden Area TL Upgrade - 1016219) | Colorado | OPGW (fiber) installation (T545) and Substation upgrade at Nada and Altair substations from 69kV to 138kV | 2018-12-03 | 2019-05-31 | 2019-05-31 |  | 7068000 |  |  | 100 | 69 | 138 | 14.12 | 795 Drake ASCR & 26/7 & Single | Steel, Wood, & Lattice | Blanket | 14.12 | Blanket | 14.1 | 25.101 (C)(5)(B) |  | 72 | Josh Bollich
1019321 | Lakeway - Marshall Ford T179 Addition (T179) (Lakeway AE Marshall Ford TL SH - 1019096) | Travis | Increase the reliability of circuit (T179) on the Lakeway (AE) – Marshall Ford 2.4 le138 kV transmission line. | 2019-01-25 | 2019-06-21 17:00 | 2019-06-21 |  | 3172000 |  |  | 100 | 138 | 138 | 2.4 | (6x1) 795 ACSR "Drake" | Steel Towers | 100 | 2.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 73 | Victor Lawal
1019603 | Lakeway - Marshall Ford Fiber Addition (T179) (LCRA Fiber Backbone FY 19 Telecom Upgrade - 1019084) | Travis | Install 2.42 miles of 72-count OPGW from Lakeway (AE) to Marshall Ford (T179). | 2019-02-13 | 2019-06-21 08:00 | 2019-06-21 |  | 542000 |  |  | 100 | 138 | 138 | 2.4 | (6x1) 795 ACSR "Drake" | Steel Towers | 100 | 2.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 74 | Victor Lawal
1017760 | Warda - Salem TL Addition (T667,T170) (Warda Circuit Breaker Addition - 1017411) | Fayette | Increase reliability of transmission facilities on the (T170) Winchester-Salem 34.8 le 138kV transmission line. Cut-in to new A-frames at existing Warda Sub and renumber Warda to Salem as (T667). | 2018-12-01 | 2018-12-20 | 2018-12-20 |  | 169000 | 131762.31 | -22.03% | 100 | 138 | 138 | 34.8 | Single (1/phase) 795kcl ACSR "Drake" | Steel monopole | 100 | 34.8 | n/a | n/a | 25.101 (C)(5)(B) |  | 75 | Manny Garcia
1019317 | Rockport - Fulton T474 TL Addition (T474) Hurricane Response System Upgrade - 1019095 | Nueces, Aransas | Increase reliability, repair storm damage, & upgrade circuit (T477) on the N Padre Tap-Port Aransas 18.23-le 69-kV TL and circuit (T474) on the Fulton-Rockport 138-kV 7.36-le 69-kV TL. | 2019-02-07 | 2019-09-23 | 2019-09-23 |  | 3836000 |  |  | 100 | 69 | 69 | 7.4 | (1x) 795 ACSR/AW Drake | Steel Monopole, Concrete Monopole | Unknown (AEP-owned) | - | - | - | 25.101 (C)(5)(B) |  | 76 | Robert Badger
1017557 | Deer Creek - Luling TL Addition (T538) (Darst Creek Circuit Breaker Addition - 1017352) | Guadalupe | Add four 138-kV, 3000A, 40kAIC circuit breakers in a ring bus configuration to Darst Creek substation | 2019-02-22 | 2019-05-23 | 2019-05-23 |  | 1104000 |  |  | 100 | 69 | 69 | 15.84 | Drake 795 ACSR, Single | Concrete & Steel | Blanket | 15.84 | Blanket | 15.84 | 25.101 (C)(5)(B) |  | 77 | Manny Garcia
1017499 | Bastrop West - Sim Gideon TL Addition (T410) (Flood Mitigation - FY2018 System Upgrade - 1017378) | Bastrop | Reduce flood risk and potential damage to substation equipment | 2019-01-04 | 2019-03-08 | 2019-03-08 |  | 1239000 | 1237334 | -0.1345% | 100 | 138 | 138 | 6.76 | Drake 795 ACSR, Single | Steel (New) & Wood H-frame(Existing) | 100 | 100 | 100 | 6.76 | 25.101 (C)(5)(B) |  | 78 | Brian Good
1019133 | Rim Rock - Turtle Creek TL Addition (T270) (Rim Rock - Turtle Creek TL Storm Hardening - 1018968) | Kerr | Increase the reliability of circuit (T270) on the Rim Rock - Turtle Creek 7.6 le 138kV transmission line | 2020-09-16 | 2021-05-21 17:00 |  |  | 8352000 |  |  | 35 | 138 | 138 | 7.6 | (1x) 795 ACSR Drake | Steel Monopole | 60; 100 | 7.6 | 60; 100 | 7.6 | 25.101 (C)(5)(B) |  | 79 | Jacob Miller
1020430 | Marshall Ford - McNeil TL Addition (T161) (SummitT161 TL Relocation - 1020390) | Travis | Relocation of the Marshall Ford to McNeil 69-kV transmission line (T161) at the Austin Energy Summit Substation. The proposed relocation of the line was requested by Austin Energy to the northern section of Summit Sub. | 2019-03-04 | 2020-04-15 17:00 | 2020-04-15 17:00 |  | 1517000 |  |  | 100 | 69 | 69 | 13.42 | Bundled 795 Drake ACSR | Steel Poles | 100; Centerline | 0.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 80 | Bradley Wallner
1018599 | Bakersfield - Solstice TL Addition (CCN) | Pecos | Construct a new 345-kV transmission line to connect LCRA TSC's existing Bakersfield station and AEP Texas' Solstice Switch Station | 2020-01-07 | 2020-12-11 |  | T-line $148 - $192M; Bakersfield Substation - $6M; Solstice Switch Station (AEP) - $38M |  |  |  | 88 | 0 | 345 | 130-190 | 1926.9 kcl ACSS/Cumberland (LCRA TSC) and 1590 ACSS (AEP Texas) | Double-circuit steel lattice towers | 0 | 0 | 150 | 68 - 92 | 48787 | 5/28/19 PUC Approved Route 24; approved route cost estimate in CCN application for transmission line $155.9M; LCRA TSC's Bakersfield substation $6.5M; AEP's Solstice Switch Station $38.4M | 82 | Brian Good
1017897 | Culberson - Kunitz TL Addition (T271) (Culberson-KunitzTL Overhaul - 1017896) | Culberson | Structure replacement upgrades to steel and concrete Poles | 2019-05-28 | 2020-06-01 | 2020-06-01 10:46 |  | 2015000 |  |  | 100 | 138 | 138 | 28.88 | Linnet; 336kcl; 0.721” | Wood | 100 | 28.88 | n/a | n/a | 25.101 (C)(5)(B) |  | 83 | Josh Bollich
1019319 | N. Padre Tap - Port A. (T-477) (Hurricane Response System Upgrade - 1019095) | Nueces | Increase the reliability, repair storm damage, and upgrade circuit (T477) on the North Padre Tap – Port Aransas 18.23-le 69-kV transmission line and circuit (T474) on the Fulton – Rockport 138-kV 7.36-le 69-kV transmission line. | 2019-10-14 | 2019-12-20 | 2019-12-27 |  | 3748000 |  |  | 100 | 69 | 69 | 15 | 795 ACSS/AW Drake x1 | Steel monopole, Concrete Monopole, Hybrid Steel/Concrete | (AEP-owned) | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 89 | Robert Badger
1019337 | Elroy - Wolf Lane (T-582) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-03-18 | 2019-05-13 | 2019-05-13 |  | 1096000 |  |  | 100 | 138 | 138 | 3.78 | 795 Drake ACSR GA2 | Wood H-frame, LD Steel H-frame, Steel Pole, Tower | 100 | 3.78 | n/a | n/a | 25.101 (C)(5)(B) |  | 90 | Robert Badger
1020260 | Red Creek - Amos Creek TL Addition (T424) (Amos Creek Substation Addition - 1020230) | Concho | Transmission line cut-in to provide transmission service to a generator. | 2019-09-03 | 2020-03-12 13:48 | 2020-03-12 13:48 |  | 2630000 |  |  | 100 | 345 | 345 | 49 | 1590 ACSR Falcon x2 | Steel Lattice tower | 100 | 49 | n/a | n/a | 25.101 (C)(5)(B) |  | 91 | Robin Mims
1019327 | Austrop - Garfield (T182) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-04-15 | 2019-11-22 | 2019-11-27 |  | 2727000 |  |  | 100 | 345 | 345 | 8.33 | Bundled 795 ACSR "Drake" | Lattice Tower | 170; Centerline | 8.33 | n/a | n/a | 25.101 (C)(5)(B) |  | 92 | Robert Badger
1019374 | Marshal Ford - McNeil T161 TL Addition (T161) (Marshall Ford-McNeil TL Relocation - 1019212) | Travis | Increase transmission service reliability to the Austin Energy Hamilton Substation. | 2019-05-01 | 2019-06-12 | 2019-06-12 |  | 1893000 |  |  | 100 | 69 | 69 | 13.4 | 4/0 & 795 kcl ACSR | Lattice Towers & Steel Poles | 100 | 13.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 93 | Robert Badger
1017654 | Winchester - Salem TL Addition (T170) (T667) (Salem-Winchester T170 TL OH - 1017654) | Fayette | Increase the reliability and capability of circuit T170 on the Salem - Winchester 37.16-le 138-kV transmission line. | 2019-06-17 | 2019-12-05 | 2019-12-05 |  | 13391000 |  |  | 100 | 138 | 138 | 37.18 | 795 ACSR Drake (single) | Wood H-frame, Steel Lattice, Steel Monopole | Varies | 37.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 94 | Bryan Cooley
1021300 | Granite Mountain – Marble Fall TL Upgrade [Marble Falls Double Circuit TL Upgrade - 1020559] | Burnet | Increase the reliability of transmission facilities on the T195 Granite Mountain – Marble Falls 4.1-le 138-kV transmission line | 2019-11-01 | 2020-04-03 17:00 | 2020-04-03 17:00 |  | 4204000 |  |  | 100 | 138 | 138 | 4.08 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies 80; 100 | 4.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 95 | Tony Rhodes
1016579 | Fair Oaks Ranch - Esparanza TL Addition (T503) [Esperanza Substation Addition - 1016187] | Kendall | LCRA TSC will build a 138kV substation and cut-in T503 to provide transmission/ metering services and real-time monitoring facilities | 2019-09-06 | 2019-10-25 | 2019-10-25 |  | 1179000 |  |  | 100 | 138 | 138 | 8.25 | Single 795 kcl ACSR | Steel Poles | 100 | 8.11 | 80 | 8.25 | 25.101 (C)(5)(B) |  | 96 | Robin Mims
1016745 | Flatonia - Hallettsville TL Addition (T132) [Flatonia - Hallettsville TL Upgrade - 1016188] | Fayette, Lavaca | Upgrade the capacity of the 18.7 le Flatonia-Hallettsville 138-kV transmission line from 128 MVA to 380 MVA using 959 ACSS Suwannee conductors and OPGW | 2019-08-29 | 2020-05-15 | 2020-05-15 12:00 |  | 10959000 |  |  | 100 | 138 | 138 | 18.68 | Single 959.6 kcl ACSS/TW | Wood H-frame & Steel Poles | 100 | 18.68 | 100 | 18.68 | 25.101 (C)(5)(B) |  | 97 | Bo Beauregard
1017708 | Geronimo - Seguin TL Addition (T499) [Jim Briley Substation Addition - 1017404] | Guadalupe | Construct a new 138-kV substation between the Geronimo Substation and Seguin Substation. LCRA TSC will extend (T-499) Geronimo to Seguin 138-kV transmission line for approximately 500 feet in and out of the Strempel Substation to ternate on A-frame structures at the substation. | 2019-09-16 | 2019-10-17 | 2019-10-17 |  | 271000 |  |  | 100 | 138 | 138 | 2.79 | 1433.6 kcl ACSS/TW | DC Concrete Poles | 100 | 2.79 | n/a | n/a | 25.101 (C)(5)(B) |  | 98 | Bradley Wallner
1019301 | Kendall - Comfort T243 TL Addition (T243) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-le 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-le 138-kV transmission circuit (T243) | 2019-10-21 | 2020-02-03 | 2020-01-31 |  | 2658000 |  |  | 100 | 138 | 138 | 1.08 | Bundled 959.6 SUWANNEE ACSS/TW | Steel Single Poles/ Tower/ Steel H-frame | 100 | 1.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 99 | Tyreeta Young
1019303 | BoerneCico - Comfort T148 TL Addition (T148) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-le 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-le 138-kV transmission circuit (T243) | 2019-09-03 08:00 | 2020-05-11 | 2020-05-11 |  | 8237000 |  |  | 100 | 138 | 138 | 16.93 | Bundled 795 DRAKE ACSR | Steel Single Poles | 100 | 16.93 | n/a | n/a | 25.101 (C)(5)(B) |  | 100 | Tyreeta Young
1018934 | Fayetteville - Winchester TL Upgrade (T165) [Fayetteville-Winchester TL Upgrade - 1018933] | Fayette | Increase capacity and capability of circuit T165 on the Fayetteville – Winchester 138-kV upgrade | 2019-09-01 | 2020-03-23 17:00 | 2020-03-23 17:00 |  | 15240000 |  |  | 100 | 138 | 138 | 18.9 | 1433 kcl ACSS/TW Merrimack | steel monopoles | 100 | 18.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 101 | Alfred Mackey
1019122 | Giddings - Lyle Wolz TL Addition (T155) [Lexington CB Addition - 1018914] | Lee | Add two new structures to accommodate substation expansion. Increase transmission service reliability to the Lexington Substation. | 2019-08-12 | 2019-10-01 | 2019-10-01 |  | 360000 |  |  | 100 | 138 | 138 | 21 | 795 ASCR | steel monopoles | 100 | 21 | n/a | n/a | 25.101 (C)(5)(B) |  | 102 | Vaibhav Pitale
1017394 | Mountain Home TL Addition (CCN) | Kerr, Gillespie, Kimble | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2021-08-01 | 2022-12-27 17:00 |  | T-line $46.5 - $58.5M; Substation $7.1 - $7.5M |  |  |  | 0 | 0 | 138 | 21-29 | 795 Kcl 26/7 ACSR “Drake” | tbd; steel or concrete poles | 0 | 0 | varies; 100 | 21-29 | 49523 | 7/6/20 - PUC Approved Route Hunt 37A; approved route cost estimate in CCN application for transmission line $57M; substation $7.3M | 103 | Bradley Wallner
1021664 | Rim Rock - Jack Furman TL Addition (T381) [Flood Mitigation - 1021663] | Kerr | Replace structure 38 on T381 due to storm water erosion. | 2019-10-29 | 2019-11-15 | 2019-11-15 |  | 181000 | 261197.78 |  | 100 | 138 | 138 | 5.68 | 336.4 ACSR (26/7) “Linnet”/ Single | Steel Monopoles & Tower | 60 | 5.689 | n/a | n/a | 25.101 (C)(5)(B) |  | 104 | Bo Beauregard
1019026 | Fayetteville - Glidden TL Addition (T176) [Fayette Area TL Upgrades - 1018913] | Fayette, Colorado | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) | 2019-09-16 | 2020-05-14 | 2020-05-14 |  | 7870000 |  |  | 100 | 138 | 138 | 20.02 | Single 959.6 ACSS/TW Suwannee & Single OPGW (AFL DNO-11243) Static | Steel Monopoles, Hybrid H-Frames | 100 | 20 | n/a | n/a | 25.101 (C)(5)(B) |  | 105 | Bryan Cooley
1020270 | Amos Creek - Bow Wood TL Addition (T709) [Amos Creek Substation Addition - 1020230 ] | Concho, Tom Green | Provide transmission service to a generator | 2019-09-03 | 2020-03-12 09:36 | 2020-05-14 |  | 335000 |  |  | 100 | 138 | 138 | 49.33 | (2x) - 1590 kcl ACSR Falcon | Steel Lattice, Steel monopole | 160 | 49.33 | n/a | n/a | 25.101 (C)(5)(B) |  | 106 | Robin Mims
1019325 | McNeil - Gilleland Creek (T147) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2020-01-20 | 2020-03-31 17:00 | 2020-03-31 17:00 |  | 1053000 |  |  | 100 | 138 | 138 | 7.62 | 1433.6 ACSS/TW "MERRIMACK" / Single | Steel Monopoles & Tower | 100 | 7.62 | n/a | n/a | 25.101 (C)(5)(B) |  | 107 | Robert Badger
1019341 | Paige - Winchester TL Addition (T615) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Bastrop | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-09-23 | 2019-12-18 | 2020-05-14 |  | 1127000 |  |  | 100 | 138 | 138 | 14.85 | Bundled Linnit and Single Drake | Steel Mono Pole, Wood H-Frames, Concrete # Poles | 100 | 14.85 | n/a | n/a | 25.101 (C)(5)(B) |  | 108 | Robert Badger
1019335 | Wells Branch - Round Rock (T527) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis, Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-09-16 | 2019-11-01 | 2019-11-01 |  | 601000 |  |  | 100 | 138 | 138 | 5.28 | (2) 795 KCL ACSR/GA2 “DRAKE” | Steel/concrete Pole, Concrete H-Frame | 100 | 5.28 | n/a | n/a | 25.101 (C)(5)(B) |  | 109 | Robert Badger
1017767 | Sim Gideon - Winchester TL Addition (T152) [Winchester Autotransformer Additions - 1017413] | Bastrop | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 986000 |  |  | 100 | 138 | 138 | 20.74 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (75;100) | 20.74 | Varies (75;100) | 20.84 | 25.101 (C)(5)(B) |  | 110 | Jack Sandel
1017769 | Smithville - Winchester TL Addition (T175) [Winchester Autotransformer Additions - 1017413] | Bastrop | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 737000 |  |  | 100 | 138 | 138 | 15.1 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (80; 100) | 15.1 | Varies (80; 100, Aerials to 180) | 14.7 | 25.101 (C)(5)(B) |  | 111 | Jack Sandel
1017771 | Winchester - Piney Creek TL Addition (T186) [Winchester Autotransformer Additions - 1017413] | Fayette | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-03-18 17:00 | 2020-05-14 |  | 709000 |  |  | 100 | 138 | 138 | 1.38 | Single 1433.6 54/19 ACSR/TW Merrimack/TW | Lattice Towers & Steel Poles | 100 | 1.38 | 100 | 1.59 | 25.101 (C)(5)(B) |  | 112 | Jack Sandel
1017773 | Winchester - Giddings TL Addition (T222) [Winchester Autotransformer Addition - 1017413] | Bastrop | Install new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-03-17 | 2020-05-14 |  | 837000 |  |  | 100 | 138 | 138 | 10.51 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies 75; 100 | 10.51 | Varies 75; 100 | 10.68 | 25.101 (C)(5)(B) |  | 113 | Jack Sandel
1017775 | Paige - Winchester TL Addition (T615) [Winchester Autotransformer Additions - 1017413] | Lee | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 850000 |  |  | 100 | 138 | 138 | 14.83 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | 100; Centerline | 14.83 | 100; Centerline | 15.09 | 25.101 (C)(5)(B) |  | 114 | Jack Sandel
1018759 | Crane - Rio Pecos TL Addition (T451) [Castle Mountain Substation Addition - 1018744] | Upton, Crane | Cut-in T451 to a new substation, Provide transmission service (new Castle Mountain substation) for Solar Prime LLC. | 2019-09-05 | 2020-03-27 17:00 | 2020-05-14 |  | 463000 |  |  | 100 | 138 | 138 | 0.4 | Bundled 795 ACSR Drake, Single 3/8 EHS Static & Single DNO-11243 OPGW | Steel Monopole Dead End | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 115 | Dave Ilges
1017649 | LaGrange - FPP 138kV TL Addition (T263) [FPP 138kV - La Grange TL Overhaul - 1017648] | Fayette | Increase the reliability and capability of circuit T263 on the FPP 138kV – La Grange 7.9-le 138-kV transmission line | 2020-01-02 | 2020-05-15 | 2020-05-15 17:00 |  | 4096000 |  |  | 100 | 138 | 138 | 7.89 | Single 795 ACSR Drake & 2 OPGW (AFL DNO-11243) & (ALCOA 52 OPT-GW) | Steel Monopole Dead Ends, Wooden H-Frame Tangents | 100 | 7.8 | n/a | n/a | 25.101 (C)(5)(B) |  | 116 | Jacob Miller
1019333 | Round Rock - Chief Brady (T378) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-11-01 | 2019-11-18 | 2019-11-18 |  | 595000 |  |  | 100 | 138 | 138 | 1.2 | (1) 795 ACSR/GA2 "Drake"; RR AF to #55B has (2) 959 ACSS/TW HS "Suwannee" | steel H-frame, steel lattice | 100; Centerline | 1.2 | n/a | n/a | 25.101 (C)(5)(B) |  | 117 | Robert Badger
1019329 | Chief Brady - Georgetown (T355) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-12-16 | 2020-03-02 | 2020-03-02 |  | 855000 |  |  | 100 | 138 | 138 | 3.17 | (1) 795 ACSR/GA2 "Drake" | Steel Lattice and pole, Steel H-Frame | 100 | 3.0 | n/a | n/a | 25.101 (C)(5)(B) |  | 118 | Robert Badger
1019339 | Georgetown - Rivery (T597) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2020-01-31 | 2020-11-30 |  |  | 878000 |  |  | 95 | 138 | 138 | 5.1 | (1) 795 ACSR/GA2 "Drake" | steel H-frame, concrete pole, steel pole | 50 Centerline; blanket | 5.10 | n/a | n/a | 25.101 (C)(5)(B) |  | 119 | Robert Badger
1019210 | Altair - Glidden TL Addition (T544) [Kleimann (Columbus) CB Addition - 1018910] | Upton, Crockett | Increase reliability of transmission facilities on the T544 Glidden-Altair 12.22-le 69-kV TL. | 2019-11-18 | 2020-02-10 | 2020-05-14 |  | 37000 |  |  | 100 | 69 | 138 | 3.33 | 795 ACSR Drake, single | Steel & Concrete monopoles | 80; Blanket | 12.41 | 80; Blanket | n/a | 25.101 (C)(5)(B) |  | 120 | Josh Bollich
1017538 | Goforth-Turnersville TL Addition (T272) [Crosswinds Substation Addition-1017349] | Hays | Acquire 7.5 acres and expand new LCRA TSC facilities with a three-ring bus configuration | 2020-03-10 | 2020-05-14 | 2020-05-14 |  | 1038000 |  |  | 100 | 138 | 138 | 3.77 | 795 ACSR Drake, single | Lattice, Wood H-frame, Steel monopole | 100 | 6.69 | 100 | 3.77 | 25.101 (C)(5)(B) |  | 121 | Bryan Cooley
1017540 | Crosswinds-Goforth TL Addition (T661) [Crosswinds Substation Addition-1017349] | Hays | Acquire 7.5 acres and expand new LCRA TSC facilities with a three-ring bus configuration | 2020-03-10 | 2020-05-14 | 2020-05-14 |  | 10000 |  |  | 100 | 138 | 138 | 3.31 | 795 ACSR Drake, single | Wood H-frame, Steel monopole | 100 | n/a | 100 | n/a | 25.101 (C)(5)(B) |  | 123 | Bryan Cooley
1014015 | Camp Wood - Leakey TL Addition (T269) [Camp Wood - Leakey TL Overhaul - 1016183] | Real | Increase the reliability of transmission facilities on the T269 Camp Wood-Leakey 17.3 le 69-kV transmission line and upgrade the line to 795 ACSR Drake conductor (111 MVA at 69-kV), 138-kV capable with an OPGW shield wire. | 2020-11-30 17:00 | 2021-06-30 |  |  | 43428000 |  |  | 0 | 69 | 138 | 17.32 | Single 795 ACSR Drake | Steel & Lattice | Varies; 60 | 17.32 | n/a | n/a | 25.101 (C)(5)(B) |  | 125 | Sarah Wilson
1019114 | Luling - Zorn TL Addition (T158) [Luling-Zorn TL Overhaul - 1019113] | Guadalupe | Increase the reliability of transmission facilities on T158 | 2020-02-03 | 2021-05-15 |  |  | 10951000 |  |  | 40 | 138 | 138 | 28.02 | 795 ACSR Drake | Concrete and Steel poles | 100 | 28.02 | n/a | 28.02 | 25.101 (C)(5)(B) |  | 126 | Vaibhav Pitale
1020456 | Hidden Valley - McNeil TL Relocation/Addition (T626) [Hidden Valley-McNeil TL Relocation - 1020380] | Travis | Provide transmission service reliability improvements | 2020-03-16 | 2020-04-29 | 2020-04-29 |  | 519000 |  |  | 100 | 138 | 138 | 0.5 | (1) 795 ACSR "Drake" | Steel Lattice Tower and Monopole | Centerline | 0.5 | Centerline | n/a | 25.101 (C)(5)(B) |  | 127 | Bradley Wallner
1020454 | Harris Branch - McNeil TL Relocation/Addition (T146) [Harris Branch - McNeil TL Relocation - 1020379] | Travis | Provide transmission service reliability improvements | 2020-02-20 | 2020-05-07 | 2020-05-07 |  | 1408000 |  |  | 100 | 138 | 138 | 6.87 | 795 ACSR Drake. | Steel Lattice Tower and Monopole | 100 | 6.87 | 100' | n/a | 25.101 (C)(5)(B) |  | 128 | Bradley Wallner
1022277 | Roma - Rio Grande City TL Addition (T465) [Escobares Substation Addition - 1022173] | Starr | Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Escobares Substation. Provide a transmission point of interconnection. | 2020-10-19 | 2021-01-21 |  |  | 2327000 |  |  | 18 | 138kV | 138kV | 13.7 | (1) Drake ACSR | Steel Monopoles | Varies 50; 80 | 12.7 | Varies;40-100 | 0.5 | 25.101 (C)(5)(B) |  | 129 | Glenn Brunson
1022830 | Giddings - Warda TL Addition (T137) [Gidding-Warda TL Upgrade - 1022731] | Fayette, Lee | Increase the reliability of transmission facilities on the T137 Giddings - Warda 9.66-le 69-kV transmission line by converting the line to 138-kV operation and increasing the transmission capacity. | 2020-04-01 | 2020-10-19 12:00 | 2020-10-16 |  | 12383000 |  |  | 100 | 0kv (De-energized) | 138kv | 9.66 | (1) 959.6 ACSS "Suwannee" | Steel and Concrete Monopoles | 100 | 9.66 | 100 | n/a | 25.101 (C)(5)(B) |  | 130 | Manny Garcia
1021401 | Burnet - Lampasas TL Addition (T219) [Andice-Bertram-Burnet TL Upgrade - 1021209] | Burnet, Lampasas | Upgrade and reconfigure Burnet Substation to facilitate the Pedernales Electric Cooperative project to upgrade and convert the Andice-Bertram-Burnet 69-kV transmission line to 138-KV operation | 2020-03-15 | 2021-05-15 |  |  | 2456000 |  |  | 30 | 138 | 138 | 23.3 | Single 795 ACSR Drake | Wood H-frames | Centerline | 23.3 | Centerline | n/a | 25.101 (C)(5)(B) |  | 131 | Bo Beauregard
1020552 | Burnet - Lampasas TL Addition (T219) [Burnet-Lampasas TL Overhaul - 1020371] | Burnet, Lampasas | Increase the reliability of transmission facilities on the T219 Burnet - Lampasas 23.4-le 138-kV transmission line. | 2020-03-15 | 2021-05-15 |  |  | 19159000 |  |  | 35 | 138 | 138 | 23.3 | Single 795 ACSR Drake | Wood H-frames | Centerline | 23.3 | Centerline | n/a | 25.101 (C)(5)(B) |  | 132 | Bo Beauregard
1021530 | Divide Substation Addition [Divide CB Addition 1021086] | Coke | Add a 345-kV circuit breaker to the existing substation. LCRA will install and maintain a single span from divide substation to Structure 1 at the generator's POI. | 2019-12-04 | 2020-06-15 17:00 | 2020-06-15 17:00 |  | 2114000 |  |  | 100 | 0 | 345 | 0.1 | Bundled Drake ACSR, 3/8 EHS, DNO-11243 | n/a generator's structures | 0 | 0 | 150 | 0.2 | 25.101 (C)(5)(B) |  | 133 | Bradley Wallner
1019285 | T271 TL Addition (T271) [Pinnacle Substation Addition - 1019007] | Culberson | LCRA TSC will build a new substation (Pinnacle) adjacent to T271 to interconnect the new 186.3 MW solar generation facility. Replace transmission structures to allow for substation cut-in and upgraded conductor and OPGW. | 2020-01-29 | 2020-10-14 17:00 | 2020-10-14 17:00 |  | 10800000 |  |  | 100 | 69 | 138 | 18.1 | Single 1433 ACSS/TW Merrimack | Steel monopole | 100 | 18.1 | 100 | n/a | 25.101 (C)(5)(B) |  | 134 | Josh Bollich
1017435 | Elgin Sw - Gilleland Creek TL Addition (T421) [Kimbro Substation Addition - 1017433] | Travis, Williamson | Provide transmission service to generator. | 2020-04-06 17:00 | 2021-01-19 17:00 |  |  | 853000 |  |  | 50 | 138 | 138 | 12.9 | (1) per phase Merrimack ACSS | Steel Dead-end Monopole | 100 | 12.9 | NA | NA | 25.101 (C)(5)(B) |  | 135 | Vaibhav Pitale
1016698 | Glidden - Altair TL Addition (T544) [Glidden Area TL Upgrade - 1016219] | Colorado | Increase the capacity and reliability of transmission facilities on the Glidden-Altair 12.2 le 69-kV transmission line (T544) and the Altair-Nada 14.12 le 69-kV transmission line (T545). | 2021-01-21 17:00 | 2021-03-15 17:00 |  |  | 858000 |  |  | 0 | 138 | 138 | 12.2 | 795 ACSR Drake | Steel & Concrete | 80 | 12.2 | 80 | 12.3 | 25.101 (C)(5)(B) |  | 136 | Josh Bollich
1016491 | Cushman - Hwy 123 TL Addition (T572) [Meadow Lake Substation Addition - 1016198] | Guadalupe | Provide transmission service along with metering and real-time monitoring facilities for GVEC's new Meadow Lake Substation. Replace structure #30 with two large angle dead end structures to route T572 into and out of the new LCRA/GVEC owned Meadow Lake. | 2020-08-17 17:00 | 2020-12-21 |  |  | 658000 |  |  | 73 | 138 | 138 | 6.48 | Single 795 ACSR Drake | Steel Monopole | 80 | 6.48 | n/a | n/a | 25.101 (C)(5)(B) |  | 137 | Robin Mims
1023383 | Altair - Eagle Lake TL Relocation (T547) [Gen Add FY 20 Altair Eagle Lake Structure Relocation 1023382] | Colorado | Move the structure back approximately 50 ft. to ensure the safety of the transmission line from the eroding river bank | 2020-03-20 | 2020-04-03 17:00 | 2020-04-03 17:00 |  | 267000 |  |  | 100 | 69 | 69 | 11.74 | 795 ACSR "Drake" 1/0 ACSR "Raven" 2/0 ACSR "Quail" 4/0 ACSR "Penquin" | Steel Monopoles Wood Monopoles Wood Hframes Wood 3 Poles | Blanket & Centerline | 11.74 | n/a | n/a | 25.101 (C)(5)(B) |  | 138 | Jack Sandel
1023677 | Asherton - Bevo TL Addition (T603) [Asherton - Bevo TL Relocation - 1022882] | Dimmit | Relocate dead-end structure #1 on the T603 Bevo to Asherton 138-kV transmission line to outside of the AEP-owned Asherton Substation. Re-route and re-ternate T603 to a new point-of-interconnection (POI) structure owned by AEP and installed by AEP outside of the Asherton Substation. | 2021-03-01 | 2020-12-18 |  |  | 543000 |  |  | 0 | 138 | 138 | 8.05 | (1) 795 Drake ACSR | Steel monopoles | AEP owned | AEP owned | AEP owned | AEP owned | 25.101 (C)(5)(B) |  | 139 | Glenn Brunson
1016493 | Cushman - Meadow Lake TL Addition (T647) [Meadow Lake Substation Add - 1016198] | Guadalupe | Provide transmission service along with metering and real-time monitoring facilities for GVEC's new Meadow Lake Substation. | 2020-08-17 17:00 | 2020-12-21 |  |  | 643000 |  |  | 73 | 138 | 138 | 3.6 | Single 795 ACSR Drake | Steel monopole | 80 | 3.6 | n/a | n/a | 25.101 (C)(5)(B) |  | 140 | Robin Mims
1020445 | HiCross - Turner TL Addition (T143) [HiCross-Turner TL Storm Harden-1020386] | Travis, Hays | Increase the reliability of transmission facilities on the T143 Hi Cross - Turnersville 8.8-le 138-kV transmission line. | 2020-06-03 08:00 | 2021-03-26 17:00 |  |  | 2610000 |  |  | 2 | 138 | 138 | 7.9 | bundled 795 ACSR Drake | Concrete and Steel monopoles | 100 | 7.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 141 | Sarah Wilson
1022213 | Hi-Cross - Turnersville TL Addition (T143) [LCRA Fiber Backbone FY20 - 1021196] | Travis, Hays | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2020-11-09 08:00 | 2021-03-26 12:00 |  |  | 1065000 |  |  | 2 | 138 | 138 | 7.9 | bundled 795 ACSR Drake | Concrete and Steel monopoles | 100 | 7.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 142 | Sarah Wilson
1019265 | Fayetteville - Bellville S TL Addition (T216) [New Bremen CB Add - 1018919] | Austin, Colorado, Fayette | Increase the reliability of transmission facilities on the T216 Fayetteville – Bellville South 28.19-les 138-kV transmission Line | 2021-04-06 17:00 | 2021-06-30 17:00 |  |  | 416000 |  |  | 0 | 138 | 138 | 0.5 | 1433.6 ACSS MERRIMACK | Steel Pole | 100 | 0.05 | n/a | n/a | 25.101 (C)(5)(B) |  | 143 | Tyreeta Young
1021775 | Twin Buttes - Brown (T551) TL Addition [Amos Creek Circuit Breaker Addition - 1021517] | Tom Green, Concho | Cut-in T551 to existing substation to provide transmission services to a generator | 2020-10-07 | 2020-11-24 |  |  | 1147000 |  |  | 98 | 345 | 345 | 88.3 | 1590 ACSR Falcon Bundled | Steel Pole | 160 | 88.3 | n/a | n/a | 25.101 (C)(5)(B) |  | 144 | Robin Mims
1023668 | Gabriel - Glasscock TL Addition (T359) [Gabriel Substation Upgrade - 1020410] | Williamson | LCRA TSC will upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-03-08 | 2022-02-15 |  |  | 361000 |  |  | 0 | 138 | 138 | 6.59 | Single 795 ACSR Drake | Steel Pole | 80 | 6.59 | n/a | n/a | 25.101 (C)(5)(B) |  | 146 | Dave Ilges
1021176 | Gabriel - Jarrell TL Addition (T224) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-02-15 |  |  | 1083000 |  |  | 5 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B) |  | 147 | Dave Ilges
1021174 | Gabriel - Georgetown East TL Addition (T223) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-02-15 |  |  | 1083000 |  |  | 5 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B) |  | 148 | Dave Ilges
1023667 | Gabriel - Rivery TL Addition (T457) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-03-08 | 2022-02-15 |  |  | 361000 |  |  | 0 | 138 | 138 | 2.43 | Bundled 795 ACSR Drake | Steel Pole | Varies | 2.43 | n/a | n/a | 25.101 (C)(5)(B) |  | 149 | Dave Ilges
1023966 | Fairland - Lago Vista TL Addition (T414) [transmission Connector Shunt NORTH - FY 2020 System Upgrade - 1023813] | Burnet, Travis | Improve the reliability of transmission facilities by installing transmission connector shunts on the 12.6-le Coronado-Fairland, 5-le Lakeway-Marshall Ford and 21.4-le Fairland-Lago Vista 138-kV transmission lines. | 2020-06-23 | 2020-07-28 | 2020-07-21 17:00 |  | 668000 |  |  | 100 | 138 | 138 | 21 | 795 Condor ACSR 795 Drake ACSR | Lattice Towers | 100 | 21 | n/a | n/a | 25.101 (C)(5)(B) |  | 150 | Jeremy Svagdis
1023967 | Coronado - Fairland TL Addition (T110) [transmission Connector Shunt NORTH - FY 2020 System Upgrade - 1023813] | Burnet, Llano | Improve the reliability of transmission facilities by installing transmission connector shunts on the 12.6-le Coronado-Fairland, 5-le Lakeway-Marshall Ford and 21.4-le Fairland-Lago Vista 138-kV transmission lines. | 2020-06-01 | 2020-06-12 17:00 | 2020-06-12 17:00 |  | 415000 |  |  | 100 | 138 | 138 | 12.4 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | 100 | 12.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 151 | Jeremy Svagdis
1023949 | Fayetteville - Salem TL Addition (T177) [transmission Connector Shunt EAST - FY 2020 System Upgrade - 1023812] | Austin, Washington, Fayette | Improve the reliability of transmission facilities by installing transmission connector shunts on the 19.3-le double circuit consisting of FPP Yard #1-Salem 345-kV and Fayetteville-Salem 138-kV transmission lines. | 2020-09-14 17:00 | 2020-09-17 | 2020-09-17 |  | 246000 |  |  | 100 | 138 | 138 | 19.32 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | Varies | 19.32 | n/a | n/a | 25.101 (C)(5)(B) |  | 152 | Jeremy Svagdis
1023948 | FPP Yard #1 - Salem TL Addition (T211) [transmission Connector Shunt EAST - FY 2020 System Upgrade - 1023812] | Austin, Washington, Fayette | Improve the reliability of transmission facilities by installing transmission connector shunts on the 19.3-le double circuit consisting of FPP Yard #1-Salem 345-kV and Fayetteville-Salem 138-kV transmission lines. | 2020-09-14 17:00 | 2020-09-17 | 2020-09-17 |  | 459000 |  |  | 100 | 345 | 345 | 27.43 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | Varies | 27.43 | n/a | n/a | 25.101 (C)(5)(B) |  | 153 | Jeremy Svagdis
1023901 | Lockhart - Luling TL Addition (T184) [transmission Connector Shunt SOUTH - FY 2020 System Upgrade - 1023814] | Caldwell | Improve the reliability of transmission facilities by installing transmission connector shunts on the 16.8-le Lockhart-Luling and 17.1-le Lockhart-Red Rock 138-kV transmission lines. | 2020-07-15 | 2020-08-05 | 2020-08-05 |  | 119000 |  |  | 100 | 138 | 138 | 16.83 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers, Wood H-Frames | Varies | 16.83 | n/a | n/a | 25.101 (C)(5)(B) |  | 154 | Jeremy Svagdis
1023918 | Lockhart - Red Rock TL Addition (T578) [transmission Connector Shunt SOUTH - FY 2020 System Upgrade - 1023814] | Bastrop, Caldwell | Improve the reliability of transmission facilities by installing transmission connector shunts on the 16.8-le Lockhart-Luling and 17.1-le Lockhart-Red Rock 138-kV transmission lines. | 2020-07-15 | 2020-08-06 | 2020-08-06 |  | 133000 |  |  | 100 | 138 | 138 | 17.11 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers, Wood H-Frames | Varies | 17.11 | n/a | n/a | 25.101 (C)(5)(B) |  | 155 | Jeremy Svagdis
1014165 | Goldthwaite - Lampasas TL Addition (T128) [Goldthwaite - Lampasas TL Overhaul - 1015217] | Mills, Hamilton, Lampasas | Increase the reliability of circuits T128 & T672 on the Goldthwaite - Lampasas 49.77-le 138-kV transmission line. | 2020-07-01 | 2021-05-13 |  |  | 2516000 |  |  | 15 | 138 | 138 | 23.74 | Single 795 Drake ACSR | Steel poles, Steel & Wood Hframes | 100; Centerline | 23.74 | n/a | n/a | 25.101 (C)(5)(B) |  | 156 | Robert Badger
1021428 | Sherwood Shores - Coronado TL Addition (T635) [Coronado-Sherwood Shores TL SH - 1021211] | Burnet | Increase the reliability of circuit T635 on the Coronado – Sherwood Shores 12.2-le 138-kV transmission line | 2020-09-14 08:00 | 2022-05-14 17:00 |  |  | 9867000 |  |  | 5 | 138 | 138 | 12.15 | Single 795 Drake ACSR | Steel Poles/Steel Lattice | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 157 | Robert Badger
1020467 | Gabriel - Rivery TL Addition (T457) [Gabriel-Rivery TL SH - 1019092] | Williamson | Increase the capacity and reliability of circuit T457 on the Gabriel – Rivery 2.4-le 138-kV transmission line | 2020-11-02 | 2021-05-14 |  |  | 7622000 |  |  | 5 | 138 | 138 | 2.43 | Bundled 795 Drake ACSR | Steel Poles | 40;100 | 2.4 | 60; 80;120; 130;150 | 2.4 | 25.101 (C)(5)(B) |  | 158 | Tolu Odunlami
1019172 | Turtle Creek - Hunt TL Addition (T240) [Turtle Creek Substation Upgrade - 1018970] | Kerr | Increase Reliability to the Turtle Creek substation | 2020-09-09 08:00 | 2020-10-06 | 2020-10-06 17:00 |  | 519000 |  |  | 100 | 138 | 138 | 0.1 | Single 336 ACSR Linnet | Wood poles | n/a | n/a | 80 (Temporary) | 0.1 (Temporary) | 25.101 (C)(5)(B) |  | 160 | Jacob Miller
1019170 | Turtle Creek - Verde Creek TL Addition (T221) [Turtle Creek Substation Upgrade - 1018970] | Kerr | Increase Reliability to the Turtle Creek substation | 2020-09-09 08:00 | 2021-05-21 |  |  | 572000 |  |  | 5 | 138 | 138 | 0.1 | Single 336 ACSR Linnet | Wood poles | n/a | n/a | 80 (Temporary) | 0.1 (Temporary) | 25.101 (C)(5)(B) |  | 161 | Jacob Miller
1023941 | Evant - Lampasas TL Addition (T672) [Goldthwaite–Lampasas TL OH - 1015217] | Lampasas, Coryell | Increase the reliability of circuits T128 & T672 on the Goldthwaite - Lampasas 49.77-le 138-kV transmission line. | 2020-07-01 | 2021-03-10 |  |  | 3355000 |  |  | 30 | 138 | 138 | 26.02 | Single 795 Drake ACSR | Steel poles, Steel & Wood Hframes | 100; Centerline | 26.02 | n/a | n/a | 25.101 (C)(5)(B) |  | 162 | Robert Badger
1024000 | Lakeway - Marshall Ford TL Addition (T180) [transmission Connector Shunt North-FY 2020 System Upgrade - 1023813] | Travis | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-07-27 | 2020-07-28 | 2020-07-28 |  | 57000 |  |  | 100 | 138 | 138 | 0.27 | Single 795 Condor ACSR/SD | Lattice Towers | 100 | 0.27 | n/a | n/a | 25.101 (C)(5)(B) |  | 163 | Jeremy Svagdis
1024054 | FPP - Lytton T255 TL Repair Addition [FPP Yard 2 - Lytton Springs transmission Line Upgrade - 1024058] | Fayette | Replace damaged equipment on the T255 FPP Yard #2 – Lytton Springs transmission line and increase the reliability of the line by installing new transmission line structure components and replacing original REDWING conductor with bundled Drake conductor. | 2020-04-17 | 2020-10-23 | 2020-05-18 |  | 3767000 |  |  | 100 | 345 | 345 | 61.1 | Bundled 715.5 Redwing ACSR; top phase between structures #30 to #77 Bundled 795 Drake ACSR | Lattice | 100 | 61.1 | n/a | n/a | 25.101 (C)(4) |  | 164 | Jack Sandel
1020874 | Fayetteville - Frelsburg TL Addition (T176) [Frelsburg Circuit Breaker Addition 1020378] | Fayette, Colorado | Increase transmission service reliability to the Frelsburg Substation. | 2020-08-10 | 2021-02-03 17:00 |  |  | 892000 |  |  | 50 | 138 | 138 | 20.06 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11243 (1)3/8" EHS Steel | Steel monopoles | 125; 75 Centerline | 20.06 | n/a | n/a | 25.101 (C)(5)(B) |  | 165 | Bradley Wallner
1019024 | Plum - Flatonia TL Addition (T133) [Fayette Area TL Upgrades - 1018913] | Fayette | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) and the Flatonia to Plum 138-kV transmission circuit (T133). | 2020-09-08 | 2021-04-26 |  |  | 10196000 |  |  | 5 | 138 | 138 | 19.63 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11242 (1)3/8" EHS Steel | Single pole and H-Frame (Steel, Wood, Concrete) | 100 | 19.53 | n/a | n/a | 25.101 (C)(5)(B) |  | 166 | Bryan Cooley
1020876 | Fayetteville - Mockingbird TL Addition (T714) [Frelsburg Circuit Breaker Addition 1020378] | Fayette, Colorado | Increase transmission service reliability to the Frelsburg Substation. | 2020-08-10 | 2021-02-03 17:00 |  |  | 44000 |  |  | 50 | 138 | 138 | 10.2 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11243 (1)3/8" EHS Steel | Steel monopoles | 75 | 10.2 | n/a | n/a | 25.101 (C)(5)(B) |  | 167 | Bradley Wallner
1020465 | Gabriel - Glasscock TL Addition (T359) [Gabriel - Glasscock TL Storm Hardening - 1019091] | Williamson | Increase the reliability and capability of circuit T359 on the Gabriel - Glasscock 6.6-le 138-kV transmission line. | 2020-10-27 | 2021-04-02 17:00 |  |  | 1531000 |  |  | 5 | 138 | 138 | 6.59 | Single 795 ACSR Drake | Single Steel Monopoles | 80 | 6.59 | n/a | n/a | 25.101 (C)(5)(B) |  | 168 | Tolu Odunlami
1021444 | Paleface - Miller Creek TL Addition (T124) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Travis, Hays, Blanco, | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124 and replacing four structures | 2020-08-03 | 2021-04-30 |  |  | 1447000 |  |  | 5 | 138 | 138 | 17 | Single 795 ACSR Drake | Single Steel Monopoles | 80 | 17 | n/a | n/a | 25.101 (C)(5)(B) |  | 169 | Robert Badger
1019263 | Bevo - Rosita Creek TL Addition (T463) [Dimmit CB Addition - 1018912] | Maverick, Dimmit | Increase the reliability of transmission facilities on the T463 Rosita Creek – Bevo 47.63-le 138-kV transmission line. | 2021-03-02 | 2021-11-12 17:00 |  |  | 1539000 |  |  | 0 | 138 | 138 | 36.85 | Single 795 ACSR Drake | Steel monopoles | Centerline | 36.85 | n/a | n/a | 25.101 (C)(5)(B) |  | 170 | Tolu Odunlami
1022229 | T626 TL Addition [LCRA Fiber Backbone FY20 - 1021196] | Travis | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2020-12-22 | 2021-02-19 |  |  | 580000 |  |  | 0 | 138 | 138 | 0.92 | 795 ACSR "Drake" 3/8" EHS Steel AFL DNO-11243 AFL ADSS "AC0729C621BE1" | Steel Lattice, H-frame, poles | 100 | .92 | n/a | n/a | 25.101 (C)(5)(B) |  | 171 | Sarah Wilson
1023975 | Bergheim – Kendall TL Addition (T656) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-23 | 2020-12-18 |  |  | 490000 |  |  | 4 | 345 | 345 | 27.23 | Bundled 795 ACSR/SD Condor | Lattice Tower | 100 | 27.23 | n/a | n/a | 25.101 (C)(5)(B) |  | 172 | Jeremy Svagdis
1023976 | Bergheim – Hays Energy TL Addition (T389) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Hays | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-11-04 | 2020-11-25 |  |  | 765000 |  |  | 5 | 345 | 345 | 34.18 | Bundled 795 ACSR/SD Condor | Lattice Tower | 100 | 34.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 173 | Jeremy Svagdis
1023982 | Bergheim – Fair Oaks TL Addition (T238) Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 59000 |  |  | 100 | 138 | 138 | 4.08 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 4.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 174 | Jeremy Svagdis
1023980 | Esperanza – Fair Oaks Ranch TL Addition (T503) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-05 | 2020-10-06 | 2020-10-06 |  | 73000 |  |  | 100 | 138 | 138 | 4.36 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 4.36 | n/a | n/a | 25.101 (C)(5)(B) |  | 175 | Jeremy Svagdis
1023977 | Kendall – Welfare TL Addition (T584) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-23 | 2020-11-03 | 2020-11-03 |  | 100000 |  |  | 100 | 138 | 138 | 10.16 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 10.16 | n/a | n/a | 25.101 (C)(5)(B) |  | 176 | Jeremy Svagdis
1023979 | Boerne – Esperanza TL Addition (T657) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-30 | 2020-10-02 | 2020-10-02 |  | 110000 |  |  | 100 | 138 | 138 | 3.9 | Single 795 ACSR/SD Condor | Lattice Tower | 85 | 3.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 177 | Jeremy Svagdis
1023978 | Boerne – Welfare TL Addition (T228) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-28 | 2020-09-30 | 2020-09-30 |  | 150000 |  |  | 100 | 138 | 138 | 9.5 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 9.5 | n/a | n/a | 25.101 (C)(5)(B) |  | 178 | Jeremy Svagdis
1023986 | Highway 46 – River Oaks TL Addition (T518) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-11-04 | 2020-11-04 | 2020-11-04 |  | 100000 |  |  | 100 | 138 | 138 | 8.64 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B) |  | 179 | Jeremy Svagdis
1023987 | River Oaks - Henne TL Addition (T237) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-21 | 2020-10-22 | 2020-10-22 |  | 78000 |  |  | 100 | 138 | 138 | 3.79 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 3.79 | n/a | n/a | 25.101 (C)(5)(B) |  | 180 | Jeremy Svagdis
1023983 | Antler – Bergheim TL Addition (T493) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-09 | 2020-10-09 | 2020-10-09 |  | 123000 |  |  | 100 | 138 | 138 | 7.18 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 7.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 181 | Jeremy Svagdis
1023985 | Antler – Highway 46 TL Addition (T610) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-19 | 2020-11-16 |  |  | 132000 |  |  | 30 | 138 | 138 | 10.4 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 10.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 182 | Jeremy Svagdis
1021481 | Brenham - Highway 36 Substation (T468) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2020-08-06 | 2020-11-05 | 2020-11-05 |  | 895000 |  |  | 100 | 138 | 138 | 2.3 | (1)959.6 ACSS Suwannee TW (1)3/8" EHS Steel NEW (1)AFL DNO-11243 | Steel/Concrete Single pole & H-Frame | Centerline; 75 | 2.3 | n/a | n/a | 25.101 (C)(5)(B) |  | 183 | Robert Badger
1021465 | Brenham - Salem TL Addition (T199) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2020-09-14 | 2020-12-17 |  |  | 675000 |  |  | 15 | 138 | 138 | 3.18 | 959.6 kcmil ACSS/TW | Steel H-frame | 100 | 3.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 184 | Robert Badger
1022278 | Pooley Rd - Luling TL Addition (T712) [Luling - Zorn TL Overhaul - 1019113] | Guadalupe, Caldwell | Increase the reliability of transmission facilities on T158 | 2020-08-17 08:00 | 2021-04-30 |  |  | 3200000 |  |  | 5 | 138 | 138 | 28.02 | (1) 795 ACSR Drake | Steel & Concrete SC Monopoles | Centerline; 80-100 | 28.02 | n/a | n/a | 25.101 (C)(5)(B) |  | 187 | Vaibhav Pitale
1024067 | Sim Gideon - Bastrop TL Addition (T172) [Sim Gideon - Structure 13 TL Upgrade 1023964] | Bastrop, Travis | Increase the reliability of transmission facilities on the T171 Austrop – Sim Gideon and T172 Bastrop – Sim Gideon 2.6-mile 138-kV double-circuit transmission line by removal and replacement of Structure #4 and Structure #5. | 2020-09-21 | 2020-12-15 |  |  | 499000 |  |  | 63 | 138 | 138 | 4.15 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 4.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 188 | Aldo Romero
1024084 | Sim Gideon - Austrop TL Addition (T171) [Sim Gideon - Structure 13 TL Upgrade 1023964] | Bastrop, Travis | Increase the reliability of transmission facilities on the T171 Austrop – Sim Gideon and T172 Bastrop – Sim Gideon 2.6-mile 138-kV double-circuit transmission line by removal and replacement of Structure #4 and Structure #5. | 2020-09-21 | 2020-12-15 |  |  | 530000 |  |  | 63 | 138 | 138 | 15.61 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 15.61 | n/a | n/a | 25.101 (C)(5)(B) |  | 189 | Aldo Romero
1023421 | Sim Gideon - Austrop T171 TL Addition (T171) [Flood Mitigation Phase II – FY 2021 - 1023189] | Bastrop, Travis | Reduce the flood risk and potential for damage to substation equipment on T547 Altair - Eagle Lake and T171 Sim Gideon - Austrop transmission lines. | 2020-10-26 | 2020-12-18 |  |  | 339000 |  |  | 40 | 138 | 138 | 15.61 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 15.61 | n/a | n/a | 25.101 (C)(5)(B) |  | 190 | Jack Sandel
1024055 | Lincoln T731 TL Addition (T731) [Lincoln Substation Upgrade - 1022729] | Lee | Provide transmission service/reactive power support to new load at the Lincoln Substation. LCRA TSA will construct a new 138-kV transmission line from the existing Lincoln Substation to the new point of interconnect at the Enterprise Substation. | 2020-09-23 | 2020-09-25 | 2020-09-25 |  | 1160000 |  |  | 100 | 0 | 138 | 0.03 | 3x1 795 DRAKE ACSR | Concrete Dead-end | n/a | n/a | BBEC Owned within Sub. | BBEC Owned within Sub. | 25.101 (C)(5)(B) |  | 191 | Manny Garcia
1021973 | T723 Motorman-Upton TL Add (T723) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2021-04-05 | 2021-11-21 |  |  | 679000 |  |  | 0 | 138 | 138 | 17.97 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 17.97 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 192 | Glenn Brunson
1023799 | T441 LCRACrane-Motorman TL Add (T441) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2021-04-05 | 2021-11-21 |  |  | 16000 |  |  | 0 | 138 | 138 | 12.16 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 30.14 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 193 | Glenn Brunson
1019051 | McCarty Ln-Hilltop T375-TL Add (T375) [Ranch Road 12 CB Addition - 1018923] | Hays | Increase the reliability of transmission facilities on the T375 McCarty Lane – Hilltop 10.65-mile 138kV transmission line. | 2020-10-26 | 2021-04-01 |  |  | 1117000 |  |  | 5 | 138 | 138 | 3.96 | 927.2 Greeley | H-Frame, Steel Pole, Lattice Tower | Varies 85 - 125 | 85/125 | n/a | n/a | 25.101 (C)(5)(B) |  | 194 | Tolu Odunlami
1018763 | Crane-Rio Pecos TL Addition (T451) [Soda Lake Substation Addition - 1018745] | Crane | Provide transmission service to a generator | 2021-03-16 08:00 | 2021-05-17 17:00 |  |  | 596000 |  |  | 0 | 138 | 138 | 12.24 | (2) 795 kcmil ACSR "Drake" | Concrete pole, steel pole | Centerline; 80 | 12.24 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 195 | Scott Stacher
1023874 | Hornsby TL Addition (T510), (T511) & (T738) [Hornsby Substation Addition -1023852] | Guadalupe, Williamson, Travis, Caldwell | Provide transmission service to a load-serving substation. | 2021-01-04 | 2023-05-15 |  |  | 3400000 |  |  | 0 | 345 | 345 | 74.6 (T510) 71.0 (T511) | (2) bundled 959 ACSS/TW Suwannee | Steel lattice and monopoles | Varies 100 - 200 | 74.6 (T510) 71.0 (T511) | 165 | 74.6 (T510) 51.0 (T511) 20.0 (T738) | 25.101 (C)(5)(A) |  | 196 | Dave Ilges
1024249 | Austin Energy Hornsby TL Addition (AEN924), (AEN1008) & (AEN1099) [Hornsby Substation Addition -1023852] | Travis | Provide transmission service to a load-serving substation. | 2021-01-04 | 2021-03-31 |  |  | 625000 |  |  | 0 | 138 | 138 | 7.2 (AEN924) 7 (AEN1008) | (2) bundled 795 ACSR Drake | Steel lattice and monopoles | Varies 90 - 100 | 7.2 (AEN924) 6 (AEN1008) 1 (AEN1099) | 80 | 7.2 (AEN924) 7 (AEN1008) | 25.101 (C)(5)(A) |  | 197 | Dave Ilges
1020471 | Eckert - Nebo TL Addition (T126) [Eckert - Nebo TL Overhaul - 1020377] | Gillespie | Increase the reliability of circuit T126 on the Eckert- Nebo 0.7 mile 69 Kv transmission line | 2020-12-04 | 2021-04-28 |  |  | 2198000 |  |  | 0 | 69 | 138 | 0.7 | Single 795 Drake | Steel Tangents H-Frames | 100 | 0.7 | n/a | n/a | 25.101 (C)(5)(B) |  | 198 | Robin Mims
1023831 | Wingarten TL Addition [Wingarten Substation Upgrade - 1022733] | Zavala | Increase transmission service reliability to the Wingarten Substation. Reroute the existing line tap of the La Pryor-Turtle Creek TL from its current configuration to a newly installed AEP owned box structure. | 2020-11-23 | 2020-12-18 |  |  | 600000 |  |  | 0 | 69 | 138 | 0.05 | 795 kcmil ACSR (26/7), one conductor/phase | Concrete pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | work within substation | 199 | Jeremy Svagdis
1022221 | T635 TL Addition [LCRA Fiber Backbone FY20 - 1021196] | Burnett, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-09-16 | 2022-05-14 |  |  | 821000 |  |  | 0 | 138 | 138 | 12.15 | Single 795 ACSR Drake | Steel Monopole | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 200 | Sarah Wilson
1021471 | Waller - Chappell Hill TL Add (T232) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington, Waller | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-02-01 | 2021-05-13 |  |  | 1420000 |  |  | 0 | 138 | 138 | 15.93 | Single 795 ACSR Drake | Wood H-Frame | Varies 75 -85 | 15.93 | n/a | n/a | 25.101 (C)(5)(B) |  | 201 | Robert Badger
1021477 | Miller Creek - Mountaintop TL Add (T426) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Blanco | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2020-12-07 | 2021-03-01 |  |  | 1167000 |  |  | 0 | 138 | 138 | 4.81 | (1x) 1433 ACSS/TW Merrimack | Steel Monopole | Centerline 60 - 100 | 4.81 | n/a | n/a | 25.101 (C)(5)(B) |  | 202 | Robert Badger
1023406 | Warda-Winchester (T170) TL Add [Warda - Winchester TL Upgrade 1023202] | Fayette | Increase the transmission capacity of T170: Warda – Winchester 138-kV transmission circuit. LCRA TSC will upgrade T170: Warda - Winchester transmission line to a minimum 105 degree F ambient temperature rating of 580 MVA at 138-kV using single 1433 Merr | 2020-11-29 12:00 | 2021-05-11 12:00 |  |  | 4750000 |  |  | 0 | 138 | 138 | 4.11 | 1-1433.6 ACSS/TW/MA3 "Merrimack" | Steel Pole | 100 | 4.11 | n/a | n/a | 25.101 (C)(5)(B) |  | 203 | Bryan Cooley
1023877 | Ft Mason-Mason (T651) TL Add [Fort Mason Circuit Breaker - 1023806] | Mason | Provide transmission service to a generator; Upgrade 138-kV ring bus to accommodate new circuit termination | 2021-02-01 | 2021-04-26 10:00 |  |  | 3306000 |  |  | 0 | 138 | 138 | .035 | 1-795 ACSR DRAKE | Steel Dead-End Pole | n/a | n/a | 100 | .018 | 25.101 (C)(5)(A) |  | 204 | Robin Mims
1023860 | Lakeway-Marshall (T180) - TL Add [Lakeway - Marshall Ford TL Upgrade - 1023808] | Travis | Increase the reliability of transmission facilities on the T180 Lakeway – Marshall Ford 0.27-mile 138-Kv transmission line by replacing the existing Condor conductor from Marshall Ford Substation structure #1A to structure #1B. | 2021-01-04 | 2021-05-31 17:00 |  |  | 903000 |  |  | 0 | 138 | 138 | 5 | Single 959 ACSS Suwannee conductor (0.27 mile from Marshall Ford Substation to Str. 1A to Str. 1B) | Steel Lattice Towers | 100 | 4.5 | n/a | n/a | 25.101 (C)(5)(B) |  | 205 | Tyreeta Young
1021459 | Wolf Lane - Wyldwood TL Addition (T141) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Bastrop | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-01-19 | 2021-05-07 |  |  | 1563159 |  |  | 0 | 138 | 138 | 5.76 | 1 x 795 Drake ACSR | steel lattice towers, wood/steel H-frame, steel monopoles | 100 | 5.76 | n/a | n/a | 25.101 (C)(5)(B) |  | 206 | Robert Badger
1024390 | OPGW Addition (T187) 1023373 [Ferguson to Wirtz Fiber Upgrade-1023373] | Burnett, Llano | Increase the reliability of the fiber network by replacing deteriorated Optical Ground Wire (OPGW) from Ferguson to Wirtz to improve telecommunication system reliability. | 2021-02-01 | 2021-05-15 |  |  | 600000 |  |  | 0 | 138 | 138 | 9.4 | 795 Drake ACSR | Lattice Towers | 100 | 9.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 207 | Christopher Grimes
1023950 | T-187 TL Addition [Ferguson - Wirtz TL Storm Hardening - 1023805] | Burnett, Llano | Increase the reliability of transmission facilities on the T187 Ferguson – Sherwood Shores 9.3-mile 138-kV transmission line from Ferguson Substation to Wirtz Substation. | 2021-02-01 | 2021-05-15 |  |  | 3575000 |  |  | 0 | 138 | 138 | 9.4 | 795 Drake ACSR | Lattice Towers | 100 | 9.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 208 | Christopher Grimes
1020882 | Ferguson - Sherwood Shores TL Addition Storm Hardening (T187) [Ferguson - Sherwood Shores TL Storm Hardening - 1020881] | Burnett, Llano | Increase the reliability of circuit T187 on the Ferguson – Sherwood Shores 3.5-mile 138-kV transmission line from Sherwood Shores Substation to the Wirtz Split. | 2021-01-02 | 2021-05-14 |  |  | 3368000 |  |  | 0 | 138 | 138 | 3.4 | 795 Drake ACSR | Steel Monopoles | centerline | 3.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 209 | Brian Good
1021982 | SherWShores-Wirtz Split TL Addition (T187) [LCRA Fiber Backbone FY20 - 1021196] | Burnett, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-09-16 | 2021-12-10 |  |  | 279246 |  |  | 0 | 138 | 138 | 3.4 | 795 Drake ACSR | Steel Monopoles | centerline | 3.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 210 | Sarah Wilson