## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
GV01-16 | Meadow Lake Substation | Guadalupe | New Substation, w 30MVA PWT, distribution bays 4 circuits | 2020-03-15 | 2021-01-29 |  | 4.9 M |  | - |  | 100% | 0 | 138 | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Complete
GV01-21 | Geronimo Substation | Guadalupe | Replace 20 MVA T1 unit with 40 MVA unit | 2021-02-01 | 2021-06-11 |  | 2.3 M |  |  |  | 99% | 138 |  | 0 | 0 | Steel | 0 | 0 | 0 | 0 |  | Construction In Progress
GV02-21 | Schumansville Substation | Guadalupe | Replace 20 MVA T2 unit with 40 MVA unit | 2021-09-01 | 2021-02-17 |  | 1.9 M |  |  |  | 0% | 138 |  | 0 | 0 | Steel | 0 | 0 | 0 | 0 |  | Construction to mobilize in September
GV03-21 | Gonzales Interchange (LCRA) - Gonzales (GVEC) T-line and Terminals | Gonzales | Upgrade relaying at both terminals and rebuild existing 69 kV line to 138 kV line w concrete poles | 2021-04-01 | 2021-11-15 |  | 3.3 M |  |  |  | 40% | 69 | 138 | 1 | 795 drake | Concrete/Steel | 60 | 1 | 60 | 1 |  | Terminal construction complete, t-line construction commences in September
GV04-21 | Cibolo Subtation 138 Terminal Addition and Upgrades | Guadalupe | Expand station to accommodate new T306 terminal and future T3, plus add breakers and switches to the existing station | 2021-06-02 | 2022-11-15 |  | 4.7 M |  |  |  | 17% | 138 |  | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Site prep work 90%, Substation construction 10%, Engineering in progress
GV05-21 | McQueeney Substaton 138 Terminal Addition | Guadalupe | Modifications and improvements to add new T306 terminal | 2021-06-02 | 2022-11-07 |  | 2.25 M |  |  |  | 35% | 138 |  | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Construction in progress