## MonthlyReportForm
Utility Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
15T62065 | Graham - Archer City 69 kV | City of Graham, Young County | Replace existing wood pole H-frames with Two (2) new single-circuit, concrete H-frame tangent structures (Str. 36/7 & 36/8). | 2021-10-04 | 2021-12-15 |  | 266075.7 | 253850 |  |  | 0 | 69 | na | 0.38826 | 4/0 ACSS | Concrete H-frames | 100 | 0.38826 | na | na | 25.101(c)(5)(B)
17T65164 | Norwood - Denton Drive 138 kV: Install OPGW | City of Dallas, Dallas County | Replace 3/8" shield wire with OPGW on the Norwood - Denton Drive138 kV Transmission Line. | 2020-04-20 | 2020-06-10 | 2020-06-10 | 318269.74 | 318270 |  |  | 100 | 138 | 138 | 3.9 | OPGW | Steel Poles | 100 | 3.9 | na | na | 25.101(c)(5)(B)
18T64006 (R6087) | Flat Branch (LaTexo) 138 kV POI | Houston County | Install a new 138 kV point of interconnection for Houston County Electric (HCEC) to their existing Latex 138 kV Substation on the Lufkin Switch - Crockett 138 kV Line. HCEC has requested to switch grids. They are currently in SPP and wish to switch to ERCOT. Install three line sectionalizing switches. | 2018-05-01 | 2020-10-30 | 2020-10-30 | 800000 | 726000 |  |  | 100 | 138 | na | 0.06 | 795 kcmil ACSR | Steel Poles | 100 | na | 100 | 0.06 | 25.101(c)(5)(A)
18T61034 0PT37605 | TxDOT Relocation, Liggett-Saginaw 138 kV Line | City of Irving, Dallas County | Install new double-circuit, steel tangent structures. Remove four (4) existing double-circuit steel tangent structures. | 2019-11-09 | 2020-05-02 | 2020-05-02 | 1193327.68 | 1193327.68 |  |  | 100 | 138 | na | 1.1239 | 1033.5 kcmil ACSR | Steel Poles | 140 | 0.56193 | na | na | 25.101(c)(5)(F)
17T62069 0PT38781 (M5260) | Everman Switch - Cedar Hill Switch 345 kV Line (Courtland-Cedar Hill Section): HT Upgrade | City of Arlington, Tarrant County | Upgrade the Courtland - Cedar Hill Switch section of Everman Switch - Cedar Hill Switch 345 kV Line. | 2018-08-20 | 2020-05-14 | 2020-05-14 | 4455604 | 4800000 |  |  | 100 | 345 | na | 20.66 | 795 kcmil ACSR | Steel Lattice | 150 | 11.3 | na | na | 25.101(c)(5)(B)
0PT37192 | Rivercrest Switch - Sulphur Springs East Tap 138 kV Line : CMPC Line Hardening | City of Sulphur Springs, Hopkins County | This is a CMPC Project that covers the cost to rebuild a section of the Rivercrest Switch - Sulphur Springs East Tap 138 kV Line in Hopkins County. The section is 0.1 miles of single-circuit wood H-Frames. | 2020-07-13 | 2020-07-23 | 2020-07-23 | 681893 | 681893 |  |  | 100 | 138 | na | 0.1 | 336.4 kcmil ACSR | Steel H-Frames | 100 | na | na | na | 25.101(c)(5)(B)
0PT37196 0PT41818 | Eskota Switch - Sweetwater Creek POI 69 kV Line | City of Sweetwater, County of Nolan | Relocate and replace 4 structures across Interstate 20 for CMPC System Hardening | 2020-08-10 | 2020-09-30 | 2020-09-30 | 710393.02 | 1325477.3 |  |  | 100 | 69 | na | 0.1 | ACSR 4/0 | Concrete Monopole, Wood Monopole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT37389 | DFW D West - DFW E East UG Fiber Installation | Tarrant County | Install 1.4 mile of UG fiber from DFW D West to DFW E East on the Liggett - Euless 138 kV Line. | 2018-12-03 | 2020-12-10 | 2020-12-10 | 565552 | 565552 |  |  | 100 | 0 | 0 | 1.4 | ADSS Fiber | UG | na | 1.1 | 30 | 0.31 | 25.101(c)(5)(B)
16T65165 0PT39960 (M4110) | Crown Road - Norwood Switching Station 138 kV Line Rebuild | City of Dallas, Dallas County | Upgrade the 9.1 mile Crown Road - Norwood Switching Station double-circuit line. Upgrade the 138 kV terminal equipment to meet or exceed 2000 A. | 2018-12-17 | 2020-04-29 | 2020-04-29 | 12229402 | 16300813 |  |  | 100 | 138 | 138 | 18.2 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | Varies | 9.1 | Varies | na | 25.101(c)(5)(B)
0PT04278 | Anna Switch - McKinney Sub 138 kV line: Cut-In to Weston Sub | City of McKinney, Collin County | Relocating Structure associated with establishing Weston Substation | 2020-04-08 | 2020-05-07 | 2020-05-07 | 146533 | 270000 |  |  | 100 | 138 | na | 0.1 | 1233.6 ACSS/TW | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
16T62099 0PT41013 (M5245) | Structure 4/5 - North Main Switch (West) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the structure 4/5 - North Main Switch (West Ckt) section of the Saginaw - Denton Ave - North Main Switch 138 kV line. The project consists of rebuilding the West circuit of the 2.1 mile line from structure 4/5 - Heritage. The rebuilt line will support 959.6 kcmil ACSS/TW conductor on double-circuit steel monopole structures. | 2019-02-04 | 2020-12-18 | 2020-12-18 | 3840000 | 3840000 |  |  | 100 | 69/138 | 138 | 2.1 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 2.1 | na | na | 25.101(c)(5)(B)
18T62003 (M5245) | Structure 4/5 - North Main Switch (East) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the structure 4/5 - North Main Switch (East Ckt) section of the North Main Switch - Richland Hills 138 kV line. The project consists of rebuilding the West circuit of the 2.1 mile line from structure 4/5 - North Main Switch. The rebuilt line will support 959.6 kcmil ACSS/TW conductor on double-circuit steel monopole structures. | 2019-02-04 | 2020-06-10 | 2020-06-10 | 1040000 | 1040000 |  |  | 100 | 69/138 | 138 | 2.1 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 2.1 | na | na | 25.101(c)(5)(B)
0PT04374 0PT38764 0PT40259 0PT39330 0PT39738 (R84063) | Wink - Notrees Sw 138 kV Line: Rebuild | City of Wink, Winkler County | Rebuild the 27.8-mile Wink Sw. Sta. - No Trees Sw. Sta. 138 kV Line using a conductor rated 2569 A or greater. Use double-circuit 138 kV structures with one circuit in place. Upgrade all line terminal and associated equipment to meet or exceed 2000 A and removal conductor and structures. | 2019-05-03 | 2020-09-01 | 2020-09-12 | 36735997.65 | 37590845.65 |  |  | 100 | 138 | na | 27.8 | 1926.9 ACSS/TW/HS | Steel Poles | 50 | 27.8 | na | na | 25.101(c)(5)(B)
19T65004 (M4226) | Tri Corner Switch - Watermill Switch 345 kV Line: Reconductor | Cities of Lancaster and Seagoville, Dallas County | Reconductor 11.5 miles from Tri Corner Switch – Watermill Switch 345 kV South circuit. | 2019-02-04 | 2020-06-30 | 2020-06-30 | 10189806.17 | 10189806.17 |  |  | 100 | 345 | na | 11.5 | (2) 959.6 kcmil ACSS/TW - Bundle Suwannee | Steel Towers | 165 | 11.5 | na | na | 25.101(c)(5)(B)
0PT37248 18T80028 (R1736) | Benbrook Junction - Rocky Creek Sw HT Upgrade | City of Benbrook, Tarrant County | Upgrade the 8 miles, Benbrook Junction to Rocky Creek portion of the Mitchell Bend - Rocky Creek 345 kV Line for High Temperature operation. | 2019-09-03 | 2020-12-14 | 2020-12-14 | 13720449.23 | 13720449.23 |  |  | 100 | 345 | 345 | 8 | (2) 1590 kcmil ACSS | Steel Poles | 100 | 8 | na | na | 25.101(c)(5)(B)
18T62005 (M5245) | Structure 4/5 - Springdale (South) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the structure 4/5 - Springdale (South Ckt) section of the North Main Switch - Richland Hills 138 kV line. The project consists of rebuilding the South circuit of the 2.6 mile line from structure 4/5 - Springdale. | 2019-02-18 | 2020-06-10 | 2020-06-10 | 690000 | 690000 |  |  | 100 | 69/138 | 138 | 2.6 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 2.6 | na | na | 25.101(c)(5)(B)
16T62072 (M5161) | Saginaw - North Main 138 kV Line: Cut in to new North Main Sub | City of Fort Worth, Tarrant County | Build a cut in to Oncor North Main Sub on the Saginaw - North Main 138 kV Line. The Interconnect will be between the existing Heritage Sub and the new North Main Sub. | 2019-03-19 | 2021-04-01 | 2021-04-01 | 697036.76 | 697037 |  |  | 100 | 138 | na | 0.1 | 959.6 kcmil ACSS/TW | Steel Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A)
16T62077 (M5161) | Connect North Main Sub To North Main Switch | City of Fort Worth, Tarrant County | Connect the North Main Sub to North Main Switch on the Randol Mill - North Main 138 kV Line. The initial line will be between the existing North Main Switch and the new North Main Sub. | 2019-03-19 | 2020-06-29 | 2020-06-29 | 659044.01 | 1057827 |  |  | 100 | 138 | na | 0.3 | 959.6 kcmil ACSS/TW | Steel Poles | 50 | 0.3 | na | na | 25.101(c)(5)(A)
0PT37277 | Temple - Minerva 69 kV Line: Relocation | City of Temple, Bell County | Relocate approximately 0.75 miles of the Temple - Minerva 69 kV Line in order to accommodate Waste Management's proposed landfill. | 2019-07-10 | 2019-11-15 | 2019-11-15 | 931000 | 1141647 |  |  | 100 | 69 | na | 0.6 | 959.6 kcmil ACSS/TW | Steel/Concrete Poles | 100 | 0.75 | 100 | 0.6 | 25.101(c)(5)(D)
0PT38413 0PT38812 (R712) | Battalion POD 138 kV Loop Line | City of Killeen, Bell County | Construct a 138 kV loop line off the Killeen Park St. 138 kV Line to aide in establishing the Battalion POD. | 2019-05-30 | 2019-09-17 | 2019-09-17 | 2587745 | 2787745 |  |  | 100 | na | 138 | 0.8 | 1-959.6 ACSS/TW/HS | Steel Poles | na | na | 70 | 0.8 | 25.101(c)(5)(A)
0PT38341 (R712) | Killeen Park Street 138 kV Line: Modifications to Serve Battalion POD | City of Killeen, Bell County | Add a second circuit to the existing Killeen Park St. 138 kV Tap Line from structure 2C/6 A to structure 1/5 A. | 2019-06-03 | 2020-11-13 | 2020-11-13 | 1800000 | 1950000 |  |  | 100 | 138 | 138 | 1.2 | 1-959.6 ACSS/TW/HS | Steel Poles | na | 0.5 | na | 0.5 | 25.101(c)(5)(C)
0PT38070 (R8341) | Wink - Culberson 138 kV Line: Modify for Riverton - Sand Lake 345 kV Line | Reeves County | Modify the Wink - Culberson 138 kV transmission line due to the new construction of the Riverton – Sand Lake 345 kV line | 2019-11-04 | 2020-05-01 | 2020-05-01 | 1300000 | 1600000 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW/HS | Steel Poles | 50 | na | 160 | 0.26 | 25.101(c)(5)(D)
0PT37287 | Valley Switch - Paris Switch 345 kV Line: Relocate for the Lower Bois d'Arc Creek Reservoir | Fannin County | Rebuild and raise the Valley – Paris 345 kV line at the request of the North Texas Municipal Water District in order to accommodate the proposed Lower Bois d’Arc Creek Reservoir. | 2019-09-25 | 2020-06-15 | 2020-06-15 | 18300000 | 20500000 |  |  | 100 | 345 | na | 12.8 | (2) 1926.9 ACSS/TW/HS Bundled | Steel Poles | 150 | 6.4 | na | na | 25.101(c)(5)(E)
0PT37288 | Valley Switch - Paris Switch 138 kV Line: Relocate for the Lower Bois d'Arc Creek Reservoir | Fannin County | Rebuild and raise the Valley – Paris 138 kV line at the request of the North Texas Municipal Water District in order to accommodate the proposed Lower Bois d’Arc Creek Reservoir. | 2019-09-18 | 2020-07-01 | 2020-07-01 | 7200000 | 8750000 |  |  | 100 | 138 | na | 6.62 | 1926.9 ACSS/TW/HS | Steel Poles | 100 | 6.62 | na | na | 25.101(c)(5)(E)
0PT38473 0PT39092 | Rebuild Screwbean Tap - Screwbean Sub 138 kV Line | Culberson County | Rebuild 0.2 miles of the Screwbean Tap - Screwbean Sub Line to accommodate the new transformer being installed in the Screwbean Sub, utilizing 1926.9 ACSS/TW "Cumberland". | 2019-11-18 | 2019-12-31 | 2019-12-31 | 806112.94 | 966112.94 |  |  | 100 | 138 | na | 0.23 | 1926.9 ACSS/TW/HS | Steel Poles | na | na | 150/100 | 0.23 | 25.101(c)(5)(B)
0PT04154 0PT39028 | Arco (DME) Switch - Collin Switch 138 kV Line: Establish Blagg Sub | City of Denton, Denton County | Cut-in approximately 0.7 miles of the Arco (DME) Switch - Collin Switch 138 kV line to establish Blagg Sub. | 2020-10-02 | 2020-12-31 | 2020-12-31 | 2129112.39 | 526108 |  |  | 100 | 138 | 138 | 0.2 | 1926.9 ACSS/TW | Steel Monopoles | 70 | 0.1 | na | na | 25.101(c)(5)(A)
0PT38731 0PT39093 | Falcon Seaboard Switch-Midland East Sub 345 kV Line: Hardening 44/5 & 44/4 | City of Big Springs, Howard County | Rebuild a section from Falcon Seaboard Switch to Midland East Substation 345 kV Line by replacing two lattice H frames with two dead-end towers. | 2020-02-22 | 2020-11-02 | 2020-11-02 | 820852.45 | 1307097.45 |  |  | 100 | 345 | na | 0.2 | (2) 795 ACSR | Steel Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38393 | Falcon Seaboard Switch-Midland East Sub 345 kV Line: Hardening 55/2 | City of Stanton, Martin County | Replace structure 55/2 with a dead-end structure to harden the line. | 2020-01-25 | 2020-05-01 | 2020-05-01 | 488000 | 613018 |  |  | 100 | 345 | 345 | 0.4 | 2 - 795 MCM ACSR Drake | Lattice Towers | 150 | 0.4 | na | na | 25.101(c)(5)(B)
0PT38582 0PT40001 | Falcon Seaboard Switch - Midland East Sub 345 kV Line : Hardening 63/1 & 63/2 | City of Midland, County of Midland | Rebuild a section of the Falcon Seaboard Switch - Midland East Sub 345 kV Line in Midland County. Replace two (2) H-frame lattice structures (63/1 & 63/2) adjacent to I-20 with dead-end towers. | 2020-02-21 | 2020-04-07 | 2020-04-07 | 802809.17 | 1037637.17 |  |  | 100 | 345 | na | 0.2 | 2 - 795 ACSR Drake | Lattice Steel Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38587 0PT40000 | Falcon Seaboard Switch - Midland East Sub 345 kV Line: Hardening 35/4 & 35/5 | City of Big Spring, County of Howard | Rebuild a section of the Falcon Seaboard Switch - Midland East Sub 345 kV Line in Howard County. | 2019-04-02 | 2020-04-07 | 2020-04-07 | 780762.77 | 1115309.77 |  |  | 100 | 345 | na | 0.2 | 2 - 795 ACSR Drake | Lattice Steel Towers | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38496 (M5285) | Bowen East 138 kV Tap Line: Conductor Removal | City of Arlington, Tarrant County | Remove the Bowen East 138 kV Tap Line. | 2020-04-14 | 2020-04-30 | 2020-04-30 | 224817.55 | 224818 |  |  | 100 | 138 | na | 1.7 | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT38456 17T65128 0PT38387 (M4202) | TI-Schroeder 138 kV UG Line: Increase double-circuit Section Ampacity | City of Dallas, Dallas County | Rebuild to increase the ampacity of the 0.5 mile double-circuit TI - Schroeder 138 kV UG Line section. | 2019-05-01 | 2020-05-22 | 2020-05-22 | 29613898 | 30000000 |  |  | 100 | 138 | 138 | 0.5 | 3-3500 kcmil Cu HPFF, 2-6000 kcmil Cu XLPE | Underground Transmission Line | 100 | 0.45 | na | na | 25.101(c)(5)(B)
0PT37683 (R6103) | Lake Creek Switch - Tradinghouse Switch (East Ckt) 345 kV Line: Lake Hall Sw. Line Work | City of Hallsburg, McLennan County | Cut in the Lake Hall Switch (Prairie Hill Wind Interconnect) into the Lake Creek Sw. - Tradinghouse Sw. (East) 345 kV Line. | 2019-11-21 | 2020-09-02 | 2020-09-02 | 849108 | 1008746 |  |  | 100 | 345 | na | 0.1 | 959.6 kcmil ACSS/TW/HS | Lattice Steel Towers | 170 | 0.1 | na | na | 25.101(c)(5)(A)
0PT04098 (M3211) | Roanoke to Coppell (BEC) 138 kV Line: Cut-In at Vineyard Switch (West) | City of Grapevine, Tarrant County | Separate and terminate the Roanoke Switch - Euless 138 kV Line to establish the new Vineyard Switch. | 2021-10-15 | 2021-10-31 |  | 400262 | 907000 |  |  | 0 | 138 | 138 | 0.13 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.13 | Varies | na | 25.101(c)(5)(B)
0PT38352 | Graham Switch - Tonkawa Switch 345 kV Line: CMPC Hardening 133/3 &133/4 | Scurry County | Replace structures 133/3 & 133/4 with dead-end structures to harden the line. | 2019-09-10 | 2019-10-11 | 2019-10-11 | 795443 | 380000 |  |  | 100 | 345 | 345 | 0.2 | 2 - 795 MCM ACSR “Drake | Lattice Towers | 190 | 0.2 | na | na | 25.101(c)(5)(B) | Cost and project was updated to include ROW estimates in November 2020. This was not accurate and the project is being revised back to its original values.
0PT38380 0PT39448 (R6071) | Tyler West Sub - Tyler Switch 138kV Line: Upgrade | Tyler, Smith County | The Tyler West - Tyler Switch 138 kV line will be upgraded and hardened to prepare the idle line to be energized. | 2019-09-16 | 2020-12-30 | 2020-12-30 | 1251985.89 | 2147670.89 |  |  | 100 | 138 | 138 | 5.3 | 795 kcmil 26/7 ACSR Drake | Steel Towers, Wood H-Frames, Concrete H-Frames, and Steel Monopoles | varies | na | varies | na | 25.101(c)(5)(B)
0PT38081 0PT40571 0PT39737 (R8493) | No Trees Switch - Andrews County South Switch 138 kV Line: Rebuild | City of Wink, Winkler County | Rebuild the 8.8 miles of single-circuit wood h-frames. The final build will utilize double-circuit steel monopoles. Re-terminate the line going to Andrews North on the first rung and terminate the new line going to the second autotransformer on the second rung. | 2019-03-29 | 2020-05-14 | 2020-05-14 | 17030968.49 | 19025422 |  |  | 100 | 138 | 138 | 8.8 | 1926 kcmil ACSS/TW | Steel and Concrete Poles | 50-125 | 8.8 | na | na | 25.101(c)(5)(B)
0PT04329 (R8444) | Installation for Canyon Wind POI, Scurry County South Switch-Canyon Wind 138 kV Line | City of Dunn, Scurry County | Installation with new single-circuit, steel monopole dead end structures. The installation is at the request of the Canyon Wind. | 2021-07-01 | 2021-12-30 |  | 1412751.89 |  |  |  | 0 | na | 138 | 0.28049 | 959 ACSS/TW Suwannee | Steel Monopole Structures | na | na | na | na | 25.101(c)(5)(A)
0PT39956 (R6092) | Jacksonville Plant Sub - Jacksonville Switch 69 kV Line: Reterm | City of Jacksonville, Cherokee County | Reterminate the Jacksonville Plant - Jacksonville Tap - Jacksonville Switch 69 kV Line for the rebuild of the Jacksonville Switch Station. | 2019-10-15 | 2019-12-18 | 2019-12-18 | 240000 | 240000 |  |  | 100 | 69 | na | 0.1 | 795 kcmil ACSR | Steel or Concrete Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT38450 | Kirkland Park Sub - Ti Sub 138 kV Line: Replace 3/8 Edhs Shield Wire | City of Dallas, Dallas County | Replace the 3/8" EHS shield wire with OPGW on the Kirkland Park - Schroeder Road section of the Kirkland Park Sub - TI Sub 138 kV Line. | 2021-03-29 | 2021-05-15 |  | 514856.41 | 514856 |  |  | 99 | 138 | na | 2.1 | OPGW | Steel Monopoles | 100 | 2.1 | na | na | 25.101(c)(5)(A)
0PT39714 (M4108) | Northaven Switch-Renner Switch 138 kV: Rebuild Alpha Rd. - Knoll Trail. | City of Dallas, Dallas County | Rebuild the 2.25 mile Alpha Road-Knoll Trail 138 kV double-circuit line using a conductor rated for 2569A or greater. | 2019-04-15 | 2020-05-25 | 2020-05-25 | 6606401.32 | 6850000 |  |  | 100 | 138 | 138 | 4.5 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 2.25 | na | na | 25.101(c)(5)(B) | The original project was Northaven-Renner (16T65090), and it was split so that we now have Northaven-Alpha Road & Knoll Trail-Preston Road North (16T65186), Preston Road North-Renner (16T65090), and Alpha Road-Knoll Trail (0PT39714). The WA that should now be associated with this project on the PUC Report is 0PT39714.
0PT40192 (R8482) | Dog House - Prospero Solar 345 kV Line | Andrews County | Install one monopole and one span of wire to connect the customer line to Doghouse Switch. | 2020-01-06 | 2020-04-16 | 2020-04-16 | 590033 | 450000 |  |  | 100 | na | 345 | 0.3 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(A)
0PT38448 (M5289) | Krum Tap Switch - Gainesville Sub 138 kV Line: Rippey Solar Interconnect | City of Gainesville, Cooke County | This project interconnects the Rippey Solar on the Krum Tap Sw - Gainesville Sub 138 kV Line at the Ray Roberts Switch. | 2020-04-07 | 2020-11-06 | 2020-11-06 |  | 1155000 |  |  | 100 | 138 | 138 | 0.3 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT37229 (M5277) | Roanoke Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (Roanoke/Euless) 138 kV line connecting to new Deen Sw. | 2020-05-05 | 2020-12-16 | 2020-12-16 | 958557.96 | 958558 |  |  | 100 | 138 | 138 | 0.1 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B)
0PT37237 (M5277) | Handley Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (Handley) 138 kV line connecting to new Deen Sw. | 2020-05-07 | 2020-12-16 | 2020-12-16 | 943604.37 | 943604 |  |  | 100 | 138 | 138 | 0.1 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B)
0PT37236 (M5277) | Hicks Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (Hicks) 138 kV line connecting to new Deen Sw. | 2020-04-10 | 2020-12-16 | 2020-12-16 | 1387626.12 | 1387627 |  |  | 100 | 138 | 138 | 0.3 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B)
0PT37238 (M5277) | Eagle Mountain Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (Eagle Mtn.) 138 kV line connecting to new Deen Sw. | 2020-05-05 | 2020-12-16 | 2020-12-16 | 1387626.12 | 1387627 |  |  | 100 | 138 | 138 | 0.3 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B)
0PT37235 (M5277) | North Main Switch - Saginaw Switch 138 kV Line: Reterminate to Deen Switch | City of Fort Worth, Tarrant County | Retermination of double-circuit (N. Main) 138 kV line connecting to new Deen Sw. | 2020-04-10 | 2021-01-22 | 2021-01-22 | 810689.33 | 810689 |  |  | 100 | 138 | 138 | 0.2 | 2-959.6 kcmil ACSS/TW | Steel Poles | na | na | na | na | 25.101(c)(5)(B)
0PT38778 (M5291) | Monticello Switch - Paris Switch 345 kV Line: Establish Woodard Switch | Lamar County | Establish a point of interconnection to the Impact Solar LLC generating facility by establishing Woodard Switch on the Monticello - Paris 345 kV transmission line. | 2020-04-16 | 2020-05-15 | 2020-05-15 |  | 2000776 |  |  | 100 | 345 | 345 | 0.25 | 2-959.6 kcmil ACSS/TW | Steel Towers | 170 | na | 370 | 0.25 | 25.101(c)(5)(A)
0PT38200 (M4232) | Carrollton East - Renner/Northaven 138 kV Line: Rebuild Farmers Branch Gillis - Structure T308A | City of Farmers Branch, Dallas County | Rebuild the 1.3 mile section of the Carrollton East - Renner Sw/Northaven Sw 138 kV Line from Farmers Branch Gillis – Structure T308A using conductor greater than 1928A. Rebuild will end at structure T308A which is where the two circuits split to Renner and Northaven respectively. | 2019-11-25 | 2020-04-03 | 2020-04-03 |  | 5500000 |  |  | 100 | 138 | na | 1.3 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 1.3 | na | na | 25.101(c)(5)(B)
0PT38236 0PT39305 (R470) | Lake Creek Switch - Waco East Switch 138 kV Line: Rebuild Lake Creek Switch - Waco LaSalle Sub | City of Waco, McLennan County | Rebuild of 7.6 mile 138 kV Line of single-circuit wooden h-frame structures to steel monopoles | 2020-01-21 | 2020-05-21 | 2020-05-21 | 12826983.46 | 12826983.46 |  |  | 100 | 138 | 138 | 7.6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 7.6 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT40107 (R470) | Lake Creek Switch - Waco East Switch 138 kV Line: Rebuild Waco LaSalle Sub - Structure 1/9 section | City of Waco, McLennan County | Rebuild of 2.2 mile 138 kV Line of single-circuit wooden h-frame structures to steel monopoles | 2020-09-10 | 2020-12-03 | 2020-12-03 |  | 4450342 |  |  | 100 | 138 | 138 | 2.2 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 2.2 | na | na | 25.101(c)(5)(B)
18T62020 0PT39481 (M5245) | Springdale - Richland HiIls (South Ckt) 138 kV Line | City of Fort Worth, Tarrant County | Rebuild the Springdale - Richland Hills (South Ckt) section of the North Main Switch - Richland Hills 138 kV line. The project consists of rebuilding the South circuit of the 3.7 mile line from Str 3/5 S - 7/3 S. | 2020-06-16 | 2020-12-18 | 2020-12-18 |  | 1057479 |  |  | 100 | 69/138 | 138 | 3.7 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 3.7 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT40145 (R8494) | Wolf Switch - Moss Switch 138 kV line: High Temp Upgrade | Ector & Ward County | Upgrade the Moss Switch – Wolf Switch 138 kV line for 120°C and 1146A, high temperature operation. | 2019-12-12 | 2019-12-21 | 2019-12-21 |  | 1007917 |  |  | 100 | 138 | 138 | 2 | 795 kcmil ACSR | Wood H-Frames | 50 | 2 | na | na | 25.101(c)(5)(B)
0PT38115 (R966) | Lewisville Switch (Brazos) - Lakepoint Switch (TNMP) Sub. 138 kV Line: Reconductor | City of Lewisville, Denton County | Upgrade 5.3 miles of the Lewisville Switch (BEC) – Lakepoint (TNMP) 138 kV Line using conductor 959.6 MCM ACSS "Suwanee” with E3X coating designed to operate at 1996 Amps and 200C. The existing 3/8" EHS shield wire will be replaced with 0.546" OD 48 count OPGW. Upgrade all line terminal and associated equipment to meet or exceed 1996 A. | 2020-02-10 | 2020-04-02 | 2020-04-02 |  | 4645000 |  |  | 100 | 138 | na | 5.3 | 959.6 kcmil ACSS/TW | Steel Towers | Varies | 5.3 | na | na | 25.101(c)(5)(A)
0PT39974 0PT40949 (R8511) | SL Pemkiff - Ringo 138kV Line: Slager Lake POD | Reagan County | Provide a 138 kV point-of-delivery (POD) for Sherrod on the Pemkiff - Ringo 138 kV line. The POD will be located approximately 1.8 miles east of the Pemkiff substation. In addition the cost to remove 1 existing concrete pole along the Pemkiff – Ringo 138 kV transmission line. This removal is required to accommodate the new Slager Lake POD for XTO Sherrod Substation. | 2020-03-13 | 2020-05-19 | 2020-05-19 |  | 1100000 |  |  | 100 | 138 | na | 0.9 | 959.6 ACSS/TW | Steel Poles | na | na | 105 | 0.5 | 25.101(c)(5)(A)
0PT39620 (R8478) | Spraberry Switch - Midland East 138 kV Line : Cloverdale POD | City of Midland, Midland County | Provide a 138 kV point-of-delivery (POD) on the Spraberry Switch - Midland East 138 kV line. The POD will be located approximately 2.0 miles southeast of the Midland East Substation. | 2020-04-17 | 2020-06-24 | 2020-06-24 |  | 2436280 |  |  | 100 | 138 | na | 0.9 | 1926.9 ACSS/TW | Steel Poles | na | na | 70 | 0.9 | 25.101(c)(5)(A)
0PT40458 (M5312) | Ringgold Magnolia Tap – Beaver Creek Tap 69 kV Line: Install Barrel Springs (Oneok) POI | Clay County | Provide a 138 kV point-of-interconnect (POI) for TNMP's Oneok on the Ringgold Magnolia Tap - Beaver Creek Tap 69 kV line. The POI will be located approximately 2.6 circuit-miles from Beaver Creek Tap. | 2020-02-13 | 2020-04-16 | 2020-04-16 |  | 1050000 |  |  | 100 | 69 | na | 0.5 | 1/0 ACSR, 959.6 ACSS/TW | Steel Poles | na | na | 100 | 0.5 | 25.101(c)(5)(A)
0PT39894 (R8485) | McKenzie Draw Switch - Midland County Northwest/Midland East Switch 138 kV Line: Kelton Windmill POD | Martin County | Establish a point of delivery on the eastern circuit of the McKenzie Draw Switch - Midland County Northwest/Midland East Switch 138 kV transmission line. | 2020-01-27 | 2020-03-09 | 2020-03-09 |  | 2100000 |  |  | 100 | 138 | na | 0.29 | 1926.9 ACSS/TW/HS | Steel Poles/ H-frame Switch | 75 | na | 70 | 0.29 | 25.101(c)(5)(A)
0PT40457 0PT40948 (R8525) | Brown - Grady 138 kV Line: Lenorah POD | Martin County | Establish a point of delivery by establishing Lenorah Switch on the Brown - Grady 138 kV transmission line. Remove concrete poles on the Brown - Grady 138 kV Line to accommodate the new Lenorah POD. | 2020-04-02 | 2020-06-08 | 2020-06-08 |  | 1950000 |  |  | 100 | 138 | 138 | 0.3 | 1-1926.9 kcmil ACSS/TW | Steel Monopoles | 70 | na | 70 | 0.3 | 25.101(c)(5)(A)
0PT39916 | McDonald Road-Big Spring Switch 138 kV Line: Loop into Hill Crest Sub | City of Big Spring, Howard County | Reconfigure McDonald Road-Big Springs Switch 138 kV line to loop into new Hill Crest Sub | 2020-01-05 | 2020-03-09 | 2020-03-09 |  | 1000000 |  |  | 100 | 138 | na | 0.02 | 1926.9 ACSS/TW | Steel DE Monopoles | 100 | 0.5 | na | na | 25.101(c)(5)(A)
0PT40226 | Big Spring Switch-Chalk 69 kV line: Modify Line for Hill Crest Sub | City of Big Spring, Howard County | Reconfigure Big Spring Switch-Chalk 69 kV Line to support the establishment of the new Hill Crest | 2020-01-02 | 2020-03-09 | 2020-03-09 |  | 1500000 |  |  | 100 | 69 | na | 0.02 | 1926.9 ACSS/TW | Steel DE 3-poles | 100 | 0.5 | na | na | 25.101(c)(5)(A)
0PT39135 (R8477) | Yucca Drive Switch-Holt Switch 138 kV Line: Loop into Turnbaugh Corner Switch | City of Goldsmith, Ector County | Looping the Holt Sw-Yucca Drive Sw 138 kV Line into the Turnbaugh Corner Switching Station | 2020-02-18 | 2020-06-15 | 2020-06-15 |  | 1800000 |  |  | 100 | 138 | na | 1 | 1926.9 ACSS/TW | Steel Monopoles | 75 | 1 | na | na | 25.101(c)(5)(A)
0PT39137 (R8477) | Turnbaugh Corner Switch-Holt Switch 138 kV Line: Loop into Turnbaugh Corner Switch | City of Goldsmith, Ector County | Establish a new transmission line from Turnbaugh Corner Switch to the customer owned Oxy Goldsmith Substation | 2020-02-13 | 2020-06-01 | 2020-06-01 |  | 800000 |  |  | 100 | 138 | na | 0.2 | 795 ACSR | Steel Monopoles | 75 | 0.2 | na | na | 25.101(c)(5)(A)
0PT40144 0PT41448 (R8493) | Wink Switch - Notrees Switch 138 kV Line : Install Second Circuit | City of Wink, Winkler County | Install second circuit to the newly rebuilt 29 miles Wink - Notrees 138 kV Line. | 2019-12-17 | 2020-05-11 | 2020-05-11 |  | 15021928 |  |  | 100 | 138 | na | 28 | 1926.9 ACSS/TW | Steel Poles | 50 | 29 | na | na | 25.101(c)(5)(C)
0PT41051 0PT41482 | Eskota Switch - Morgan Creek Switch 138 kV Line : Structure Replacements | City of Sweetwater, County of Nolan | Replace 2 H-Frame structures and remove 1 H-Frame structure. | 2020-08-27 | 2020-09-30 | 2020-09-30 |  | 453091.08 |  |  | 100 | 138 | na | 0.1 | 795 ACSR | Steel, Monopoles | 70 | 0.1 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT40946 | Comanche Switch - Corn Trail Switch 345 kV Line: CMPC Insulator Replacement | Comanche/ Comanche County | Replace insulators on the Comanche - Corn Trail 345 kV Line. | 2020-03-10 | 2020-06-23 | 2020-06-23 |  | 467396 |  |  | 100 | 345 | 345 | 7.7 | 2 - 1590 kcmil ACSR Falcon | Steel Lattice Towers | 160 | 7.7 | na | na | 25.101(c)(5)(B)
0PT41067 | Benbrook South Tap Rebuild | City of Benbrook, Tarrant County | Upgrade the conductor on the 0.2 mile Benbrook South Tap 138 kV Line. | 2020-02-04 | 2020-03-15 | 2020-03-15 |  | 550000 |  |  | 100 | 138 | na | 0.2 | 795 ACSR | Concrete/Steel Poles | 75 | na | na | na | 25.101(c)(5)(B)
0PT39277 (M3213) | Royse Switch - Oates (TMPA) 138 kV Line: Fate Sub Cut-in | City of Fate, Rockwall County | Separate and terminate the Royse Switch - Oates (TMPA) 138 kV Line to establish the new Fate Substation. | 2020-03-23 | 2020-05-04 | 2020-05-04 |  | 1147948 |  |  | 100 | 138 | 138 | 0.2 | BUNDLED (2X) 959.6 kcmil ACSS/TW | Steel Poles | Varies | 0.2 | Varies | na | 25.101(c)(5)(A)
18T64093 0PT37433 (R6061) | Jewett Switch - Crockett 138 kV Line: Rebuild Centerville Sub to Pleasant Springs | Leon County | Rebuild the 7.6 mile section from Centerville to Pleasant Springs of the Jewett - Crockett 138 kV Line using double-circuit monopole construction with only one circuit installed. | 2020-01-06 | 2020-05-05 | 2020-05-05 |  | 6945795.06 |  |  | 100 | 138 | 138 | 7.6 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 7.6 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT04097 0PT41190 (M3211) | Vineyard Switch - Flower Mound 138kV Line: Disconnect and Rebuild Vineyard Switch to McKamy Tap | City of Grapevine, Tarrant County | Extend the McKamy Tap line section into the new Vineyard Switch | 2021-07-15 | 2021-10-31 |  |  | 3815919 |  |  | 0 | 138 | 138 | 1.5 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.5 | Varies | 0.97 | 25.101(c)(5)(A) | Costs updated to include associated ROW estimates.
0PT04105 (M3211) | Vineyard Switch - Coppell 138kV Line: Disconnect and Rebuild Vineyard Switch to McKamy Tap | City of Grapevine, Tarrant County | Disconnect the Grapevine Junction - Coppell line section and extend to the new Vineyard Switch | 2021-07-15 | 2021-10-31 |  |  | 6648486 |  |  | 0 | 138 | 138 | 1.5 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.5 | Varies | 0.97 | 25.101(c)(5)(A)
0PT04103 (M3211) | Roanoke to Coppell (BEC) 138 kV Line: Cut-In at Vineyard Switch (East) | City of Grapevine, Tarrant County | Disconnect the Grapevine Junction - Coppell line section and extend to the new Vineyard Switch | 2021-07-15 | 2021-10-31 |  |  | 1395620 |  |  | 0 | 138 | 138 | 1.5 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.5 | Varies | 0.97 | 25.101(c)(5)(A)
0PT40370 0PT40913 (R8489) | Vealmoor - Brown 138 kV Line: Vealmoor Retermination | Borden County | The scope of this project is to reterminate the Vealmoor - Brown 138 kV Line at its new terminal location at Vealmoor. This retermination will be 275 feet, utilizing one (1) new single circuit monopole dead-end. Existing dead-end structure 1/1 will be reused to route the line north. | 2020-02-23 | 2020-03-01 | 2020-03-01 |  | 303000 |  |  | 100 | 138 | 138 | 0.05 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 0.05 | Varies | na | 25.101(c)(5)(A)
0PT40690 0PT40914 (R8489) | Luther - Vealmoor 138 kV Line: Vealmoor Retermination | Borden County | The scope of this project is to reterminate the Vealmoor - Luther 138 kV Line at its new terminal location at Vealmoor. This retermination will be 300 feet, utilizing only new conductor and shield wire. No new structures will be installed as a part of this project. | 2020-02-24 | 2020-03-01 | 2020-03-01 |  | 59000 |  |  | 100 | 138 | 138 | 0.06 | 795 MCM ACSR Drake | Steel Poles | Varies | 0.06 | Varies | 0 | 25.101(c)(5)(A)
0PT40691 0PT40915 (R8489) | Longdraw - Vealmoor 345 kV Line: Vealmoor Retermination | Borden County | The scope of this project is to reterminate the Longdraw - Vealmoor 345 kV Line at its new terminal location at Vealmoor. | 2020-01-26 | 2020-03-01 | 2020-03-01 |  | 355700 |  |  | 100 | 138 | 138 | 0.09 | 2 - 795 MCM ACSR Drake | Steel Poles | Varies | 0.09 | Varies | 0 | 25.101(c)(5)(A)
0PT40102 | TxDOT Relocation I30 Crossing Forney-Mesquite 138kV Line | City of Mesquite, Dallas County | Relocation with new double circuit, steel monopole dead end and tangent structures. | 2020-02-05 | 2020-04-28 | 2020-04-28 |  | 909704 |  |  | 100 | 138 | na | 0.6 | 795 ACSR Drake | Steel Monopole Structures | 100 | 0.3 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT40112 | TxDOT Relocation I635 Crossing Forney-Mesquite 138kV Line | City of Mesquite, Dallas County | Relocation with new double circuit, steel monopole dead end and tangent structures. | 2020-02-06 | 2020-04-28 | 2020-04-28 |  | 1164170 |  |  | 100 | 138 | na | 1.3121 | 795 ACSR Drake | Steel Monopole Structures | 100 | 0.65606 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
14T61006 | Relocation for Skyline Landfill, Waxahachie-Ferris-Trinity Hts. 69kV Line | City of Ferris, Dallas County | Relocation with new single circuit, steel monopole dead end structures. | 2020-03-09 | 2020-05-15 | 2020-05-15 |  | 2053820 |  |  | 100 | 69 | na | 1.1945 | 959 ACSS/TW Suwannee | Steel Monopole Structures | 100 | 1.1945 | 100 | 0.71496 | 25.101(c)(5)(D) | Structure relocation is at the request of Waste Management of Texas Inc. and is 100% reimbursable by Waste Management of Texas Inc..
0PT39936 | Relocation for Bremond Mine, Lake Creek-Jewett-Twin Oak 345kV Line | City of Bremond, Robertson County | Relocation with new double circuit, steel lattice tower dead end and tangent structures. | 2020-08-22 | 2020-11-07 | 2020-11-07 |  | 1050259 |  |  | 100 | 345 | na | 0.79186 | 1590 ACSR Falcon (Bundled) | Steel Lattice Structures | 230 | 0.79186 | 230 | 0.40341 | 25.101(c)(5)(D) | Structure relocation is at the request of Luminant and is 100% reimbursable by Luminant.
0PT40495 | TxDOT Relocation US 59 Lufkin-Diboll East Loop 138kV Line | City of Diboll, Angelina County | Relocation with new single circuit, concrete H-frame tangent structures. | 2020-03-23 | 2020-04-28 | 2020-04-28 |  | 747185 |  |  | 100 | 138 | na | 0.54129 | 336 ACSR Linnet (Non-Bundled) | Concrete H-frame Structures | 100 | 0.54129 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT40403 0PT40911 (R4101) | Commerce – Bonham 138 kV Line: Loring POI for Rayburn Lower Bois d’Arc Water Treatment Plant | Fannin County | Establish the point of interconnection to Rayburn Electric Cooperative’s Vinson substation for the Lower Bois d’Arc Creek Water Treatment Plant on the Commerce - Bonham 138 kV transmission line. | 2020-04-01 | 2020-06-22 | 2020-06-22 |  | 1147132.37 |  |  | 100 | 138 | na | 0.27 | 795 ACSR | Steel Poles/ H-frame Switch | 100 | 0.27 | 120 | na | 25.101(c)(5)(A) | Costs updated to include associated ROW estimates.
0PT40198 | Greenville Ave SW - Matilda Sub 138 kV Line : Pumping Plant Replacement | City of Dallas, Dallas County | Replace the two existing 1000 gallon pumping plants at Greenville Ave SW with newer refurbished Schroeder 4500 gallon pumping plant. | 2020-02-28 | 2020-06-23 | 2020-06-23 |  | 663176 |  |  | 100 | 138 | na | na | 600 CU HPFF | Underground Transmission Line | na | na | na | na | 25.101(c)(5)(B)
0PT40216 | Polk St. Sub - Polk Terminal 138 kV Line: Replace Terminations | City of Dallas, Dallas County | Replace the 138 kV Underground Transmission Terminations at Polk ST. SUB and Polk Terminal SUB | 2020-10-12 | 2020-11-06 | 2020-11-06 |  | 715000 |  |  | 100 | 138 | na | na | 600 CU HPFF | Underground Transmission Line | na | na | na | na | 25.101(c)(5)(B)
0PT40602 | Canton Switch - Canton Sub 138 kV Line : Replace STR's 1/1 - 1/3 | Van Zandt County | This is a CMPC project to replace STR's 1/1, 1/2, and 1/3 with (1) one steel dead-end pole and (1) one steel or concrete tangent pole. | 2020-04-20 | 2020-06-01 | 2020-06-01 |  | 325000 |  |  | 100 | 138 | na | 0.25 | 336 kcmil ACSR | Steel Poles | 100 | na | na | na | 25.101(c)(5)(B)
0PT40610 | Edgemere Sub - Bandera Sub 138 kV Line : Terminations Replacement | City of Dallas, Dallas County | Replace existing terminations at Edgemere Terminal and Bandera Sub. | 2020-10-23 | 2020-11-07 | 2020-11-07 |  | 736000 |  |  | 100 | 138 | na | na | 900 kcmil Alu Okonite Cable | Underground Transmission Line | na | na | na | na | 25.101(c)(5)(B)
0PT39279 (R8242) | Jack Rabbit 138 kV Station: Cut-In | City of Odessa, Ector County | Line work and structure relocations to cut-in the Odessa – Midessa South Switch 138 kV Line to the new Jack Rabbit 138 kV Substation. | 2020-03-23 | 2020-05-12 | 2020-05-12 |  | 2000000 |  |  | 100 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Steel Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT39796 (M5294) | Everman - Cedar Hill 345 kV line | City of Kennedale, Tarrant | The 0.8 mile re-route will remove 6 steel tower structures. The new build will utilize six (7) dead-end steel monopole structures and three (2) double circuit tangent monopole structures. The existing 2-795 ASCR "Drake" conductor and shield wires will remain. | 2020-02-10 | 2020-05-11 | 2020-05-11 |  | 3557262 |  |  | 100 | 345 | na | 0.8 | 795 kcmil ACSR | Steel Poles | 100 | 0.8 | na | na | 25.101(c)(5)(B)
0PT39783 (M5294) | Everman - Mansfield 138 kV line | City of Kennedale, Tarrant County | To build the 0.8 mile 138 kV line extension in the Everman Switch - Mansfield 138 kV line from existing structure 2/7 to the new Kennedale 138 kV terminals. This line will utilize steel monopole construction, seven (7) dead-end structures and four (4) tangent structures with anchor bolted foundations. | 2019-05-07 | 2020-06-19 | 2020-06-19 |  | 2368188 |  |  | 100 | 138 | na | 0.8 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 0.8 | na | na | 25.101(c)(5)(A)
0PT40082 | Bulldog - Coyote 138 kV Line: CMPC Pole Raise/Replace | City of Big Spring, Howard County | Replace 2 poles to meet clearance on Bulldog-Coyote 138kV Line | 2020-03-16 | 2020-04-09 | 2020-04-09 |  | 350000 |  |  | 100 | 138 | na | 0.1 | 795 ACSR | Concrete Monopole | 70 | 0.1 | na | na | 25.101(c)(5)(B) | Legacy Sharyland Project
0PT39270 (R8497) | China Lake Sub - Sandstone SW (TNMP) 138 kV Line: Establishing China Lake Sub | Ward County | Line work associated with establish China Lake Substation | 2020-04-08 | 2020-06-23 | 2020-06-23 |  | 1200000 |  |  | 100 | 138 | na | 0.3 | 959.6 kcmil ACSS/TW Suwannee | Steel Monopoles | na | na | 100 | 0.3 | 25.101(c)(5)(A)
0PT40957 | Norwood - E Levee 138 kV Line: Harry Hines Sub Cut In | City of Dallas, Dallas County | This project is associated with establishing Harry Hines Substation by connecting the Norwood - East Levee 138 kV Line. | 2020-09-28 | 2020-12-28 | 2020-12-28 |  | 1329601 |  |  | 100 | 138 | na | 0.25 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 50 | 0.25 | 100 | 0.2 | 25.101(c)(5)(A)
0PT39986 (R8486) | Spraberry Switch - Odessa EHV Switch 138 kV Line : Camp Pasture (Concho Parks) POD | Ector County | The scope of this project is to build a POD to COG Operating LLC's Concho Parks Substation on the Spraberry Switch - Odessa EHV Switch 138 kV Line. | 2020-02-17 | 2020-03-01 | 2020-03-01 |  | 1280536 |  |  | 100 | 138 | na | 0.2 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT40413 (M4232) | Carrollton East – Renner/Northaven 138kV Line: Rebuild Carrollton East – Farmers Branch Gillis | City of Farmers Branch, Dallas County | Rebuild the 2.9 mile section of the Carrollton East - Renner Sw/Northaven Sw 138 kV Line from Carrollton East – Farmers Branch Gillis using conductor greater than 1928A. | 2020-03-29 | 2021-03-01 | 2021-03-01 |  | 11739544 |  |  | 100 | 138 | na | 2.9 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 100 | 2.9 | na | na | 25.101(c)(5)(B)
0PT40246 | Eagle Mountain Switch - Weatherford Switch 138 kV Line : Reconfigure Azle Sub Termination Point | City of Fort Worth, Tarrant County | Reterminate the Eagle Mountain - Weatherford Switch 138 kV line at its new terminal location at Azle sub | 2020-04-09 | 2020-06-20 | 2020-06-20 |  | 805440.55 |  |  | 100 | 138 | na | 0.05 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 150 | 0.15 | na | na | 25.101(c)(5)(A)
0PT39965 | Corsicana Sub - Hillsboro Sub 69 kV Line : CMPC Line Hardening (Str. 3/13 & 3/14) | City of Hillsboro, Hill County | Relocate and replace 2 structures across I-35 for CMPC System Hardening | 2020-05-18 | 2020-06-01 | 2020-06-01 |  | 450000 |  |  | 100 | 69 | na | 0.05 | 3/0 ACSR Pigeon | Steel Poles | 50 | 0.15 | na | na | 25.101(c)(5)(B)
0PT40209 (M4295) | Sherry Switch - Fish Creek Switch 138 kV Line: Lakecrest Sub Cut-In | City of Grand Prairie, Dallas County | Line work associated to connecting the Lakecrest 138 kV Substation adjacent to the Fish Creek 138/69 kV Switch. | 2020-04-06 | 2020-10-06 | 2020-10-06 |  | 650000 |  |  | 100 | 138 | na | 0.2 | 2 - 959.6 kcmil ACSS/TW/HS Suwannee | Steel Poles | 150 | 0.2 | na | na | 25.101(c)(5)(A)
17T62174 (M5276) | Hilltop-White Settlement 69 kV Line: Sylvan 69 kV POI (BEC) | City of Weatherford, Parker County | Install a 69 kV POI for the Sylvan (BEC) Substation located in the Hilltop – White Settlement 69 kV Line. | 2020-04-20 | 2020-06-01 | 2020-06-01 |  | 1200000 |  |  | 100 | 69 | na | 1.29 | 2 - 4/0 ACSR Penguin | Steel and Concrete Poles | 175 | 1.29 | na | na | 25.101(c)(5)(A)
0PT39822 0PT39909 0PT39910 (M5295) | Chisholm Grid - Hicks Switch 138 kV Line: Provide a 138 kV POI for Chisholm Grid LLC Merchant Plant (MP) | City of Fort Worth, Tarrant County | Provide a 138 kV Interconnection for Chisholm Grid LLC Merchant Plant (MP). | 2020-02-18 | 2020-12-15 | 2020-12-15 |  | 910100 |  |  | 100 | 138 | na | 0.2 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Poles | na | na | 70 | 0.2 | 25.101(c)(5)(A)
0PT41139 0PT42208 0PT42644 | Crown Rd - Las Colinas 138 kV Line: CMPC Erosion Control | City of Dallas, Dallas County | This is an erosion control project that will mitigate the damage caused to Las Colinas Sub and structure 2/3 by a catastrophic slope failure. The project will entail installing a seacant pile wall to prevent future movement of the soil and re-grading to control the surface erosion. | 2020-07-24 | 2020-12-01 | 2020-12-01 |  | 2093742 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
18T64121 (R6073) | Athens Switch - Tyler West 69 kV Line: Retermination at Tyler Switch | City of Tyler, Smith County | Reterminate the Athens Switch - Tyler West 69 kV Line into Tyler Switch utilizing one new single circuit three pole structure. Also construct a bypass around Tyler Switch in order to construct the new Tyler Switch. | 2020-02-21 | 2020-12-18 | 2020-12-18 |  | 852000 |  |  | 100 | 69 | na | 0.1 | 4/0 ACSR and 2/0 ACSR Penguin | Steel Monopoles | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT40117 (R8356) | Odessa EHV Switch - Wolf Switch 138 kV Line : Rebuild Section | City of Monahans, Ward County | Rebuild a 2.3 mile section of the Odessa EHV - Monahans - Wolf Switch 138 kV Line to accommodate the Odessa EHV/Moss-Wolf section of the Odessa EHV/Moss - Riverton 345 kV Line. | 2020-03-09 | 2020-07-23 | 2020-07-23 |  | 2000000 |  |  | 100 | 138 | na | 2.3 | 2 - 1926.9 kcmil ACSS/TW/HS Cumberland | Steel Poles | 75 | 2.3 | na | na | 25.101(c)(5)(B)
18T64118 0PT40570 (R6071) | Tyler - Swan #1 69 kV Line: Upgrade Black Fork Switch - Tyler Sub Section to 138 kV | City of Tyler, Smith County | Convert the Black Fork Switch – Tyler Sub Section from 69 kV to 138 kV by utilizing four single circuit steel monopole structures | 2020-03-14 | 2020-05-21 | 2020-05-21 |  | 1407315.6 |  |  | 100 | 69 | 138 | 0.3 | 2 - 795 kcmil ACSR Drake | Steel Monopoles | 100 | 0.3 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT39398 | Leon Switch - Dublin Switch 69 kV Line : Magellan Pod | Comanche County | Line work to establish Magellan POD | 2020-04-10 | 2020-05-18 | 2020-05-18 |  | 210000 |  |  | 100 | 69 | na | 0.1 | 1/0 ACSR Raven | Steel Poles/ H-frame Switch | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT40534 | Morgan Creek Switch - Cosden Sub 138 kV Line : Line Work To Establish Brelyn Sub | City of Cahoma, Howard County | Cut in to existing Morgan Creek - Cosden 138kV Line in order to establish new Brelyn Substation | 2020-03-18 | 2020-04-16 | 2020-04-16 |  | 481000 |  |  | 100 | 138 | na | 0.1 | 959 kcmil ACSS Suwannee | Concrete H-Frame | 100 | na | na | na | 25.101(c)(5)(A)
0PT40552 | Taylor Sub - Hutto Switch 138 kV Line : Relocation At Request Of City Of Hutto | City of Hutto, Williamson County | Relocate structures to accommodate future land development for the City of Hutto | 2021-03-29 | 2021-05-15 |  |  | 2020834 |  |  | 0 | 138 | na | 0.8 | 1926.9 kcmil ACSS Cumberland | Steel Monopole | 100 | na | 80 | na | 25.101(c)(5)(F)
0PT40715 (M3092) | Austin Ranch Sub - Josey Sub (BEPC): Construct Line | City of The Colony, Denton County | Construct a 138 kV line from Austin Ranch Substation to establish Josey Substation | 2021-09-15 | 2021-11-15 | [5 empty] | 0 | 138 | na | 0.1 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Dead ends | na | na | 100 | 0.1 | 25.101(c)(5)(A)
0PT40707 | Yucca Drive Switch - Wink Sub 69 kV Line : Dooley Sub Cut-in | City of Monahans, Ward County | Cut-in the Yucca Drive Switch - Wink Sub 69 kV Line to establish the new Dooley Substation | 2020-04-20 | 2020-06-30 | 2020-06-30 |  | 191378 |  |  | 100 | 69 | na | 0.4 | BUNDLED (2X) 4/0 Penguin | Wood H-Frames | 50 | 0.4 | 50 | 0.4 | 25.101(c)(5)(A)
0PT41116 0PT04037 0PT41115 0PT41143 0PT41149 (M5066) | Hood - DeCordova 138 kV Line | City of Granbury, Hood County | Reterminate the existing Hood - DeCordova, Benbrook - DeCordova, Everman - DeCordova, Cleburne - DeCordova, Comanche Peak - DeCordova from the existing DeCordova Sw. Sta. to the new Carmichael Bend Sw. Sta. | 2020-03-22 | 2020-12-28 | 2020-12-28 |  | 5184792 |  |  | 100 | 138/345 | na | 2.5 | 959.6 kcmil ACSS/TW Suwannee & 1926.9 ACSS/TW Cumberland | Steel Towers and Poles | 600 | 3.5 | na | na | 25.101(c)(5)(A)
0PT41144 0PT41151 0PT41155 (M5066) | Carmichael - DeCordova 138 kV Line | City of Granbury, Hood County | Connect the new Carmichael Bend Sw. Sta. to the DeCordova Sw. Station and reterminate the Mitchell Bend - DeCordova line from the existing DeCordova Sw. Sta. to the new Carmichael Bend Sw. Sta. | 2020-09-03 | 2021-04-15 |  |  | 3515606 |  |  | 99 | 345 | 138 | 2.5 | 1590 kcmil ACSR 54/19 Falcon 959.6 kcmil ACSS/TW Suwannee | Steel Towers and Poles | 600 | 2.5 | na | na | 25.101(c)(5)(A)
0PT41215 (R8465) | Screwbean Tap - Screwbean Sub 138 kV Line: Rebuild 1/1 to 1/5 | Culberson County | Rebuild a portion of the Screwbean Tap - Screwbean Sub 138 kV line | 2020-10-14 | 2020-12-28 | 2020-12-28 |  | 1234000 |  |  | 100 | 138 | na | 0.8 | 1926.9 kcmil ACSS/TW/HS Cumberland | Steel Poles | na | na | 150/ 100 | 0.8 | 25.101(c)(5)(B)
0PT41240 (R6126) | Whinstone Sub - Sandow Switch 138 kV Line: Install Whinstone POD | City of Rockdale, Milam County | This project is associated with establishing new POD from Sandow Switch to Whinstone US, Inc. | 2020-02-18 | 2020-04-08 | 2020-04-08 |  | 460000 |  |  | 100 | 138 | na | 0.08 | (2) 959 ACSS/TW Suwannee | Steel Poles | 100 | 0.08 | na | na | 25.101(c)(5)(A)
0PT39419 (M5293) | Valley Switch – Commerce Switch 138 kV Line: Connect Gober 138 kV Switch | Wolfe City, Fannin County | Connect the Gober 138 kV Switch to the Bonham – Wolf City 138 kV line section of the Valley Switch – Commerce Switch 138 kV Line approximately 3.5 circuit miles from Wolfe City to establish a 138 kV point-of-interconnection (POI) for Coniglio Solar Generator. | 2020-10-05 | 2020-12-09 | 2020-12-09 |  | 1162315 |  |  | 100 | 138 | na | 0.1 | 795 MCM ACSR | Steel poles | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT39806 | Stone Creek Switch - Denison Tap 138 kV Line: CMPC Line Hardening (Str 11/11 & 11/12) | City of Denison Grayson County | Replace Structures 11/11 and 11/12 adjacent to US-75 in Denison, TX with concrete monopole structures | 2020-04-16 | 2020-05-04 | 2020-05-04 |  | 504900 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR Drake | Concrete Monopole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT39807 0PT40675 | Stone Creek Switch - Denison Tap 138 kV Line: CMPC Line Hardening (Str 17/4 & 17/5) | City of Denison Grayson County | Replace Structures 17/4 and 17/5 adjacent to US-75 in Denison, TX with steel H-Frame structures | 2020-04-07 | 2020-05-04 | 2020-05-04 |  | 642676.83 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR Drake | Steel H- Frame | 70 | 0.1 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT41178 | Barber Lake Switch - Morgan Creek Switch 138 kV Line: CMPC Line Hardening Str. 5/1 & 5/2 (West Circuit) | Mitchell County | Replace wood H Frame structures 5/1 and 5/2 on the West circuit of the Barber Lake Switch - Morgan Creek Switch 138 kV Line crossing the Union Pacific Railroad west of Colorado City, TX with concrete H Frame structures. | 2020-04-27 | 2020-05-08 | 2020-05-08 |  | 307607 |  |  | 100 | 138 | na | 0.1 | 636 ACSR Grosbeak | Concrete H- Frame | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41180 | Barber Lake Switch - Morgan Creek Switch 138 kV Line: CMPC Line Hardening Str. 5/1 & 5/2 (East Circuit) | Mitchell County | Replace wood H Frame structures 5/1 and 5/2 on the East circuit of the Barber Lake Switch - Morgan Creek Switch 138 kV Line crossing the Union Pacific Railroad west of Colorado City, TX with concrete H Frame structures. | 2020-04-24 | 2020-05-04 | 2020-05-04 |  | 304905 |  |  | 100 | 138 | na | 0.1 | 636 ACSR Grosbeak | Concrete H- Frame | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41198 (R8496) | Stanton East Switch - Big Spring Switch 138 kV Line: Cut in Beals Creek Sub | Howard County | Cut in the Stanton East - Big Spring 138 kV line to establish the new Beals Creek Sub | 2020-04-19 | 2020-05-04 | 2020-05-04 |  | 214764 |  |  | 100 | 138 | na | 0.2 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Monopole | 50 | 0.2 | na | na | 25.101(c)(5)(A)
0PT38203 0PT40990 (R8462) | Shipwreck Sub - Midkiff Sw 138 kV Rebuild | Reagan County Upton County | Rebuild the 69 kV transmission line from Shipwreck Sub to Midkiff SW as a double circuit 138 kV transmission line on steel structures. | 2020-05-29 | 2020-11-10 | 2020-11-10 |  | 13695453 |  |  | 100 | 69 | 138 | 20.6 | 959.6 kcmil ACSS Suwannee | Steel Monopoles | 50 | 10.3 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT03963 (R6073) | Canton Switch - Elkton Switch 138 kV: Retermination at Tyler Switch | City of Tyler, Smith County | Connect the new Tyler Switch station to the 138 kV Elkton Switch and Canton Switch stations. | 2020-10-26 | 2020-12-09 | 2020-12-09 |  | 242113 |  |  | 100 | 138 | na | 0.1 | 795 kcmil 26/7 ACSR Drake | Steel Poles | 100 | na | na | na | 25.101(c)(5)(A)
0PT41322 (R6071) | Tyler - Tyler West 138 kV: Retermination at Substations | City of Tyler, Smith County | Connect the new Tyler 138 kV substation to the Tyler West Substation. | 2020-05-25 | 2020-10-23 | 2020-10-23 |  | 980278 |  |  | 100 | 69 | 138 | 0.25 | 795 kcmil 26/7 ACSR Drake | Steel Poles | varies | na | na | na | 25.101(c)(5)(A)
0PT39802 | Denison Dam Tap - Valley Switch 138 kV Line: CMPC Line Hardening | City of Denison, Grayson County | Relocate and replace 3 structures across US-75 for CMPC System Hardening | 2020-03-05 | 2020-04-20 | 2020-04-20 |  | 576138 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR Drake | Concrete & Wood H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT39805 | Stone Creek Switch - Denison Tap 138 kV Line: CMPC Line Hardening | City of Sherman, Grayson County | Relocate and replace 2 structures across US-75 for CMPC System Hardening | 2020-03-26 | 2020-04-20 | 2020-04-20 |  | 616768 |  |  | 100 | 138 | na | 0.1 | 795 kcmil ACSR Drake | Concrete H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41092 | Corn Trail Switch - Brown Switch 345 kV Line: CMPC Insulator Replacement | Comanche/ Comanche County | Replace insulators on the Corn Trail - Brown 345 kV Line. | 2020-03-25 | 2021-10-30 |  |  | 2635498 |  |  | 76 | 345 | 345 | 45.1 | 2 - 1590 kcmil ACSR Falcon | Steel Lattice Towers | 160 | 45.1 | na | na | 25.101(c)(5)(B)
0PT41134 | DART Cotton Belt Relocation Northaven Sw. Sta.-Renner Sw. Sta. 138kV Line | City of Addison, Dallas County | Relocation with new double circuit, steel monopole dead end and tangent structures. | 2021-02-24 | 2021-03-31 |  |  | 1629745 |  |  | 99 | 138 | na | 1.0833 | 1926 ACSS/TW Cumberland (Non-Bundled) | Steel Monopole Structures | varies | 0.54167 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Dallas Area Rapid Transit (DART) and is 100% reimbursable by the Dallas Area Rapid Transit (DART).
0PT41225 | TxDOT NTE 3C Relocation I-35 Crossing Eagle Mtn-Roanoke 345kV (Alliance Substation Tap) Line | City of Keller, Tarrant County | Relocation with new double circuit, steel lattice tangent structures. | 2020-03-23 | 2020-04-28 | 2020-04-28 |  | 516263 |  |  | 100 | 345 | na | 1.0227 | 1590 ACSR Falcon (Bundled) | Steel Lattice Structures | 150 | 0.51136 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41470 | TxDOT US 59 Nacogdoches Relocation Nacogdoches-Loop South Section 138kV Line | City of Nacogdoches, Nacogdoches County | Relocation with new single circuit, concrete H-frame tangent structures. | 2020-03-09 | 2020-04-28 | 2020-04-28 |  | 656236 |  |  | 100 | 138 | na | 0.33049 | 336 ACSR Linnet (Bundled) | Concrete H-frame Structures | 100 | 0.33049 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT40515 | Gainesville North Switch - Spring 138 kV Line : System Hardening (str. 41/9 & 42/1) | City of Gainesville, Cooke County | Replace Structures 41/9 & 42/1 adjacent to I-35 in Gainesville, TX consisting of existing single-circuit wooden H-frames with concrete H-frames. | 2021-09-15 | 2021-12-31 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR | Concrete H-Frame | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38167 (M4178) | Plano West Sub-Richardson East Sub 138 kV Line: Retermination line at Plano Switch | City of Richardson, Collin County | Retermination Line work on the Plano West Sub - Richardson East Sub 138 kV line. | 2020-03-26 | 2020-12-01 | 2020-12-01 |  | 455000 |  |  | 100 | 138 | na | 0.25 | 2-959.6 kcmil ACSS/TW | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A) | This is a 100% reimbursable project by Texas Instruments
0PT41602 (M4178) | Allen Switch- Plano West Switch 138 kV Line: Establish POD | City of Richardson, Collin County | Retermination Line work on the Allen Switch - Plano West Switch 138 kV line. | 2020-03-26 | 2020-12-01 | 2020-12-01 |  | 556000 |  |  | 100 | 138 | na | 0.25 | 2-959.6 kcmil ACSS/TW | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A) | This is a 100% reimbursable project by Texas Instruments
0PT40559 | Wink Switch – Culberson Switch 138 kV Line: Cut In Willow Wells Substation | City of Odessa, Winkler County | Establish the new Willow Wells Substation as a Point of Delivery for Oasis petroleum out of the Willow Wells substation. | 2020-04-20 | 2020-05-15 | 2020-05-15 |  | 1150000 |  |  | 100 | 138 | na | 0.1 | 1926 ACSS/TW Cumberland (Non-Bundled) | Steel Monopole Structures | 50 | 0.1 | na | na | 25.101(c)(5)(A) | The new transmission line is going to reside on Oncor fee owned property.
0PT40577 0PT41514 | Stone Creek Switch - Gainesville Sub 69 kV Line : Camp Howze Tap MCPc Line Hardening (str. 4/6 & 4/7) | City of Gainesville, Cooke County | Replace Structures 4/6 & 4/7 adjacent to I-35 in Gainesville, TX consisting of existing single-circuit wooden H-frames with concrete H-frames. | 2021-10-01 | 2021-12-31 | [5 empty] | 0 | 69 | na | 0.3 | 1/0 ACSR | Concrete H-Frame | 147 | 0.3 | na | na | 25.101(c)(5)(B)
0PT40814 0PT40883 0PT41439 | Saint Lawrence - East Stiles 138 kV Line: Blissard Retermination | Glasscock County | Reterminate the Saint Lawrence - East Stiles 138 kV line at a new terminal location in Blissard Sub. The new Blissard Sub will be located immediately east of the existing Saint Lawrence Sub. | 2020-04-06 | 2020-05-15 | 2020-05-15 |  | 393766.46 |  |  | 100 | 138 | 138 | 0.1 | 1926.9 ACSS/TW | Steel Poles | 90 | 0.1 | 90 | 0.07 | 25.101(c)(5)(A) | Costs updated to include associated ROW estimates.
0PT41233 (M3211) | Roanoke Switch - Euless 138 kV Line: OPGW Replacement | City of Grapevine, Tarrant County | Replace the existing shield wire on the 7/8 - Grapevine Ball Street section (1.8 miles) of the Roanoke Switch - Euless 138 kV Line with 0.546” OD 48 count OPGW. Additionally, Grapevine Junction will be reconfigured by re-terminating the conductor from structure 15/10W to 15/10E. | 2021-09-20 | 2021-09-30 |  |  | 495463 |  |  | 0 | 138 | 138 | 1.8 | 1926.9 ACSS/TW | Steel Poles | Varies | 1.8 | na | na | 25.101(c)(5)(A)
0PT41264 | Canton Switch - Elkton Switch 138 kV Line : Replace Str's 36/8 & 36/8a | Van Zandt County | Replace existing wood 4-Poles with new wood 3-Poles for structures 36/8A and 36/8. Replace Floating Deadends and Jumpers to Wave Trap. | 2020-04-22 | 2020-05-01 | 2020-05-01 |  | 155000 |  |  | 100 | 138 | 138 | 0.1 | 636 ACSR | Wood Poles | 100 | 0.1 | na | na | 25.101(c)(5)(B)
17T65200 | West Levee - Norwood 345 kV: Install OPGW | City of Dallas, Dallas County | Replace 3/8" shield wire with OPGW to the West Levee - Norwood 345 kV 0.1 miles 2 spans | 2020-05-02 | 2020-12-15 | 2020-12-15 |  | 105489 |  |  | 100 | 345 | 345 | 0.1 | OPGW | Steel Poles | 150 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41453 (R6126) | Sandow SES (Tie #3) - Sandow Switch 138kV Line: Relocate Sandow Sw Terminal | City of Rockdale, Milam County | Relocation of Sandow Switching Station - Alcoa Switching Station 138 kV Line #3 to the position in Sandow Switching Station served by 138 kV breakers No. 9300 and 9305 to establish POD. | 2020-03-19 | 2020-04-08 | 2020-04-08 |  | 360000 |  |  | 100 | 138 | na | 0.1 | 2-959 ACSS/TW Suwannee | Steel Poles | 100 | 0.1 | 100 | 0.1 | 25.101(c)(5)(A)
0PT37449 (M4131) | Cedar Hill Sw - Sorcey Road Sub - Cedar Hill Sub 138kV Line Rebuild (Phase 1) | City of Cedar Hill, Dallas County | Upgrade the 2.6-mile Sorcey Road Sub to Cedar Hill Sw 138 kV line. | 2020-12-03 | 2021-05-15 |  |  | 9690000 |  |  | 86 | 138 | na | 2.6 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 250 | 2.6 | na | na | 25.101(c)(5)(B)
0PT03990 (M4131) | Cedar Hill Sw - Sorcey Road Sub - Cedar Hill Sub 138kV Line Rebuild (Phase 2) | City of Cedar Hill, Dallas County | Upgrade the 1.7-mile Cedar Hill Sub to Sorcey Road Sub 138 kV line. | 2021-09-16 | 2021-12-15 | [5 empty] | 0 | 138 | na | 1.7 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 250 | 1.7 | na | na | 25.101(c)(5)(B)
0PT03996 (M4131) | Cedar Hill Sw - Sorcey Road Sub - Cedar Hill Sub 138kV Line Rebuild (Phase 3) | City of Cedar Hill, Dallas County | Upgrade the 0.8-mile Duncanville South Loop 138 kV line. | 2021-09-13 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.8 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 75 | 0.8 | na | na | 25.101(c)(5)(B)
0PT41582 (M5313) | Krum West Switch - Anna Switch 345 kV Line: Connect Cedar Elm 345 kV Switch | City of Era, Cook County | Line work associated with connecting the 345 kV Cedar Elm Switch | 2020-10-14 | 2020-12-14 | 2020-12-14 |  | 1940000 |  |  | 100 | 345 | na | 0.2 | 2-1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 100 | 0.1 | 100 | 0.1 | 25.101(c)(5)(A)
0PT39030 | Temple Elm Creek Sub - Belton Sub 138 kV Line : Relocation for BNSF | City of Tyler, Bell County | Relocation of structure 33/16 on the North Temple - Belton 138 kV Line for BNSF Railway to accommodate railroad modifications. The existing structure is a 150' DCSP tangent. | 2020-07-30 | 2020-10-12 | 2020-10-12 |  | 600000 |  |  | 100 | 138 | na | 0.01 | 2- 1590 ACSR Falcon | Steel Monopoles | 100 | 0.01 | na | na | 25.101(c)(5)(E)
0PT41445 | Eagle Mountain Switch - Weatherford Switch 138 kV Line: Raise Structure 61/8 | Azle, Parker County | Raise and replace structure 61/8 with a taller wood H-Frame to accommodate BEPC's new distribution bay. | 2020-03-30 | 2020-04-01 | 2020-04-01 |  | 36323 |  |  | 100 | 138 | 138 | 1.2 | 636 ACSR | Wood H-Frame | 50 | 1.2 | na | na | 25.101(c)(5)(B)
0PT40459 0PT42382 (R8524) | Riverton Switch - Tunstill POD 138 kV Line: Install Roadrunner POD for BP's Aspen | Reeves County | Establish the point of delivery to BPX Energy’s Aspen substation on the Riverton Switch – Tunstill POD 138 kV transmission line. | 2020-08-17 | 2020-12-02 | 2020-12-02 |  | 1932614 |  |  | 100 | 138 | na | 0.19 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Poles & H-Frame Switch | 70 | na | 70 | 0.19 | 25.101(c)(5)(A) | Costs updated to include associated ROW estimates.
0PT39453 (R8521) | Midessa South Switch - Midland Airport Sub 138 kV Line: Install Nobles POD for Diamondback's Spanish Trails Sub | Midland County | Establish the point of delivery to Diamondback’s Spanish Trails substation on the Midessa South Switch – Midland Airport 138 kV transmission line. | 2020-08-07 | 2020-12-02 | 2020-12-02 |  | 505000 |  |  | 100 | 138 | na | na | 1590 kcmil ACSR Falcon | Steel Poles & H-Frame Switch | 75 | na | na | na | 25.101(c)(5)(A)
0PT39979 0PT41106 (R8533) | SL Brown - Grady 138 kV Line: Oceanic POD for Endeavor's Olympus Sub | Martin County | Establish the point of delivery to Endeavor Energy’s Olympus substation on the Brown - Grady 138 kV transmission line. | 2020-08-14 | 2020-12-09 | 2020-12-09 |  | 2053000 |  |  | 100 | 138 | na | 0.22 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles & H-Frame Switch | 70 | na | 100 | 0.22 | 25.101(c)(5)(A)
0PT40386 0PT41330 (R8537) | SL Brown - Grady 138 kV Line : Install Red Salt POD For Diamondback Cobra | Martin County | Establish the point of delivery to Diamondback’s Cobra substation on the Brown - Grady 138 kV transmission line. | 2020-08-16 | 2020-10-07 | 2020-10-07 |  | 2545000 |  |  | 100 | 138 | na | 0.38 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles & H-Frame Switch | 70 | na | 100 | 0.38 | 25.101(c)(5)(A)
0PT39402 (R8536) | Spraberry Switch - Midland East Sub 138 kV Line: Fairgrounds POD for Centurion's Midland Tank Farm | Midland County | Establish a point of delivery to Centurion Pipeline, LLC on the Spraberry - Midland East 138 kV line. | 2020-09-22 | 2020-12-09 | 2020-12-09 |  | 1733385 |  |  | 100 | 138 | na | 0.15 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles & H-Frame Switch | 50 | na | 100 | 0.15 | 25.101(c)(5)(A)
0PT39833 (R8540) | LCRA Crane – Crane East 138 kV Line : Manning (Hazel) POD for Concho Chickadee Neal via LCRA Motorman Switch | Upton County | Establish the point of delivery from LCRA’s Motorman Switch to Concho’s Chickadee Neal on the Crane – Crane East 138 kV (LCRA) transmission line. | 2021-11-01 | 2021-12-30 |  |  | 0 |  |  | 0 | 138 | na | 0.11 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles & H-Frame Switch | na | na | 100 | 0.11 | 25.101(c)(5)(A)
18T64017 | Salado - Round Rock 138 kV Line: cut-in to establish Salado South Substation | Bell County | This project will cover the cost to cut-in the Salado - Round Rock 138 kV line to establish the new Salado South Substation. | 2020-07-31 | 2020-12-01 | 2020-12-01 |  | 949748 |  |  | 100 | 69/138 | 138 | 0.2 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 100 | 0.2 | na | na | 25.101(c)(5)(A)
18T64094 0PT37434 (R6061) | Jewett Switch - Crockett 138 kV Line: Rebuild Jewett Switch to Centerville Sub | City of Jewett Vicinity, Jewett County | Rebuild the 7.2 mile section from Jewett Switch to Centerville Substation of the Jewett - Crockett 138 kV Line, using double-circuit structures with one circuit in place. | 2019-09-08 | 2020-12-14 | 2020-12-14 |  | 15454717 |  |  | 100 | 138 | 138 | 7.2 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 7.2 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT39859 | Hillsboro Sub - Elm Mott Sub 69 kV Line : Tower Replacement | Hill County | Replace damaged tower 107 on the Hillsboro - Elm Mott 69 kV line. | 2020-04-28 | 2020-06-01 | 2020-06-01 |  | 119314 |  |  | 100 | 69 | 69 | 0.1 | 1/0 MCM Cu | Steel Lattice Tower | 70 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42028 | Stryker Creek Switch - Tyler Grande Switch 138 kV Line: Structure 4/6 to 4/8 Insulator Failure | City of Tyler, Cherokee County | Replaced damaged insulators due to storm damage | 2020-03-04 | 2020-03-06 | 2020-03-06 |  | 430000 |  |  | 100 | 138 | 138 | 0.2 | 1233.6 kcmil ACSS/TW Yukon | Concrete Poles | 100 | 0.2 | na | na | 25.101(c)(3) | Emergency Storm Restoration
0PT41539 (R8526) | Owl Hills Sub - Tunstill POD 138 kV Line : Install Second Circuit | Culberson and Reeves Counties | Install second circuit to the Owl Hills - Tunstill POD 138 kV Line. | 2020-02-24 | 2021-05-15 |  |  | 10258859 |  |  | 46 | 138 | na | 18.5 | 1926.9 kcmil ACSS/TW | Steel Poles | 70 | 18.5 | na | na | 25.101(c)(5)(C) | Second circuit to the 48582 Owl Hills - Tunstill POD 138 kV Line CCN.
0PT41577 | Saginaw Switch - Roanoke Switch 138 kV Line : Tower Replacement | Haltom City, Tarrant County | Damaged leg extension on structure 03/04 on the Saginaw Switch - Roanoke Switch 138 kV line. The scope entails replacing the existing structure with a double circuit concrete tangent pole. | 2020-09-22 | 2020-12-01 | 2020-12-01 |  | 273254 |  |  | 100 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Concrete Pole | 125 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38110 (M5278) | Everman Switch - Venus Switch 345 kV Line : Reterminate at Timberview Switch | City of Everman, Tarrant County | Reterminate the Everman Switch - Venus Switch 345 kV Line from Everman Switch to new Timberview Switch. | 2021-08-16 | 2021-12-15 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38112 (M5278) | Benbrook Switch - Everman Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Reterminate the Benbrook Switch - Everman Switch 345 kV Line from the Everman Switch to new Timberview Switch. | 2021-08-16 | 2021-12-15 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38113 (M5278) | Everman Switch - Cedar Hill Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Reterminate the Everman Switch - Cedar Hill Switch 345 kV Line from the Everman Switch to new Timberview Switch | 2021-08-16 | 2021-12-15 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38114 (M5278) | Everman Switch - DeCordova Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Retermination the Everman Switch - DeCordova Switch 345 kV Line from Everman Switch to new Timberview Switch | 2021-08-16 | 2021-12-15 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT41761 (R6127) | Navarro Switch - Watermill Switch 345 kV Line : Line modification to connect Elrod Switch | City of Corsicana, Navarro County | Line work associated with connecting the 345 kV Elrod Switch | 2021-03-11 | 2021-05-31 |  |  | 1716000 |  |  | 34 | 345 | na | 0.1 | 2-1590 kcmil ACSR Falcon | Steel Tower | 160 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41810 (R984) | Allen Sw - Monticello Sw 345kV Line: Stouts Creek Cut In | City of Sulphur Springs, Hopkins County | Line work associated with connecting the 345 kV Stouts Creek Switch | 2021-10-01 | 2022-04-12 | [5 empty] | 0 | 345 | na | 35 | 2-795 kcmil ACSR Drake | Steel Tower | 170 | 35 | na | na | 25.101(c)(5)(A)
0PT42027 | Jewett Switch - Big Brown Switch 345 kV Line : Structure 28/4 Insulator Failure | City of Palestine, Freestone County | This Work Authorization is for the material and labor associated with replacing damaged insulator at Structure 28/4 due to storm damage on the Jewett Switch - Big Brown Switch 345 kV Line. | 2020-03-04 | 2020-03-13 | 2020-03-13 |  | 459000 |  |  | 100 | 345 | 345 | 32.91 | 795 ACSR "Drake" | Steel Lattice | 160 | 32.91 | na | na | 25.101(c)(3) | Emergency Storm Restoration
17T65237 (M4216) | Simpson Stuart - Camp Wisdom 138 kV Line: Rebuild | City of Dallas, Dallas County | Upgrade the 3.7 mile Simpson Stuart - Camp Wisdom Road 138 kV Line section of the Cedar Hill - Watermill 138 kV Line. | 2020-10-21 | 2021-05-15 |  |  | 5734334 |  |  | 99 | 138 | 138 | 3.7 | 959.6 kcmil ACSS/TW | Steel Poles | Varies | 3.7 | Varies | na | 25.101(c)(5)(B)
19T63004 0PT41332 (R9025) | Ennis Creek Sw. Sta. - Bec Salt Creek Sw. Sta. 69 kV: Rebuild To 138 kV (eng) | City of Snyder, Scurry County | Rebuild the existing 9.0 mile single circuit wood pole Ennis Creek – Cogdell 69 kV line as the Ennis Creek – Rough Creek 138 kV Line utilizing 138 kV double circuit steel poles with one circuit in place. | 2020-08-10 | 2020-12-23 | 2020-12-23 |  | 11482370.56 |  |  | 100 | 69 | 138 | 9 | 959.6 kcmil ACSS/TW | Steel Poles | 50 | 9 | 70 | 0.8 | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT42274 0PT42275 (R8548) | Wolf - Aroya 138kV Line: Reterminate Aroya End at Yucca to establish Wolf - Yucca #2 Circuit 138 kV Line Wink - Yucca 138kV Line: Reterminate Yucca End at Aroya Switch to establish Wink - Aroya 138 kV Line | City of Monahans, Ward County | Disconnect the existing Yucca Drive Switch – Wink Switch 138 kV Line and Aroya Switch – Wolf Switch 138 kV Lines where the two lines intersect. Connect the lines in the new configuration to create the new Yucca Drive Switch – Wolf Switch 138 kV Line. Connect the lines in the new configuration to create the new Aroya Switch – Wink Switch 138 kV Line. | 2020-04-23 | 2021-05-15 |  |  | 730000 |  |  | 99 | 138 | na | 0.2 | 959 kcmil ACSS/TW Suwannee & 2-959 kcmil ACSS/TW Suwannee | Steel Poles & Wood Poles | 75 | 0.2 | na | na | 25.101(c)(5)(B) | This project is planned to reconfigure two existing circuits to reduce operational constraints in the area due to continued load growth. In order to complete this reconfiguration prior to the summer clearance moratorium, Oncor is unable to list this project in compliance with 16 Tex. Admin Code § 25.83(c)(1), but is instead providing 20 days’ pre-construction notice with today’s filing.
0PT04031 (R9026) | Dermott Switch - Golden Switch 138 kV Line: Ennis Creek Switch Station Retermination | City of Snyder, Scurry County | This project is to reterminate the Dermott Switch - Golden Switch 138 kV Line at its new terminal following the rebuild of the Ennis Creek Switch Station. | 2020-09-16 | 2020-12-23 | 2020-12-23 |  | 841896 |  |  | 100 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Steel Poles | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42070 0PT42842 (R8346) | Odessa North - Odessa Basin Switch - Odessa Basin 69 kV Line: Retermination | Odessa County | Reterminate the Odessa North - Odessa Basin Switch - Odessa Basin 69 kV Line to aid in the demolition of Odessa Basin Switch station by installing one single-circuit steel pole. | 2020-09-08 | 2020-11-09 | 2020-11-09 |  | 453225.23 |  |  | 100 | 69 | 69 | 0.1 | 959.6 kcmil ACSS/TW | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT41677 (M364) | Texas Instruments Sub - Beltline Sub 138 kV Line- Structure replacement | City of Richardson, Dallas County | Replace existing tower T-448 on the Texas Instruments Sub- Beltline Sub 138kV and install a new double circuit span into the rebuilt Richardson Spring Valley Sub. | 2020-10-24 | 2020-12-15 | 2020-12-15 |  | 1344098 |  |  | 100 | 138 | 138 | 0.1 | 1926.9 kcmil ACSS/TW | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41191 | TxDOT I-20 at CR 1250 Relocation Midessa 138kV tap line | City of Midland, Midland County | Relocation of structure on Midessa 138 kV tap line. | 2020-09-08 | 2020-11-07 | 2020-11-07 |  | 1087902 |  |  | 100 | 138 | na | 1.036 | 1926 ACSS Cumberland | Steel Monopole Structures | 75 | 0.51799 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41129 | 2020 CMPC Big Spring District, Morgan Creek Switch-Falcon Seaboard Sub. 345 kV Line Str. 19/5 | City of Big Spring, Howard County | Rebuild the section of the Morgan Creek-Midland East 345 kV Line that crosses South Farm to Market (FM) 821 in Howard County | 2020-09-27 | 2020-11-01 | 2020-11-01 |  | 489358 |  |  | 100 | 345 | na | 0.33 | 2-795 ACSR Drake | Lattice Tower Structure | 150 | 0.33 | na | na | 25.101(c)(5)(B)
0PT41131 | 2020 CMPC Odessa District, Falcon Seaboard Sub.-Midland East Sub. 345 kV Line, Str. 68/2 | City of Midland, Midland County | Rebuild the section of the Morgan Creek-Midland East 345 kV Line that crosses N. County Rd. 1135 in Midland County | 2020-09-23 | 2020-10-17 | 2020-10-17 |  | 675424 |  |  | 100 | 345 | na | 0.38 | 2-95 ACSR Drake | Lattice Tower Structure | 150 | 0.38 | na | na | 25.101(c)(5)(B)
0PT41118 | 2020 CMPC Sweetwater District, Morgan Creek Switch-Falcon Seaboard Sub. 345 kV Line, Str. 12/5 | City of Colorado City, Mitchell County | Rebuild the section of the Morgan Creek-Midland East 345 kV Line that crosses N. County Rd. 1135 in Midland County. | 2020-10-05 | 2020-11-01 | 2020-11-01 |  | 489358 |  |  | 100 | 345 | na | 0.35 | 2-795 ACSR Drake | Lattice Tower Structure | 150 | 0.35 | na | na | 25.101(c)(5)(B)
0PT39676 | Carrollton East Switch - Northaven Switch 138 kV Line: Farmers Branch Retermination | City of Addison, Dallas County | Reterminate the existing Carrollton East Switch - Northaven Switch 138 kV Line at Farmers Branch Substation to a new structure. | 2020-09-21 | 2020-12-02 | 2020-12-02 |  | 369671 |  |  | 100 | 138 | na | 0.1 | 795 ACSR Drake | Steel Poles | 70 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41977 | Sweetwater No.2 Sub - Colorado City Sub 69 kV Line: Line work associated with Loraine Sub Decommission | City of Loraine, Mitchell County | Line work associated with the decommission of Loraine Sub. | 2021-04-03 | 2021-05-31 |  |  | 119570 |  |  | 99 | 69 | na | 0.1 | 4/0 ACSR Penguin | Wood Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41189 0PT40230 (R8506) | SL Clearfork Switch - Telephone Road Switch 345 kV Line: Line work to establish Gardendale 345 kV Switch NTUSU Clearfork Switch - Telephone Road Switch 345 kV Line: Retirements and Modifications Only | City of Andrews, Andrews County | Line work to cut into Clearfork Switch - Telephone Road Switch 345 kV Line to establish Gardendale 345 kV Switch. | 2020-09-19 | 2020-10-26 | 2020-10-26 |  | 1462757 |  |  | 100 | 345 | na | 0.1 | 2-1926.9 kcmil ACSS/TW Cumberland | Steel Towers | 135 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41505 (R8380) | Yucca Drive Switch - Sand Lake Switch 138 kV Line: Modify for Sand Lake - Solstice 345 kV Line | Ward County | Modifying the existing Yucca Drive Switch - Sand Lake Switch 138 kV Line by lowering it from Structure 35/3 to Structure 35/5 for new the Sand Lake - Solstice 345 kV Line to fly over the existing 138 kV line. | 2020-09-11 | 2020-10-08 | 2020-10-08 |  | 950000 |  |  | 100 | 138 | 138 | 0.4 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Poles | 70 | 0.2 | na | na | 25.101(c)(5)(B)
0PT41108 | Eagle Mountain Ses - Wichita Falls 138 kV Line: Hb 4150 Lake Arrowhead Crossing | City of Henrietta, Clay County | Rebuild 0.1 mile section of the Eagle Mountain SES - Wichita Falls 138 kV line which crosses Lake Arrowhead. | 2020-09-11 | 2020-12-01 | 2020-12-01 |  | 212670 |  |  | 100 | 138 | na | 0.2 | 636 km ASCR | Steel Poles | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT41701 | Eskota Switch - Morgan Creek Switch 138 kV Line : Erosion Control | City of Colorado, Mitchel County | Build a erosion control guards around tower 131/18 on the Eskota - Morgan Creek 138 kV line. A series of culverts will be installed on both sides of the tower to divert the water around the tower and protect the structure from future erosion. A retaining wall will also be installed and filled with selective backfill in the eroded area to ensure structural integrity in the soil. | 2020-12-01 | 2020-12-04 | 2020-12-04 |  | 611682 |  |  | 100 | 138 | na | na | 636 ACSR Grosbeak & 795 ACSR Drake | Steel Lattice Tower | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41738 | Forest Grove Switch - Eustace SE Switch 138 kV Line : Retirement Only | Henderson County | This project is to retire 3.8 miles of the old Forest Grove Switch - Eustace SE 138 kV Line. | 2020-07-28 | 2020-08-21 | 2020-08-21 |  | 230000 |  |  | 100 | 138 | 0 | 3.8 | 1033 ACSR Curlew | Wood H-Frames | 160 | 3.8 | na | na | 25.101(c)(5)(B)
0PT41912 | Sulphur Springs Switch - Canton Switch 138 kV Line : Hb 4150 Lake Tawakoni Crossing | City of Willis Point, Hunt County | This is to rebuild a 0.1 mile section of the Sulphur Springs – Canton Switch 138 kV Line. | 2020-09-16 | 2020-12-01 | 2020-12-01 |  | 512793 |  |  | 100 | 138 | na | 0.15 | 795 ACSR Drake | Steel Poles | 100 | 0.15 | na | na | 25.101(c)(5)(B)
17T62074 17T80086 (R4103) | Paris Switch-Rivercrest/Tenaska 138 kV Line (Lamar Jct-Reno Tap Section):Rebuild | City of Paris, Lamar County | Rebuild the Lamar Tap - Reno Tap line section of the Paris Switch - Rivercrest - Tenaska 138 kV Line. | 2020-08-11 | 2020-12-09 | 2020-12-09 |  | 14175844.17 |  |  | 100 | 138 | na | 5.3 | 2-959.6 MCM ACSS/TW/HS Suwannee | Steel Poles | 100 | 5.3 | 100 | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT42509 (M4268) | Oakland Avenue Tap - Oakland Avenue Sub 138 kV Line : Install OPGW | City of Dallas, Dallas County | Reconductor the Oakland Avenue Tap – Oakland Avenue Substation 138 kV line section | 2020-10-02 | 2020-11-30 | 2020-11-30 |  | 1940000 |  |  | 100 | 138 | na | 0.64 | 927.2 MCM ACAR | Steel Towers | 100 | 0.64 | na | na | 25.101(c)(5)(B)
0PT39227 (M5288) | Valley Switch - Commerce Switch 138 kV Line : Establish Copperhead Switch (Phoenix/GSE 1) | City of Bonham, Fannin County | Build 0.6 mile double-circuit tap to establish Copperhead Switch to pick-up merchant plant station, Phoenix (GSE 1). | 2020-10-26 | 2021-02-07 | 2021-02-07 |  | 3086380 |  |  | 100 | na | 138 | 0.64 | 959.6 ACSS/TW | Steel Poles | na | na | 100 | 0.6 | 25.101(c)(5)(A)
0PT42291 (R9025) | Dermott Switch - Scurry South Switch 345 kV Line: Replace Str. 7/1 | City of Snyder, Scurry County | Replace structure 7/1 on the Dermott - Scurry South 345 kV line to provide additional clearance for the Ennis Creek - Rough Creek 138 kV Line Rebuild utilizing a new 345 kV tower. | 2020-11-06 | 2020-12-23 | 2020-12-23 |  | 300000 |  |  | 100 | 345 | na | 0.1 | 2-1926.9 kcmil ACSS/TW | Steel Tower | 160 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38084 (M4245) | Norwood Switch - Denton Drive Switch 138 kV Line: Reconductor | City of Dallas, Dallas County | Reconductor the Norwood Switch - Denton Drive Switch 138 kV Line. | 2020-10-06 | 2021-05-15 |  |  | 8800954 |  |  | 99 | 138 | na | 3.9 | 959.6 kcmil ACSS/TW (Bundled) | Steel Poles | 100 | 3.9 | na | na | 25.101(c)(5)(B)
0PT41981 | Yucca Drive Switch - Northern Natural Gas 69 kV Line: Coyanosa Substation Retermination | City of Coyanosa, Pecos County | Reterminate the Coyanosa Station in the Yucca Drive Switch - Northern Natural Gas 69 kV Line. | 2021-10-25 | 2021-12-01 | [5 empty] | 0 | 69 | na | 0.5 | 4/0 ACSR Penguin | Steel Poles | 50-75 | 0.5 | 65-90 | 0.3 | 25.101(c)(5)(A)
0PT41002 (R8546) | McDonald Road Sw. – Spraberry Sw. 138 kV Line: Thirtysix Draw POD for CrownQuest Operating Wrage Sub | City of Midland, Glasscock County | Establish the point of delivery to CrownQuest Operating’s Wrage on the McDonald Road Sw. – Spraberry Sw. 138 kV transmission line. | 2020-11-09 | 2021-03-17 | 2021-03-17 |  | 1203000 |  |  | 100 | 138 | na | 0.22 | 959 ACSS/TW | Steel Poles/ H-frame Switch | 50 | 0.22 | 90 | na | 25.101(c)(5)(A)
0PT39834 (R8544) | Andrews North - McKenzie Draw Switch 138 kV Line: Install Dillon POD for Diamondback's Cats POD | City of Andrews, Martin County | Establish the point of delivery to Diamondback’s Cats substation on the Andrews North – McKenzie Draw 138 kV transmission line. | 2020-12-03 | 2021-03-16 | 2021-03-16 |  | 1881000 |  |  | 100 | 138 | na | 0.17 | 1926 ACSS/TW | Steel Poles/ H-frame Switch | 70 | na | 100 | 0.17 | 25.101(c)(5)(A)
0PT42244 0PT43238 (M5318 ) | Stone Creek Switch - Anna Switch 138 kV Line: Spirit POI for Rayburn's East Fork Sub | City of Anna, Collin County | Establish the point of delivery to Rayburn Country Electric Cooperative’s East Fork substation on the Stone Creek Switch – Anna Switch 138 kV transmission line. | 2021-03-02 | 2021-05-10 |  |  | 1973000 |  |  | 95 | 138 | na | 0.19 | 2- 959 ACSS/TW | Steel Poles/ H-frame Switch | 70 | 0.19 | 100 | na | 25.101(c)(5)(A)
18T65206 (M3047) | Renner Switch- Allen Switch/Plano Tennyson Switch 138 kV Line: Rebuild STR 11/4D - Plano Tennyson | City of Plano, Collin County | Rebuild the existing Renner - Allen/Plano Tennyson 138 kV line with double circuit, bundled conductor | 2021-06-07 | 2021-12-15 | [5 empty] | 0 | 138 | na | 1.7 | 2-959.6 ACSS/TW/HS Suwannee | Steel Poles | 100 | 1.7 | na | 100 | 25.101(c)(5)(B)
0PT42436 (R6071) | Tyler Northwest Switch - Tyler Northeast Sub 138 kV: Reterminate to Tyler Northwest Switch | City of Tyler, Smith County | Reterminate the existing 138 kV line from Shamburger - Black fork into the Tyler Northwest Station | 2021-04-26 | 2021-05-15 |  |  | 263606 |  |  | 99 | 138 | na | 0.1 | 959.6 ACSS/TW/HS Suwannee | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT40854 0PT42533 (R6079) | Tyler Switch - Elkton Switch 138kV Line Rebuild | City of Tyler, Smith County | Rebuild the 5.3 mile Tyler Switch - Elkton Switch 138kV Line, using 138kV double-circuit structures with one circuit in place using a conductor rated 2071 A or greater. | 2021-01-18 | 2021-05-15 |  |  | 11272304 |  |  | 76 | 138 | na | 5.3 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 5.3 | na | na | 25.101(c)(5)(B)
0PT41578 0PT41235 (R3003) | SL AEE – White River 345kV: Retermination at Blackwater Draw | City of Lubbock, Lubbock County | Reterminate the two circuits currently coming into Abernathy station into their newly constructed terminal locations at Blackwater Draw which is located on same property roughly 800' north. | 2021-01-04 | 2021-03-25 | 2021-03-25 |  | 2292400 |  |  | 100 | 345 | na | 1.4 | 2-959.6 ACSS/TW | Steel Poles | 100 | 0.45 | 100 | 0.95 | 25.101(c)(5)(A)
0PT42077 | Edgewood Switch - Terrell Switch 69 kV Line: HB 4150 Lake Tawakoni Crossing | City of Wills Point, Hunt County | Rebuild section of the Edgewood - Iron Bridge-Terrell Switch 69kV line which crosses Lake Tawakoni. | 2020-10-02 | 2020-12-01 | 2020-12-01 |  | 82581 |  |  | 100 | 69 | na | 0.15 | 4/0 ACSR Penguin | Steel Poles | 100 | 0.15 | na | na | 25.101(c)(5)(B)
0PT39373 (M4314) | Anna Switch to Anna Tap 138 kV Line: Rebuild | City of Melissa, Collin County | Rebuild the Anna Switch - Anna Tap 138-kV Line. | 2021-01-13 | 2021-05-15 |  |  | 17197276 |  |  | 66 | 138 | na | 16.4 | 2-959.6 kcmil ACSS/TW | Steel Poles | Varies | 8.2 | na | na | 25.101(c)(5)(B)
0PT40827 (M5274) | Eagle Mountain Switch - Deen Switch 138 kV Line: Rebuild Eagle Mountain Switch - Rosen Heights Tap | City of Saginaw, Tarrant County | Rebuild the Eagle Mountain Switch to Rosen Heights Tap section of the Eagle Mountain Switch - Deen Switch 138 kV line. | 2020-11-03 | 2021-05-15 |  |  | 24819800 |  |  | 52 | 138 | na | 20 | 2-959.6 kcmil ACSS/TW | Steel Poles | Varies | 10 | na | na | 25.101(c)(5)(B)
0PT38119 (R6069) | Lufkin Sw. - Herty Sw. 138 kV Line | City of Angelina, Lufkin County | Rebuild of Herty North Switch (Renamed Redland Switch) will require the retermination of the single circuit Herty North Sw. – Lufkin Sw. 138 kV line. | 2021-04-08 | 2021-05-15 |  |  | 1119280 |  |  | 67 | 138 | na | 0.3 | 1926 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(B)
0PT41976 (R6069) | Nacogdoches Southeast Switch - Herty North Switch 138 kV Line | City of Angelina, Lufkin County | Retermination of the single circuit Nacogdoches Southeast Sw. – Herty North Sw. 138 kV line. | 2020-10-13 | 2021-05-15 |  |  | 821203 |  |  | 93 | 138 | na | 0.3 | 1926 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT41975 (R6069) | Herty North Sw. - Huntington Sw. 138 kV Line | Angelina/ Lufkin | Retermination of the double circuit Herty North Sw. – Huntington/Lufkin East 138 kV line. | 2021-04-15 | 2021-05-15 |  |  | 1433700 |  |  | 95 | 138 | na | 0.3 | 1926 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT38602 | Morgan Creek Switch - Falcon Seaboard 345kV Line: 345kV Lattice Hardening (6/5) | Mitchell County | Rebuild a section of the Morgan Creek switch – Falcon Seaboard Switch 345 kV Line in Mitchell County. | 2020-10-09 | 2020-11-02 | 2020-11-02 |  | 438478 |  |  | 100 | 345 | na | 0.1 | 2-795 ACSR Drake | Steel Tower | 100 | 1 | na | na | 25.101(c)(5)(B)
0PT42248 (R6131) | Brown Switch - Killeen Switch 345 kV Line: Establish Buckhorn Switch | Mills County | Build a cut in the Brown Switch - Killeen Switch 345 kV Line to establish the new Buckhorn Switching Station. | 2020-11-14 | 2021-05-14 |  |  | 1490000 |  |  | 75 | 345 | na | 0.4 | 2 -1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole, Steel Tower | 160 | 0.2 | na | 0.2 | 25.101(c)(5)(A)
0PT42088 0PT42233 (R8322) | SL South Midland Switch-Pronghorn Switch 138 kV Line: Loop in and out the Cottonfield 138 Substation | City of Midland/Midland County | Loop in and out the SL South Midland Switch - Pronghorn Switch 138 kV Line to establish the new Cottonfield 138 kV substation. | 2020-10-15 | 2020-12-03 | 2020-12-03 |  | 710000 |  |  | 100 | 138 | na | 0.1 | 795 ACSR/959 ACSS | Steel Poles | 70 | 0.1 | na | na | 25.101(c)(5)(A)
0PT39788 (M5294) | Everman Switch-Cleburne Switch 138 kV Line: Terminate the line at the new Burleson Switch | City of Burleson/Tarrant County | Reterminate the Everman Switch-Cleburne Switch 138 kV line at Burleson Switch | 2020-11-10 | 2021-05-15 |  |  | 820000 |  |  | 49 | 138 | na | 0.3 | 1926 ACSS/TW | Steel Poles | 200 | 0.3 | na | na | 25.101(c)(5)(A)
0PT39797 (M5294) | Marrs Switch-Bourland Sub 138 kV Line: Terminate line at the Burleson Switch | City of Burleson/Tarrant County | Reterminate the Marrs Switch-Bourland Sub 138 kV Line at Burleson Switch | 2021-02-24 | 2021-05-15 |  |  | 401000 |  |  | 34 | 138 | na | 0.3 | 1926 ACSS/TW | Steel Poles | 90 | 0.3 | na | na | 25.101(c)(5)(A)
0PT41854 0PT42038 | Martin Lake Switch - Stryker Creek Switch 345 kV Line: HB 4150 Martin Lake Crossing | Rusk County | Rebuild a section of the Martin Lake Switch - Stryker Creek Switch 345 kV Line that crosses Lake Martin. | 2021-04-15 | 2021-05-31 |  |  | 1345745 |  |  | 24 | 345 | na | 0.2 | 2-1590 ACSR Falcon | Steel Lattice Tower | 300 | 0.1 | na | na | 25.101(c)(5)(B)
0PT39517 | Forney Switch - Tri-Corner Switch 345 kV Line: CMPC Erosion Control -- STR #25/1 | Seagoville City, Dallas County | Scope entails replacing tower with a double circuit steel pole and relocating structure away from the river. | 2020-11-09 | 2020-12-01 | 2020-12-01 |  | 442508 |  |  | 100 | 345 | na | 0.1 | 2-795 ACSR | Steel Pole | 150 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42284 | Trinidad Switch - Hillsboro Switch 138 kV Line: HB 4150 Richland Chambers Lake Crossing | Navarro County | Rebuild a section of the Trinidad Switch - Hillsboro Switch 138 kV Line that crosses Richland Chambers Reservoir. | 2020-10-13 | 2020-12-15 | 2020-12-15 |  | 474673 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW | Concrete H-Frame | 175 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41920 | Long Lake Tap - Big Brown Sub 138 kV Line: HB 4150 Lake Fairfield Crossing | City of Fairfield, Freestone County | Rebuild a section of the Long Lake Tap - Big Brown Sub 138 kV Line. | 2020-11-09 | 2020-12-22 | 2020-12-22 |  | 591104 |  |  | 100 | 138 | na | 0.3 | 795 ACSR Drake | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(B)
0PT42574 | China Grove Switch - Radium - Paint Creek 138 kV Line: HB 4150 Lake Stamford Crossings | City of Haskell, Haskell County | Rebuild a section of the China Grove - Radium - Paint Creek 138 kV Line. | 2021-09-15 | 2021-10-29 | [5 empty] | 0 | 138 | na | 1 | 636 ACSR Grosbeak | Steel Poles | 50 | 1 | na | na | 25.101(c)(5)(B)
0PT40858 | Jacksboro Switch - Krum West Switch 345 kV Line: Failed Dead End Replacements | City of Decatur, Wise County | Replace line dead-end terminals and insulator assemblies on the Jacksboro - Krum West 345 kV line. | 2020-12-04 | 2021-12-17 |  |  | 590000 |  |  | 22 | 345 | na | 0.1 | 1590 kcmil ACSR | Steel Towers | 100 | 0.1 | na | na | 25.101(c)(5)(B)
17T65032 | Royse City - Commerce 69kV Line: Scatter Branch Sub Line Work | City of Neylandville, County of Hunt | Line work associated with establishing the new Scatter Branch Substation | 2020-11-09 | 2020-12-28 | 2020-12-28 |  | 1863737 |  |  | 100 | 69 | na | 0.75 | 1926.9 kcmil ACSS/TW | Steel Poles | 75 | 0.75 | na | na | 25.101(c)(5)(A)
17T65244 (M3047) | Renner TPL - Allen / Plano Tennyson 138 kV Line: Rebuild Renner TPL - STR 11/4D | City of Plano, Collin County | Rebuild Renner - Structure 11/4D section of the Renner TPL - Allen / Plano Tennyson 138 kV Line. | 2020-11-12 | 2021-05-15 |  |  | 10295534 |  |  | 56 | 138 | na | 3.6 | 2-959.6 kcmil Suwannee ACSS/TW | Steel Poles | varies | 3.6 | na | na | 25.101(c)(5)(B)
0PT42555 | NTUSU AJ Swope Sub - Alibates Sub 345 kV Line : Galloping Device Installation | City of Amarillo, Potter County | Install galloping devices on several spans of the AJ Swope - Alibates 345 kV Line. | 2020-12-07 | 2020-12-17 | 2020-12-17 |  | 324240 |  |  | 100 | 345 | na | 0.19 | 2-1926 ACSS/TW | Steel Towers | 175 | 0.19 | na | na | 25.83(a)(3)
0PT42557 | NTUSU Ogallala - Tule Canyon 345 kV Line: Galloping Device Installation | City of Tulia, Swisher & Carson County | Install galloping devices on several spans of the Ogallala - Tule Canyon 345 kV Line. | 2020-12-12 | 2020-12-17 | 2020-12-17 |  | 136586 |  |  | 100 | 345 | na | 1.57 | 2-1926 ACSS/TW | Steel Towers | 175 | 1.57 | na | na | 25.83(a)(3)
0PT41579 | Argyle Sub - Krum Tap Switch 138 kV Line : Structure Replacement | City of Denton, Denton County | Relocate 3 H-frame structures to avoid future impact of nearby river. | 2020-10-05 | 2020-11-01 | 2020-11-01 |  | 281063 |  |  | 100 | 138 | na | 0.1 | 795 ACSR | Concrete and Wood H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42686 (M3058) | Royse Switch-Terrell Switch: Establish Quinlan Tap 138/69 kV Autotransformer | Royse City/Rockwall County | Rebuild a section on the Royse Switching Station - Terrell Substation 69 kV Line for the installation of the Quinlan Tap 138/69 kV Autotransformer. | 2021-02-08 | 2021-05-15 |  |  | 1882000 |  |  | 99 | 69/138 | 138 | 0.15 | 1590 ACSR Falcon | Steel Poles, H-frame Switch | 100 | 0.15 | na | na | 25.101(c)(5)(A)
0PT42236 (M4311) | Waxahachie Sub - Ennis South Sub 138 kV Line: Reterminate section from Ennis West Switch to Sterrett Switch into Ennis West Switch | City of Ennis, Ellis County | Reterminate the Waxahachie Sub - Ennis South Sub 138 kV Line section from Ennis West Switch - Sterrett Switch into its new bay position at Ennis West Switching Station. | 2021-02-09 | 2021-05-15 |  |  | 901230 |  |  | 34 | 138 | na | 0.2 | 1926.9 ACSS/TW | Steel Monopoles | 100 | 0.2 | na | na | 25.101(c)(5)(A)
0PT42526 (M4311) | Waxahachie Sub - Ennis South Sub 138 kV: Reterminate into Ennis West Switch | City of Ennis, Ellis County | Reterminate the Waxahachie Sub - Ennis South Sub 138 kV Line section from Ennis West Switch - Ennis South Sub into its new bay position at Ennis West Switching Station | 2021-02-26 | 2021-05-15 |  |  | 1253766 |  |  | 34 | 138 | na | 0.1 | 1926.9 ACSS/TW | Steel Monopoles | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT42531 0PT43472 | Sweetwater Downtown Tap - Sweetwater Downtown Substation 138 kV Line: Replace Structures 101/1 & 1/1 | City of Sweetwater, Nolan County | Replace tap structure (101/1) with a new Heavy Duty H-Frame Switch structure and replace two line sectionalizing switches and install an additional switch and replace existing structure (1/1) with a SC wood pole. | 2020-11-17 | 2020-12-21 | 2020-12-21 |  | 1001927 |  |  | 100 | 138 | na | 0.1 | 336 ACSR Linnett | Steel H-Frame Switch & Wood monopole | 25 | 0.1 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT42618 0PT43240 | Eskota Switch - Morgan Creek Switch 138 kV Line: Replace Structures 100/10 & 101/2 | City of Sweetwater, Nolan County | Replace structures (100/10) & (101/2) with wood H-Frames with steel crossarms and double insulators. A temporary bypass will be utilized for this project. | 2020-11-08 | 2020-12-21 | 2020-12-21 |  | 575912 |  |  | 100 | 138 | na | 0.1 | 795 ACSR Drake | Wood H-Frames | 50 | 0.1 | na | na | 25.101(c)(5)(B) | Costs updated to include associated ROW estimates.
0PT38743 | Oran Sub - Mineral Wells Sub 138 kV Line : Erosion Control | City of Mineral Wells/Palo Pinto County | Install erosion control guards around structures 02/08 on the Oran Sub - Mineral Wells Sub 138 kV line. | 2020-11-05 | 2020-12-01 | 2020-12-01 |  | 158557 |  |  | 100 | 138 | na | 0.1 | 1590 ACSR | Wood H-frame | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT41580 | Tyler Grande Sub - Overton Sub 138 kV Line : Structure Replacement | City of Arp, Smith County | Relocate structure 61/02 on the Tyler Grande Sub – Overton Sub 138 kV line. | 2020-12-08 | 2020-12-21 | 2020-12-21 |  | 200981 |  |  | 100 | 138 | na | 0.3 | 4/0 CU | Wood H-frame | 100 | 0.3 | na | na | 25.101(c)(5)(B)
0PT43075 (M5274) | Rosen Heights Tap No 1 (West) : Rebuild Tap Point | City of Fort Worth, Tarrant County | Reconfigure the existing Rosen Heights Tap (west circuit) from a hard tap to 3-way switch configuration. | 2021-03-04 | 2021-05-15 |  |  | 618456 |  |  | 38 | 138 | na | 0.1 | 2-959.6 kcmil ACSS/TW | Steel Poles | 75 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43076 (M5274) | Rosen Heights Tap No 2 (East) : Rebuild Tap Point | City of Fort Worth, Tarrant County | Reconfigure the existing Rosen Heights Tap (east circuit) from a hard tap to 3-way switch configuration. | 2021-03-04 | 2021-05-15 |  |  | 617512 |  |  | 25 | 138 | na | 0.1 | 2-959.6 kcmil ACSS/TW | Steel Poles | 75 | 0.1 | na | na | 25.101(c)(5)(B)
17T62191 0PT39212 (M5155) | Handley SES - Sherry 138 kV Line: Rebuild Handley SES - Pantego Sub Section (Phase 1) | City of Arlington, Tarrant County | Rebuild the Handley SES - Pantego Sub Section (Phase 1) of the Handley SES - Sherry 138 kV Line. | 2021-09-16 | 2021-12-15 | [5 empty] | 0 | 138 | na | 3.8 | 1926.9 kcmil ACSS/TW | Steel Poles | Varies | 3.8 | na | na | 25.101(c)(5)(B)
0PT43066 | Liggett Switch - Euless 138kV Line: Reterminate at Irving Valley View Sub | City of Irving, Dallas County | Reterminate Liggett Switch - Euless 138kV Line at Irving Valley View Substation. | 2021-04-10 | 2021-05-15 |  |  | 164012 |  |  | 50 | 138 | na | 0.1 | 2-1033.5 ACSR Curlew | Steel Poles | 140 | 0.1 | na | na | 25.101(c)(5)(A)
0PT40191 0PT42105 (R1721) | Elm Mott - Bosque (BEC) 138kV Line: Rebuild Elm Mott Switch - Rogers Hill Sub (BEC) | City of Elm Mott, McLennan County | Rebuild the Elm Mott Switch - Rogers Hill Sub (BEC) section of the Elm Mott Switch to Bosque Switch (BEC) 138 kV Line. | 2021-01-13 | 2021-05-15 |  |  | 7325451 |  |  | 92 | 138 | na | 5.6 | 2 - 959.6 MCM ACSS/TW/HS “Suwannee” | Steel Poles | 100 | 5.6 | na | na | 25.101(c)(5)(B)
0PT42346 | Hutto - Round Rock - Gabriel 138 kV Line: Midnight Sub Cut- In | City of Round Rock, Williamson County | Line work associated with establishing Midnight Substation. This work is occurring on the Hutto Switch - Round Rock - Gabriel 138kV line. | 2021-09-20 | 2021-10-15 | [5 empty] | 0 | 138 | na | 0.4 | 795 ACSR | Wood H-Frames | 100 | 0.4 | na | na | 25.101(c)(5)(A)
0PT41461 (M5315) | Farmersville Switch - Monticello Switch 345 kV Line : Delilah Solar Generator Interconnect | Franklin County | Establish a 345 kV point-of-interconnection (POI) for Delilah Solar Generator at Thorn Tree 345 kV Switch. | 2021-03-08 | 2021-05-31 |  |  | 3900000 |  |  | 70 | 345 | na | 0.2 | 2-1926.9 ACSS/TW Cumberland | Steel Poles and Towers | 170 | 0.2 | na | na | 25.101(c)(5)(A)
18T65207 (M4088) | Northaven Switch - Morrison Lane Switch 138 kV Double Circuit Line Section: Rebuild Northaven - Welch Road - Marsh Lane | City of Dallas, Dallas County | Rebuild 2.9 mile section of Northaven Switch - Morrison Lane Switch 138 kV Double Circuit Line from Northaven to Marsh Lane Sub. | 2021-08-15 | 2021-12-15 | [5 empty] | 0 | 138 | na | 5.8 | 1926.9 ACSS/TW | Steel Poles | 100 | 2.9 | na | na | 25.101(c)(5)(B)
0PT38695 (R463) | Waco West Switch – Waco East Switch 138kV Line: Rebuild Waco West Switch - Structure 1/8 Line Section | City of Waco, McLennan County | Rebuild the 10.6-mile Waco West Switch - Structure 1/8 138 kV line section of the Waco West Switch – Waco East Switch 138 kV Line. | 2021-02-21 | 2021-12-15 |  |  | 20528867 |  |  | 8 | 138 | na | 10.6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 10.6 | na | na | 25.101(c)(5)(B)
0PT41773 (R6128) | Navarro Switch - Watermill Switch 345 kV Line: Establish Big Onion Switch | City of Ennis, Ellis County | Establish a point of interconnection to the Solar Strategic Energy generating facility by establishing Big Onion Switch on the Navarro - Watermill 345 kV transmission line. | 2021-02-10 | 2021-04-21 |  |  | 1550000 |  |  | 99 | 345 | na | 0.1 | 2-1926.9 kcmil ACSS/TW | Steel Towers | 160 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43220 | Navy Kickapoo Switch - Holliday 69 kV Line: Storm Damage (TSP20017) | City of Archer, Archer County | Replace 8 wood pole structures, including 24 insulators, and 3 cross arms Holliday Sub - Navy Kickapoo Sub 69 kV Line. | 2020-08-17 | 2020-08-22 | 2020-08-22 |  | 185007.21 |  |  | 100 | 69 | NA | 0.57 | 4/0 ACSR | Wood Monopoles | 50 | 0.57 | na | na | 25.101(c)(3) | Storm Damage Restoration
0PT43218 | Holliday - Seymour 69 kV Line: Storm Damage (TSP20017) | City of Wichita Falls, Wichita County | Replace 4 wood pole structures and 21 insulator assemblies Holliday Sub - Seymour Sub 69 kV Line. | 2020-08-17 | 2020-08-22 | 2020-08-22 |  | 89072.43 |  |  | 100 | 69 | NA | 0.8 | 4/0 ACSR | Wood Monopoles | 50 | 0.8 | na | na | 25.101(c)(3) | Storm Damage Restoration
0PT43219 | Holliday - Electra 69 kV Line: Storm Damage (TSP20017) | City of Electra, Wichita County | Replace 1 cross arms on the Holliday - Electra 69 kV Line. | 2020-08-17 | 2020-08-21 | 2020-08-21 |  | 16609.62 |  |  | 100 | 69 | NA | 0.01 | 4/0 ACSR | Wood H-frames | 50 | 0.01 | na | na | 25.101(c)(3) | Storm Damage Restoration
0PT43229 | NTUSU Driver - Hadacol Corner 138 kV Line: Damage | City of Midland, Midland County | Replace 4 spans of conductor, OPGW, and 5 structures worth of insulators as the result of fire damage. | 2020-08-18 | 2020-09-01 | 2020-09-01 |  | 290783.85 |  |  | 100 | 138 | NA | 0.63 | 959 ACSS/TW | Steel Deadends, Concrete Tangents | 75 | 0.63 | na | na | 25.101(c)(3) | Emergency Project
0PT43288 | NTUSU Driver - SkyWest 138 kV Line: OPGW Damage | City of Midland, Midland County | Replace 3 spans of OPGW as the result of fire damage. | 2020-08-20 | 2020-09-01 | 2020-09-01 |  | 57042.42 |  |  | 100 | 138 | NA | 0.36 | 959 ACSS/TW | Steel Deadends, Concrete Tangents | 75 | 0.36 | na | na | 25.101(c)(3) | Emergency Project
0PT43237 | Sherry Switch - Fish Creek Switch 138 kV Line (South Circuit): Damage Restoration | City of Grand Prairie, Dallas County | Replace 2 lattice towers with 2 steel monopoles and replace conductor and shield wire on the Sherry Sw - Fish Creek Sw 138 kV Line. | 2020-08-19 | 2020-10-06 | 2020-10-06 |  | 520049 |  |  | 100 | 138 | na | 0.97 | 795 ACSR, Drake, Single | Steel Monopoles | Variable | 5150 | na | na | 25.101(c)(3) | Emergency Project
0PT43249 | Sherry Switch - Fish Creek Switch 138 kV Line (North Circuit) : Damage Restoration | City of Grand Prairie, Dallas County | Replace conductor and install 2 steel monopoles on the Sherry Sw - Fish Creek Sw 138 kV Line. | 2020-08-19 | 2020-10-06 | 2020-10-06 |  | 520049 |  |  | 100 | 138 | na | 0.97 | 795 ACSR, Drake, Single | Steel Monopoles | Variable | 5150 | na | na | 25.101(c)(3) | Emergency Project
0PT42445 | Willow Creek Switch - Hicks Switch 345 kV | Wise County | The scope of this project involves relocating an existing TE 69190 Tower (24/05) on the Willow Creek Switch - Hicks Switch 345 kV Line. | 2020-11-11 | 2020-12-01 | 2020-12-01 |  | 160619 |  |  | 100 | 345 | na | 23.99 | 1926 ACSS/TW | Lattice Tower | 160 | 24 | na | na | 25.101(c)(5)(B)
0PT42438 | Commerce Switch - Sulphur Springs Switch 138 kV Line : Erosion Control | Commerce City | Structure 06/01 concrete H-frame on the edge of the creek bed experiencing high levels of exposure. This project entails relocating the structure experiencing the erosion issues. | 2020-11-30 | 2020-12-21 | 2020-12-21 |  | 548677 |  |  | 100 | 138 | na | 35 | 795 ACSR | H-Frame | 100 | 35 | na | na | 25.101(c)(5)(B)
0PT41581 | Valley Switch - Commerce Switch 138 kV Line : Erosion Control | Fannin County | Installing erosion control guards around structures 01/06 - 01/07 on the Valley Switch - Commerce Switch 138 kV line. | 2020-12-02 | 2020-12-28 | 2020-12-28 |  | 376000 |  |  | 100 | 138 | na | 25.9 | 795 ACSR | Lattice Tower | 100 | 25.9 | na | na | 25.101(c)(5)(B)
0PT41709 | Shamburger Switch - Martin Lake Switch 345 kV Line : Erosion Control | Overton City | Large degrees of erosion around structure 24/05 on the Shamburger - Martin Lake 345kV line. Scope entails installing erosion control guards. | 2020-11-24 | 2020-12-01 | 2020-12-01 |  | 368593 |  |  | 100 | 345 | na | 43.4 | 1590 ACSR | Lattice Tower | 160 | 43.4 | na | na | 25.101(c)(5)(B)
0PT42378 | Handley-Liggett 138 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent & dead end structures. | 2021-04-21 | 2021-12-15 |  |  | 2474886 |  |  | 2 | 138 | na | 2 | 959 ACSS "Suwannee" (Non-Bundled) | Steel Pole | varies | 1.0021 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42380 | Handley-Saginaw 138 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent & dead end structures. | 2021-04-26 | 2021-12-15 |  |  | 2560873 |  |  | 21 | 138 | na | 2 | 1926 ACSS "Cumberland" (Non-Bundled) & 1233 ACSS "Yukon" (Non-Bundled) | Steel Pole | varies | 0.99527 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42381 | Handley-Richland Hills 69 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new single circuit, steel monopole, tangent & dead end structures. | 2021-05-15 | 2021-07-15 |  |  | 2236717 |  |  | 0 | 69 | na | 0.99 | 300 ACSR "Ostrich" (Non-Bundled) & 959 ACSS "Suwannee" (Non-Bundled) | Steel Pole | varies | 0.98902 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT43252 | Hutto Switch Station - Round Rock 138 kV Line: Relocate Str. 11/2 | City of Hutto, Williamson County | Relocate structure 11/2 on the Hutto Switch - Round Rock 138 kV Line | 2020-11-23 | 2020-11-24 | 2020-11-24 |  | 105339 |  |  | 100 | 138 | na | 0.02 | 1590 ACSR | DC Steel Monopole | 100 | 0.02 | na | na | 25.101(c)(5)(E)
0PT38651 (R9038) | Means Sub - North Andrews Switch 138 kV Line: North Andrews Switch Retermination | Andrews County | Rebuild a 0.1 mile section of the Means – Fullerton 69 kV Line to reterminate from the 69 kV terminal into the new 138 kV terminal at North Andrews Substation. | 2021-02-10 | 2021-05-15 |  |  | 746780.05 |  |  | 99 | 69 | 138 | 0.1 | 959 ACSS | Steel Monopoles | Varies | 0.1 | na | na | 25.101(c)(5)(B)
0PT40925 0PT42534 (R6097) | Eustace SE Tap - Eustace Sub 138 Kev Line : Rebuild | City of Mabank, Henderson County | Rebuild the 2.1-mile Eustace Southeast Tap - Eustace 138 kV Line Section of the Eustace Southeast Switch (RCEC) - Mabank 138 kV Line using a conductor rated for 2071A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2021-03-04 | 2021-12-15 |  |  | 3827444 |  |  | 97 | 138 | na | 2.1 | 2- 1926.9 MCM ACSS/TW/HS "Cumberland" | Steel Pole | 100 | 2.1 | na | na | 25.101(c)(5)(B)
0PT42091 0PT42650 (R6097) | Pauline Sub - Mabank Sub 138 kV Line : Rebuild | City of Mabank, Henderson County | Rebuild the 3.4-mile Pauline Sub - Mabank Sub 138 kV Line Section of the 9.3-mile Eustace Southeast Switch (RCEC) - Mabank 138 kV Line Section using a conductor rated for 2071A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2021-09-20 | 2021-12-15 | [5 empty] | 0 | 138 | na | 3.4 | 2- 1926.9 MCM ACSS/TW/HS "Cumberland" | Steel Pole & H- Frame | 50 | 3.4 | na | na | 25.101(c)(5)(B)
0PT39174 | Grandview 138 kV Tap Line: Sl 338 Relocation For TxDOT | City of Odessa, Ector County | Relocation with new double circuit, steel monopole, tangent structures. | 2021-02-01 | 2021-05-15 |  |  | 694284 |  |  | 99 | 138 | na | 1.1 | 795 ACSR "Drake" (Non-Bundled) | Steel Pole | 75 | 0.54545 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT39793 | Cedar Hill-Tri Corner 345 kV: Loop 9 Relocation For TxDOT | City of Ferris, Dallas County | Relocation with new double circuit, steel lattice tower, tangent structures. | 2021-03-02 | 2021-05-15 |  |  | 1798843 |  |  | 99 | 345 | na | 2.22 | 959 ACSS "Suwannee" (Bundled) | Steel Tower | 250, shared | 1.11 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41780 0PT43427 (R8541) | Dog House Switch - Prospero Solar ll Poi 345 kV Line: Construct Line Section To Connect Prospero Solar ll To Dog house | Andrews County | Install one full tension deadend and one span of wire from Dog house Switch. New deadend will serve as demarcation point for interconnection with Prospero Solar II. | 2021-01-11 | 2021-04-01 | 2021-04-01 |  | 457505 |  |  | 100 | na | 345 | 0.03 | 959 ACSS/TW | Steel Pole | na | na | 160 | 0.03 | 25.101(c)(5)(A)
0PT42090 (R6097) | Eustace Sub - Pauline Sub 138 kV Line : Rebuild | City of Mabank, Henderson County | Rebuild the 3.8-mile Eustace Sub - Pauline Sub 138 kV Line Section of the 9.3-mile Eustace Southeast Switch (RCEC) - Mabank 138 kV Line Section using a conductor rated for 2071A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2021-06-01 | 2021-12-15 |  |  | 4835000 |  |  | 0 | 138 | na | 3.8 | 2- 1926.9 MCM ACSS/TW/HS "Cumberland" | Steel Pole | 100 | 3.8 | na | na | 25.101(c)(5)(B)
0PT41843 0PT41275 (R8308) | Big Spring Switch - Stanton East Switch 138 kV Line: Line work associated with Natural Dam Station Retermination NTUSU Big Spring Switch - Stanton East Switch 138 kV Line: Natural Dam Retirements and Modifications Only | Howard County | Reterminate the Big Spring Switch - Stanton East Switch 138 kV Line at Natural Dam Station | 2021-09-16 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.23 | 959 ACSS/TW | Steel Pole | 70 | 0.23 | na | na | 25.101(c)(5)(A)
0PT43279 (R8308) | Big Spring West Tap - Stanton East Switch 138 kV Line: Raise line for Natural Dam | Howard County | Structure modification to accommodate the retermination into Natural Dam Station | 2021-02-07 | 2021-05-15 |  |  | 436548 |  |  | 99 | 138 | na | 0.2 | 4/0 ACSR | Steel Pole | Varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT43162 | Wink Sub - Wink Basin Sub 69 kV Line: Shifting Sands Sub Line Cut-In | City of Kermit, Winkler County | Line work in aid of establishing Shifting Sands Sub. | 2021-05-10 | 2021-07-01 |  |  | 890000 |  |  | 0 | 69 | na | 0.3 | 336 kcmil ACSR Linnet & 4/0 AWG ACSR Penguin | Steel Pole | 50 | 0.3 | na | na | 25.101(c)(5)(A)
0PT42341 0PT43006 | Riverton - Kyle Ranch 138 kV Line: Cut-in to Establish Alcatraz Sub | City of Orla, Loving County | Build 0.8-mile double-circuit tap to establish Alcatraz Sub. | 2021-04-07 | 2021-05-15 |  |  | 2742876 |  |  | 34 | na | 138 | 0.8 | 1926.9 kcmil ACSS/TW/HS Cumberland | Steel Poles | na | na | 70 | 0.8 | 25.101(c)(5)(A)
0PT42065 (M5316) | Riley Switch (AEP) - Bowman Switch 345 kV Line: Byrd Road Switch Cut-In for Ajax Wind | Near City of Wichita Falls, Wichita County | Establish a point of interconnection to the Western Trail Wind generating facility by establishing Byrd Road Switch on the Riley - Bowman 345 kV transmission line. | 2021-03-11 | 2021-05-15 |  |  | 1904313 |  |  | 45 | 345 | na | 0.21 | 2-1926.9 kcmil ACSS/TW | Steel Tower, Steel Pole | 160 | na | 400 | 0.18 | 25.101(c)(5)(A)
0PT41736 0PT42802 (M4315) | Ennis Switch - Desoto Switch 138 kV Line: Cut In Pebble Creek Switch | City of Red Oak, Ellis County | Separate and terminate the Ennis Switch - Desoto Switch 138 kV Line to establish the new Pebble Creek Switch. | 2021-03-05 | 2021-11-15 |  |  | 3163564 |  |  | 83 | 138 | 138 | 0.5 | 2 - 959.6 MCM ACSS/TW/HS “Suwannee” | Steel Pole | 100 | na | 75 | 0.5 | 25.101(c)(5)(A)
0PT39818 (M5279) | Bryan Ave Sub - Forest Hill Switch 69 kV Line : Forest Hill Switch Station Retermination | City of Fort Worth, Tarrant County | Re-terminate the Bryan Ave - Forest Hill Switch 69-kV Line into Marrs Switch. | 2021-04-21 | 2021-12-15 |  |  | 413500 |  |  | 34 | 69 | 69 | 0.05 | 795 MCM ACSR Drake | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41822 0PT42106 (R1721) | Elm Mott - Bosque (BEC) 138 kV Line: Rebuild Rogers Hill Sub (BEC) - Bosque Switch (BEC) | City of Elm Mott, McLennan County | Rebuild the Rogers Hill Sub (BEC) - Bosque Switch (BEC) section of the Elm Mott Switch to Bosque Switch (BEC) 138 kV Line. | 2021-04-20 | 2021-12-15 |  |  | 15593878 |  |  | 1 | 138 | na | 13.7 | 959.6 MCM ACSS/TW/HS “Suwannee” | Steel Pole | 100 | 13.7 | na | na | 25.101(c)(5)(B)
0PT41113 | TxDOT Loop 9 Relocation Waxahachie-Ferris-Trinity Hts. 69 kV Line | City of Ferris, Dallas County | Relocation with new single circuit, steel monopole, dead end structures. | 2021-03-01 | 2021-05-15 |  |  | 911688 |  |  | 99 | 69 | na | 0.04 | 959 ACSS "Suwannee" (Non-Bundled) | Steel Pole | Varies | 0.044886 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41119 | TxDOT SH 5 Relocation Anna Sw.-Valley Jct. 345 kV Line | City of Anna, Collin County | Relocation with new double circuit, steel monopole, tangent structures. | 2021-03-01 | 2021-05-15 |  |  | 370435 |  |  | 34 | 345 | na | 0.38 | 1590 ACSR "Falcon" (Bundled) | Steel Pole | 230, shared | 0.18807 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41124 | TxDOT SH 5 Relocation Anna Sw.-Anna 138 kV Tap Line | City of Anna, Collin County | Relocation with new double circuit, steel monopole, tangent structures. | 2021-03-10 | 2021-05-15 |  |  | 267067 |  |  | 67 | 138 | na | 0.38 | 959 ACSS "Suwannee" (Non-Bundled) | Steel Pole | 230, shared | 0.18769 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41123 | TxDOT Loop 9 Relocation Wilmer-Watermill 138 kV Line | City of Ferris, Dallas County | Relocation with new single circuit, steel monopole, tangent & dead end structures. | 2021-03-01 | 2021-05-15 |  |  | 3238124 |  |  | 99 | 138 | na | 1.52 | 795 ACSR "Drake" (Non-Bundled) & 959 ACSS "Suwannee" (Non-Bundled) | Steel Pole | varies | 1.5246 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41130 | TxDOT Loop 9 Relocation Trinidad-Liggett 138 kV Line | City of Ferris, Dallas County | Relocation with new single circuit, concrete H-frame, tangent structures. | 2021-05-12 | 2021-05-31 |  |  | 686090 |  |  | 0 | 138 | na | 0.55 | 336 ACSR "Linnet" (Bundled) | Concrete H-Frame | 100 | 0.55038 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41127 | TxDOT Loop 9 Relocation Limestone-Watermill 345 kV Line | City of Ferris, Dallas County | Relocation with new double circuit, steel lattice tower, tangent structure. | 2021-04-19 | 2021-05-15 |  |  | 565614 |  |  | 41 | 345 | na | 0.84 | 1590 ACSR "Falcon" (Bundled) | Steel Tower | 160 | 0.42273 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT43430 (M4108) | Northaven Switch - Renner Switch 138 kV Line: Upgrade Line Switches (302, 4418, 4487, 4558) to 3200 Amp | Dallas County | Upgrade Line Switches 302, 4418, 4487, and 4558 on structures T110, T110A, T11S, and T111N to 3200 Amp Switches. | 2021-03-03 | 2021-03-31 |  |  | 550000 |  |  | 99 | 138 | na | 0.1 | 1-1926.9 kcmil ACSS/TW | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42990 (M4095) | Mountain Creek Switch - Norwood Switch 138 kV Line : Install Sectionalizing Switch At TRA Tap | City of Dallas, Dallas County | Install Manually Operated, Sectionalizing Switch at TRA Tap | 2021-09-20 | 2021-11-30 |  |  | 745000 |  |  | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42820 | Audelia Termination-lake Highlands 138 kV Line: Pumping Plant Replacement | City of Dallas, Dallas County | Replacing the two existing UG Transmission HPFF Pressurization Plants at lake Highland Sub with a new HPFF Pressurization Plant. | 2021-09-20 | 2021-12-31 | [5 empty] | 0 | 138 | na | 0 | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT42412 | Tradinghouse Switch - Elm Mott 345 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Modify a section of the Tradinghouse Switch - Elm Mott 345 kV Line. | 2021-04-08 | 2021-05-15 |  |  | 1871664 |  |  | 34 | 345 | na | 0.9 | 2-795 ACSS/E3X/MA5 | Steel Tower | 160 | 0.9 | na | na | 25.101(c)(5)(A) | Lake Remediation project for HB-4150
0PT42409 | Lake Creek Switch - Elm Mott 138 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Provide a clearance upgrade from structure 1/1 thru structure 1/5 section of the Lake Creek Switch - Elm Mott 138 kV Line. | 2021-03-24 | 2021-12-31 |  |  | 2718935 |  |  | 8 | 69 | 138 | 6.8 | 795 kcmil ACSR Drake | Steel Pole | 100 | 5.2 | 50 | 0.06 | 25.101(c)(5)(A) | Lake Remediation project for HB-4150
0PT40674 0PT43239 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line: Convert Duval To Bryan Ave To 138 kV | City of Fort Worth, Tarrant County | Rebuild a portion of the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal locations at the Duval Switch Station and at the Bryan Ave Switch Station for the 138 kV line conversion. | 2021-03-08 | 2021-12-15 |  |  | 11873738 |  |  | 29 | 69 | 138 | 6.7 | 959.6 ACSS/TW "Suwannee" | Steel Poles | 50 | 4.97 | na | na | 25.101(c)(5)(B)
0PT40622 0PT43239 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line : Line Conversion To 138 kV (Handley Switch-Duval Section) | City of Fort Worth, Tarrant County | Reterminate the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal location at the Handley Switch Station and at the Duval Switch Station for the 138 kV line conversion. | 2021-07-15 | 2022-02-28 | [5 empty] | 0 | 69 | 138 | 0.3 | 959.6 ACSS/TW Suwannee | Steel Poles | 50 | 0.3 | na | na | 25.101(c)(5)(B) | Upgrade to 138 kV and extend alignment to Handley 138 kV Station
0PT39817 | Stanton East Switch - Spraberry Switch 69 kV Line : CMPC Line Hardening (str. 13/6 & 13/7) | City of Stanton, Martin County | Rebuild the section of the Stanton East Switch - Spraberry Switch 69 kV Line that crosses Interstate 20 in Martin County. | 2021-05-03 | 2021-06-30 |  |  | 920000 |  |  | 0 | 69 | na | 0.22 | 4/0 ACSR, 959 ACSS | Wood and Steel Pole | 50 | 0.22 | na | na | 25.101(c)(5)(B)
0PT39814 | Stanton East Switch - Spraberry Switch 69 kV Line : CMPC Line Hardening (str. 24/12 & 24/13) | City of Stanton, Martin County | Rebuild the section of the Stanton East Switch - Spraberry Switch 69 kV Line that crosses Interstate 20 in Martin County. | 2021-04-09 | 2021-06-30 |  |  | 908026 |  |  | 34 | 69 | na | 0.13 | 4/0 ACSR | Wood and Steel Pole | 50 | 0.13 | na | na | 25.101(c)(5)(B)
0PT39813 | Morgan Creek Sw. - Big Spring Sw. 69 kV Line: Iatan Howard Tap CMPC Line Hardening | City of Coahoma, Howard County | Replace structures adjacent to the highway on Iatan Howard Tap section of the Morgan Creek Switch to Big Spring Switch line | 2021-05-17 | 2021-06-30 |  |  | 535858 |  |  | 0 | 69 | na | 0.1 | 1/0 ACSR | Concrete and Wood Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38650 (R9038) | Means Sub - North Andrews Switch 138 kV Line: Means Sub Rebuild | Andrews County | Reterminate the Means – North Andrews Sw 69 kV Line at its new terminal location at Means Substation, which is being converted from 69 kV to 138 kV. | 2021-03-06 | 2021-04-05 | 2021-04-05 |  | 355334 |  |  | 100 | 69 | 138 | 0.1 | 959 ACSS | na | 75 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38235 (R9039) | Fullerton Switch - North Andrews Switch 138 kV Line: Fullerton Switch Retermination | Andrews County | Rebuild a section of the Fullerton Switch - North Andrews Switch 138 kV Line to reterminate from the 69 kV terminal into the new 138 kV terminal at Fullerton Switch Station. | 2021-03-01 | 2021-05-15 |  |  | 1060655 |  |  | 99 | 69 | 138 | 0.2 | 959 ACSS | Steel Pole | 75 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38098 | Means Sub - Fullerton Switch 69 kV Line: Fullerton Switch Retermination | Andrews County | Reterminate the Means – Fullerton Switch 69 kV Line at its new 138 kV terminal location at Fullerton 138 kV Switching Station. | 2021-03-10 | 2021-05-15 |  |  | 189972 |  |  | 99 | 69 | 138 | 0.1 | 959 ACSS | Steel Pole | 85 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43606 (R8503) | Wink Switch – Wink Sub 138 kV line: Reconductor from POI to Wink Switch for TNMP Wink Sub | Winkler County | Re-establish the point of delivery for Texas-New Mexico Power’s Wink substation on the Wink Sw. – Wink Sub 138 kV transmission line. | 2021-03-26 | 2021-05-15 |  |  | 255000 |  |  | 99 | 138 | na | 0.15 | 1926 ACSS/TW | Steel Pole | Varies | 0.15 | na | na | 25.101(c)(5)(B)
0PT43635 (R8503) | Wink Switch – Wink Sub 69 kV line: Re-termination from POI to Wink Switch for TNMP Wink Sub | Winkler County | Re-establish the point of delivery for Texas-New Mexico Power’s Wink substation on the Wink Sw. – Wink Sub 69 kV transmission line. | 2021-03-16 | 2021-05-15 |  |  | 985866 |  |  | 64 | 69 | na | 0.17 | 1926 ACSS/TW | Steel Pole | Varies | 0.17 | na | na | 25.101(c)(5)(B)
0PT43687 0PT42347 | Brown - Grady 138 kV Line: Flat Land Substation Cut In | City of Lenorah, Martin County | Cut in the Brown - Grady 138 kV Line to establish the new Flat Land substation. | 2021-04-26 | 2021-05-15 |  |  | 1061670 |  |  | 25 | 138 | na | 0.1 | 1926.9 ACSS/TW & 959.6 ACSS/TW | Steel Pole | 70 | 0.1 | 70 | 0.07 | 25.101(c)(5)(A) | Sharyland project
0PT42008 (M4317) | Waxahachie Sub - Ennis South Sub 138 kV Line: Reterminate section from Ennis West Switch to Sterrett Switch into Ennis West Switch | Palmer, Ellis County | Loop the Ennis Switch - Desoto Switch 138 kV Line into Palmer substation and convert the Palmer 69 kV substation to 138 kV operation. | 2021-05-17 | 2021-12-15 |  |  | 3991010 |  |  | 0 | 69 | 138 | 1 | 1926.9 ACSS/TW | Steel Pole | 80 | 1 | na | na | 25.101(c)(5)(B)
0PT42991 (M4095) | Mountain Creek Switch - Norwood Switch 138 kV Line : Install Sectionalizing Switch At Tra Tap | City of Dallas, Dallas County | Install Manually Operated, Sectionalizing Switch at TRA Tap. | 2021-04-01 | 2021-05-15 |  |  | 735000 |  |  | 34 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | na | na | 100 | 0.1 | 25.101(c)(5)(B)
0PT42830 | Polk St. Sub-Davis St. Sub 138 kV Line: Replace U.G. Terminations | City of Dallas, Dallas County | Replace the 138 kV Underground Transmission Terminations at Polk St and Davis St. Sub | 2021-03-15 | 2021-06-30 |  |  | 800000 |  |  | 99 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT42833 | Audelia Termination-Lake Highlands 138 kV Line: Replace U.G. Terminations | City of Dallas, Dallas County | Replace the 138 kV Underground Transmission Terminations at Audelia and Lake Highlands Sub. | 2021-03-29 | 2021-06-30 |  |  | 770000 |  |  | 99 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
19T62004 (R1735) | Everman Switch-Venus Switch 345 kV Line: High Temperature Upgrade (WEST Line) | City of Everman, Tarrant County | Replace 33 Towers to maintain NESC Clearances, while operating under high temperature | 2021-03-08 | 2021-12-31 |  |  | 9750000 |  |  | 8 | 345 | na | 17.3 | 795 ACSR | Steel Tower | 150 | 17.3 | na | na | 25.101(c)(5)(A)
0PT04039 (R1735) | Everman Switch -Venus Switch 345 kV Line: High Temperature Upgrade (East Line) | City of Everman, Tarrant County | Rebuild East Circuit of the Everman Switch - Venus Switch 345kV Line for high temperature upgrade. | 2021-09-13 | 2021-12-15 |  |  | 1255490 |  |  | 0 | 345 | na | 17.3 | 795 ACSR | Steel Tower | 150 | 17.3 | na | na | 25.101(c)(5)(B)
0PT43330 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 10/3 | City of Graham, Young County | Replace structure 10/3 on the Graham Switch - Tonkawa Switch 345 kV Line. | 2021-04-26 | 2021-12-31 |  |  | 626485 |  |  |  | 345 | na | 0.2 | 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT38645 (R9039) | Fullerton Switch - North Andrews Switch 138 kV Line : North Andrews Switch Retermination | Andrews County | Reterminate the Fullerton Switch - North Andrews Switch 69 kV Line at its new 138 kV terminal location at North Andrews Switch. | 2021-04-19 | 2021-05-15 |  |  | 314520 |  |  |  | 69 | 138 | 0.1 | 959 ACSS/TW Suwannee | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT38643 (R9039) | Fullerton Switch - North Andrews Switch 138 kV Line: Rebuild | Andrews County | Rebuild a 0.1 mile section of the Fullerton Switch - North Andrews Switch 69 kV Line to permanently bypass the Andrews Switch 69 kV terminals. | 2021-04-14 | 2021-05-15 |  |  | 608519 |  |  |  | 69 | 138 | 0.1 | 959 ACSS/TW Suwannee | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT04146 (R9054) | Yucca Drive Switch - Lotebush Switch 138 kV Line: Riverview Substation | City of Pyote, Ward County | Cut in the Yucca Drive Switch - Lotebush Switch 138 kV Line to establish the new Riverview substation. | 2021-04-13 | 2021-06-30 |  |  | 1224257 |  |  | 27 | 138 | na | na | 2-959 ACSS/TW Suwannee | Steel Pole | 75 | na | na | na | 25.101(c)(5)(A) | Establishing existing in line station.
0PT43605 0PT43796 0PT44802 (R8579) | Yosemite – Triangle 138 kV Line: Germania POD for Bob White Electric's (DE3) Javaid West Sub | Midland County | Establish the point of delivery to Bobwhite Electric’s (DE3 Operating) Javaid West substation on the Yosemite - Triangle 138 kV transmission line. | 2021-04-01 | 2021-06-25 |  |  | 1906105 |  |  | 13 | 138 | na | 0.06 | 959 ACSS/TW Suwanee | Concrete Poles/ H-frame Switch | 70 | na | 70 | 0.06 | 25.101(c)(5)(A)
0PT42410 | Lake Creek Switch - Tradinghouse Switch 345 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Reconductor a section of the Lake Creek Switch - Tradinghouse Switch 345 kV Line. | 2021-03-18 | 2021-05-15 |  |  | 4249522 |  |  | 40 | 345 | na | 3.6 | 2-795 ACSS/E3X/MA5 Drake | Steel Tower | 160 | 3.6 | na | na | 25.101(c)(5)(B) | Lake Remediation project for HB-4150
0PT40627 (R8523) | Andrews County South Switch - Fullerton Switch 138 kV Line : POI for Rodeo Solar Generator | Andrews County | Install one span of wire to connect the customer owned transmission line to Rodeo Solar to existing Nelson Switch. | 2021-09-20 | 2021-12-31 | [6 empty] | 138 | na | 0.03 | 1590 ACSR Falcon | Steel Pole | na | na | 60 | 0.03 | 25.101(c)(5)(A)
0PT38904 (M4275) | Payne Switch - Royce City 138 kV Line: Rebuild Anna Tap - Greenbrier Switch | City of Melissa, Collin County | Rebuild Anna Tap - Greenbrier Switch section of the Payne Switch - Royce City 138 kV Line. | 2021-05-17 | 2021-12-15 |  |  | 17281028 |  |  | 0 | 138 | na | 9.6 | 1926.9 ACSS/TW Cumberland | Steel and Concrete Poles | Varies | 9.6 | na | na | 25.101(c)(5)(B)
0PT40829 (M5274) | Eagle Mountain Switch - Deen Switch 138 kV Line: Rebuild Rosen Heights Tap - Deen Switch | City of Saginaw, Tarrant County | Rebuild the Rosen Heights Tap - Deen Switch section of the Eagle Mountain Switch - Deen Switch 138 kV line. | 2021-09-20 | 2021-12-15 | [5 empty] | 0 | 138 | na | 8 | 2-959.6 ACSS/TW Suwannee | Steel Poles | Varies | 8 | na | na | 25.101(c)(5)(B)
0PT43686 | Ferris Switch - Waxahachie OCF 69kV Line: Rebuild Ferris - Str 28/253 | City of Waxahachie, Ellis County | Rebuild the structure 17/458 to structure 28/353 section of the Ferris Switch to Waxahachie OCF 69kV Line. | 2021-06-07 | 2021-12-31 | [5 empty] | 0 | 69 | na | 11.5 | 959.6 MCM ACSS/TW/HS Suwannee | Steel Pole | Varies | 11.5 | na | na | 25.101(c)(5)(B)
0PT43332 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 27/5 | City of Throckmorton, Throckmorton County | Replace structure 27/5 with a 47506 window tower deadend. | 2021-05-03 | 2021-12-31 |  |  | 606013 |  |  |  | 345 | na | 0.1 | 2-795 ACSR Drake | Lattice Tower | 140 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43333 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 44/4 | City of Throckmorton, Throckmorton County | Replace structure 44/4 with a 47506 window tower deadend. | 2021-04-20 | 2021-12-31 |  |  | 606013 |  |  | 2 | 345 | na | 0.1 | 2-795 ACSR Drake | Lattice Tower | 140 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42854 | Monticello Switch - Paris Switch 345 kV Line : HB 4150 Monticello Lake Crossing | Mt Pleasant/Titus County | This project includes reconductoring and an installation of a structure on Monticello SW - Woodard Sw 345 kV. | 2021-03-19 | 2021-11-15 |  |  | 3011751 |  |  | 67 | 345 | na | 2.5 | 2-795 ACSS Drake | Lattice Tower | Varies | 2.5 | na | na | 25.101(c)(5)(B)
0PT40263 | Wichita Falls North- Pleasant Valley Switch 69 kV Line : CMPC Line Hardening (Str. 3/17 & 4/1) | City of Wichita Falls, Wichita County | Rebuild the section of the Wichita Falls North - Pleasant Valley 69 kV. | 2021-07-05 | 2021-12-31 | [6 empty] | 69 | na | 0.3 | 336 ACSR Linnet | Steel H-Frame & Wood H-Frame | 50 | 0.3 | na | na | 25.101(c)(5)(B)
0PT43952 (M4271) | Parkdale Switch - Sargent Road Switch 138 kV Line : High temp upgrade | City of Dallas, Dallas County | Upgrade the Parkdale Switch – Sargent Road Switch 138 kV Line for high temperature operation. | 2021-04-21 | 2021-12-31 |  |  | 600000 |  |  | 76 | 138 | na | 5 | 1233.6 ACSS/TW Yukon | Steel Tower | 200 | 5 | na | na | 25.101(c)(5)(A)
0PT43334 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 54/2 | Haskell County | Replace structure 54/2 with a 47506 window tower deadend. | 2021-05-14 | 2021-12-31 |  |  | 609950 |  |  |  | 345 | na | 0.2 | 2- 795 ACSR | Steel Tower | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43338 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 35/2 | Throckmorton County | Replace structure 35/2 with a 47506 window tower deadend. | 2021-05-14 | 2021-12-31 |  |  | 615170 |  |  |  | 345 | na | 0.2 | 2- 795 ACSR | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT42413 | Sam Switch - Tradinghouse Switch 345 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Modify a section of the Sam Switch - Tradinghouse Switch 345 kV Line. | 2021-09-27 | 2021-12-15 | [6 empty] | 345 | na | 0.8 | 2-795 ACSS/E3X/MA5 Drake | Steel Tower | 160 | 0.8 | na | na | 25.101(c)(5)(B) | Lake Remediation project for HB-4150
0PT42411 | Temple Pecan Creek/Lake Creek - Tradinghouse Switch 345 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Modify a section of the Temple Pecan Creek/Lake Creek - Tradinghouse Switch 345 kV Line. | 2021-09-27 | 2021-12-15 | [6 empty] | 345 | na | 0.6 | 2-795 ACSS/E3X/MA5 Drake | Steel Tower | 160 | 0.6 | na | na | 25.101(c)(5)(B) | Lake Remediation project for HB-4150
0PT43339 0PT43941 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 63/2 | Haskell County | Replace structure 63/2 with a 47506 window deadend. | 2021-04-26 | 2021-12-31 |  |  | 564700 |  |  | 34 | 345 | na | 0.2 | 2- 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101 c (5)(b)
0PT42340 (R762) | Killeen Switch - Belton Station/Killeen Switch - Killeen Fort Hood Station 138 kV line: Cut In Killeen Stagecoach Sub | Bell County | Line Work Associated with establishing Stagecoach Sub approximately located near structure 1/7. | 2021-05-10 | 2021-12-01 |  |  | 887921 |  |  | 0 | 138 | na | 0.8 | 1926.9 ACSS Cumberland | Steel Poles | 100 | 0.4 | na | na | 25.101 c (5)(a)
0PT42497 | Mountain Creek Switch - West Dallas Sub 138 kV Line : Replace Failed Structures | City of Dallas, Dallas County | Replace failed str 244 on the Mountain Creek Switch - West Dallas Sub 138 kV line. | 2021-04-12 | 2021-04-21 |  |  | 134758 |  |  | 99 | 138 | na | 0.1 | 336.4 MCM ACSR Linnet | Concrete Pole | 40 | 0.1 | na | na | 25.101 c (3) | Emergency Project
0PT42803 (R9037) | Means Sub - Fullerton Switch 138 kV Line : Monument Draw 138 kV Cut-in (69kV) | Andrews County | Reterminate the Means – Fullerton Switch 69 kV Line at its new 138 kV terminal location at Fullerton 138 kV Switching Station. | 2021-03-01 | 2021-04-05 | 2021-04-05 |  | 177767 |  |  | 100 | 69 | 138 | 0.1 | 959 ACSS Suwannee | Steel Pole | 80 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42890 | NW Carrolton-Renner 138 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new double circuit, steel monopole, tangent structure. | 2021-03-27 | 2021-05-15 |  |  | 645339 |  |  | 34 | 138 | na | 0.3 | 927.2 ACAR | Steel Tower | 100 | 0.3 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT43331 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 19/2 | City of Graham, Young County | Replace structure 19/2 with a 47506 window tower deadend. | 2021-04-16 | 2021-12-31 |  |  | 608000 |  |  |  | 345 | na | 0.2 | 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT42889 | Northlake-Northaven 138 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation of structure T-334 on NW Carrollton-Renner 138 kV line. | 2021-03-27 | 2021-05-15 |  |  | 645339 |  |  | 99 | 138 | na | 0.3 | 2-795 ACSR Drake | Steel Tower | 100 | 0.3 | na | na | 25.101(C)(5)(F)
0PT39810 | Snyder Sub - Ennis Creek Switch 69 kV Line : CMPC Line Hardening (Str. 2/20 & 2/21) | City of Snyder, Scurry County | Rebuild the section of Snyder Sub - Ennis Creek Switch 69 kV line that crosses US-84 in Snyder, TX. | 2021-06-01 | 2021-12-31 | [5 empty] | 0 | 69 | na | 0.2 | 4/0 ACSR Penguin | Concrete Pole & Wood Pole | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43342 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 105/2 | City of Sweetwater, Fisher County | Replace structure 105/2 on the Graham Switch – Tonkawa Switch 345 kV line that crosses FM1085 in Fisher county with window tower deadend. | 2021-04-20 | 2021-11-05 |  |  | 522975 |  |  | 34 | 345 | na | 0.2 | 2- 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43343 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 114/3 | City of Sweetwater, Fisher County | Replace structure 114/3 on the Graham Sw. _Tonkawa Sw. 345 kV line with a window tower deadend. | 2021-04-20 | 2021-11-12 |  |  | 522615 |  |  | 2 | 345 | na | 0.2 | 2- 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT39811 | Morgan Creek Switch - Big Spring Switch 69 kV Line : CMPC Line Hardening (Str. 46/9 - 46/11) | Westbrook City, Mitchell County | Rebuild the section of structures 46/ 6- 46/14 of the Morgan Switch - Big Spring Switch 69 kV line. | 2021-09-16 | 2021-12-31 | [5 empty] | 0 | 69 | na | 0.5 | 336 ACSR Linnet | Wood Pole | 50 | 0.5 | na | na | 25.101(c)(5)(B)
0PT43221 | Northhaven Switch-Renner Switch 138 kV: DART Relocation for Cotton Belt Knoll Trail | City of Addison, Dallas County | Relocation of structures on the Northhaven Switch-Renner Switch 138 kV line to accommodate the Cotton Belt Rail Crossing at Knoll Trail in Addison, TX. | 2021-10-07 | 2021-10-31 | [5 empty] | 0 | 138 | na | 0.07 | 1926 ACSS/TW Cumberland | Steel Pole | varies | 0.07 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Dallas Area Rapid Transit (DART) and is 100% reimbursable by the Dallas Area Rapid Transit (DART).
0PT42680 | NW Carrollton-Hackberry Junction 345 kV: DART Relocation for Cotton Belt Cypress Waters Station | City of Coppell, Dallas County | Addition of structure T-704A on NW Carrollton-Hackberry Junction 345 kV line. | 2021-09-15 | 2021-10-31 | [6 empty] | 345 | na | 0.23 | 2-1590 ACSR Falcon | Steel Tower | varies | 0.23 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Dallas Area Rapid Transit (DART) and is 100% reimbursable by the Dallas Area Rapid Transit (DART).
0PT43341 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 98/2 | Jones County | Replace structure 98/2 on the Graham Switch - Tonkawa Switch 345 kV Line that crosses US highway 180 W. | 2021-04-20 | 2021-12-31 |  |  | 623423 |  |  | 2 | 345 | 0 | 0.2 | 2-795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(C)(5)(B)
0PT42004 (M4317) | Ferris Switch - Corsicana Switch 69 kV Line: Rebuild Str. 3/2 to Rice Sub to 138 kV | Ennis Texas, Ellis County and Rice Texas, Navarro County | Rebuild the Ferris Switch - Corsicana Switch 69 kV Line from structure 3/2 to Rice Substation and convert to 138 kV operation. Disconnect the Ferris Switch - Corsicana Switch 69 kV Line at Ferris 69 kV Switch and Structure 3/2 near Ennis Southeast. Establish the Ennis Southeast - Rice 138 kV Line Section by converting and upgrading the 6.7-mile of Ferris Switch - Corsicana Switch 69 kV Line from Structure 3/2 to Rice Substation. | 2021-06-01 | 2021-12-15 | [6 empty] | 69 | 138 | 6.7 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 6.7 | na | na | 25.101(c)(5)(B)
0PT43666 | Holliday Sub - Baylor Switch 69 kV Line : Rebuild 23 Miles | Cities of Holliday, Dundee, Baylor, Counties of Baylor, Archer | Rebuild the existing 23 mile single circuit wood pole Holliday - Baylor 69 kV line utilizing 138 kV double circuit steel poles with one circuit in place. | 2021-05-17 | 2021-12-24 |  |  | 23155765 |  |  |  | 69 | na | 23 | 959.6 ACSS Suwannee | Steel Pole | 50 | 23 | na | na | 25.101(c)(5)(B)
0PT40396 (R6132) | Sam Switch – Tradinghouse Switch 345 kV Line: Four Brothers Switch Cut In for Sun Valley Solar | Hill county | Establish the Four Brothers Switching Station on the Sam Switch - Tradinghouse Switch 345 kV line. | 2021-09-27 | 2021-12-16 | [6 empty] | 345 | na | 0.11 | 2 -959.6 ACSS/TW Swannee | Steel pole & Steel Towers | 170 | na | na | na | 25.101(c)(5)(A)
0PT43644 | Collin Switch - Stone Creek Switch 138 kV Line: Prosper Substation Cut In | City of Prosper, Collin County | Cut in Prosper Substation on the Collin Switch - Stone Creek Switch 138 kV Line. | 2021-05-05 | 2021-05-15 |  |  | 1149437 |  |  | 34 | 138 | na | 0.2 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(A)
16T64146 | Temple Substation - Little River Substation 69 kV Line: CMPC Rebuild | Bell County | Rebuild the Temple Substation - Little River Substation 69 kV Line section | 2021-06-07 | 2021-12-31 | [5 empty] | 0 | 69 | na | 7.5 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 50 | 7.4 | na | na | 25.101(c)(5)(B)
0PT43492 0PT44173 0PT44830 (R8563) | North Andrews Switch - Means 138 kV Line: Install Landfill POD to Re-terminate Exxon Means POD | City of Andrews, Andrews County | Establish the Landfill Point of Delivery (POD) by disconnecting the existing Exxon Means Tap from the Andrews North Sw. - Mckenzie Draw Sw. 138 kV line and connecting to the Andrews North Sw. - Fullerton Sw. 138 kV line. | 2021-10-18 | 2021-11-15 | [6 empty] | 138 | na | 0.4 | 959.6 ACSS/TW Swannee | Steel Poles | 50 | 0.15 | 75 | 0.37 | 25.101(c)(5)(A)
0PT43305 (R6119) | Waco West Switch - Temple Elm Creek Switch 138 kV Line : Moores Mill Station Cut In | City of Temple, Bell County | Cut in the Moores Mill Substation on the Waco West - Temple Elm Creek 138 kV Line. | 2021-06-28 | 2021-11-15 | [5 empty] | 0 | 138 | na | 0.45 | 959.6 ACSS/TW Swannee | Steel Pole | 50 | 0.16 | 100 | 0.3 | 25.101(c)(5)(A)
0PT38116 0PT39387 (M5279) | Everman Switch - Marrs Switch 138 kV Lines #3 & #4 Rebuild | City of Fort Worth, Tarrant County | Rebuild the 4.2-mile Everman Switch - Forest Hill Switch - Marrs Switch 138 kV Lines #3 & 4. | 2021-09-20 | 2021-12-15 | [5 empty] | 0 | 138 | na | 4.2 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | 50 | 4.2 | na | na | 25.101(c)(5)(B)
0PT42829 | Trinidad Switch - Corsicana Sub 138 kV Line : HB 4150 Richland Chambers Crossing | City of Corsicana, Navarro County | Reconductoring the north circuit of the Trinidad Switch - Corsicana Sub 138 kV Line as well as installing new davit arms and raising structures in order to meet clearance. | 2021-09-17 | 2021-10-15 | [6 empty] | 138 | na | 1.2 | 795 ACSS/TW E3X Drake | Steel Pole | 100 | 1.2 | na | na | 25.101c(5)(B)
0PT43597 (R8573) | Dermott Switch - Endurance Park Storage POI 138 kV Line : Install line for Endurance Park Storage POI | City of Dermott, Scurry County | Install a 138 kV Point of Interconnection (POI) for Endurance Park Storage. | 2021-09-20 | 2021-12-16 | [5 empty] | 0 | 345 | na | 0.2 | 1926 ACSS Cumberland | Steel Pole | 800 | 0.2 | na | na | 25.101(c)(5)(A)
0PT43340 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 88/3 | Jones County | Replace structure 88/3 on the Graham Switch - Tonkawa Switch 345 kV Line that crosses US highway 180 W. | 2021-04-10 | 2021-12-31 |  |  | 625476 |  |  | 34 | 345 | 0 | 0.2 | 2 - 795 ACSR Drake | Steel Tower | 150 | 0.2 | na | na | 25.101(C)(5)(B)
0PT44509 (R8584) | Culberson Switch - Horseshoe Springs Switch 138 kV Line : Reterminate at new Culberson Switch terminal | Culberson County | Re-terminate east Culberson Switch - Horseshoe Springs Switch 138kV circuit line at existing north Culberson Switch – Sand Lake Switch 138 kV circuit line termination. | 2021-05-24 | 2021-06-01 |  |  | 521319 |  |  |  | 138 | na | 0.14 | 1926.9 ACSS/TW/HS Cumberland | Steel Poles | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT44510 (R8585) | Culberson Switch - Sand Lake Switch 138 kV Line : Reterminate at new Culberson Switch terminal | Culberson County | Re-terminate north Culberson Switch – Sand Lake Switch 138 kV circuit line at existing east Culberson Switch - Horseshoe Springs Switch 138kV circuit line termination. | 2021-05-17 | 2021-06-01 |  |  | 479489 |  |  |  | 138 | na | 0.05 | 1926.9 ACSS/TW/HS Cumberland | Steel 3-Pole | 70 | 0.1 | na | na | 25.101(c)(5)(A)
0PT42900 | Valley-NW Carrollton 345 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new steel 2-pole, angle structure on Valley-NW Carrollton 345 kV Line. | 2021-04-20 | 2021-05-15 |  |  | 732760 |  |  | 99 | 345 | na | 0.29 | 2-795 ACSR Drake | Steel Tower | varies | 0.29 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT42893 | Royse-NW Carrollton 345 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new double circuit, steel lattice, tangent structure on Royse-NW Carrollton 345 kV Line. | 2021-04-18 | 2021-05-15 |  |  | 558395 |  |  | 63 | 345 | na | 0.26 | 2-1590 ACSR Falcon | Steel Tower | varies | 0.26 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT42097 0PT44856 (R8526) | Riverton Switch - Tunstill POD 138 kV Line : Install Second Circuit | Reeves County | Install second circuit to the Riverton - Tunstill POD 138 kV Line. | 2021-06-21 | 2021-12-15 | [6 empty] | 138 | na | 5.4 | 1926.9 kcmil ACSS/TW | Steel Poles | 70 | 5.4 | na | na | 25.101(c)(5)(C) | Second circuit to the Riverton - Tunstill POD 138 kV Line CCN.
0PT38463 (R9015) | Big Spring - Buzzard Draw 69 kV: Rebuild the line to operate at 138kV | Howard County | This project is to rebuild the 21 mile section of Big Spring to Buzzard Draw 69 kV Line. | 2021-07-05 | 2021-12-15 | [5 empty] | 0 | 69 | 138 | 21.3 | 959.6 ACSS/TW/HS Suwannee | Steel and Concrete Poles | 50 | 21.3 | na | na | 25.101(c)(5)(B)
0PT41307 0PT44855 (R8526) | Horseshoe Springs Switch - Owl Hills 138 kV Line : Install Second Circuit | Reeves County | Install a new 30-mile, 138 kV second conductor on existing double-circuit structures from Horseshoe Springs Switch to Owl Hills. | 2021-08-09 | 2021-12-27 | [5 empty] | 0 | 138 | na | 30 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 70 | 30 | na | na | 25.101(c)(5)(C)
0PT44350 (M5274) | Hicks Switch - Deen Switch 138 kV Line: Replace Structure 12/1 | City of Saginaw, Tarrant County | Replace structure 12/1 on the Hicks Switch - Deen Switch 138 kV Line. | 2021-09-20 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0 | na | na | 25.101(c)(5)(B)
0PT44236 | China Grove - Lamesa 138 kV Line: HB 4150 JB Thomas Lake Crossing | Borden County | Replace 3 structures located along the China Grove - Lamesa 138 kV Line, approximately .5 miles. | 2021-05-06 | 2021-05-15 |  |  | 263915 |  |  | 99 | 138 | na | 0.5 | 636 ACSR Grosbeak | Wood Poles | 50 | 0.5 | na | na | 25.101(c)(5)(B)
0PT44478 | Waxahachie Sub - S. Ennis Switch 138 kV Line : HB 4150 Bardwell Lake Crossing | City of Bardwell, Ellis County | This rebuild will involve raising the cross arms on two (2) single-circuit wood H-frame structures on Waxahachie Sub - S. Ennis Switch 138 kV Line. | 2021-09-20 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR Drake | Wood H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43543 | Watermill Switch - Seagoville Switch 138 kV Line : Erosion Control | City of Lancaster, Dallas County | Install erosion control guards around structure 3/3 on line Watermill - Seagoville 138 kV. | 2021-09-15 | 2021-12-31 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR Drake | Steel Tower | 250 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43542 | Waco West Switch - Lake Creek Switch 138 kV Line : Structure Replacement | City of Waco, McLennan County | Structure 10/10 on Waco West - Lake Creek 138 kV line will be relocated away from eroding creek by the district and erosion control guards will be installed. | 2021-09-15 | 2021-12-31 | [5 empty] | 0 | 138 | na | 0.1 | 636 ACSR Grosbeak | Wood H-Frame | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT44753 (R8538) | Midland East Switch - Buffalo Sub 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Buffalo Sub 138 kV Line to the Midland East Switch Station. | 2021-09-15 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.25 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | Varies | 0.25 | na | na | 25.101(c)(5)(A)
0PT44752 (R8538) | Midland East Switch - Midland County Northwest Switch 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Midland County Northwest Switch 138 kV Line to the Midland East Switch Station. | 2021-09-15 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.5 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | Varies | 0.5 | na | na | 25.101(c)(5)(A)
0PT44751 (R8538) | Midland East Switch - McKenzie Draw Switch 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - McKenzie Draw Switch 138 kV Line to the Midland East Switch Station. | 2021-09-15 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.5 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | Varies | 0.5 | na | na | 25.101(c)(5)(A)
0PT44750 (R8538) | Midland East Switch - Midessa South Switch 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Midessa South Switch 138 kV Line to the Midland East Switch Station. | 2021-09-15 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.25 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | Varies | 0.25 | na | na | 25.101(c)(5)(A)
0PT44736 | Temple - Taylor 69 kV Line: Replace structures damaged from Ice Storm | City of Temple, Bell County | Replace structures on the Temple - Taylor 69kV Line that failed from the ice storm. | 2021-03-12 | 2021-03-24 | 2021-03-24 |  | 172800 |  |  | 100 | 69 | na | 0.1 | 3/0 ACSR Pigeon | Wood Poles | 55 | 0.1 | na | na | 25.101(c)(3)
0PT44640 0PT44924 (R6161) | Lake Brownwood Tap - Lake Brownwood Sub 69 kV Line : Rebuild | City of Brownwood, Brown County | Rebuild the 2.3 mile Lake Brownwood Tap - Lake Brownwood Sub 69 kV Line. | 2021-08-02 | 2021-11-15 | [5 empty] | 0 | 69 | na | 2.3 | 959.6 ACSS/TW Suwannee | Steel Poles, Concrete Poles | Varies 35-128 | 2.3 | na | na | 25.101(c)(5)(B)
0PT44497 | Edgemere Sub - Bandera Sub 138 kV Line : Rebuild Cathodic Protection System | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the Edgemere Sub - Bandera Sub 138 kV Line. | 2021-08-09 | 2021-12-31 | [5 empty] | 0 | 138 | na | na | 900 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT44493 (R6151) | Temple Switch - Killeen Switch 345 kV Line : Relocate and Raise Str 5/2 | City of Temple, Bell County | This project is to relocate and raise Structure 5/2 on the Temple to Killeen 345 kV Line due to the Temple to Little River 69 kV Line rebuild project. | 2021-09-16 | 2021-12-31 | [5 empty] | 0 | 345 | na | 0.1 | 795 ACSR Drake 2-959.6 ACSS/TW/HS Suwannee | Steel Tower | 250 | 0.1 | na | na | 25.101(c)(5)(B)
0PT44492 (R6151) | Bob Poague Sub - Seaton Sub 69 kV Line : Relocate and Raise Str 7/4 | City of Temple, Bell County | This project is to relocate and raise Structure 7/4 on the Bob Poague to Seaton 69 kV Line due to the Little River Road expansion project as well as the Temple to Little River 69 kV Line rebuild project. | 2021-07-08 | 2021-12-31 | [5 empty] | 0 | 69 | na | 0.1 | 795 ACSS Drake | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT44491 | North Network Sub - Bryan Sub 138 kV Line : Rebuild Cathodic Protection System | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the North Network Sub - Bryan Sub 138 kV Line . | 2021-08-30 | 2021-12-31 | [5 empty] | 0 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT44488 | Greenville Ave Switch - Matilda Sub 138 kV Line: Rebuild Cathodic Protection System | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the Greenville Ave Switch - Matilda Sub 138 kV Line. | 2021-09-27 | 2021-12-31 | [5 empty] | 0 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT44370 | Randol Mill - Heritage Sub 138 kV Line : OPGW Only | City of Fort Worth, Tarrant County | Install a splice box at structure 7/12. | 2021-10-18 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT44352 | Decatur - Chico West - Oran 69 kV Line: HB4150 Lake Bridgeport Crossing | City of Chico, Wise County | Line work associated with providing additional clearance over the Lake Bridgeport crossing | 2021-09-20 | 2021-12-15 | [5 empty] | 0 | 69 | na | 0.5 | 959.6 ACSS/TW Suwannee | Steel Poles | 40-50 | 0.5 | na | na | 25.101(c)(5)(C)
0PT43222 (R4023) | Willow Creek Switch - Clear Crossing Switch 345 kV Line : Modify one circuit of a double circuit 345 kV transmission line | City of Throckmorton, Throckmorton County | Line work associated with connecting the 345 kV Tecumseh Creek Switch | 2021-09-10 | 2021-11-18 | [5 empty] | 0 | 345 | na | 0.3 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 200 | 0.3 | 25.101(c)(5)(A)
0PT42965 | Venus Sw - Gerdau Sw 138 kV Line: Install Change of Ownership Point for Gerdau’s Furnace A Circuit. | City of Midlothian, Ellis County | Install one steel deadend to serve as point of interconnection with Gerdau. | 2021-09-15 | 2021-12-01 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | Variable | 0.1 | na | na | 25.101(c)(5)(A)
0PT42348 | Watermill to Cedar Hill 138 kV Line: Reindeer Substation Cut In | City of Lancaster, Dallas County | Line work associated with establishing Reindeer Substation | 2021-10-01 | 2021-12-15 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS Cumberland | Steel Poles | 250 | 0.1 | na | na | 25.101 c (5)(a)
0PT43688 0PT43094 (R8552) | SL Telephone Road Sub - Tall City Sub 138kV Line: Rebuild | Midland County | Rebuild the Telephone Road-Tall City 138 kV Line | 2021-08-02 | 2021-12-01 | [5 empty] | 0 | 138 | na | 12 | 1926.9 ACSS/TW Cumberland | Steel Poles | 70 | 12 | na | na | 25.101(c)(5)(C)
0PT40576 0PT41142 | Navarro Sub - Wortham Junction 69 kV Line : CMPC Line Hardening (Str. 6/17-6/19) | Richland City, Navarro County | Rebuild a section of the Navarro – Wortham Junction 69 kV Line in Navarro County. | 2021-07-26 | 2021-12-31 | [5 empty] | 0 | 69 | na | 0.2 | 3/0 ACSR Pigeon | Wood Pole | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT44851 | Graham - Breckenridge 138 kV Line: Gunsolus Sub Line Connection | City of Breckenridge, Stephens County | Build new loop line section from existing Breckenridge to the new Gunsolus Switch and then back to Breckenridge. | 2021-10-11 | 2021-12-15 | [5 empty] | 0 | na | 138 | 0.3 | 959.6 ACSS Suwannee | Steel Pole | na | na | 100 | 0.3 | 25.101(c)(5)(A)
0PT44472 (R6151) | Temple Sub - Little River Sub 69 kV Line: Reroute for Little River Road Expansion | City of Temple, Bell County | This project is to re-route and rebuild the section of line affected by the Little River Road Expansion and Blackland Road Extension projects. | 2021-06-14 | 2021-12-31 | [5 empty] | 0 | 69 | na | 0.35 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 50 | 0.35 | na | na | 25.101(c)(5)(B)
0PT43980 (R8504) | Sand Lake Switch - TNMP's Cochise Switch 138 kV Line: Install Single Span to TNMP | Ward county | Terminate Texas-New Mexico Power’s two 138 kV lines out of Cochise Switch at Sand Lake Switch. | 2021-08-01 | 2021-12-15 | [5 empty] | 0 | na | 138 | 0.08 | 1926 ACSS/TW Cumberland | Steel poles | 100 | 0.09 | na | na | 25.101(c)(5)(A)
0PT45010 (R8581) | Wink Basin Tap No 1 East 69 kV Line: Wink Basin Sub - Wink Gulf Tap 69 kV Section Rebuild | City of Kermit, Winkler County | Rebuild the 1.9 mile Wink Basin Sub - Wink Gulf Tap 69 kV section on the Wink Basin Tap No 1 East 69 kV line | 2021-06-01 | 2021-12-15 | [5 empty] | 0 | 69 | 138 | 1.9 | 1926 ACSS/TW Cumberland | Steel Poles | 50 | 1.9 | na | na | 25.101(c)(5)(B)
0PT44327 (R8581) | Wink Switch - Keystone No 1 East 69 kV Line: Shifting Sands Sub - Wink Gulf Tap 69 kV Section Rebuild | City of Kermit, Winkler County | Rebuild the 12.6 mile Shifting Sands Sub - Wink Gulf Tap 69 kV section on the Wink Switch - Keystone No 1 East 69 kV line. | 2021-06-01 | 2021-12-15 | [5 empty] | 0 | 69 | 138 | 12.6 | 1926 ACSS/TW Cumberland | Steel Poles | 50 | 12.6 | na | na | 25.101(c)(5)(B)
0PT44275 0PT44345 (R8452) | Horseshoe Springs Switch - Owl Hills Substation 138 kV Line : Cut-in at Drill Hole Switch | Culberson County | Tap both circuits on the Horseshoe Springs - Owl Hills double circuit 138 kV line to establish the new Drill Hole Switch. | 2021-09-01 | 2021-12-15 | [6 empty] | 138 | na | 0.42 | 795 ACSR Drake | Steel Poles | 70 | 0.21 | na | na | 25.101(c)(5)(A) | Oncor Station property.
0PT42385 (M4302) | Ennis Switch - Ennis Sub 138 kV Line: Retermination at Shankle Switch | City of Ennis, Ellis County | Reterminate the Ennis Switch - Ennis Sub 138kV line to its new bay position at the new Shankle Switch. | 2021-08-30 | 2021-12-15 | [6 empty] | 138 | na | 0.1 | 1926 ACSS/TW Cumberland | Steel Pole | 85 | 0.1 | na | na | 25.101(c)(5)(A)
0PT45129 | Eagle Mountain Switch - Bennett Road Switch 138 kV Line: CMPC Clearance Violation Remediation | City of Saginaw, Tarrant County | Replace structure 1/5 with a new tangent to remediate an existing clearance violation. | 2021-11-01 | 2021-12-15 | [6 empty] | 138 | na | 0.3 | 795 ACSR Drake | Steel Pole | 150 | 0.3 | na | na | 25.101(c)(5)(B)
STATIONS
0PT03998 (M3047) | Plano Tennyson Switch: Upgrade line terminal and associated equipment to meet or exceed 3200 A | City of Plano, Denton County | Upgrade line terminal and associated equipment to meet or exceed 3200 A as a part of upgrading the Renner TPL Plano Tennyson 138 kV Line | 2021-11-01 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03999 (M3047) | Renner Switch: Upgrade line terminal and associated equipment to meet or exceed 3200 A | City of Plano, Denton County | Upgrade line terminal and associated equipment to meet or exceed 3200 A as a part of upgrading the Renner Switch - Allen Switch/Plano Tennyson Switch 138 kV | 2021-01-19 | 2021-12-15 |  |  | 997861 |  |  | 93 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03981 (M5155) | Sherry Switch: Two Line Terminal Upgrade | City of Arlington, Tarrant County | Upgrade line terminal and associated equipment to meet as a part of upgrading the Handley Sherry 138 kV Double-circuit Line | 2022-01-17 | 2022-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40632 (R3050) | Ogallala Switch : Install Terminal for Nazareth Solar | City of Nazareth, Castro County | Install one 345 kV, 3200 A circuit breaker at Install a 345 kV (POI) for customer's generator (TX Nazareth Solar, LLC). | 2021-07-16 | 2022-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65069 (M4216) | Camp Wisdom Sub: Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | City of Dallas, Dallas County | Install three 138 kV sectionalizing switches and upgrade all line terminal and associated equipment to meet or exceed 2000 A as apart of upgrading the 11.5-mile Watermill Sw. Sta. - Camp Wisdom Road 138 kV line. | 2020-10-01 | 2020-12-07 | 2020-12-07 |  | 995282 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41211 | Elm Fork Pump Sub : Install one transformer and a feeder breaker | City of Carrollton, Denton County | Install one transformer and a feeder breaker | 2020-05-20 | 2020-12-04 | 2020-12-04 |  | 2294139 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40492 | Parkdale Switch : Replace circuit breakers | City of Dallas, Dallas County | Replace three circuit breakers | 2020-11-09 | 2020-12-11 | 2020-12-11 |  | 579525.38 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41077 | Richardson Spring Valley Sub : Rebuild Substation by relocating both transformers inside the station | City of Richardson, Dallas County | Rebuild Substation by relocating both transformers inside the station | 2020-06-06 | 2021-03-09 | 2021-03-09 |  | 4610004 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40485 | Snyder Switch : Replace two circuit breakers | City of Snyder, Scurry County | Replace one 69 kV circuit breaker and one 138 kV circuit breaker | 2021-04-12 | 2021-04-30 |  |  | 246340 |  |  | 99 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41498 | Willow Wells Sub : Install 2nd transformer and two feeder breakers | City of Odessa, Winker County | Install second transformer and two feeder breakers. | 2020-02-02 | 2020-12-21 | 2020-12-21 |  | 2109618 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41490 | Witt Rd Sub: Install second transformer with three feeder breakers | City of Lancaster, Dallas County | Install second transformer with three feeder breakers | 2020-03-30 | 2020-10-15 | 2020-10-15 |  | 2021287 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39073 0PT41172 (R4102) | Allens Creek POI: Establish 138 kV Point of Interconnection | Fannin County | Allens Creek POI: Establish 138 kV Point of Interconnection for Rayburn Interconnect, located in the Valley-Paris Sw. line. | 2019-12-10 | 2020-06-24 | 2020-06-24 |  | 656532.92 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT37562 | Alligator Draw Sub : Establish station with two transformers and two feeder breakers. | City of Orla, Culberson County | Alligator Draw Sub : Establish station with two transformers and two feeder breakers on the new Horseshoe Springs Sw. Sta. Owl Hills 138 kV Line | 2019-09-17 | 2020-02-17 | 2020-02-17 |  | 5725089 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40140 (R8495) | Andrews County South Switch : Install Auto #2 and establish the new Wink Switch terminal. Upgrade No Trees Switch line terminal for the existing Wink circuit. | City of Andrews, Andrews County | Install Auto #2 Install and establish the new Wink Switch terminal. Upgrade all line terminal and associated equipment for the existing No Trees – Wink line as a part of rebuilding the 8.8-mile No Trees Sw. Sta. - Andrews County South Sw. Sta. 138 kV Line. | 2019-09-03 | 2020-03-27 | 2020-03-27 |  | 4699579 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT01033 13T80021 | Azle Sub: Install the third transformer with one feeder breaker | City of Azle, Tarrant County | Azle Sub: Install the third transformer with one feeder breaker | 2020-02-26 | 2020-06-26 | 2020-06-26 |  | 4285845 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT38971 | Benbrook Sub : Create a loop in loop out, install FID's and install new Sub IV protection for transformer #1 and #2 | City of Fort Worth, Tarrant County | Create a loop in loop out, install FID's and install new protection for transformer #1 and #2 | 2019-09-16 | 2019-12-31 | 2019-12-31 |  | 2399766 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65108 17T80064 18T80009 (M4264) | Blackland Switch: Establish 138 kV station | City of Fate, Rockwall County | Install a 138 kV point of interconnection with a 3-breaker 138 kV ring bus arrangement on the Royse Sw. Sta. - Terrell Sw. Sta. 138 kV Line. | 2018-10-11 | 2019-12-20 | 2019-12-20 |  | 5864790.76 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT04155 0PT38702 | Blagg Sub: Establish Substation with one Transf. and Two Feeder Breakers: | City of Denton, Denton County | Establish Substation with one Transf. and Two Feeder Breakers | 2020-07-28 | 2020-12-31 | 2020-12-31 |  | 4832694.4 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT38284 0PT39470 (R8441) | Boulder POD : 138 kV Point of Delivery | City of Odessa | Establish Boulder a 138kV point of delivery for customer owned station on the south circuit of the Wink – Culberson 138 kV Double-circuit Line. | 2019-11-26 | 2020-06-10 | 2020-06-10 |  | 1352805.65 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT03966 (R6073) | Canton Tap Switch: Modify Tyler Switch Line Relaying | City of Forney, Kaufman County | Modify relaying for ring bus terminal at Tyler Switch | 2020-08-03 | 2020-12-14 | 2020-12-14 |  | 86173.57 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39750 | Carrollton Frankford Rd Sub : Convert Station One and Two to 125 VDC and Replace Breakers | City of Carrollton, Denton County | Update protection, convert station one and two to 125 VDC and replace breakers | 2019-10-31 | 2020-06-24 | 2020-06-24 |  | 597449 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65033 (M4110) | Carrollton NW Sub: Upgrade 138 kV Norwood & Lakepoint Lines | City of Carrollton, Denton County | Upgrade all terminal and associated equipment as a part of upgrading the NW Carrollton – Norwood Sw. Sta. 138 kV Double-circuit line. | 2018-11-15 | 2020-06-23 | 2020-06-23 |  | 435226 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65018 (P109) | Centerville Switch: Upgrade line, auto and bus relaying | City of Dallas, Dallas County | Upgrade line, auto and bus relaying at Centerville Switch. | 2019-09-09 | 2020-06-26 | 2020-06-26 |  | 1678074 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37566 (R8456) | Chimney Well POD : Provide a 138 kV point-of-delivery (POD) | City of Odessa, Ector County | Establish Chimney Well POD for customer owned station, a 138 kV on the Horseshoe Springs Sw - Owl Hills 138kV line. | 2019-10-21 | 2020-05-01 | 2020-05-01 |  | 921244.66 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04158 | China Springs Substation: Install one Transf. #2 and 1-25 kV Feeder and install Distribution Automation on Feeders 2401 and 2403 | City of China Spring, McLennan County | Install Bank #2 with one Transformer and One Feeder Breaker. Includes installation of Distribution Automation on Feeders 2401 and 2403. | 2019-07-12 | 2019-12-01 | 2019-12-01 |  | 1243074 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39490 (R1739C) | Comanche Peak 345 kV Switch : Upgrade Mitchell Bend to Double Breaker Double Bus | Glen Rose County | Upgrade Mitchell Bend line terminal to Double Breaker Double Bus | 2020-01-31 | 2020-05-21 | 2020-05-21 |  | 1212265 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04086 0PT42590 0PT38128 (M5277) | Deen Switch: Establish Station to Replace Saginaw 138 kV Switch | City of Fort Worth, Tarrant County | Establish Deen Switch station by installing sixteen 138 kV circuit breakers in a breaker-and-a-half arrangement. | 2019-10-07 | 2020-12-24 | 2020-12-24 |  | 20360176.34 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39812 0PT40079 (R8407) | Dollarhide Sub: Modify bus to loop 138kV line in and out of station | City of Odessa, Winkler County | Modify bus to loop line in and out of station as a part of rebuilding the No Trees Switch - Andrews County South Switch 138 kV line. | 2020-03-02 | 2020-04-29 | 2020-04-29 |  | 1204386.4 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT37283 | Du Puy (Waco West) Sub : Replace Transformer by Rebuilding the Existing Substation | City of Waco, McLennan County | Establish Du Puy Substation with three transformers and ten feeder breakers. | 2019-09-16 | 2020-04-01 | 2020-04-01 |  | 5906786 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04035 (R9026) | Ennis Creek Switch: 138 kV Station Rebuild | City of Snyder, Scurry County | Rebuild the 138 kV Ennis Creek Switch with a 3-breaker 138 kV ring bus arrangement. | 2020-05-20 | 2020-12-16 | 2020-12-16 |  | 4204788 |  |  | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39276 0PT38814 | Fate Sub: Establish Substation with one transformer and two feeder breakers | City of Fate, Rockwall County | Establish Substation with one transformer and two feeder breakers | 2020-04-06 | 2020-06-26 | 2020-06-26 |  | 5825991.24 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39341 (M5161) | Heritage Sub : Convert transformer #1 to 138 kV and upgrade protection on CB | City of Fort Worth, Tarrant County | Convert Transformer #1 to 138 kV and upgrade line protection on circuit breaker. | 2020-04-06 | 2020-12-28 | 2020-12-28 |  | 187469 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39386 (M5295) | Hicks Switch: Modification for interconnect and convert line communication for line to fiber | City of Fort Worth, Tarrant County | Modifications for interconnect and convert the line communication for line to fiber. | 2019-04-01 | 2021-03-17 |  |  | 1857917 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38362 (R6101) | Holly Ervin POD : Establish a 138 kV Point of Interconnection | City of Palestine, Anderson County | Establish Holly Ervin POD for customer owned station, 138kV point of delivery on the Big Brown Tap - Long Lake 138kV line. | 2019-07-22 | 2019-12-20 | 2019-12-20 |  | 1477517.87 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
19T62005 | International Airport Sub: Replace 12.5 kV Substation | City of Fort Worth, Tarrant County | Rebuild the existing 138/12.5 kV Substation by replacing the existing 12.5 kV distribution switchgear with outdoor air insulated distribution circuit breakers at Stations 1 and 2. | 2019-06-05 | 2019-12-30 | 2019-12-30 |  | 5421782 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Legacy Sharyland Project
0PT37311 (M4286) | Kemp Ranch Switch (Venus Switch) : Install two 138 kV point of interconnections by constructing a 138 kV switching station in a breaker-and-a-half bus arrangement. | City of Midlothian, Ellis County | Install two 138 kV POD for customer owned stations by constructing a 138 kV Kemp Ranch Switching station in a breaker-and-a-half bus arrangement. | 2019-03-04 | 2019-12-02 | 2019-12-02 |  | 11506348 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38360 0PT39011 (R6103) | Lake Hall Switch : Establish 345 kV Switching Station to Provide POI | City of Waco, McLennan County | Establish 345 kV switching station by installing two 345 kV transmission line exits and provide one interconnection point from a 345 kV three breaker ring bus arrangement. | 2019-09-16 | 2020-08-17 | 2020-08-17 |  | 7224561.62 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT38367 (M5286) | Latigo (McPherson (BEC)) POI : Install a new 138 kV point of interconnection for the McPherson (BEC) 138 kV Substation | City of Fort Worth, Tarrant County | Establish a new 138 kV point of interconnection for the McPherson (BEC) 138 kV Substation located in the Roanoke Sw. Euless Sw. 138 kV Line. | 2019-07-22 | 2021-02-28 |  |  | 860751 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
17T65009 (M5041) | Liggett Switch: 138 kV Cedar Hill Terminal upgrade, 345 kV protective relay upgrades and replace the Norwood switch transfer trip panel | City of Irving, Dallas County | Upgrade all terminal and associated equipment as a part of upgrading the Cedar Hill Sw. Sta. Liggett 138 kV line. | 2018-01-10 | 2020-03-11 | 2020-03-11 |  | 1630734 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
16T62037 (M5161) | North Main Switch: Install two 138 kV, 2000 A circuit breakers with provisions for an additional 138 kV circuit. | City of Fort Worth, Tarrant County | Install two 138 kV, 2000 A circuit breakers with provisions for an additional 138 kV circuit. | 2019-12-22 | 2020-12-23 | 2020-12-23 |  | 3730993 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT01788 (M4110) | Norwood Substation: Upgrade 138 kV NW Carrollton Line Terminals | City of Irving, Dallas County | Upgrade all terminal and associated equipment as a part of upgrading the NW Carrollton Norwood Sw. Sta. 138 kV double-circuit line. | 2019-03-23 | 2020-06-10 | 2020-06-10 |  | 286343 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
18T65027 (P100) | Norwood Substation: 345 kV Bus Auto #1 & 138 kV yard relay upgrade | City of Irving, Dallas County | Upgrade protective relaying within the 345 kV and 138 kV switchyards at Norwood Substation | 2019-02-25 | 2020-06-11 | 2020-06-11 |  | 2500000 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37340 | Odessa EHV Switch : Install security measures | City of Odessa, Midland County | Install security measures at switching station. | 2020-02-03 | 2020-12-29 | 2020-12-29 |  | 2102168 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04005 (R9028) | Odessa North Switch: Remove 69 kV terminal and re-terminate the new Cowden North - Odessa North 138 kV Line | City of Odessa, Ector County | Remove 69 kV terminal and re-terminate the new Cowden North - Odessa North 138 kV Line. | 2019-08-05 | 2020-04-01 | 2020-04-01 |  | 518029 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39370 (R6089) | Palestine Sub : Modify relaying for the new Blackburn Switch terminal. | City of Palestine, Anderson County | Modify relaying for the new Blackburn Switch terminal by adding a transfer trip receiver | 2019-09-15 | 2020-02-28 | 2020-02-28 |  | 116126 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
16T62052 14T80047 | Panther Island Sub | City of Fort Worth, Tarrant County | Remove and rebuild the North Main Substation to the south of Heritage Sub and North Main Switch as Panther Island Sub consisting of two transformers and eight feeder breakers | 2019-12-02 | 2020-06-29 | 2020-06-29 |  | 6150086.43 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT38606 0PT39359 (R8473) | Railside Switch : Establish POD by installing four 138 kV circuit breakers in a ring-bus arrangement | City of Odessa, Wink County | Provide two 138 kV PODs for customer owned stations on the Wink Switch No Trees Switch 138 kV Line by establishing four 138 kV circuit breakers in a ring-bus arrangement. | 2019-09-03 | 2019-12-30 | 2019-12-30 |  | 4564269 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39224 | Richardson Spring Creek-Install 4th Transformer and Two Feeder Breakers | City of Dallas, Dallas County | Install 4th Transformer and Two Feeder Breakers | 2019-10-25 | 2020-06-17 | 2020-06-17 |  | 2073664 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT37647 (R8454) | Rondo STATCOM | Odessa County | Install one +250/-250 Mvar Dynamic Reactive Device and one 138 kV circuit breaker at Quarry Field 138 kV Sw. Station | 2019-09-15 | 2019-12-19 | 2019-12-19 |  | 33058594 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04026 0PT39368 | Rough Creek Sub: Establish 138-12.5 kV Station | Scurry County | Convert the station to operate at 138 kV by replace the existing substation with a two transformer station. | 2020-02-15 | 2020-06-15 | 2020-06-15 |  | 4978865.01 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT38854 (R8474) | Shin Oak 138 kV POD : Establish Point of Delivery | City of Wink, Winkler County | Establish a 138 kV POD for customer owned station on the Yucca Switch Moss Switch 138 kV Line. | 2019-11-04 | 2019-12-27 | 2019-12-27 |  | 614379 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04051 (M4226) | Tri Corner Switch: 345 kV rung 4 addition | City of Seagoville, Dallas County | Install three 345 kV, 3200 A circuit breakers to create the Watermill Sw. Sta. to Trinidad 345 kV Line Terminal as a part of the reconductor of Tri Corner Switching Station. Watermill Switching Station. 345 kV line | 2019-01-30 | 2020-02-19 | 2020-02-19 |  | 2186397.78 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38928 0PT40520 (R8477) | Turnbaugh Corner Switch: Establish 138 kV switching station | Odessa County | Establish a switching station with a 3-breaker 138 kV ring bus arrangement for a 138 kV POI for customers generator. | 2019-10-14 | 2020-05-16 | 2020-05-16 |  | 4470574 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT03971 | Tyler Substation: Rebuild to 138 kV | City of Tyler, Smith County | Convert Tyler Sub to 138kV by replacing two transformers with two transformers and install one feeder breaker. | 2020-01-09 | 2020-06-26 | 2020-06-26 |  | 7116396 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04099 17T80061 (M3211) | Vineyard (formerly Grapevine) Switch: Establish 138 kV Station | City of Grapevine, Tarrant County | Establish the Vineyard 138 kV Switch approximately 0.2 miles south of McKamy Tap by installing twelve 3200 A, 138 kV circuit breakers in a breaker-and-a-half arrangement. | 2019-08-29 | 2019-12-20 | 2019-12-20 |  | 18812196.93 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39201 | West Network Sub-Rebuild station adjacent to existing station | City of Dallas, Dallas County | Rebuilding of West Network Substation includes replacing switchgear containing twelve feeder breakers and three transformers. | 2020-05-20 | 2021-05-15 |  |  | 16333958 |  |  | 84 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04289 0PT37602 | Weston Substation: Establish one substation transformer and two feeder breakers | City of McKinney, Dallas County | Establish one substation transformer and two feeder breakers | 2020-02-20 | 2021-05-01 |  |  | 5832085.12 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39591 0PT39613 | Willow Wells Sub: Install one transformer and two feeder breakers | Odessa County | Install one transformer and two feeder breakers | 2020-02-19 | 2020-06-16 | 2020-06-16 |  | 4272325.2 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT38773 (R8289) | Wolf Switch: Establish 345 kV three rung breaker and a half | City of Monahans, Ward County | Establish switching station by installing nine 345 kV circuit breakers in a three rung breaker and a half arrangement with two autotransformers and three 138 kV circuit breakers. | 2019-11-21 | 2020-07-02 | 2020-07-02 |  | 20150000 |  |  | 100 | 138 | 138/345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38646 (M5289) | Ray Roberts Switch : Establish Station for POI | City of Gainesville, Cooke County | Install a 138 kV (POI) Connect the Ray Roberts 138 kV Switch to the Gainesville Switch – Spring Switch (BEC) and install three circuit breakers | 2020-06-12 | 2020-12-17 | 2020-12-17 |  | 4222333 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39579 0PT41234 | Hill Crest: Rebuild station to replace existing station with one transformer & three feeder breakers | City of Big Springs, Howard County | Rebuild station to replace the existing station with one transformer and three feeder breakers | 2020-01-15 | 2020-06-16 | 2020-06-16 |  | 2848043.33 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT38704 (P121) | Handley Switch : Bus Protection Upgrade | City of Fort Worth, Tarrant County | Replace 138 kV bus protection and install new 138 kV breaker and associated switches/CCVT's. | 2020-08-18 | 2020-12-15 | 2020-12-15 |  | 1597389 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39269 0PT38405 | China Lake Sub : Establish Substation with one transformer and two feeder breakers | City of Pyote, Ward County | Establish substation with one transformer and two feeder breakers | 2020-02-26 | 2020-06-26 | 2020-06-26 |  | 4473464.62 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39746 | Allen Switch : Security Updates | City of Plano, Denton County | Security Updates | 2020-10-28 | 2020-12-23 | 2020-12-23 |  | 1856896 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39900 (R8486) | Camp Pasture POD | City of Odessa, Ector County | Provide a 138 kV (POD) on the south circuit of the Spraberry Switch – Midessa South Switch/Odessa EHV Switch 138 kV Double-Circuit Line. Install motor operated SCADA control on three 138 kV 3200 A line sectionalizing switches, provide customer revenue metering. | 2020-04-04 | 2020-06-26 | 2020-06-26 |  | 580615 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39273 | Cedar Hill Sub: Install one transformer | City of Cedar Hill, Dallas County | Add second transformer, transformer #4, convert the distribution load and move away from transformer #1 and #2. | 2020-02-03 | 2020-06-29 | 2020-06-29 |  | 2161780 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04046 (R6061) | Centerville I45 Sub: 138 kV Line Terminal Upgrade | City of Buffalo, Leon County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A as a part of the rebuild of the Crockett Switching Station - Jewett Switching Station 138 kV Line. | 2020-01-31 | 2020-05-28 | 2020-05-28 |  | 334820 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
17T65011 (M5041) | Dalworth Substation 138 kV line terminal upgrade | City of Arlington, Tarrant County | Upgrade all terminal and as a part of upgrading the Cedar Hill Sw. Sta. Liggett 138 kV line. Includes replacing high side switches on both transformers and adding FIDs to both transformers. | 2020-07-18 | 2020-12-18 | 2020-12-18 |  | 1850000 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39275 0PT38451 | Dooley Sub : Replace one transformer | City of Monahans, Ward County | Rebuild existing Northward Sub with one transformer and establish new Dooley Sub with one transformer | 2020-04-05 | 2020-06-30 | 2020-06-30 |  | 3514683.05 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39272 | Edgecliff Sub : Install Second Transformer #4 with Two Feeder Breakers | City of Fort Worth, Tarrant County | Install Transformer #4 with two feeder breakers, rebuild the bus, upgrade station #3 bus to standard and relaying to Suburban IV. | 2020-09-17 | 2020-12-30 | 2020-12-30 |  | 3949536 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39911 0PT40872 | Elbow Sub : Replace Transformer #1 with one transformer | City of Big Springs, Howard County | Replace Transformer #1 with one transformer | 2020-05-12 | 2020-06-29 | 2020-06-29 |  | 1462792 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Legacy Sharyland Project
0PT39466 (M5293) | Gober Switch: Establish a switching station for a 138 kV POI | City of Gober, Fannin County | Install three 138 kV, 3200 A circuit breakers in a ring bus arrangement to establish a 138 kV (POI). Connect this switching station to the Bonham Wolf City 138 kV line section of the Valley Switch. | 2020-07-09 | 2020-12-09 | 2020-12-09 |  | 4029773 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39759 (R750) | Hutto Switch : 345/138kV autotransformer #2 | City of Hutto, Williamson County | Install a new autotransformer, one 345 kV, 3200 A circuit breaker and two 138 kV, 3200 A circuit breakers at Hutto Switch. Install two 37.5 MVAR reactors on the tertiary of the new autotransformer. | 2020-01-16 | 2020-06-19 | 2020-06-19 |  | 4716132 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39278 15T80011 | Jack Rabbit Sub : Establish Substation with one Transformer, and three feeder Breakers | City of Odessa, Ector County | Establish Substation with one Transformer, and three feeder Breakers | 2019-12-12 | 2020-06-18 | 2020-06-18 |  | 4244804.37 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39895 (R8485) | Kelton Windmill POD: Establish POD | City of Odessa, Ector County | Provide a 138 kV (POD) on the east circuit of the McKenzie Draw Switch – Midland County Northwest/Midland East Switch 138 kV Double-Circuit Line. Install motor operated SCADA control on three 138 kV 3200 A line sectionalizing switches, provide customer revenue metering. | 2020-03-30 | 2020-06-26 | 2020-06-26 |  | 535682 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39748 | Kennedale Sub : Establish substation with two transformers | City of Kennedale, Tarrant County | Establish substation by installing Bank #3 and Bank #4 with two transformers and four feeder breakers. This will be done by looping the Everman – Cleburne 138 kV Line into station. | 2020-04-08 | 2020-06-29 | 2020-06-29 |  | 4194465 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39486 | Lakecrest Sub (Fish Creek) : Establish Substation with one Transformer and Three Feeder Breaker | City of Grand Prairie, Dallas County | Establish Substation with one transformer and three feeder breakers | 2020-05-08 | 2020-12-30 | 2020-12-30 |  | 4390668 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40696 | Lakewood Sub : Replace transformer #1 and #2 | City of Fort Worth, Tarrant County | Replace transformer #1 and #2 with Delta-Wye transformers due to transformer #2 failing and requiring replacement. | 2019-10-07 | 2020-04-14 | 2020-04-14 |  | 1393478 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40652 0PT40908 (R4101) | Loring POI : Establish 138 kV POI | Clay County, TX | Install motor operated Scada control on three 138 kV 2000 A line sectionalizing switches as a part of installing a 138 kV POI located in the Commerce Sw. - Bonham Sw. 138kV line. | 2020-04-05 | 2021-05-14 |  |  | 547154.62 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT04282 | Pauline Substation: Install one Transf. #2 and one 25kV Feeder | City of Mabank, Henderson County | Install one transformer #2 and One Feeder Breaker | 2020-08-24 | 2020-12-28 | 2020-12-28 |  | 1968298 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT01087 14T80005 | Salado South Substation: Establish Salado South Substation with one transformer and two feeder breakers | City of Salado, Bell County | Establish Salado South Substation with one transformer and two feeder breakers | 2020-04-27 | 2020-12-18 | 2020-12-18 |  | 2950570 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT01906 14T80017 | Scatter Branch Substation: Establish New Substation with One Transformer and Two 25 kV Feeder Breakers | City of Greenville, Hunt County | Establish New Substation with one transformer and Two 25 kV Feeder Breakers | 2020-06-12 | 2020-12-22 | 2020-12-22 |  | 5322690.16 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT40274 (R8511) | Slager Lake POD : Provide a 138 kV (POD) | Reagan County | Install motor operate Scada control on three 138 kV 2000 A line sectionalizing switches as a part of installing a 138 kV POD on the Pemkiff-Ringo 138 kV Line. | 2020-04-13 | 2020-06-29 | 2020-06-29 |  | 588514 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39694 (R8489) | Vealmoor Switching Station: Install second autotransformer | City of Big Springs, Howard County | Upgrade the switch by installing a second auto transformer and re-configuring the switching station. Install a 4-breaker ring bus arrangement with four 345 kV, 3200 A circuit breakers. | 2019-10-01 | 2020-06-15 | 2020-06-15 |  | 25000000 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | NTSU project
0PT40162 (R8493) | Wink Switch : Install 138 kV circuit breaker | City of Wink, Winkler County | Install one 3200 A, 138 kV circuit breaker and reterminate the Wink Switch – Yucca Drive Switch 138 kV Line onto the fifth rung and terminate the new Wink Switch – Andrews County South Switch 138 kV Line on the fourth rung. | 2020-01-29 | 2020-06-16 | 2020-06-16 |  | 620365 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38701 (M5291) | Woodard Switch : Establish Station for (POI) | City of Deport, Lamar County | Install a 345 kV (POI) at Woodard 345 kV Switch. Connect the Woodard 345 kV Switch to the Monticello Switch Paris Switch 345 kV line section. Install three 345 kV, 3200 A circuit breakers at Woodard 345 kV Switch. | 2020-02-12 | 2020-06-01 | 2020-06-01 |  | 7029097 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40476 | Adobe Meadows Sub : Replace oil circuit breaker (BZO) with FID | City of Midland, Midland County | Replace oil circuit breaker (BZO) with FID and install retrofit transformer protection panels. | 2020-10-18 | 2020-12-07 | 2020-12-07 |  | 413082 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04036 16T80064 (M5066) | Carmichael Bend Switch: Rebuild the existing Decordova Switching Station in a breaker-and-a-half bus arrangement. | City of Granbury, Hood County | Rebuild the existing Decordova 345/138 kV Sw. Sta. with a 12-breaker, 138 kV breaker-and-a-half bus arrangement, and a 5-breaker 345 kV breaker-and-a-half bus arrangement. | 2020-06-05 | 2020-12-28 | 2020-12-28 |  | 23776545.14 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT40694 (M5066) | Comanche Peak Switch 138 kV: Replace relaying on Decordova terminal to Carmichael Bend | City of Glen Rose, Somervell County | Replace Relaying in the 138 kV Comanche Peak Control house for the Decordova bay to work with the new Carmichael Bend Switchyard. | 2020-10-07 | 2020-12-18 | 2020-12-18 |  | 318031 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40227 0PT43641 (R8506) | Gardendale Switch : Install a 345 kV point-of-interconnection (POI) | City of Andrews, Andrews County | Establish a three 345 kV, 3200 A circuit breakers ring bus to install a 345 kV(POI). The POI will be located on the Clearfork Switch Telephone Road Switch 345 kV Line. | 2020-04-23 | 2020-10-26 | 2020-10-26 |  | 6166160 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT40659 (R8525) | Lenorah POD : Establish 138 kV POD | City of Lenorah, Martin County | Install Scada control on three 138 kV 2000 A line switches, two 138 kV 2000A isolation switches and one set of 138 kV revenue metering with associated structures and equipment as a part of establishing a 138 kV (POD) on the Grady Switch Brown Switch 138 kV Line. | 2020-04-07 | 2020-07-15 | 2020-07-15 |  | 1292715 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38868 16T80023 | Monument Draw Sub: Establish substation with one transformer and two feeder breakers | City of Andrews, Andrews County | Establish substation with one transformer, two feeder breakers | 2020-03-27 | 2020-12-08 | 2020-12-08 |  | 4241336 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT04287 | Morris Dido Substation: Install one Transformer #2 and two Feeder Breakers | City of Fort Worth, Tarrant County | Install one transformer #2 with two Feeder Breakers | 2020-07-08 | 2020-12-28 | 2020-12-28 |  | 1786931 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40871 0PT39915 | Blissard Sub: Establish one substation next to the existing Saint Lawrence Sub | City of Garden City, Glasscock County | Blissard Sub: Establish one substation next to the existing Saint Lawrence Sub. | 2020-03-19 | 2020-06-23 | 2020-06-23 |  | 3257919 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Legacy Sharyland Project
0PT40918 | Odessa EHV CREZ Switch : Security system installed | City of Odessa, Midland County | Security system installed | 2020-10-01 | 2020-12-29 | 2020-12-29 |  | 1044061 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40703 (M3037) | Royse Switch: Replace the existing 138 kV fuseless capacitor banks with 110.4 Mvar | City of Royce City, Rockwall County | Remove capacitor Bank #1 that's connected to the North 138 kV Bus. Replace the existing 138 kV fuseless capacitor banks with 110.4 Mvar, 138 kV supervisory-controlled transmission capacitor banks on 138 kV south bus. Install three new FIDS for switching capacitors. | 2020-02-27 | 2020-06-01 | 2020-06-01 |  | 958638 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40874 | Grady Sub : Install one Transformer #2 with two Feeder Breakers | City of Lenorah, Martin County | Install one Transformer #2 with two Feeder Breakers. | 2020-02-19 | 2020-06-10 | 2020-06-10 |  | 1885509 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Legacy Sharyland Project
0PT40876 0PT39914 | Triangle Sub : Install one Transformer on #2 | City of Stanton, Martin County | Install a second transformer and remove transformers #1 and #2 at Stanton Substation. Complete installation of fiber for line protection, modify 138 kV bus protection to provide redundancy. | 2022-02-17 | 2022-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39281 0PT41845 | Sulphur Springs East Sub : Install Second Transformer and Two Feeder Breakers | City of Sulphur Springs, Hopkins County | Install Second transformer with Two Feeder Breakers | 2020-08-07 | 2020-12-28 | 2020-12-28 |  | 2708193.89 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT37353 (R6073) | Tyler Northwest Sub: Remove the 138-69 kV Auto and demo the 138 kV bus at Tyler NW | City of Tyler, Smith County | Remove the 138/69kV Auto, remove the 69 kV Circuit Breaker, remove the associated relay panels and demo the 138kV bus at Tyler NW. Relocate the 138/69 kV auto to Tyler Switch. | 2020-08-05 | 2020-12-15 | 2020-12-15 |  | 210000 |  |  | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39292 | Tyler Southwest Sub : Install 2nd Transformer and two Feeder Breakers | City of Tyler, Smith County | Install second Transformer and two Feeder Breakers | 2020-07-31 | 2021-05-15 |  |  | 1238958 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03968 (R6073) | Tyler Switch: Rebuild to a four(4) breaker 138 kV ring bus | City of Tyler, Smith County | Upgrade the existing station by installing four 2000 A or greater, 138 kV circuit breakers and associated equipment in a 4-breaker ring bus arrangement. Install one autotransformer and associated equipment. | 2020-06-01 | 2020-12-23 | 2020-12-23 |  | 5592300 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03969 (R6071) | Tyler West Sub: Retire 69 kV | City of Tyler, Smith County | After the completion of R6071 (Black Fork Sw. Sta. Tyler West Tyler Sw. Sta. 69 kV Line Conversion to 138 kV) and R6073 (Tyler Sw. Sta.) projects remove station. | 2020-08-20 | 2020-12-22 | 2020-12-22 |  | 1017891 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39289 | Waxahachie Sub : Replace two Transformers with one upgraded Transformer and add 2 Feeder Breakers | City Azle, Tarrant County | Replace two Transformers with one upgraded Transformer and add 2 Feeder Breakers | 2021-07-05 | 2021-12-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39744 | Celeste Sub : Install FID and new control center for separation of the POI from TMPA | City of Sulphur Springs, Hopkins County | Install a FID and new control center complete with relaying protection for all Oncor owned equipment to establish plant separation at Celeste substation | 2020-03-24 | 2020-12-16 | 2020-12-16 |  | 897899 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40497 | Graham 69 Switch : Replace 69 kV circuit breakers | City of Graham, Young County | Replace two 69 kV circuit breakers | 2020-03-25 | 2020-05-12 | 2020-05-12 |  | 267228 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40615 (R8523) | Nelson Switch : Establish a 138 kV POI for Rodeo Solar Generator | City of Odessa, Ector County | Establish a 138 kV (POI) for Rodeo Solar Generator by installing one 138 kV, 3200 A circuit breaker in existing ring-bus. | 2020-09-18 | 2021-04-29 |  |  | 1240255 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Cost and project was updated to include ROW estimates in November 2020. This was not accurate and the project is being revised back to its original values.
18T65011 | Lake Hubbard Switch: Protective relay upgrade | City of Garland, Dallas County | Upgrade East and West 138 kV bus protection to provide redundancy for three phase faults. | 2020-11-30 | 2021-05-31 |  |  | 460708.55 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Project re-added to report. Line item was inadvertently removed from the September and October reports.
0PT40488 | Palestine South Switch : Replace 138 kV circuit breaker | City of Palestine, Anderson County | Replace 138 kV circuit breaker. | 2020-08-22 | 2020-11-16 | 2020-11-16 |  | 253406 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40647 (R8537) | Red Salt POD : Establish 138 kV POD | City of Big Spring, Howard County | Install three motor operated 138 kV 2000 A line sectionalizing switches as part of installing a 138 kV (POD) substation on the Brown - Grady 138 kV transmission line. | 2020-08-05 | 2020-12-18 | 2020-12-18 |  | 752389 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40493 | Richardson East Sub: Replace 138 kV circuit breaker | City of Richardson, Dallas County | Replace two 138 kV circuit breaker . | 2020-10-12 | 2021-02-19 | 2021-02-19 |  | 392583 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40926 (M486) | Sargent Road Switch : Install second transformer | City of Dallas, Dallas County | Install second autotransformer, one 3200 A circuit breakers. | 2020-03-13 | 2020-05-14 | 2020-05-14 |  | 2035196 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40484 | Temple Switch: Replace 69 kV and 138 kV circuit breakers | City of Temple, Bell County | Replace 69 kV and 138 kV circuit breakers. | 2020-09-18 | 2020-10-26 | 2020-10-26 |  | 619777 |  |  | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39045 (M5290) | Arbala 138 kV Switch : Establish station for 138 kV POI for Solemio Solar Generator | City of Sulphur Springs, Hopkins County | Install a 138 kV POI for Solemio Solar Generator at Arbala 138 kV switch. Connect the Arbala 138 kV switch to the Sulphur Springs Switch- Commerce Switch 138 kV line section. | 2022-05-02 | 2022-11-10 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40335 0PT43083 (M5313) | Cedar Elm Switch : Establish a 345 kV switching station for Era Wind Generator | City of Sanger, Fresno County | Establish switching station by installing three 345 kV, 5000 A circuit breakers in a ring bus arrangement for a 345 kV (POI) for the Era wind Wildcat Creek Wind Farm facility. | 2020-06-15 | 2020-12-30 | 2020-12-30 |  | 7478769 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT38349 0PT42924 (M5288) | Copperhead Switch: Establish Station for (POI) for Phoenix Solar | City of Bonham, Fannin County | Install a 138 kV (POI) for Phoenix Solar Generator at Copperhead 138 kV Switch. Connect the Copperhead 138 kV Switch to the Bonham -Wolf City 138 kV line section of the Valley Switch-Commerce Switch 138 kV line. | 2020-07-01 | 2021-03-04 | 2021-03-04 |  | 4221247 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT41008 (R8536) | Fairgrounds POD : Establish 138 B567 kV POD | City of Midland, Midland County | Install three motor operated Scada controlled 138 kV 3200 A line sectionalizing switches as part of installing two 138 kV (POD) | 2020-10-03 | 2020-12-14 | 2020-12-14 |  | 822820 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40938 | Harry Hines Sub : Establish Substation with one transformer and a switchgear building with twelve circuit breakers for eight feeders | City of Dallas, Dallas County | Establish Substation with one transformer and a switchgear building with twelve circuit breakers for eight feeders. | 2020-08-17 | 2020-12-24 | 2020-12-24 |  | 5583889 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41001 0PT43058 (R8533) | Oceanic POD : Establish 138 kV POD | City of Big Springs, Howard County | Install three motor operated 138 kV 2000 A line sectionalizing switches as part of installing a 138 kV (POD) substation on the Brown - Grady 138 kV transmission line. | 2020-08-18 | 2020-11-12 | 2020-11-12 |  | 766820 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT40655 0PT42395 (R8524) | Roadrunner (formerly Aspen) POD : Establish 138 kV Point of Interconnection | City of Odessa, Ector County | Install motor operate Scada control on three 138 kV 3200 A line sectionalizing switches, a 138 kV circuit breaker, and provide customer revenue metering as a part of installing a as a part of installing a 138 kV (POD). | 2020-09-28 | 2021-04-15 |  |  | 1385854 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT41462 | Alkali Lake Sub : Replace transformers #1 & #2 | City of Stanton, Martin County | Replace transformers #1 & #2 | 2020-10-21 | 2020-12-14 | 2020-12-14 |  | 2443568 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40614 (R8431) | Culberson Switch : Install a new 3200 A, 138 kV circuit breaker in an existing ring bus for a POI for LCRA | City of Odessa, Ector County | Install a new 3200 A, 138 kV circuit breaker in an existing ring bus for a POI for LCRA. | 2020-08-28 | 2020-11-24 | 2020-11-24 |  | 671330 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04152 | Farmers Branch Substation: Install bank #4 with one transformer and one circuit breaker | City of Dallas, Dallas County | Install bank #4 with one transformer and one circuit breaker. | 2020-02-22 | 2020-12-09 | 2020-12-09 |  | 3326427 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41196 | Las Colinas Sub : Installation of piers for the stabilization of the station | City of Irving, Dallas County | Installation of piers for the stabilization of the station. | 2020-07-24 | 2021-06-30 |  |  | 750105 |  |  | 99 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40650 (R8540) | Manning POD: Establish a 138 kV POD | City of Odessa, Ector County | Establish a 138 kV POD on the LCRA Crane East - Crane 138 kV line. | 2020-12-11 | 2021-12-31 |  |  | 922339 |  |  | 85 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40412 (R8521) | Nobles POD : Provide a 138 kV POD | City of Midland, Midland County | Establish Nobles POD for customer owned station, a 138 kV POD on the Midessa South - Midland Airport 138 kV line. | 2020-08-15 | 2021-04-30 |  |  | 857254.49 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41600 (M4178) | Plano Texas Instrument Switch : Establish POD | City of Richardson, Dallas County | Install two 138 kV circuit breakers to establish a 138 kV POD on the Plano West Switch – Allen Switch and Plano West Switch – Richardson East Switch 138 kV lines. | 2020-04-05 | 2020-12-15 | 2020-12-15 |  | 6129808 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
19T63016 (R8444) | Scurry County South Switch: Add 138 kV line terminal for Canyon Wind | City of Snyder, Scurry County | Install a new 138 kV bay with two 138 kV, 3200 A circuit breakers and associated equipment to install a 138 kV POI for customer's generator. | 2021-11-15 | 2021-12-30 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41232 (M4286) | Venus Switch : Dismantle and remove all out-of-service 138 kV switch-yard facilities due to establishment of Kemp Ranch Switch | City of Dallas, Dallas County | Dismantle and remove all out-of-service 138 kV switch-yard facilities due to establishment of Kemp Ranch Switch. | 2020-06-11 | 2020-10-06 | 2020-10-06 |  | 692000 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39790 (M5294) | Burleson Sub: Establish substation with a 4-breaker ring bus arrangement | City of Burleson, Tarrant County | Establish substation with a 4-breaker ring bus arrangement and remove the existing 138 kV capacitor bank from Burleson Substation. | 2020-10-05 | 2021-05-15 |  |  | 5026314 |  |  | 94 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41089 (M5066) | Decordova Switch : Reconfigure the station to connect new 138 kV lines from Carmichael Bend Switch | Hood County | Reconfigure the station to connect new 138 kV lines from Carmichael Bend Switch to two circuit breakers. Auto will be stored in place and remove all other 138 kV breakers in the yard. | 2020-11-20 | 2020-12-21 | 2020-12-21 |  | 1850528 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38516 (R9037) | Fullerton Switch: Construct the third breaker-and-a-half rung of 138 kV circuit breakers | City of Andrews, Andrews County | Construct the third breaker-and-a-half rung of 138 kV circuit breakers. Terminal equipment minimum capability of 2000 A or greater. Remove the Fullerton 69 kV Substation. | 2020-12-19 | 2021-05-15 |  |  | 2400000 |  |  | 99 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41110 | Horsehead Draw Sub : Add second transformer with two feeder breakers | City of Odessa, Ector County | Add second transformer with two feeder breakers | 2020-07-06 | 2020-12-17 | 2020-12-17 |  | 2096238 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41497 | Jack Rabbit Sub : Install 2nd transformer with two feeder breakers | City of Odessa, Ector County | Install second transformer with two feeder breakers. | 2020-01-06 | 2021-05-15 |  |  | 2079653 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41542 (R8462) | Midkiff Switch : Remove Midkiff 69 kV switch | City of Odessa, Upton County | Remove Midkiff 69 kV Switch | 2020-05-04 | 2020-10-08 | 2020-10-08 |  | 505820 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38205 (R8462) | Midkiff Switch: Install 138 kV circuit breaker | City of Odessa, Ector County | Install one 3200 A, 138 kV circuit breaker and close the normally open switch at Shipwreck Substation. | 2020-08-21 | 2020-12-15 | 2020-12-15 |  | 1269711 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41509 (M4312) | Renner Switch : Replace SVC 1 and SVC 2 Controls | City of Plano, Collin County | Upgrading control system. | 2020-03-16 | 2021-05-15 |  |  | 7983373 |  |  | 40 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41551 | Stanton Sub : Install a fourth transformer at Stanton Substation with a one transformer, remove transformers #1 and #2 at Stanton Substation and demo 69 kV wood structure | City of Stanton, Martin County | Install a fourth transformer at Stanton Substation with a one transformer, remove transformers #1 and #2 at Stanton Substation and demo 69 kV wood structure. | 2020-08-28 | 2020-12-10 | 2020-12-10 |  | 2143550 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41988 (R8462) | Shipwreck Sub : Terminate line from Midkiff | Reagan County | Terminate line from Midkiff. | 2020-08-23 | 2020-12-01 | 2020-12-01 |  | 318217 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39282 0PT39322 | Poolville Sub : Establish Substation with one transformer and two feeder breakers | City of Weatherford, Parker County | Establish Substation with one transformer and two feeder breakers. | 2021-01-26 | 2021-05-15 |  |  | 4307846.9 |  |  | 53 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT39502 (R6127) | Elrod 345 kV Switch : Establish station with a 345 kV, 3 breaker ring bus station for POI | City of Corsicana, Navarro County | Establish station with a 345 kV, 3 breaker ring bus station for POI. | 2020-11-17 | 2021-05-31 |  |  | 7045687.86 |  |  | 98 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41313 (M3058) | Quinlan Tap : Establish a radial line terminal by installing a one autotransformer with a 69 kV breaker | City of Royce City, Rockwall County | Establish a radial line terminal by installing a one autotransformer with a 69 kV breaker. | 2020-08-14 | 2021-05-15 |  |  | 2308995 |  |  | 94 | na | 69/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40390 (R6128) | Big Onion Switch : Establish station with 3-breaker, 345 kV ring-bus arrangement for POI | City of Ennis, Ellis County | Establish station with 3-breaker, 345 kV ring-bus arrangement for POI. | 2020-10-14 | 2021-04-21 |  |  | 7067651 |  |  | 99 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41798 (R3016) | Double Mountain Switch : Install one 75 MVAR reactor | Lubbock County | Install one 75 MVAR reactor | 2020-09-05 | 2021-06-15 |  |  | 2818273 |  |  | 88 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41685 15T80045 | Cottonfield Sub : Establish substation with transformer and two 25 kV feeder breakers | City of Stanton, Martin County | Establish substation with transformer and two 25 kV feeder breakers. | 2020-06-12 | 2020-12-22 | 2020-12-22 |  | 4641381.21 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT41537 | Valley 345 kV Switch : Replace 345 kV DFR | City of Savoy, Fannin | Replace 345 kV DFR | 2020-12-04 | 2020-12-10 | 2020-12-10 |  | 202906 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41799 (R3017) | Fiddlewood Switch : Install one 75 MVAR reactor on the 345 kV south bus | Lubbock County | Install one 75 MVAR reactor on the 345 kV south bus | 2020-06-16 | 2021-06-15 |  |  | 2848009 |  |  | 83 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41309 | Wall Street Sub : Remove station #4 transformer and switchgear and install UG distribution bays for Station #3, and reconfigure 138 kV bus | City of Dallas, Dallas County | Remove station #4 transformer and switchgear and install UG distribution bays for Station #3, and reconfigure 138 kV bus. | 2021-01-18 | 2021-05-15 |  |  | 2000000 |  |  | 81 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40937 | Coyanosa Sub : Replace transformer #1 | City of Pecos, Reeves County | Replace transformer #1 | 2021-06-14 | 2021-12-01 |  |  | 3281351 |  |  | 0 | na | 69/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41528 | TI Dallas Sub: Replace CB #012 | City of Dallas, Dallas County | Replace CB #012 | 2020-11-16 | 2020-12-17 | 2020-12-17 |  | 367788.12 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40479 | Armstrong Sub: Replace flash bus | City of Dallas, Dallas County | Replacing flash bus by installing three FIDS and retrofit transformer protection panels on three transformers. | 2020-10-27 | 2020-12-11 | 2020-12-11 |  | 970000 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41831 | China Grove Switch : Upgrade 138 kV bus protection and 138 kV/69 kV auto protection relaying | Mitchell County | China Grove Switch : Upgrade 138 kV bus protection and 138 kV/69 kV auto protection relaying | 2020-09-29 | 2021-05-31 |  |  | 2017975 |  |  | 94 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40648 (R8544) | Dillon POD : Establish 138 kV POD | Martin County | Provide a 138 kV (POD) on the Andrews North McKenzie Draw 138 kV line by installing three138 kV 3200 A motor operated sectionalizing switches and low-voltage metering. | 2021-01-12 | 2021-11-15 |  |  | 764362.68 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41776 (R8541) | Dog House Switch: Install two 345 kV, 3200 A circuit breakers, POI | City of Andrews, Andrews County | Install two 345 kV, 3200 A circuit breakers POI, ensure all terminal and associated equipment meets or exceeds 3200 A. | 2021-01-21 | 2021-04-01 | 2021-04-01 |  | 2754580 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40611 | Graham 345 kV Switch: Auto protection upgrade | Young County | Upgrade 138 kV/345 kV auto protection panels (2 panels total) and (1) Tertiary reactor panel. Modify 345 kV DC system to allow fully redundant DC sources. Add 345 kV bus CCVT's C & D buses. Replace 345 kV C&D house battery chargers with 35A. | 2020-10-19 | 2022-05-15 |  |  | 1180134.37 |  |  | 86 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40543 | Graham Plant Switch : Bus protection upgrade scope | Young County | Modify relaying to include installing two gen interconnection/separation schemes, and upgrade 138 kV Bus A&B protection. Add 138 kV bus CCVT's on A & B buses to provide backup for single-breaker line protection. | 2020-10-22 | 2022-05-01 |  |  | 1438784.96 |  |  | 98 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39271 | LTV Sub : Install breaker to relieve overloaded Grand Prairie feeders | City of Dallas, Dallas County | Install breaker to relieve overloaded Grand Prairie feeders. | 2020-06-29 | 2021-02-05 | 2021-02-05 |  | 2536057.82 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40475 | North Breckenridge Sub : Replace FID | City of Breckenridge, Stephens County | Replace FID with new 1200A, 40kA S&C circuit switcher | 2020-10-02 | 2020-12-30 | 2020-12-30 |  | 263417 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41312 | Renner Sub: Replace one 138 kV cap bank relay panel | City of Plano, Denton County | Replace one 138 kV cap bank relay panel. | 2020-09-26 | 2020-12-16 | 2020-12-16 |  | 338767 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41311 | Renner Switch : Replace two 138 kV cap bank relay panels | City of Plano, Denton County | Replace two 138 kV cap bank relay panels on two circuit breakers. | 2020-10-05 | 2020-12-07 | 2020-12-07 |  | 573201 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41627 (R984) | Stouts Creek Switch : Establish Station for (POI) | Hopkins County | Establish station by installing three 345 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement for a (POI). Station will connect to the Allen Switch- Monticello Switch 345 kV line. | 2021-10-15 | 2022-04-12 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41535 | Temple Pecan Creek Switch : Replace the 138 kV and 345 kV DFR | City of Temple, Bell County | Replace the 138 kV and 345 kV DFR | 2020-08-17 | 2020-11-13 | 2020-11-13 |  | 210749 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41908 (R8546) | Thirtysix Draw POD: Establish 138 kV POD | Glasscock County | Provide a 138 kV (POD) on the Spraberry Switch - McDonald Road Switch 138 kV line by installing three 138 kV 2000 A motor operated sectionalizing switches and low-voltage metering. | 2019-12-19 | 2021-04-06 | 2021-04-06 |  | 708758.79 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42420 | Tyler Grande Switch : Replace one failed circuit breaker | City of Tyler, Smith County | Replace one failed circuit breaker | 2020-05-04 | 2020-06-29 | 2020-06-29 |  | 479573 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(d) | Emergency Project
0PT39848 | Waco West Sub : Demo and retire station | City of Waco, McLennan County | Demo and retire station as part of rebuilding station at new location called Du Puy Substation | 2020-06-15 | 2020-11-03 | 2020-11-03 |  | 391310 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41084 0PT43619 (R6131) | Buckhorn Switch: Establish a 345 kV switching station for POI | City of Goldthwaite, Mills County | Establish switching station with a 3-Breaker ring bus. The POI will be located within Oncor's Brown Switch - Killeen Switch 345 kV double-circuit line. | 2020-11-14 | 2021-06-01 |  |  | 7346402 |  |  | 91 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT41795 0PT43016 (M5316) | Byrd Road 345 kV Switch: Establish 345 kV switch station in a 3-Breaker ring bus switchyard for POI | City of Electra, Wichita County | Establish a 345 kV switching station POI by installing three 345 kV, 3200 A circuit breakers in a ring bus. | 2020-10-09 | 2021-05-21 |  |  | 7321207.93 |  |  | 98 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT41218 (M4311) | Ennis West Switch: Install 138 kV circuit breakers | City of Ennis, Ellis County | Install 138 kV circuit breakers and re-terminate Oncor line terminals | 2021-01-12 | 2021-05-15 |  |  | 2281324.25 |  |  | 82 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40478 | Fairmont Sub : Replace flash bus by installing four FIDS and retrofit transformer protection panels | City of Dallas, Dallas County | Replace flash bus by installing four FIDS and retrofit transformer protection panels on all transformers | 2020-10-02 | 2020-12-15 | 2020-12-15 |  | 1049666.22 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40687 | Loraine Sub: Decommission Substation | City of Sweetwater, Nolan County | Decommission substation | 2021-04-05 | 2021-05-31 |  |  | 313505 |  |  | 99 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40995 (R8481) | Quarry Field Switch: Establish 345 kV switching station | Loving County | Establish switching station with a 345 kV four rung breaker-and-a-half configuration with 5000 A two 345/138 kV autotransformers, four 138 kV circuit breakers and four 13.8 kV reactors. | 2020-09-21 | 2021-05-15 |  |  | 20740520 |  |  | 79 | na | 138/345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38759 (R6069) | Redland Switch: Rebuild Herty North Switch with a 6-breaker 138 kV breaker-and-a-half bus arrangement | City of Lufkin, Angelina County | Rebuild Herty North Switch with a 6-breaker 138 kV breaker-and-a-half bus arrangement. | 2020-08-25 | 2021-05-15 |  |  | 8859445 |  |  | 94 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03989 (M4088) | Welch Road Sub: Upgrade all line terminal and associated equipment to meet or exceed 3000 A | City of Dallas, Dallas County | Welch Road Sub: Upgrade all line terminal and associated equipment to meet or exceed 3000 A | 2021-09-16 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39691 (R9038) | Andrews North Sub: Establish a new 138 kV line terminal at Andrews North Substation | Andrews County | Establish a new 138 kV line terminal at Andrews North Substation as apart of converting the Fullerton Switch - Andrews North Line (East) to operate at 138 kV. | 2020-11-10 | 2021-05-15 |  |  | 2081468 |  |  | 90 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42588 | Burnett Switch Replace failed autotransformer #2 with a 138-69 kV autotransformer | City of Wichita Falls, Sedgwick County | Replace failed autotransformer #2 with a 138-69 kV autotransformer. | 2021-03-04 | 2021-07-01 |  |  | 464360 |  |  | 40 | na | 69/138 | na | na | na | na | na | na | na | 25.83(d) | Emergency project
0PT42130 | Irving Valley View Sub : Install transformer #4 with one transformer and two feeder breakers | City of Irving, Dallas County | Install transformer #4 with one 138/25 kV transformer and two feeder breakers. | 2020-12-03 | 2021-05-15 |  |  | 3726946.03 |  |  | 84 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42611 | Italy Sub : Replace the single-phase transformer with one three phase transformer and install 1 additional feeder breaker | City of Italy, Ellis County | Replace the single-phase transformer with one three phase transformer and install 1 additional feeder breaker. | 2020-10-13 | 2020-12-15 | 2020-12-15 |  | 1212415 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42127 | John Day Sub : Install transformer #2 with a 138-25 kV | City of Fort Worth, Tarrant County | Install transformer #2 with a 138-12 kV. | 2020-10-11 | 2021-03-01 | 2021-03-01 |  | 2059939.52 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41597 (M5223) | Keller Wall Price 138 kV Sub: Replace the two existing capacitor banks | City of Keller, Tarrant County | Replace the two existing capacitor banks with two supervisory-controlled transmission capacitor banks. | 2021-01-25 | 2021-05-15 |  |  | 1686860 |  |  | 51 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38749 (M4245) | Norwood Switch: Upgrade two 138 kV circuit breakers | City of Irving, Dallas County | Upgrade two 138 kV circuit breakers. | 2021-01-13 | 2021-05-15 |  |  | 290612 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42333 (M5277) | Saginaw Switch : Dismantle and retire station | City of Fort Worth, Tarrant County | Dismantle and retire station as a part of establishing Deen Switch station. | 2020-08-31 | 2021-05-15 |  |  | 844750 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42621 | Southlake Sub : Replace failed transformer #1 | City of Fort Worth, Tarrant County | Replace failed transformer #1, with spare transformer removed from Round Rock South. | 2020-06-06 | 2020-08-04 | 2020-08-04 |  | 1375866 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d) | Emergency project
0PT41249 0PT43623 (M5315) | Thorn Tree Switch : Establish switching station to install a 345 kV for POI | City of Mount Vernon, Franklin County | Establish switch station in a 9-breaker 345 kV breaker-and-a-half arrangement. | 2020-12-15 | 2021-05-31 |  |  | 14415063.69 |  |  | 96 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42530 | Sweetwater Tap: Install motor operate Scada control on three 138 kV line sectionalizing switches | City of Sweetwater, Nolan County | Install motor operate Scada control on three 138 kV line sectionalizing switches and install trans-closure to replace the existing control house. | 2020-10-27 | 2021-06-30 |  |  | 724445 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39690 (R9038) | Means Sub: Convert the station from 69 kV to 138 kV | City of Andrews, Andrews County | Convert the station from 69 kV to 138 kV and connect to the Fullerton Switch - North Andrews 138 kV line (East). | 2020-12-14 | 2021-05-15 |  |  | 1007308 |  |  | 99 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42368 0PT42657 | Keystone Sub : Establish station by installing a one transformer with two feeder breakers | City of Odessa, Winkler County | Establish station by installing one transformer with two feeder breakers. | 2021-02-05 | 2021-07-01 |  |  | 749724.36 |  |  | 63 | na | 69/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03991 (M4131) | Sorcey Road Sub: Upgrade line terminal and associated equipment | City of Dallas, Dallas County | Upgrade line terminal and associated equipment as a part of upgrading the Cedar Hill Sw. Sta. – Sorcey Road – Cedar Hill 138 kV line. | 2021-03-31 | 2021-05-15 |  |  | 1181727.53 |  |  | 28 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03992 (M4131) | Cedar Hill Switch Sub: Upgrade line terminal and associated equipment | City of Cedar Hill, Dallas County | Upgrade line terminal and associated equipment as a part of upgrading the Cedar Hill Sw. Sta. – Sorcey Road – Cedar Hill 138 kV. | 2021-09-16 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42207 0PT42302 | Alcatraz Sub : Establish substation with two transformers and four feeder breakers | Loving County | Establish substation with two transformers and four OH feeder breakers. | 2021-01-25 | 2021-05-15 |  |  | 5923526 |  |  | 70 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41719 (R6079) | Elkton Switch: Upgrade all line terminal and associated equipment | City of Tyler, Smith County | Upgrade all line terminal and associated equipment as a part of rebuilding the 5.3-mile Tyler Switch - Elkton Switch 138 kV line | 2021-01-07 | 2021-05-15 |  |  | 385477 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42121 | Midland West Sub : Install transformer #4 by adding one transformer and one feeder breaker with UG exit | City of Odessa, Midland County | Install transformer #4 by adding one transformer and one feeder breaker with UG exit. | 2021-02-26 | 2021-06-30 |  |  | 1813969 |  |  | 65 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42838 (M4046) | Watermill Switch : Replace one overdutied 345 kV CB | City of Lancaster, Dallas County | Replace one overdutied 345 kV CB | 2021-04-15 | 2021-05-15 |  |  | 668390.83 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41624 0PT44479 (M4315) | Pebble Creek Switch: Establish 138 kV switching station | City of Red Oak, Ellis County | Establish 138 kV switching station for (POD) | 2021-03-29 | 2021-11-15 |  |  | 5600194 |  |  | 70 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42129 16T80062 | Midnight Sub (Round Rock North): Establish two transformers and three 25 kV UG feeder breakers | City of Temple, Bell County | Establish two transformers and three feeder breakers. | 2021-03-05 | 2021-06-15 |  |  | 8006154.01 |  |  | 36 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT42134 | Loving Sub : Replace transformer #1 & #2 with two transformers and four feeder breakers with UG feeder exits | Loving County | Replace transformer #1 & #2 with two transformers and four feeder breakers with UG feeder exits. | 2021-02-21 | 2021-06-30 |  |  | 2118306 |  |  | 56 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39692 16T80017 (R9039) | Frankel City Sub : Convert station from 69 kV to 138 kV | City of Andrews, Andrews County | Convert station from 69 kV to 138 kV | 2021-03-08 | 2021-05-15 |  |  | 577899 |  |  | 72 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42665 (M3092) | Austin Ranch Sub : Establish a POI 138 kV for Brazos | City of The Colony, Denton County | Establish a 138 kV POI at Austin Ranch. Install two LS switches | 2021-04-06 | 2021-06-01 |  |  | 256060 |  |  | 60 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42794 | Plano Shiloh Road Sub : Install a third transformer at Plano Shiloh Rd and three breakers | City of Plano, Collin County | Install a third transformer at Plano Shiloh Rd and three breakers | 2021-03-30 | 2021-05-15 |  |  | 6182250 |  |  | 8 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42143 | Driver Sub : Install transformer #4 with one transformer and two feeders | City of Odessa, Midland County | Install transformer #2 with one transformer and two UG feeder breakers | 2021-01-05 | 2021-06-15 |  |  | 2640072 |  |  | 40 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04147 0PT37291 | Riverview Sub : Establish one transformer and two feeder breakers | Ward County | Establish one transformer and two feeder breakers. | 2021-01-22 | 2021-06-30 |  |  | 4336570 |  |  | 42 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03997 (M3047) | Plano Coit Road Sub: Upgrade line terminal and associated equipment | City of Plano, Collin County | Upgrade line terminal and associated equipment as a part of upgrading the Renner Switch - Allen Switch/Plano Tennyson Switch 138 kV | 2021-03-01 | 2021-05-15 |  |  | 519104 |  |  | 60 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03986 (M4088) | Marsh Lane Switch: Upgrade all line terminal and associated equipment | City of Dallas, Dallas County | Upgrade all line terminal and associated equipment as a part of the rebuilding the Northaven Sw. Station - Morrison Lane Sw. Station 138 kV double-circuit line | 2021-10-15 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42155 | Bulldog Sub : Install transformer #2 with one transformer and three feeder breakers | City of Big Springs, Howard County | Install transformer #2 with one transformer and three feeder breakers | 2021-01-21 | 2021-05-15 |  |  | 2460007 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41447 (M5317) | Toco Switch: Add a single line terminal to establish POI | City of Toco, Lamar County | Add a single line terminal to the existing ring-bus for the POI. | 2021-09-20 | 2022-04-14 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42145 | Canal Road Sub : Install transformer #2 with one transformer and two feeder breakers | City of Odessa, Winkler County | Install transformer #2 with one transformer and two feeder breakers | 2021-01-14 | 2021-06-15 |  |  | 2605207 |  |  | 96 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42133 | Screwbean Sub : Replace transformer #1 with one transformer and two feeder breakers with UG feeder exits | City of Salt Flat, Hudspeth County | Replace transformer #1 with one transformer and two feeder breakers with UG feeder exits. | 2021-03-05 | 2021-06-30 |  |  | 2490653.41 |  |  | 10 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42240 | Thorntonville Sub : Install transformer #2 with one transformer with two feeder breakers | City of Monahans, Ward County | Install transformer #2 with one transformer with two feeder breakers. | 2021-02-12 | 2021-05-15 |  |  | 1913069 |  |  | 92 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39291 | Frisco West Sub : Install transformer #2 with one transformer and two feeder breakers | City of Frisco, Collin County | Install transformer #2 with one transformer and two feeder breakers | 2021-01-22 | 2021-05-15 |  |  | 1930958 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41783 (R9038) | Andrews Switch : Remove & retire station as a part of Fullerton Switch - North Andrews Switch 138 kV Conversion East | Andrews County | Remove & retire station as a part of Fullerton Switch - North Andrews Switch 138 kV Conversion East | 2021-05-03 | 2021-05-15 |  |  | 289286.64 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42139 | Celina Southeast Sub : Install transformer #2 with one transformer and two UG feeder breakers | City of Celina, Collin County | Install transformer #2 with one transformer and two 25 kV feeder breakers. | 2023-01-16 | 2023-05-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39495 (M4314) | Anna Switch: Add 138 kV line terminal and upgrade one CB line terminal and replace MDAR relaying panels | City of Melissa, Collin County | Add 138 kV line terminal and upgrade one CB line terminal and replace MDAR relaying panels. | 2021-01-16 | 2021-05-15 |  |  | 1244972.79 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42516 | Britton Road Sub : Install one 25 kV feeder on transformer #1 and energize transformer #3 | City of Mansfield, Tarrant County | Install one 25 kV feeder on transformer #1 and energize transformer #3 | 2021-02-22 | 2021-07-31 |  |  | 2167007 |  |  | 36 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42176 | Brookhollow Sub : Install transformer #3 with one transformer and two feeder breakers | City of Arlington, Tarrant County | Install transformer #3 with one transformer and two feeder breakers. | 2021-02-28 | 2021-05-15 |  |  | 2900455 |  |  | 87 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41016 (M5222) | Duval Sub: Remove 69 kV station and establish 138-12.5 kV station | City of Fort Worth, Tarrant County | 69 kV station and establish 138-12.5 kV station | 2021-07-05 | 2021-12-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40560 (R6132) | Four Brothers Switch : Establish 345 kV switch bus with a 3-breaker arrangement | City of Waco, Hill County | Establish 345 kV switch bus with a 3-breaker arrangement | 2021-11-15 | 2022-05-19 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03978 (M5155) | Handley Switch: Upgrade line terminal and associated equipment | City of Fort Worth, Tarrant County | Upgrade line terminal and associated equipment as a part of upgrading the Handley – Sherry 138 kV double-circuit line. | 2021-09-16 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03979 (M5155) | Lakewood Sub: 138 kV terminal upgrade | City of Fort Worth, Tarrant County | Upgrade line terminal and associated equipment as a part of upgrading the Handley – Sherry 138 kV double-circuit line. | 2021-09-10 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41222 (R8308) | Natural Dam Sub: Station Expansion | City of Big Springs, Howard County | Upgrade the 138 kV switch by installing one 3200 A, 138 kV circuit breaker in a 5-breaker ring bus arrangement. | 2021-02-01 | 2021-12-15 |  |  | 1095864 |  |  | 10 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42227 | Owl Hills Sub : Install transformer #3 and two feeder breakers | Culberson County | Install transformer #3 and two feeder breakers. | 2021-01-17 | 2021-05-15 |  |  | 2936452.63 |  |  | 37 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03980 (M5155) | Pantego Sub: 138 kV terminal upgrade | City of Arlington, Tarrant County | Upgrade line terminal and associated equipment as a part of upgrading the Handley – Sherry 138 kV double-circuit line. | 2021-06-01 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41451 0PT42232 (M4302) | Shankle Switch: Establish 138 kV breaker and a half station (formerly Ennis Switch) | City of Ennis, Ellis County | Establish station by installing eight 138 kV, 3200 A circuit breakers in a breaker-and-a-half bus arrangement. | 2021-06-17 | 2021-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42652 | Shipwreck Sub : Install the 3rd transformer with two feeder breakers | City of Odessa, Reagan County | Install the 3rd transformer with two feeder breakers. | 2021-04-16 | 2021-08-01 |  |  | 2759170 |  |  | 22 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41031 18T80022 (M5278) | Timberview Switch: Establish 345 kV Switch | City of Everman, Tarrant County | Establish 345 kV switch bus with a 15-breaker and-a-half bus arrangement. | 2021-06-01 | 2021-12-15 |  |  | 20561331.36 |  |  | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40993 (M4314) | Anna Southeast Sub: Upgrade 138 kV terminal equipment and re-configure station arrangement | City of Melissa, Collin County | Upgrade the 138 kV terminal equipment to 3200A and reconfigure station arrangement for new double circuit line connection. | 2021-03-17 | 2021-05-15 |  |  | 511434 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38750 (M4245) | Denton Drive Switch: Upgrade East bus and terminal 138 kV circuit breaker(s) to 3200A, convert circuit breaker line relaying to fiber | City of Dallas, Dallas County | Upgrade terminal circuit breaker to 3200A as a part of upgrading the 3.9-mile Norwood Switch – Denton Drive Switch 138 kV double-circuit line. | 2021-02-07 | 2021-05-15 |  |  | 892375 |  |  | 88 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03995 (M4131) | Eagle Ford Sub: 138 kV Cedar Hill Switch - Sorcey Road line terminal upgrade | City of Dallas, Dallas County | Upgrade line terminal and associated equipment as a part of upgrading the Cedar Hill Switch – Sorcey Road – Cedar Hill 138 kV line. | 2021-03-22 | 2021-05-15 |  |  | 277040 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42128 0PT42305 | Flat Land (Red Lake) Sub : Establish Flat Land Sub with two transformers and two feeder breakers. | City of Stanton, Martin County | Establish Flat Land Sub with two transformers and two feeder breakers. | 2021-02-25 | 2021-05-15 |  |  | 5071350.8 |  |  | 74 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42713 (R8526) | Horseshoe Springs Switch : Establish line terminal by installing one 3200A, 138 kV circuit breaker(s) | City of Orla, Culberson County | Establish line terminal by installing one 3200A, 138 kV circuit breaker(s). | 2021-04-10 | 2021-12-15 |  |  | 462379 |  |  | 44 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42835 (R8559) | Moss Switch : Replace two overdutied 138 kV circuit breaker(s) | City of Odessa, Ector County | Replace overdutied 138 kV circuit breaker(s) | 2021-03-18 | 2021-05-15 |  |  | 444277 |  |  | 50 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43129 (R987) | Plano West Switch : 138 kV bus configuration modification | City of Richardson, Dallas County | Remove the bus link between transformer #1 & #2 and between two switches. Install motor operated sectionalizing switches between transformer #1- transformer #3. | 2021-02-08 | 2021-05-15 |  |  | 544024 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42712 (R8526) | Riverton Switch : Establish line terminal by installing one 3200A, 138 kV circuit breaker(s) | City of Orla, Culberson County | Establish line terminal by installing one 3200A, 138 kV circuit breaker(s). | 2021-03-02 | 2021-12-15 |  |  | 1165607 |  |  | 92 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT02809 (M4250) | South Hampton Sub: Upgrade all line terminal and associated equipment | City of Duncanville, Dallas County | Upgrade all line terminal and associated equipment as apart of upgrading the 9.1-mile Cedar Hill Switch - Camp Wisdom Road Switch 138 kV line | 2021-09-15 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43044 (R6071) | Tyler Northwest Sub : Terminate Shamburger Switch line | City of Tyler, Smith County | Terminate Shamburger Switch line into Tyler NW Substation. Remove the 138 kV circuit breaker(s) and associated relaying. | 2021-02-01 | 2021-06-30 |  |  | 871191.18 |  |  | 65 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41700 (R6097) | Eustace Sub: Upgrade terminal equipment | City of Eustace, Henderson County | Upgrade terminal equipment as a part of rebuilding the Eustace Southeast Switch (RCEC) - Mabank 138 kV line section. | 2021-06-01 | 2021-12-15 |  |  | 364653 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42672 | Brownwood Switch : Upgrade cap bank protection to current standards | City of Brownwood, Brown County | Upgrade cap bank protection to current standards. | 2021-03-12 | 2021-05-15 |  |  | 990421 |  |  | 99 | na | na | na | na | na | na | na | na | na | 25.83(d)
0PT42797 (R4023) | Tecumseh Creek Switch: Establish 345 kV station for POI | City of Graham, Young County | Establish 345 kV, three breaker ring bus with circuit breakers to provide a POI. | 2021-04-23 | 2021-11-18 |  |  | 7174910 |  |  |  | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41994 | Bowman Switch : Bus and auto relay upgrades and auto equipment | City of Wichita Falls, Wichita County | Bus and auto relay upgrades. | 2021-04-26 | 2021-12-15 |  |  | 2487506 |  |  |  | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43601 0PT43465 | Lonesome Draw Sub : Install transformer #3 and two breakers | City of Midkiff, Upton County | Install one transformer with two feeder breakers and transfer feeder exit from bank #1 to the new transformer. | 2021-02-25 | 2021-06-15 |  |  | 3047166 |  |  | 46 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03987 (M4088) | Morrison Lane Switch: Upgrade all line terminal and associated equipment | City of Dallas, Dallas County | Upgrade all line terminal and associated equipment as a part of the rebuilding the Northaven Switch Station - Morrison Lane Switch Station 138 kV double-circuit line. | 2022-03-01 | 2022-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43602 0PT43314 | Prosper Sub : Establish substation with one transformer and two feeder breakers | City of Prosper, Collin County | Establish substation with one transformer and two feeder breakers. | 2021-04-27 | 2021-06-30 |  |  | 8512765 |  |  | 2.5 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41963 0PT42300 | Gamma (formerly Palmer) Substation : Establish a new substation adjacent to Palmer substation with one transformer and two feeder breakers | City of Palmer, Ellis County | Establish a new substation adjacent to Palmer substation with one transformer and two feeder breakers. | 2021-03-12 | 2021-12-15 |  |  | 4189501 |  |  | 80 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41217 (R8503) | Wink Switch: 138 kV breaker addition | City of Wink, Winkler County | Install one 138 kV 3200A breaker to terminate the new 138 kV Wink line being converted from 69 kV. | 2021-03-09 | 2021-05-15 |  |  | 777638 |  |  | 91 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42179 | Campion (formerly Bluebonnet Lakes) Sub : Establish station with one transformer and two feeder breakers | City of Grand Prairie, Dallas County | Establish station with one transformer and two feeder breakers. | 2021-12-01 | 2022-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42634 | Rocky Creek Switch : Replace MDAR relaying panel for one circuit breaker and replace DFR | City of Crowley, Tarrant County | Replace MDAR relaying panel for circuit breaker. | 2021-05-03 | 2021-05-15 |  |  | 252000 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42377 (M4247) | Carrollton Northwest Switch : Replace the existing autotransformer | City of Carrollton, Denton County | Replace the existing autotransformer and install one 345 kV, 3200A circuit breaker on the 345 kV bus. | 2021-07-12 | 2021-12-31 | [5 empty] | 0 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42637 | Comanche Switch : Replace MDAR relaying panel for one circuit breaker | City of Comanche, Comanche County | Replace MDAR relaying panel for one circuit breaker. | 2021-04-18 | 2021-05-31 |  |  | 361225 |  |  | 99 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38196 (M4232) | Carrollton East Sub : Upgrade terminals | City of Carrollton, Denton County | Upgrade terminals as a part of re-conductoring the Carrollton East Switch - Renner Switch/Northaven Switch 138 kV double-circuit line section. | 2021-02-04 | 2021-03-29 | 2021-03-29 |  | 256892 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43714 0PT44807 (R8579) | Germania POD : Establish 138 kV POD | City of Odessa, Midland County | Establish a 138 kV POD substation on the Yosemite - Triangle 138 kV transmission line. | 2021-04-24 | 2021-06-25 |  |  | 793723 |  |  |  | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41323 (M5134) | Calmont Switch: Install one capacitor bank consisting of three 18.4 MVAR stages | City of Fort Worth, Tarrant County | Install one capacitor bank consisting of three 18.4 MVAR stages of voltage and supervisory controlled 138 kV transmission capacitors at Calmont 138 kV Switch. | 2021-08-23 | 2021-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43683 | Courtland Sub : Replace failed 345-25 kV Transformer #1 | City of Arlington, Tarrant County | Replace failed 345-25 kV transformer #1 with Britton Rd Spare | 2020-11-17 | 2021-04-01 | 2021-04-01 |  |  |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(d) | Emergency project
0PT03994 (M4131) | Duncanville South Sub: Upgrade line terminal and associated equipment | City of Duncanville, Dallas County | Upgrade line terminal and associated equipment as a part of upgrading the Cedar Hill Switch Station – Sorcey Road – Cedar Hill 138 kV line | 2021-09-20 | 2021-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42261 (R6069) | Herty North Switch : Dismantling and retire the existing station | City of Lufkin, Angelina County | Dismantling and retire the existing station as a part of rebuilding Herty North Switch with a 6-breaker 138 kV breaker-and-a-half bus arrangement to establish Redland Switch. | 2021-07-22 | 2021-12-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41599 (M4093) | Mountain Creek Switch : Install two 138 kV, 3200 A circuit breakers | City of Dallas, Dallas County | Install two 138 kV, 3200 A circuit breakers for Mountain Creek Switch- Cedar Crest Switch 138 kV double-circuit line. | 2021-09-08 | 2021-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41754 0PT40063 | Oil Mill Lake Sub : Rebuild Marlin sub on new site | City of Marlin, Walls County | Establish station to replace Marlin with two transformers. Connect the station to the Marlin Switch – Groesbeck Switch 69 kV line and install three 138 kV line sectionalizing switches. | 2021-04-15 | 2021-12-15 |  |  | 5356546 |  |  |  | 69 | 69, 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44112 | Reagan Street Sub : Replace failed transformer #2 | City of Dallas, Dallas County | Replace failed transformer #2 | 2020-12-22 | 2021-02-11 | 2021-02-11 |  | 464201 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43555 (R8492) | Rexall Switch : Replace two 138 kV circuit breakers with auto sectionalizing switches | City of Odessa, Midland County | Replace two 138 kV circuit breakers with auto sectionalizing switches | 2021-11-01 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41964 (M4317) | Rice Sub : Convert to 138 kV as a part establishing the Ennis Southeast – Rice 138 kV line section | Navarro County | Convert to 138 kV as a part establishing the Ennis Southeast – Rice 138 kV line section by converting and upgrading the 6.7-mile of Ferris Switch – Corsicana Switch 69 kV line from structure 3/2 to substation. | 2021-07-05 | 2021-12-15 | [6 empty] | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43060 | Valley South Switch : Install Security Measures | City of Savoy, Fannin | Install security measures at switching station. | 2021-10-04 | 2021-12-31 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42512 | Venus Switch : Establish a new transformer with two feeder breakers | City of Venus, Ellis County | Establish a new transformer with two feeder breakers | 2021-05-03 | 2021-12-01 |  |  | 3636039 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42153 14T80018 17T80007 | Stagecoach Sub : Establish station with one transformer and two feeder breakers | City of Killeen, Bell County | Establish station with one transformer and two feeder breakers. | 2021-05-10 | 2021-12-01 |  |  | 5884419.42 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43812 | SL Windmill Switch : Replace RTU | Carson County | Replace RTU | 2021-05-31 | 2021-12-31 |  |  | 392113 |  |  |  | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43811 | SL Alibates Switch : Replace RTU | City of Hereford, Deaf Smith County | Replace RTU | 2021-08-16 | 2021-12-31 |  |  | 360800.6 |  |  |  | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43523 0PT41769 0PT41759 | Moores Mill Sub : Establish substation with one transformer and four feeder breakers | City of Temple, Bell County | Establish substation with one transformer and four feeder breakers | 2021-06-07 | 2021-11-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42651 | Kennedale Sub : Remove the existing 345 kV transformers from substation and install a 3rd transformer | City of Kennedale, Tarrant County | Remove the existing 345 kV transformers from substation and install a 3rd transformer and complete distribution feeder exit work | 2021-06-14 | 2021-12-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42148 | Mansfield Sub : Install transformer #3 with one transformer and two feeder breakers | City of Mansfield, Tarrant County | Install transformer #3 with one transformer and two feeder breakers | 2021-06-14 | 2021-12-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39293 | Elkhart Sub : Install transformer #2 with one transformer and one feeder breaker | Elkhart County | Install transformer #2 with one transformer and one feeder breaker | 2021-07-05 | 2021-12-01 | [6 empty] | na | 69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39290 | Lake Brownwood Sub : Establish a new substation with one transformer and two feeder breakers | City of Brownwood, Brown County | Establish a new substation with one transformer and two feeder breakers and demolish the existing station. | 2021-07-05 | 2021-12-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43503 | Graham 345 kV Switch : Replace two circuit switchers with 345 kV circuit breakers | City of Graham, Young County | Replace two circuit interrupters #6333 and #6353 with 345 kV breakers and add leaker management | 2021-08-02 | 2021-12-15 | [6 empty] | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43638 | Midland Downtown Sub : Replace two existing transformers and add one feeder breakers to bank #1. | City of Midland, Midland County | Replace two existing transformers and add one feeder breakers to bank #1 | 2021-08-23 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44269 | Roanoke Switch : Replace failing tertiary reactors on auto#1 | City of Roanoke, Denton County | Replace three 13.8 kV tertiary reactors for Auto #1. | 2021-02-08 | 2021-04-16 | 2021-04-16 |  | 601814.37 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(d) | Emergency project
0PT39494 0PT38777 (M4275) | Greenbrier Switch (formerly Princeton) : Establish Switching Station | City of Princeton, Collin County | Establish switching station adjacent to the existing Princeton POD by installing six 138 kV circuit breakers in a breaker-and-a-half arrangement as part of the line upgrade from Anna Tap - Princeton Switch. | 2021-10-18 | 2022-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43517 | Hemphill Switch : Replace two 138 kV circuit breakers | City of Fort Worth, Tarrant County | Replace two 138 kV circuit breakers | 2021-06-28 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43515 | Stryker Creek Switch : Replace two 138 kV circuit breakers | City of Troup, Cherokee County | Replace two 138 kV circuit breakers | 2021-09-20 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43511 | Sherman South Switch : Replace one 138 kV circuit breaker | City of Sherman, Grayson County | Replace one 138 kV circuit breaker | 2021-10-11 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43504 | Fisher Road Switch : Replace one 138 kV circuit breaker | City of Wichita Falls, Wichita Falls County | Replace one 138 kV circuit breaker | 2021-10-04 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43502 | Monticello Switch : Replace one 345 kV circuit breaker and replace EPS metering 345 kV CCVTS | City of Mount Pleasant, Titus County | Replace one 345 kV circuit breaker | 2021-10-04 | 2021-12-15 | [6 empty] | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42711 0PT43445 (R8452) | Drill Hole (formerly known as Owl Hills West) Switch: Install two capacitor banks consisting of three 18.4 MVAR stages | Culberson County | Install two capacitor banks consisting of three 18.4 MVAR stages of voltage and supervisory controlled 138 kV transmission capacitors on each circuit of the Horseshoe Springs Switch – Riverton Switch 138 kV double-circuit line. | 2021-06-01 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42511 0PT42659 | Sandhills Sub : Install transformer #2 and add two feeder breakers | City of Crane, Crane County | Install transformer #2 and add two feeder breakers | 2021-06-01 | 2021-12-01 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42174 | Temple Southeast Sub : Install transformer #2 and add two feeder breakers | City of Temple, Bell County | Install transformer #2 and add two feeder breakers | 2021-09-13 | 2021-12-01 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40959 0PT41841 | Reindeer Sub : Establish substation with one transformers and two feeder breakers | City of Lancaster, Dallas County | Establish substation with one transformers and two feeder breakers | 2021-08-02 | 2021-12-01 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44371 | Goddard Sub : Replace switchgear with outdoor feeder breakers and install distribution automation on two feeders | City of Midland, Midland County | Replace switchgear with outdoor feeder breakers and install distribution automation on two feeders | 2021-06-14 | 2021-12-01 | [6 empty] | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43862 | Landfill POD : Establish 138kV Point of Delivery | Andrews County | Landfill POD : Establish 138kV Point of Delivery | 2021-08-09 | 2021-11-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41041 0PT42306 (R8479) | Courtney Creek (Pecos) Switch: Establish 138/69 kV Switching Station | Pecos County | Establish the Courtney Creek 138/69 kV Switch in order to tie into AEP's Rio Pecos Switch - Fort Stockton Switch 138 kV line. The switching station will be installed initially as a 5-breaker 138 kV breaker-and-a-half arrangement with one 138/69 kV autotransformer and one 69 kV line terminal. | 2021-08-02 | 2021-12-15 | [6 empty] | na | 138/69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39677 (M5279) | Forest Hill Sub : Create a Loop In - Loop Out Connection | City of Fort Worth, Tarrant County | Create a loop in - loop out connection and install associated equipment as a part of reconductoring the 4.0-mile Everman Switch - Rolling Hills - Marrs Switch 138 kV double-circuit line | 2021-07-26 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04063 (M5274) | Eagle Mountain Switch: Modify relaying for 138 kV Deen Switch double circuit | City of Fort Worth, Tarrant County | Upgrade to fiber communications and modify relaying on two 138 kV circuit breakers for the new 138 kV Deen Switch double circuit as a part of rebuilding the Eagle Mountain Switch - Deen Switch 138 kV double-circuit line. | 2021-09-16 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38428 (R9015) | Big Spring Switch: Install 138 kV Buzzard Draw Switch line terminal | City of Big Spring, Howard County | Install breaker, switches, CVTs, line relaying and associated foundations, steel, bus, jumpers and cable. | 2021-08-01 | 2021-12-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38429 (R9015) | Buzzard Draw Switch: Install 138 kV Big Spring Switch line terminal | City of Ackerly, Howard County | Install breaker, switch, CCVTs, LAs, line relaying and associated foundation, steel, bus, jumpers and cable and remove the 69 kV Big Spring Switch line terminal equipment. | 2021-09-20 | 2021-12-15 | [6 empty] | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39492 (M364) | Richardson Sub : Upgrade line terminal as a part of upgrading the Plano West Switch - Richardson Collins 138 kV line | City of Richardson, Dallas County | Upgrade line terminal as a part of upgrading the Plano West Switch - Richardson Collins 138 kV line | 2021-09-16 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41032 (M5278) | Everman Switch: Reconfigure 345 kV station by constructing a 4-breaker 345 kV in a ring bus arrangement | City of Fort Worth, Tarrant County | Reconfigure 345 kV station by constructing a 4-breaker 345 kV in a ring bus arrangement. | 2021-09-01 | 2021-12-15 | [6 empty] | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41214 (M4134) | Lake Hubbard Switch: Install two 138 kV circuit breakers | City of Garland, Dallas County | Install two 138 kV circuit breakers and upgrade the Prairie Creek line terminal equipment. | 2021-09-27 | 2021-12-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41995 | Morgan Creek Switch : Bus and auto relay upgrades and equipment replacement and replace two 345 kV circuit breakers | City of Colorado City, Mitchell County | Replace MDAR relaying panel for one circuit breaker. Upgrade 138 kV RTU. | 2021-09-20 | 2022-06-15 | [6 empty] | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43519 | Bells Switch : Replace one 69 kV circuit breaker | City of Bells, Grayson County | Replace one 69 kV circuit breaker | 2021-09-20 | 2021-12-31 | [6 empty] | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43953 (R8538) | Midland East Switch: 138 kV station rebuild | City of Midland, Midland County | Rebuild the 138 kV switch as an 13-breaker initial, 18-breaker ultimate breaker-and-a-half arrangement. | 2021-07-14 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44443 0PT44618 | Blain (formerly known as Dew) Sub : Establish substation with one transformer and two feeder breakers | City of Dew, Freestone County | Establish substation with one transformer and two feeder breakers | 2021-07-01 | 2022-02-01 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41017 0PT41805 | Stuart (formerly Bryan Avenue) Substation: Convert Station from 69 kV to 138 kV operation by rebuilding a new substation to replace the existing station | City of Fort Worth, Tarrant County | Rebuild a new substation to replace the four existing transformers and switchgear feeder breakers with two transformers and eight new switchgear type feeder breakers. | 2021-04-12 | 2022-03-31 |  |  | 8238720 |  |  | 10 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Station grading began prior to reporting on the MCPR. All construction work has ceased and will resume 45 days from the reporting date on June 28.
0PT43010 0PT40574 | Gunsolus Creek Substation : Establish a new station with two transformers and seven feeder breakers on a new site to replace Breckenridge Sub. | City of Breckenridge, Stephens County | Establish a new station with two transformers and seven feeder breakers on a new site to replace Breckenridge Substation. | 2021-08-09 | 2021-12-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42161 | Belton Southwest Sub : Replace transformers # 1 and #2 with two transformers and one breaker to each transformer | City of Belton, Bell County | Replace transformers #1 and #2 and add a breaker to each transformer | 2021-08-02 | 2021-12-01 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41996 | Odessa EHV Switch : Relay upgrades for 138 kV Bus A, 345 kV Bus D, auto #1 and auto # 3. | Odessa County | Upgrade relaying for 138 kV bus A, 345 kV bus D, 345/138 kV auto #1 and auto # 3. Also modify fiber aided line protection for 345 kV Odessa Switch | 2021-09-01 | 2021-12-31 | [6 empty] | 345/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41229 0PT39325 | Bell Mountain (formerly Hudson Oaks) Substation : Establish substation with one transformer and two feeder breakers | City of Hudson Oaks, Parker County | Establish substation with one transformer and two feeder breakers | 2021-08-02 | 2021-12-01 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41015 (M5222) | Handley Switch: Remove 69 kV station, and add 138 kV terminal by using the existing autotransformer position | City of Fort Worth, Tarrant County | Remove all existing 69 kV equipment from the station and add 138 kV terminal by using the existing autotransformer position. | 2021-07-19 | 2022-02-28 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT02811 (M4250) | Duncanville Substation: Upgrade all line terminal and associated equipment | City of Duncanville, Dallas County | Upgrade all line terminal and associated equipment as a part of upgrading the Cedar Hill Switch - Camp Wisdom Road Switch 138 kV line | 2021-10-11 | 2022-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40561 (R990) | Birthright Switch: Establish 3 breaker ring bus switch and modify relaying at Monticello Switch and Farmersville Switch | Birthright County | Establish 345 kV ring-bus switch in the Farmersville Switch-Monticello Switch 345 kV line and give generator one point-of-interconnection | 2022-01-03 | 2022-05-19 | [6 empty] | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41219 (R8504) | Sand Lake Switch: 138 kV line terminal additions | Ward County | Install four 138 kV, 3200 A circuit breakers (two new half positions) and associated equipment to terminate the new 138 kV Cochise lines. | 2021-08-02 | 2021-12-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41705 (R6097) | Mabank Substation: Upgrade terminal equipment | City of Mabank, Henderson County | Upgrade terminal equipment to meet or exceedas 3200 A a part of rebuilding the Eustace Southeast Switch (RCEC) - Mabank 138 kV line section. | 2021-09-20 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41998 | Forest Grove Switch : Bus and autotransformer relay upgrades | Henderson County | Bus and autotransformer relay upgrades | 2021-09-13 | 2021-12-15 | [6 empty] | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42035 (R4027) | Krum West Switch: Add a 345 kV, 5000 A breaker terminal for generator point of interconnection (POI) | City of Krum, Denton County | Add a 345 kV, 5000 A breaker terminal for generator point-of-interconnection (POI) | 2021-09-13 | 2021-12-16 | [6 empty] | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42336 (R6155) | St. Johns Switch: Establish 345 kV switch in a 3-breaker ring bus arrangement to provide a new generator 345 kV point of interconnection (POI) | Falls County | Establish a 345 kV generator point of interconnection (POI) in the Rattlesnake Road Switch-Jewett Switch 345 kV line by establishing St. Johns 345 kV Switch by installing three 345 kV 3200 A circuit breakers in a ring bus arrangement | 2021-10-01 | 2022-04-14 | [6 empty] | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43512 | Oran Switch : Replace one 138 kV circuit breaker | City of Graford, Palo Pinto County | Replace one 138 kV circuit breaker | 2021-11-08 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43516 | East Levee Switch : Replace one 138 kV circuit breaker | City of Dallas, Dallas County | Replace one 138 kV circuit breaker | 2021-09-24 | 2021-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44089 | Beacon Hill Substation : Establish station with one transformer and two feeder breakers | City of Sweetwater, Nolan County | Establish substation with one transformer and two feeder breakers | 2021-07-15 | 2022-02-01 | [6 empty] | na | 138/69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44871 | Plano Coit Rd Substation : Replace the switch with a FID | City of Plano, Collin County | Replace switch with a Fault Interruptable Device (FID). | 2021-03-27 | 2021-04-30 |  |  | 396200 |  |  | 90 | na | na | na | na | na | na | na | na | na | 25.83(d) | Emergency project
CCN APPLICATIONS - APPROVED
13T80013 16T80061 | New Bethel 345 kV Loop Line | Anderson, Freestone, Navarro and Henderson Counties | This project is to construct the new double-circuit New Bethel 345 kV Line connecting the proposed New Bethel Switching station to a connection along one of four existing 345 kV transmission line segments in the region. | 2021-12-31 | 2022-12-31 |  | 26,499,000 (t-line) 7,232,000 (stations) |  |  |  |  | na | 345 | 27 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | na | na | 160 | 13.5 | 44672 | Application Filed 7/10/2015. Administrative Approval received on 09/25/2015.
17T80077 0PT38181 0PT38182 0PT38179 0PT38178 0PT38426 (97.31%) 19T63008 0PT38517 0PT38518 0PT38372 0PT38838 (R8356) (R8429) (R8351) | Odessa EHV - Riverton and Moss - Riverton 345 kV Line | Crane, Ector, Loving, Reeves, Ward, and Winkler Counties | This project is to construct the new double-circuit 345 kV line connecting the Odessa EHV Switching Station and the Moss Switching Station to the Riverton Switching Station. | 2019-03-06 | 2020-12-20 | 2020-12-20 | 199,729,000 (t-line) 23,832,000 (stations) | 248,571,042 (t-line) 18,840,070 (stations) |  |  | 100 | 345 | 345 | 216.7 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | 150 | 15.9 | 160 | 100.4 | 48095 | Application Filed 3/16/2018. Final Order issued on 9/17/2018.
0PT37302 0PT38601 0PT04138 0PT38858 (50%) (R8428) | Owl Hills - Tunstill POD 138 kV Line | Culberson and Reeves Counties | Construct the new single-circuit 138 kV line connecting the proposed Owl Hills Substation to the Tunstill POD. | 2019-05-04 | 2020-12-10 | 2020-12-10 | 20,628,000 (t-line) 1,847,000 (stations) | 27,244,439 (t-line) 3,100,331 (stations) |  |  | 100 | na | 138 | 18.7 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 18.7 | 48582 | Application Filed 8/31/2018. Administrative Approval received on 11/20/2018.
17T80032 0PT04024 0PT38884 (R9027) | Cogdell - Clairemont 138 kV Line | Kent and Scurry Counties | This project is to construct the new double-circuit 138 kV line connecting the Oncor existing Cogdell Substation to the Brazos Electric existing Clairemont Substation. One circuit will be installed initially. | 2019-04-17 | 2020-12-30 | 2020-12-30 | 10,197,500 (t-line) na (stations) (Oncor Portion) | 18,589,374 (t-line) na (station) (Oncor Portion) |  |  | 100 | na | 138 | 11.9 (Oncor Portion) | 959.6 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 11.9 (Oncor Portion) | 47808 | Application Filed 12/11/2017. Final Order issued on 1/18/2019.
0PT39679 0PT39819 0PT38948 (R8482) (R8284) | Clearfork - Dog House 345 kV Line | Andrews County | Construct the new 345 kV transmission line connecting the existing Clearfork Switchyard to the proposed Dog House Switchyard. | 2019-10-23 | 2020-06-01 | 2020-06-01 | 14,304,695 (t-line) 6,995,400 (stations) | 14,104,673 (t-line) 8,282,514 (stations) |  |  | 100 | na | 345 | 10.3 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | 175 | 10.3 | 48861 | Application Filed 11/28/2018. Administrative Approval received 2/6/2019.
NA | Stiles - Coates 138 kV Line | Reagan County | Construct the new 138 kV transmission line connecting the existing Stiles station to the proposed Coates station. | 2021-12-31 | 2023-12-31 |  | 9682000 |  |  |  |  | na | 138 | 8 | 959.6 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 100 | 8 | 46726 | Application Filed 1/17/2017. Final Order issued on 9/29/2017.
0PT37182 0PT40453 0PT38505 0PT38427 (4.43%) (R8380) (R8420) | Sand Lake - Solstice 345 kV Line | Pecos, Reeves, and Ward Counties | This project is to construct the new double-circuit 345 kV line connecting the Oncor Sand Lake Switch to the AEP Texas Solstice Switch. | 2019-06-21 | 2020-12-28 | 2020-12-28 | 49,110,000 (t-line) 17,600,000 (stations) (Oncor Portion) | 68,922,778 (t-line) 22,523,721 (stations) (Oncor Portion) |  |  | 100 | na | 345 | 89 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | na | na | 160 | 44.5 | 48785 | Application Filed 11/7/2018. Final Order issued on 6/26/2019.
0PT38174 0PT40267 0PT04144 (50%) 0PT40670 0PT40867 (50%) 0PT38426 (2.69%) (R8427) | Riverton - Kyle Ranch 138 kV Line | Loving and Reeves Counties | Construct the new single-circuit 138 kV line connecting the Riverton Switch station to the Kyle Ranch Substation. | 2020-06-08 | 2020-12-10 | 2020-12-10 | 19,207,000 (t-line) 3,040,000 (stations) | 21,226,008 (t-line) 3,301,428 (stations) |  |  | 99.5 | na | 138 | 15.2 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 15.2 | 49304 | Application Filed 3/28/2019. Administrative Approval received on 7/17/2019. This project covers the work necessary to construct the PUCT approved route, as well as an additional three (3) miles of line between the Kyle Ranch endpoint as described in this CCN and the relocated Kyle Ranch station as described in Docket No. 49302.
0PT38573 0PT38506 0PT38427 (95.57%) 0PT38426 (2.69%) (R8443) | Riverton - Sand Lake 345 kV Line Circuit Addition (Phase 2) | Reeves and Ward Counties | Add the second circuit on the vacant circuit position of the Riverton - Sand Lake 345 kV Line that will be operated at 345 kV. | 2019-06-21 | 2020-12-18 | 2020-12-18 | 29,200,000 (t-line) 1,185,000 (station) | 24,561,647 (t-line) 1,454,167 (station) |  |  | 100 | 138 | 345 | 39.9 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | 160 | 39.9 | na | na | 49723 | Application Filed 7/19/2019. Administrative Approval received on 10/7/2019.
0PT38176 0PT04088 0PT04087 0PT04144 (50%) 0PT42631 0PT37531 0PT40867 (50%) (R8384) (R8412) | Kyle Ranch - Quarry Field 138 kV Line | Loving County | Construct the new single-circuit 138 kV line connecting the Kyle Ranch Substation to the Quarry Field Switch station. | 2019-03-18 | 2022-04-01 |  | 16,832,000 (t-line) 15,855,000 (stations) | Line: Cost not available, line construction has not begun 18,959,901 (stations) |  |  | 50 | na | 138 | 12.4 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 12.4 | 49302 | Application Filed 3/28/2019. Final Order issued on 3/2/2020. This project had three (3) miles moved to project Riverton - Kyle Ranch 138 kV Line Docket No. 49304 and the remainder is superseded it by project Kyle Ranch - Quarry Field 138 kV Line Docket No. 51737
18T65163 0PT38449 0PT04020 0PT04021 (M4268) | Sargent Road - Oakland Ave. Tap 138 kV Line | Dallas County | Construct the new single-circuit 138 kV line connecting Sargent Road Switch to Oakland Avenue Tap installed completely within Oncor fee-owned property. | 2019-07-10 | 2020-12-11 | 2020-12-11 | 4,940,000 (t-line) 1,375,000 (stations) | 4,460,100 (t-line) 1,424,358 (stations) |  |  | 100 | na | 138 | 2.5 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 2.5 | na | 2.5 | 50217 | Application Filed 11/21/2019. Notice of approval issued on 3/4/2020.
0PT41156 0PT42396 0PT40679 0PT41331 0PT41511 0PT42120 (R8534) | Johnson Draw POD - Salt Flat Road 138 kV Line | Midland County | Construct the new single-circuit 138 kV line connecting the Salt Flat Road Switch to the proposed Johnson Draw POD. | 2020-11-11 | 2021-05-15 |  | 5,257,000 (t-line) 1,461,000 (stations) | 5,257,000 (t-line) 1,502,572 (stations) |  |  | 99 | na | 138 | 2.8 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 2.8 | 50560 | Application Filed 3/5/2020. Notice of approval issued on 5/26/2020.
0PT39531 (R9057) | Bearkat - Longshore 345 kV Line | Glasscock and Howard Counties | Construct the new single-circuit 345 kV line connecting the WETT Bearkat Switch to the Oncor Longshore Switch. | 2022-04-01 | 2022-12-30 |  | 29,339,500 (t-line) 1,700,000 (station) (Oncor Portion) |  |  |  |  | na | 345 | 30.8 | 1926.9 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 160 | 30.8 | 50410 | Application Filed 1/14/2020. Final order issued on 5/7/2021.
CCN APPLICATIONS - PENDING
0PT44498 (R8384) | Kyle Ranch - Quarry Field 138 kV Line (Modification of route approved in Docket No. 49302) | Loving County | Construct the new single-circuit 138 kV line connecting the relocated Kyle Ranch Substation to the Quarry Field Switch station. | 2021-10-31 | 2022-03-31 | [6 empty] | na | 138 | 11.3 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 11.3 | 51737 | Application Filed 2/4/2021.This project covers the work necessary to obtain PUCT approval for a modified route between the relocated Kyle Ranch station location in Docket No. 49302 and the Quarry Field switch.
CCN APPLICATIONS - Oncor / LP&L: The following projects are being reported on behalf of Oncor and the City of Lubbock, by and through Lubbock Power & Light
0PT39835 0PT39844 0PT39623 0PT39631 0PT39632 (56.2%) (R3005) (R3002) (R3003) | Ogallala - Abernathy 345 kV Line | Castro, Hale and Swisher Counties | Construct the new single-circuit 345 kV line connecting the existing Ogallala station to the existing Abernathy station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-15 | 2021-06-15 |  | 87,876,048 (t-line) 8,304,600 (stations) | 88,807,431 (t-line) 9,122,137 (stations) |  |  | 99 | na | 345 | 57.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 57.9 | 48625 | Application Filed 9/6/2018. Final Order issued on 9/26/2019.
0PT39896 0PT40341 0PT39625 0PT41983 0PT39632 (25.7%) 0PT39633 (55.3%) 0PT40608 0PT44515 0PT44516 (R3008) (R3003) (R3001) | Abernathy - Wadsworth 345 kV Line | Hale and Lubbock Counties | Construct the new single-circuit 345 kV line connecting the existing Abernathy station to the existing Wadsworth station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-15 | 2021-06-15 |  | 56,736,759 (t-line) 9,403,700 (stations) | 56,702,358 (t-line) 9,635,269 (stations) |  |  | 94 | na | 345 | 32.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 32.9 | 48668 | Application Filed 9/20/2018. Final Order issued on 10/14/19. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39845 0PT41440 0PT41442 0PT39634 0PT39635 0PT39628 0PT39626 0PT41832 0PT39633 (44.7%) 0PT41847 0PT44486 0PT44487 (R3006) (R3004) (R3010) (R3009) (R3001) | Wadsworth - New Oliver - Farmland 345 kV Line (WNF) | Lubbock and Lynn Counties | Construct the new single-circuit 345 kV line connecting the existing Wadsworth station to the existing Farmland station, routed through one of two options for the proposed New Oliver station. This project is part of the LP&L integration into the ERCOT system. | 2020-03-24 | 2021-06-15 |  | 67,769,000 (t-line) 20,638,000 (stations) | 77,538,361 (t-line) 24,168,146 (stations) |  |  | 69 | na | 345 | 41.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 41.9 | 48909 | Application Filed 12/19/2018. Originally filed under the NTU predecessor report. Final Order issued on 1/23/20. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39845 0PT41452 0PT39732 0PT39967 0PT39629 0PT39630 (R3006) (R3001) (R3014) (R3013) | Southeast - New Oliver - Oliver 115 kV Line (SNO) | Lubbock County | Construct the new single-circuit 115 kV line connecting the existing Southeast station to the existing Oliver station, routed through one of two options for the proposed New Oliver station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-20 | 2021-06-15 |  | 20,688,000 (t-line) 31,248,000 (stations) | 21,452,317 (t-line) 27,949,110 (stations) |  |  | 97 | na | 115 | 17.8 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | 60 | 17.8 |  | Application Filed 12/19/2018. Originally filed under the NTU predecessor report. Final Order issued on 1/23/20. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39846 0PT41891 0PT39637 0PT39968 0PT39636 0PT41986 0PT39632 (18.1%) 0PT44518 0PT44519 (R3007) (R3011) (R3003) | Abernathy - North - North Loop 345/115 kV Line | Hale and Lubbock Counties | Construct the new transmission line connecting the existing Abernathy station to the northern portion of LP&L's planned 115 kV loop line, routed through one of three options for the proposed North station. Depending on which North station is used, this line will be either a single-circuit 345 kV line or a combination of single-circuit 345 kV and double-circuit 115 kV line. This project is part of the LP&L integration into the ERCOT system. | 2019-12-21 | 2021-06-15 |  | 39,782,000 (t-line) 33,367,000 (stations) | 44,361,677 (t-line) 20,274,578 (stations) |  |  | 76 | na | 115/345 | 34.3 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers (345 kV) Steel Poles (115 kV) | na | na | 175 (345 kV) 60 (115 kV) | 24.6 | 49151 | Application Filed 2/19/2019. Final Order issued on 3/12/2020. Originally filed under the NTU predecessor report.

## EntryInstructions
General Instructions for Entering Information
1. Please use "na" whenever appropriate to reduce ambiguity, except in the "Costs," "Percent Complete," and "Percent Variance" columns. 2. Any new or revised entry must be entered using a red font and highlighted in yellow. In the month following the red font entry, change the previous month's red entries back to black and make any new entries for the new month in red. This aids PUCT staff in quickly identifying any changes from the previous month's report. 3. On the final monthly report on an existing line in which one of the attributes as listed in the attribute spreadsheets below has changed, enter that data in a bolded green font.
Utility's Project Number | Enter the Utility's Project Number. No duplicate numbers are allowed in this column.
Project Name | Enter the name of the project. If possible, use the same name as was reported to ERCOT in any reports.
Location (City/County) | Enter the names of the counties where the project is located. Also enter the names of cities, if appropriate. Please delineate all county and city names with commas only. (e.g., Liberty, Chambers, Anahuac, etc.)
Description | Describe the project in enough detail to allow the Commission to ensure that the work does not require a CCN, if the utility does not intend to apply for a CCN. Include any significant or relevant detail not being reported in other columns. Do not include Point of Delivery and add periods to all sentences.
Estimated (or Actual) Start Date | Enter the estimated project starting date. When construction begins, please replace the estimated date with the actual date of the start of construction
Finish Date (Construction Complete) | Enter the date (mm/dd/yy) when the construction related to the project has been completed.
Date Energized (If Applicable) | Enter the date (mm/dd/yy) the project was energized or restored to service (if applicable).
Initial Estimated Project Cost | CCN Projects Only: Enter the estimated cost from the CCN application. When reporting both T-Line and Substation Costs, enter them separately in the same cell. (e.g., "$3,946,000 T-Line; $1,768,000 Substation") This number shall not be changed in future months unless the Application is amended. Please DO NOT use links to other sheets within the workbook. Non-CCN Projects Only: No entry is needed; Enter the estimated cost in the
Final Estimated Project Cost | CCN Projects: Enter the latest available estimated cost for the month that construction starts. This number shall not be changed after construction begins. and a cost variance explanation is not required unless requested by PUC Staff For Non-CCN Projects: Enter the initial estimated cost. Estimate revisions are not necessary
Final Actual Project Cost | Enter the actual, final project cost after the project has been energized and all costs have been recorded. Omit the project from all following reports.
% Variance | The cells contain a formula for calculating the percent variance of the final actual cost with respect to the final estimated cost. This is essentially a calculation of the percent of the cost over-run or under-run. Please do not change these cells.
Percent Complete | State the construction progress of the project as a percent. Please use only an integer and do not write"%." Do not report the percent of money spent.
Existing Voltage | Enter the nominal system existing voltage, if any. In the event of a voltage upgrade, this will be the "before" voltage. If the project is for a new line, enter "na." For projects involving multiple voltages, please delineate the voltages by a comma, (e.g., "69,138"). Please do not write "volts."
Upgraded or New Voltage | Enter the nominal system voltage after upgrading or if new line construction is involved. Please use the same practices described in the "Existing Voltage" column. Please do not write "volts."
Circuit Length (Miles) | Enter the total circuit length. Example: For a new double-circuit line using 10 miles of new ROW, the circuit length would be 20 miles. Please enter only a number, if possible. Please do not write "miles."
Conductor Type & Size & Bundling | Describe the conductor characteristics, including whether double or single circuit or mixed. Lengthy explanations shall be made in the Project Description column. (Format should be Quantity - Conductor Size and Type). Do not include quotations for supplier given code words or the word bundled.
Structure Type(s) | Describe structure types and materials used.
Existing ROW Width (Feet) | Enter width of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Entries such as "60,80,100" or "60 - 100" or "centerline" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
Existing ROW Length (Miles) | Enter length of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Make detailed explanations, if needed, elsewhere. Please do not write "miles."
New ROW Width (Feet) | Enter width of new ROW. The entry type is unrestricted. Entries such as "60,80,100" or "60 - 100" or "centerline" or "railroad" or "street" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
New ROW Length (Miles) | Enter new (additional) ROW length, in miles. Please do not write "miles."
Rule Section or PUC Control Number | Enter the PUC Substantive Rule 25.101 section(s) which are applicable. For multiple section applicability, please delineate by commas, e.g., "25.101(c)(5)(A), 25.101(c)(5)(B)" for a project incorporating a line extension (A) and a voltage upgrade on the existing line which is being extended (B). If the project involves a CCN Application, enter ONLY the .5-digit control number. Please do not write "docket," "CCN" or other text, except when needed in citing Rule 25.101. Should the project include work done under both CCN and 25.101(c)(5), follow the same practices and delineate with commas.
Comments | Enter information not included elsewhere, including reimbursed costs. A cost variance explanation is no longer required for non-CCN projects. However, utilities will be required to submit a Cost Analysis only for CCN Projects. See Note below.
139510
0PT39030 SB

## 16T80061 & 16T64136
Project No. 16T80061 & 16T64136 - New Bethel 345 kV Loop Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1963) | Estimated cost once a route is approved and CCN granted (Route 1963) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2952000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 601000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 2959000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8324000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 11663000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 26499000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 26499000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | N/A | N/A
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 499000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3341000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 338000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2467000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 6645000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 587000 | Costs not yet available | Costs not yet available
Estimated Project Total | 7232000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 33731000
139510
0PT39030 SB |  | City of Tyler, Bell County

## 16T80079 & 0PT04007
Project No. 16T80079 & 0PT04007 & 0PT38665- Riverton - Sand Lake 345 kV Line - Transmission Line Project (Operating at 138 kV)
| Estimated cost included in CCN Application (Route 56) | Estimated cost once a route is approved and CCN granted (Route 54) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4781000 | 10039938 | 11269080.35
Engineering and Design (Utility) | 1773000 | 976563 | 94656.38
Engineering and Design (Contract) | 1987000 | 1621845 | 3521837.08
Procurement of Material & Equipment (including Stores) | 14486000 | 20013049 | 20370686.3
Construction of Facilities (Utility) | 0 | 0 | 0
Construction of Facilities (Contract) | 24456000 | 32067030 | 25348280.95
Estimated Total Cost | 47483000 | 64718425 | 60604541.06
Other (all costs not included in the above categories) |  | 0 | 0
Estimated Project Total | 47483000 | 64718425 | 60604541.06
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | 0
Engineering and Design (Contract) | 500000 | 501523 | 594751.68 | USE
Procurement of Material & Equipment (including Stores) | 4000000 | 3521325 | 3977143.27
Construction of Facilities (Utility) | 100000 | 323791 | 361070.93
Construction of Facilities (Contract) | 4150000 | 2888255 | 6341831.15
Estimated Total Cost | 8750000 | 7234894 | 11274797.03
Other (all costs not included in the above categories) | 0 | 3349399 | 0
Estimated Project Total | 8750000 | 10584293 | 11274797.03
Reported on Monthly Construction Report | 56233000 | 75302718 | 71879338.09
139510
0PT39030 SB |  | City of Tyler, Bell County

## 17T80077
Project No. 17T80077, 0PT38181, 0PT38182, 0PT38179, 0PT38178, 0PT38426, 19T63008, 0PT38517, 0PT38518 - Odessa EHV - Riverton and Moss - Riverton 345 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1180) | Estimated cost once a route is approved and CCN granted (Route 1180) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 21540000 | 29205738 | Costs not yet available
Engineering and Design (Utility) | 5322000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2269000 | 2877377 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 74495000 | 76498142 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 96103000 | 103610002 | Costs not yet available
Estimated Total Cost | 199729000 | 212191259 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 36379783 | Costs not yet available
Estimated Project Total | 199729000 | 248571042 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 245000 | 166800 | Costs not yet available
Engineering and Design (Contract) | 922857 | 908706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 15969607 | 9781320 | Costs not yet available
Construction of Facilities (Utility) | 2270494 | 479109 | Costs not yet available
Construction of Facilities (Contract) | 4424042 | 5436125 | Costs not yet available
Estimated Total Cost | 23832000 | 0 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 2068010 | Costs not yet available
Estimated Project Total | 23832000 | 18840070 | Costs not yet available
Reported on Monthly Construction Report | 223561000 | 267411112
139510
0PT39030 SB |  | City of Tyler, Bell County

## 18T80036
Project No. 18T80036, 0PT04001, 0PT38840, 0PT04138 (50% of WA) - Horseshoe Springs - Owl Hills 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 508) | Estimated cost once a route is approved and CCN granted (Route 508) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2827000 | 3662400 | 3724056.39
Engineering and Design (Utility) | 970000 | 2474576
Engineering and Design (Contract) | 1402000 | 2739308 | 2717040.26
Procurement of Material & Equipment (including Stores) | 9019000 | 13818723 | 14650878.09
Construction of Facilities (Utility) | 0 | 34819 | 37535.28
Construction of Facilities (Contract) | 19815000 | 17582835 | 19018002.76
Estimated Total Cost | 34033000 | 40312661 | 40147512.78
Other (all costs not included in the above categories) |  |  | 0
Estimated Project Total | 34033000 | 40312661 | 40147512.78
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 577700 | N/A
Engineering and Design (Utility) | 90000 | 0 | 0
Engineering and Design (Contract) | 80000 | 94300.66 | 14066.02
Procurement of Material & Equipment (including Stores) | 1752000 | 2464654.45 | 1744414.32
Construction of Facilities (Utility) | 226500 | 403438.41 | 304343
Construction of Facilities (Contract) | 602000 | 1368937.48 | 934357.25
Estimated Total Cost | 2750500 | 4909031 | 2997180.59
Other (all costs not included in the above categories) | 117500 | 154000 | 0
Estimated Project Total | 2868000 | 5063031 | 2997180.59
Reported on Monthly Construction Report | 36901000 | 45375692 | 43144693.37
139510
0PT39030 SB |  | City of Tyler, Bell County

## 17T80032
Project No. 17T80032 & 0PT04024 - Cogdell - Clairemont 138 kV Line - Transmission Line Project
*THIS IS A JOINT PROJECT WITH BRAZOS ELECTRIC POWER - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 125) | Estimated cost once a route is approved and CCN granted (Route 39) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1226000 | 2189374 | Costs not yet available
Engineering and Design (Utility) | 378500 | 900000 | Costs not yet available
Engineering and Design (Contract) | 438000 | 900000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2930000 | 3925000 | Costs not yet available
Construction of Facilities (Utility) | 0 | 1685000 | Costs not yet available
Construction of Facilities (Contract) | 5225000 | 8990000 | Costs not yet available
Estimated Total Cost | 10197500 | 18589374 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 10197500 | 18589374 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | N/A | N/A | N/A
Engineering and Design (Utility) | N/A | N/A | N/A
Engineering and Design (Contract) | N/A | N/A | N/A
Procurement of Material & Equipment (including Stores) | N/A | N/A | N/A
Construction of Facilities (Utility) | N/A | N/A | N/A
Construction of Facilities (Contract) | N/A | N/A | N/A
Estimated Total Cost | N/A | N/A | N/A
Other (all costs not included in the above categories) | N/A | N/A | N/A
Estimated Project Total | N/A | N/A | N/A
Reported on Monthly Construction Report | 10197500 | 18589374
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37302
Project No. OPT37302, 0PT38601 - Owl Hills - Tunstill POD 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 15) | Estimated cost once a route is approved and CCN granted (Route 15) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1769000 | 4038047 | Costs not yet available
Engineering and Design (Utility) | 607000 | 0 | Costs not yet available
Engineering and Design (Contract) | 830000 | 3505474 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5734000 | 8210994 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 11688000 | 11489924 | Costs not yet available
Estimated Total Cost | 20628000 | 27244439 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 20628000 | 27244439 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | N/A | N/A
Engineering and Design (Utility) | 90000 | 0 | Costs not yet available
Engineering and Design (Contract) | 0 | 14301 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1250000 | 1862654.45 | Costs not yet available
Construction of Facilities (Utility) | 155000 | 309438.41 | Costs not yet available
Construction of Facilities (Contract) | 352000 | 913937.48 | Costs not yet available
Estimated Total Cost | 1847000 | 3100331.34 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 1847000 | 3100331.34 | Costs not yet available
Reported on Monthly Construction Report | 22475000 | 30344770.34
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37182
Project No. 0PT37182, 0PT40453, OPT38505, 0PT38427- Sand Lake - Solstice 345 kV Line - Transmission Line Project
*THIS IS A JOINT PROJECT WITH AEP TEXAS - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 320) | Estimated cost once a route is approved and CCN granted (Modified Route 320) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4561500 | 10739693 | Costs not yet available
Engineering and Design (Utility) | 1058500 | 694256 | Costs not yet available
Engineering and Design (Contract) | 1348000 | 1105909 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 16793500 | 13285278 | Costs not yet available
Construction of Facilities (Utility) | 500 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25348000 | 38847631 | Costs not yet available
Estimated Total Cost | 49110000 | 64672767 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 4250011 | Costs not yet available
Estimated Project Total | 49110000 | 68922778 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 400000 | 444635 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13200000 | 17005560 | Costs not yet available
Construction of Facilities (Utility) | 1210000 | 1065160 | Costs not yet available
Construction of Facilities (Contract) | 2026000 | 4008366 | Costs not yet available
Estimated Total Cost | 16836000 | 22523721 | Costs not yet available
Other (all costs not included in the above categories) | 764000 | 0 | Costs not yet available
Estimated Project Total | 17600000 | 22523721 | Costs not yet available
Reported on Monthly Construction Report | 66710000 | 91446499
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT38174
Project No. 0PT38174 ,0PT40267 & 0PT04144 - Riverton - Kyle Ranch 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 7) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1694000 | 2387508 | Costs not yet available
Engineering and Design (Utility) | 517000 | 1258500 | Costs not yet available
Engineering and Design (Contract) | 876000 | 1300000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4866000 | 7416500 | Costs not yet available
Construction of Facilities (Utility) | 0 | 708500 | Costs not yet available
Construction of Facilities (Contract) | 11254000 | 8155000 | Costs not yet available
Estimated Total Cost | 19207000 | 21226008 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 19207000 | 21226008 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 70000 | 194717 | Costs not yet available
Engineering and Design (Utility) | 0 | 115906.71 | Costs not yet available
Engineering and Design (Contract) | 200000 | 13288.25 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1900000 | 1852954.57 | Costs not yet available
Construction of Facilities (Utility) | 120000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 750000 | 1124561.47 | Costs not yet available
Estimated Total Cost | 3040000 | 3301428 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 3040000 | 3301428 | Costs not yet available
Reported on Monthly Construction Report | 22247000 | 24527436
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT38176
Project No. 0PT38176, 0PT04088, 0PT04087, 0PT04144 - Kyle Ranch - Quarry Field 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 11) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1382000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 422000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 834000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4424000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 9770000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 16832000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 16832000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 2270000 | 2282394 | Costs not yet available
Engineering and Design (Utility) | 0 | 300000 | Costs not yet available
Engineering and Design (Contract) | 500000 | 390782 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 7700000 | 7837492 | Costs not yet available
Construction of Facilities (Utility) | 585000 | 2363273 | Costs not yet available
Construction of Facilities (Contract) | 4800000 | 5766660 | Costs not yet available
Estimated Total Cost | 15855000 | 18940601 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 19300 | Costs not yet available
Estimated Project Total | 15855000 | 18959901 | Costs not yet available
Reported on Monthly Construction Report | 32687000 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39679
Project No. 0PT39679, 0PT39819, 0PT38948 - Clear Fork - Dog House Line - NTU Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost once a route is approved and CCN granted | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1051381 | 1051381 | Costs not yet available
Engineering and Design (Utility) | 32509 | 0 | Costs not yet available
Engineering and Design (Contract) | 632401 | 641000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 7237942 | 5723710 | Costs not yet available
Construction of Facilities (Utility) | 97793 |  | Costs not yet available
Construction of Facilities (Contract) | 5169697 | 5618865 | Costs not yet available
Estimated Total Cost | 14221723 | 13034956 | Costs not yet available
Other (all costs not included in the above categories) | 82972 | 1069717 | Costs not yet available
Estimated Project Total | 14304695 | 14104673 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 10400 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 3195 | Costs not yet available
Engineering and Design (Contract) | 724600 | 132129 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3217100 | 685666 | Costs not yet available
Construction of Facilities (Utility) | 0 | 3364336 | Costs not yet available
Construction of Facilities (Contract) | 3043300 | 3413805 | Costs not yet available
Estimated Total Cost | 6995400 | 7599131 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 683383 | Costs not yet available
Estimated Project Total | 6995400 | 8282514 | Costs not yet available
Reported on Monthly Construction Report | 21300095 | 22387187
139510
0PT39030 SB |  | City of Tyler, Bell County

## NA
Project No. NA - Stiles - Coates 138 kV Line - NTU Transmission Line Project
| Estimated cost included in CCN Application (Route B4) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3347000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 249000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 733000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2070000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 222000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2915000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 9536000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 146000 | Costs not yet available | Costs not yet available
Estimated Project Total | 9682000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 161000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 84000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 893000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4376000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 432000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2780000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 8726000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 8726000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 18408000 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39835
Project No. 0PT39835, 0PT39623, 0PT39631, 0PT39632 - Ogallala - Abernathy 345 kV Line - NTU Transmission Line Project (Dkt. 48625)
| Estimated cost included in CCN Application (Route 4) | Estimated cost once a route is approved and CCN granted (Route 4a) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 13575702 | 14502458.3192 | Costs not yet available
Engineering and Design (Utility) | 165760 | 186171.1163 | Costs not yet available
Engineering and Design (Contract) | 3430680 | 3126596.9787 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 35371142 | 33506760.9081 | Costs not yet available
Construction of Facilities (Utility) | 356601 | 0 | Costs not yet available
Construction of Facilities (Contract) | 34795274 | 37485443.6777 | Costs not yet available
Estimated Total Cost | 87695159 | 88807431 | Costs not yet available
Other (all costs not included in the above categories) | 180889 | 0 | Costs not yet available
Estimated Project Total | 87876048 | 88807431 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 507200 | 441197.96 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4883800 | 4431568.67 | Costs not yet available
Construction of Facilities (Utility) | 0 | 302334.32 | Costs not yet available
Construction of Facilities (Contract) | 2913600 | 3947036.33 | Costs not yet available
Estimated Total Cost | 8304600 | 9122137.28 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 8304600 | 9122137.28 | Costs not yet available
Reported on Monthly Construction Report | 96180648 | 97929568.28
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39896
Project No. 0PT39896 - Abernathy - Wadsworth 345 kV Line - NTU Transmission Line Project (Dkt. 48668)
| Estimated cost included in CCN Application (Route 1) | Estimated cost once a route is approved and CCN granted (Route 1) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 7979470 | 9543014.7112 | Costs not yet available
Engineering and Design (Utility) | 110471 | 150723.6435 | Costs not yet available
Engineering and Design (Contract) | 1917538 | 1785293.9269 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 21275928 | 19474125.3795 | Costs not yet available
Construction of Facilities (Utility) | 202943 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25127504 | 25749200.3389 | Costs not yet available
Estimated Total Cost | 56613854 | 56702358 | Costs not yet available
Other (all costs not included in the above categories) | 122905 | 0 | Costs not yet available
Estimated Project Total | 56736759 | 56702358 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 77935 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 605500 | 359797 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5266900 | 4710275.06 | Costs not yet available
Construction of Facilities (Utility) | 0 | 236755.19 | Costs not yet available
Construction of Facilities (Contract) | 3531300 | 4250506.42 | Costs not yet available
Estimated Total Cost | 9403700 | 9635268.67 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 9403700 | 9635268.67 | Costs not yet available
Reported on Monthly Construction Report | 66140459 | 66337626.67

## 0PT39845
Project No. 0PT39845 - Wadsworth - New Oliver - Farmland 345 kV Line (WNF) and Southeast - New Oliver - Oliver 115 kV Line (SNO) - NTU Transmission Line Projects (Dkt. 48909)
| Wadworth - New Oliver - Farmland 345 kV Line |  |  |  | Southeast - New Oliver - Oliver 115 kV Line
| Estimated cost included in CCN Application (Route 20) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete |  | Estimated cost included in CCN Application (Route 9) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs: |  | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 8257000 | 11775886.9771 | Costs not yet available | Right-of-Way and Land Acquisition | 4471000 | 5164970.0609 | Costs not yet available
Engineering and Design (Utility) | 117000 | 178363.3316 | Costs not yet available | Engineering and Design (Utility) | 120000 | 62760.5556 | Costs not yet available
Engineering and Design (Contract) | 2794000 | 3791870.5499 | Costs not yet available | Engineering and Design (Contract) | 1530000 | 1649065.0706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 27393000 | 27464811.7198 | Costs not yet available | Procurement of Material & Equipment (including Stores) | 4298000 | 5126788.2332
Construction of Facilities (Utility) | 314000 | 0 | Costs not yet available | Construction of Facilities (Utility) | 216000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 28726000 | 34327428.4216 | Costs not yet available | Construction of Facilities (Contract) | 9921000 | 9448733.0797 | Costs not yet available
Estimated Total Cost | 67601000 | 77538361 | Costs not yet available | Estimated Total Cost | 20556000 | 21452317 | Costs not yet available
Other (all costs not included in the above categories) | 168000 | 0 | Costs not yet available | Other (all costs not included in the above categories) | 132000 | 0 | Costs not yet available
Estimated Project Total | 67769000 | 77538361 | Costs not yet available | Estimated Project Total | 20688000 | 21452317 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities |  | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 564000 | 1376048 | Costs not yet available | Right-of-Way and Land Acquisition | 0 | 152894.2 | Costs not yet available
Engineering and Design (Utility) | 0 | 21830.19 | Costs not yet available | Engineering and Design (Utility) | 105000 | 27328.31 | Costs not yet available
Engineering and Design (Contract) | 1617000 | 1000798.39 | Costs not yet available | Engineering and Design (Contract) | 1075000 | 635862.34 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 10517000 | 10394558.73 | Costs not yet available | Procurement of Material & Equipment (including Stores) | 25465000 | 21705484.59 | Costs not yet available
Construction of Facilities (Utility) | 0 | 497613.72 | Costs not yet available | Construction of Facilities (Utility) | 170000 | 523401.98 | Costs not yet available
Construction of Facilities (Contract) | 7940000 | 10877297.09 | Costs not yet available | Construction of Facilities (Contract) | 4433000 | 4904138.78 | Costs not yet available
Estimated Total Cost | 20638000 | 24168146.12 | Costs not yet available | Estimated Total Cost | 31248000 | 27949110.2 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 20638000 | 24168146.12 | Costs not yet available | Estimated Project Total | 31248000 | 27949110.2 | Costs not yet available
Reported on Monthly Construction Report | 88407000 | 101706507.12 | Costs not yet available | Reported on Monthly Construction Report | 51936000 | 49401427.2 | Costs not yet available

## 0PT39846
Project No. 0PT39846 - Abernathy - North - North Loop 345/115 kV Line - NTU Transmission Line Project (Dkt. 49151)
| Estimated cost included in CCN Application (Route 25) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4871000 | 8342781.3539 | Costs not yet available
Engineering and Design (Utility) | 237000 | 95753.4343 | Costs not yet available
Engineering and Design (Contract) | 2720000 | 1799694.4634 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13414000 | 14554335.7083 | Costs not yet available
Construction of Facilities (Utility) | 230000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 18124000 | 19569112.0401 | Costs not yet available
Estimated Total Cost | 39596000 | 44361677 | Costs not yet available
Other (all costs not included in the above categories) | 186000 | 0 | Costs not yet available
Estimated Project Total | 39782000 | 44361677 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 300000 | Costs not yet available
Engineering and Design (Utility) | 115000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2141000 | 610437.2 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 21621000 | 13689359.68 | Costs not yet available
Construction of Facilities (Utility) | 150000 | 506821.26 | Costs not yet available
Construction of Facilities (Contract) | 9340000 | 5167959.8 | Costs not yet available
Estimated Total Cost | 33367000 | 20274577.94 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 33367000 | 20274577.94 | Costs not yet available
Reported on Monthly Construction Report | 73149000 | 64636254.94

## 0PT38573
Project No. 0PT38573, 0PT38506, 0PT38427, 0PT38426 - Riverton - Sand Lake 345 kV Line Circuit Addition - Transmission Line Project (Phase 2)
| Estimated cost included in CCN Application | Estimated cost once a route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 0 | 648304 | Costs not yet available
Engineering and Design (Utility) | 1400000 | 281000 | Costs not yet available
Engineering and Design (Contract) | 1900000 | 485000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 12500000 | 11332089 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 13400000 | 11815254 | Costs not yet available
Estimated Total Cost | 29200000 | 24561647 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 29200000 | 24561647 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 155000 | 82677 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 665000 | 785964 | Costs not yet available
Construction of Facilities (Utility) | 78000 | 140876 | Costs not yet available
Construction of Facilities (Contract) | 287000 | 414784 | Costs not yet available
Estimated Total Cost |  | 1424301 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 29866 | Costs not yet available
Estimated Project Total | 1185000 | 1454167 | Costs not yet available
Reported on Monthly Construction Report | 30385000 | 26015814 | Costs not yet available

## 18T65163
Project No. 18T65163, 0PT04021, 0PT38449, 0PT04020 - Sargent Road - Oakland Ave. Tap 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 0 | 35000 | Costs not yet available
Engineering and Design (Utility) | 80000 | 100000 | Costs not yet available
Engineering and Design (Contract) | 440000 | 270000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 750000 | 670100 | Costs not yet available
Construction of Facilities (Utility) | 170000 | 220000 | Costs not yet available
Construction of Facilities (Contract) | 3500000 | 3165000 | Costs not yet available
Estimated Total Cost | 4940000 | 4460100 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 4940000 | 4460100 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 120000 | 0 | Costs not yet available
Engineering and Design (Contract) | 195000 | 331882 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 610000 | 595572 | Costs not yet available
Construction of Facilities (Utility) | 130000 | 153277 | Costs not yet available
Construction of Facilities (Contract) | 320000 | 343627 | Costs not yet available
Estimated Total Cost | 1375000 | 1424358 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 1375000 | 1424358 | Costs not yet available
Reported on Monthly Construction Report | 6315000 | 5884458

## 0PT39531
Project No. 0PT39531 - Bearkat (WETT) - Longshore 345 kV Line Transmission Line Project
*THIS IS A JOINT PROJECT WITH WETT - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 102) | Estimated cost once a route is approved and CCN granted (Route 69) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3125500 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 771500 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1170000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8803500 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 15469000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 29339500 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 29339500 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | Costs not yet available | N/A
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 150000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 810000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 60000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 390000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 1410000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 290000 | Costs not yet available | Costs not yet available
Estimated Project Total | 1700000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 31039500 | Costs not yet available | Costs not yet available

## 0PT41156
Project No. 0PT41156, 0PT42396, 0PT40679, 0PT41331, 0PT41511 & 0PT42120 - Johnson Draw POD - Salt Flat Road Switch 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 62000 | 175000 | Costs not yet available
Engineering and Design (Utility) | 50000 | 50000 | Costs not yet available
Engineering and Design (Contract) | 795000 | 662000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1600000 | 1600000 | Costs not yet available
Construction of Facilities (Utility) | 150000 | 150000 | Costs not yet available
Construction of Facilities (Contract) | 2600000 | 2620000 | Costs not yet available
Estimated Total Cost | 5257000 | 5257000 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 5257000 | 5257000 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 1000 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 210000 | 219023 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 610000 | 602796 | Costs not yet available
Construction of Facilities (Utility) | 170000 | 104446 | Costs not yet available
Construction of Facilities (Contract) | 470000 | 576307 | Costs not yet available
Estimated Total Cost | 1461000 | 1502572 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 1461000 | 1502572 | Costs not yet available
Reported on Monthly Construction Report | 6718000 | 6759572

## 0PT44498
Project No. 0PT38176 - Kyle Ranch - Quarry Field 138 kV Line - Transmission Line Project (Modification Of Route Approved In Docket No. 49302)
| Estimated cost included in CCN Application (Modified Route) | Estimated cost once a route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1260000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 386000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 827000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4077000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 10611000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 17161000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 17161000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | 0
Engineering and Design (Utility) | 0 | 0 | 0
Engineering and Design (Contract) | 0 | 0 | 0
Procurement of Material & Equipment (including Stores) | 0 | 0 | 0
Construction of Facilities (Utility) | 0 | 0 | 0
Construction of Facilities (Contract) | 0 | 0 | 0
Estimated Total Cost | 0 | 0 | 0
Other (all costs not included in the above categories) | 0 | 0 | 0
Estimated Project Total | 0 | 0 | 0
Reported on Monthly Construction Report | 17161000 | Costs not yet available | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County