## Specific Instructions
General Instructions for Entering Information - 2008
NOTES:
1. Please use "na" whenever appropriate to reduce ambiguity, except in the "Costs," "Percent Complete," and "Percent Variance" columns.
Column Title: | 2. Any new or revised entry must be entered using a red font. In the month following the red font entry, change the previous month's red entries back to black and make any new entries for the new month in red. This aids PUCT staff in quickly identifying any changes from the previous month’s report.
Utility's Project Number | Enter the Utility's Project Number. No duplicate numbers are allowed in this column.
Project Name | Enter the name of the project. If possible, use the same name as was reported to ERCOT in any reports.
Location (City/County) | Enter the names of the counties where the project is located. Also enter the names of cities, if appropriate. Please delineate all county and city names with commas only. (e.g., Liberty, Chambers, Anahuac, etc.)
Description | Describe the project in enough detail to allow the Commission to ensure that the work does not require a CCN, if the utility does not intend to apply for a CCN. Include any significant or relevant detail not being reported in other columns.
Estimated (or Actual) Start Date | Enter the estimated project starting date. When construction begins, please replace the estimated date with the actual date of the start of construction.
Finish Date (Construction Complete) | Enter the date (dd/mm/yy) when the construction related to the project has been completed.
Date Energized (If Applicable) | Enter the date (dd/mm/yy) the project was energized or restored to service (if applicable).
Initial Estimated Project Cost | CCN Projects Only: Enter the estimated cost from the CCN application. When reporting both T-Line and Substation Costs, enter them separately in the same cell. (e.g., "$3,946,000 T-Line; $1,768,000 Substation") This number should not be changed in future months unless the Application is amended. Please DO NOT use links to other sheets within the workbook. Non-CCN Projects Only: No entry is needed; Enter the estimated cost in the Final Estimated Cost column.
Final Estimated Project Cost | CCN Projects: Enter the latest available estimated cost for the month that construction starts. This number should not be changed after construction begins. For Non-CCN Projects: Enter the initial estimated cost. Estimate revisions are not necessary, and a cost variance explanation is not required unless requested by PUC Staff .
Final Actual Project Cost | Enter the actual, final project cost after the project has been energized and all costs have been recorded. Omit the project from all following reports.
% Variance | The cells contain a formula for calculating the percent variance of the final actual cost with respect to the final estimated cost. This is essentially a calculation of the percent of the cost over-run or under-run.
Percent Complete | State the approximate construction progress of the report as a percent. Please use only an integer and do not write"%." Do not report the percent of money spent.
Existing Voltage | Enter the nominal system existing voltage, if any. In the event of a voltage upgrade, this will be the "before" voltage. If the project is for a new line, enter "na." For projects involving multiple voltages, please delineate the voltages by a comma, e.g., "69,138" and explain further in comments or project description, if needed for clarification. Please do not write "volts."
Upgraded or New Voltage | Enter the nominal system voltage after upgrading or if new line construction is involved. Please use the same practices described in the"Existing Voltage" column. Please do not write "volts."
Circuit Length (Miles) | Enter the total circuit length. Example: For a new double-circuit line using 10 miles of new ROW, the circuit length would be 20 miles. Please enter only a number, if possible. Please do not write "miles."
Conductor Type & Size & Bundling | Describe the conductor characteristics, including whether double or single circuit or mixed. Length explanations should be made in the Project Description column.
Structure Type(s) | Describe structure types and materials used.
Existing ROW Width (Feet) | Enter width of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Entries such as "60,80,100" or "60 - 100" or "centerline" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
Existing ROW Length (Miles) | Enter length of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Make detailed explanations, if needed, elsewhere. Please do not write "miles."
New ROW Width (Feet) | Enter width of new ROW. The entry type is unrestricted. Entries such as "60,80,100" or "60 - 100" or "centerline" or "railroad" or "street" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
New ROW Length (Miles) | Enter new (additional) ROW length, in miles. Please do not write "miles."
Rule Section or PUC Control Number | Enter the PUC Rule 25.101 section(s) which are applicable. For multiple section applicability, please delineate by commas, e.g., "25.101(c)(5)(A),25.101(c)(5)(B)" for a project incorporating a line extension (A) and a voltage upgrade on the existing line which is being extended(B). If the project is approved under a CCN, please enter ONLY the 5-digit control number. Please do not write "docket," "CCN" or other indicators. Should the project encompass work done under both CCN and exempted sections, follow the same practices and delineate with commas.
Comments | Enter information not included elsewhere, including reimbursed costs, references to any required Affidavits of Notice or Landowner Consent statements, etc.
Note on A18: aboling: If applicable.

## Sugg.Practices(TabNotOnWebsite)
SUGGESTED SPREADSHEET PRACTICES
VERY IMPORTANT: Any new or revised entry MUST be entered using a red font. In the month following the red font entry, change the previous month's red entries back to black and make any new entries for the new month in red. This aids PUCT staff in quickly identifying any changes from the previous month’s report.
Please enter your Utility Name and Month in the top center header. Also, please enter the appropriate data in the bottom left footer. Your personal contact information WILL NOT appear in the report posted at the PUC website. Please do not change the right-hand header and footer.
Adjust Row and Column Heights and Widths to a pleasing dimension as you wish. Vertical centering is recommended to improve readability when using the "Wrap Text" Feature.
Please do not use multiple Rows for any project. Each project should occupy only one line. If necessary, however, multiple project numbers may be entered in the same cell in the "Project Number" column. Use the "Wrap Text" feature throughout the spreadsheet and the "Row Height Autofit" feature for all lines except for the header.
Never enter identical project numbers in the "Project Number" column. If your internal practices split a project into multiple parts, use distinguishing suffixes, such as 103668XYA and 103668XYB.
If a project number has not been assigned for a project, please create one (a "dummy") to use in your construction reports, rather than leaving the cell empty. Continue using that project number, revising later if you like, but please use red font in the "Project Number" cell to indicate any change in the number.
Please do not insert extra rows between projects. PUCT staff must delete any extra lines to properly compile report data.
Please do not enter “NA” or any other text in the "Estimated," "Final" or "% Variation" numerical columns. Text in those columns must be manually removed before PUC staff can compile the report.
A percent variation calculation formula is contained within the "% VAR." column. Please leave this formula as it is. However, if you copy & paste data and overwrite those cells, don't worry about it.
In the "Rule Section...." column, enter the PUC assigned docket number (if project requires a CCN) or the PUC exemption qualifying section or sections (if the project is exempt from CCN requirements). Do not enter "EXEMPT."
Monthly Construction Progress Reports may be found at the PUCT website. Individual utility MCPR worksheets for each utility are contained within each month's compiled report at: http://www.puc.state.tx.us/electric/reports/cpr/index.cfm.
Please contact Allen Boling at (512)936-7402 or allen.boling@puc.state.tx.us for assistance or clarification, including questions (or advice) about MS Excel spreadsheets.
For Subst. Rule §25.83(c)(3) notice compliance purposes, the PUC contact will be Allen Boling, at (512) 936-7402 or (888) 782-8477. Hearing and speech-impaired individuals with text telephones (TTY) may contact Mr. Boling at (512) 936-7136 or Relay Texas at (800) 735-2989.
Suggested Language (after providing utility contact information with the utility as the primary contact): "In the event you have unresolved questions or complaints after discussing these activities with (utility name), you may contact Allen Boling at the PUCT, at P.O. Box 13326, Austin, Texas 78711-3326, or call Mr. Boling at (512)936-7402 or (888)782-8477 or by e-mail at allen.boling@puc.state.tx.us. Hearing and speech-impaired individuals with text telephones (TTY) may contact Mr. Boling at the PUCT and (512)936-7136 or Relay Texas at (800)735-2989."

## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
STE07519 | IH45-DELANEY RD | Galveston County | Raise line over IH45 TXDOT Request | 2019-10-01 |  |  |  | 650000 |  |  | 96% | 138 | N/A | 0 | 795 | STEEL | N/A | N/A |  |  | 25.101(c)(5)(B) | In Construction
STE09120 | Rebuild Heights to PHR Line 3 | Galveston County | Rebuild trans line from Heights Sub to PH Robinson | 2019-12-09 |  |  |  | 14500001 | 13440561 | -7.306% | 100% | 138 | 138 | 7.27 | 636 bundled | STEEL | 80 | 7.27 | N/A | N/A | 25.101(c)(5)(B) | Complete
STE09220 | Rebuild Freeway Park to PHR Line 6 | Galveston County | Rebuild trans line from Freeway Park Sub to PH Robinson | 2019-12-09 |  |  |  | 11964070 |  |  | 98% | 138 | 138 | 4.9 | 636 bundled | STEEL | 80 | 4.9 | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE02720 | Glen Rose Sub Rebuild | Sommervell County | C/Out and upgrade existing XFMRS upgrade distribution bays, add oil containment | 2019-12-09 | 2020-12-28 |  |  | 5500000 |  |  | 99% | 69 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE03020 | Gomez Substation 138kV Converstion | Reeves County | Convert existing Gomez Substation to a 138kV Substation | 2020-06-19 |  |  |  | 3200000 |  |  | 60% | 69 | 138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE09120 | Pecos Main 138kV Switch Yard (1) | Reeves County | upgrade switchyard 138k conversion | 2020-05-01 | 2020-12-15 |  |  | 10500000 | 9694714 | -7.669% | 100% | 69 | 138 | n/a | n/a |  | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Complete
NTE08317 | Pig Creek South Modification- v01 | Reeves County | Tie in the 138kv line from Tarbush to AEP's Pig Creek Station | 2021-01-05 | 2021-02-12 |  |  | 1000001 |  |  | 99% | 138 | 138 | 0.25 | 1926 ACSS | STEEL | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE08020 | Convert Lonestar Line to 138kV | Ward County | This project is necessary to convert the area transmission system from 69kV to 138kV | 2020-06-23 | 2021-05-28 |  |  | 5130000 | 5939836 | 15.79% | 100% | 69 | 138 | 5.5 | 1926 ACSS | STEEL | 30 | 5.5 | 80 | 5.5 | 25.101(c)(5)(B) | Complete
STE09020 | Attwater Switching Station & TLine | Galveston County | Build a new switching station and tie line to interconnect the TOPAZ Generation Plant | 2020-08-01 |  |  |  | 11850000 |  |  | 99% | N/A | 138 | 1 | 2x - 795ACSS | Steel Monopole | N/A | N/A | 40 | 0.5 | 25.101(c)(5)(B) | Pending final charges
STE03020 | West Cloumbia Local | BRAZORIA COUNTY | Station rebuild | 2020-06-15 |  |  |  | 8736000 |  |  | 98% | 138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
STE07620 | West Columbia Local T-Line | BRAZORIA COUNTY | Reroute existing T-Line into sub rebuild | 2020-11-16 |  |  |  | 1300000 |  |  | 99% | 138 | 138 | N/A | 636 ACSR | Steel/Concrete | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE07821 | Rebuild Line E Pecos Main-Cedarvale | Ward County | Line rebuild | 2021-02-01 | 2021-04-30 |  |  | 2975873 |  |  | 99% | 138 | 138 | 7.5 | 959 ACSS | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE07921 | Rebuild Line D Pecos Main-Cedarvale | Ward County | Line rebuild | 2021-09-15 | 2021-07-12 |  |  | 2976223 |  |  | 10% | 138 | 138 | 7.5 | 959 ACSS | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE08021 | Rebuild Line M-138-A Wink-Oncor Wink | Winkler County | Line rebuild | 2021-03-08 | 2021-05-14 |  |  | 1249191 |  |  | 99% | 138 | 138 | 0.5 | 1926 ACSS | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE08121 | Convert Line M-69-A Wink-Oncor Wink to 138kV | Winkler County | Convert line from 69kV to 138kV | 2021-03-08 | 2021-05-15 |  |  | 1073459 |  |  | 99% | 69 | 138 | 0.5 | 959 ACSS | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE02621 | Swoose II ESR - Pyote Sub | Ward County | Adding line terminal to connect customer battery storage | 2021-01-04 |  |  |  | 2092000 |  |  | 95% | 138 | n/a | n/a | n/a | n/a | N/A | N/A | N/A | N/A |  | In Construction
NTE02721 | Flower Valley II ESR - Flat Top Sub | Reeves County | Adding line terminal to connect customer battery storage | 2021-01-04 |  |  |  | 2092000 |  |  | 95% | 138 | n/a | n/a | n/a | n/a | N/A | N/A | N/A | N/A |  | In Construction
NTE03119 | install 20 MVA XFMR @ Pyote | Reeves County | adding transformer and distrubution bay | 2021-01-04 |  |  |  | 3171574 |  |  | 99% | 138 | n/a | n/a | n/a | n/a | N/A | N/A | N/A | N/A |  | Pending final charges
NTE09121 | 16th St to Soaptree Line Rebuild | Pecos County | rebuild line | 2021-01-04 |  |  |  | 20933521 |  |  | 99% | 138 | n/a | n/a | n/a | n/a | N/A | N/A | N/A | N/A |  | Pending final charges
NTE02121 | County Road XFMR #3 | Reeves County | adding transformer and distrubution bay | 2021-01-04 |  |  |  | 3190722 |  |  | 99% | 138 | n/a | n/a | n/a | n/a | N/A | N/A | N/A | N/A |  | Pending final charges
NTE02821 | Elm St XFMR #3 | Reeves County | adding transformer and distrubution bay | 2021-01-04 |  |  |  | 3192164 |  |  | 99% | 138 | n/a | n/a | n/a | n/a | N/A | N/A | N/A | N/A |  | Pending final charges
NTE08421 | Cedarvale-Sand Lake Double Ckt | Ward County | Install 1 mile of double ckt 138kV | 2021-03-29 | 2021-05-14 |  |  | 1950813 |  |  | 99% | N/A | 138 | 1 | 1926 ACSS & 959 ACSS | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE08521 | Rebuild Wink-Kermit#1 10 miles | Winkler County | Line rebuild | 2021-09-16 |  |  |  | 4996002 |  |  |  | 69 | N/A | 10 | 795 ACSR | Steel/Concrete | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pre-Construction
STE02216 | Butler Rd T3 Addition | Galveston County | Install 2nd xfmr and distran | 2021-02-01 | 2021-06-04 |  |  | 3192702 |  |  | 99% | N/A | 138 | N/A | N/A | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
STE02421 | Seminole T2 Addition | Galveston County | Install 2nd xfmr and distran | 2021-01-06 | 2021-06-05 |  |  | 3190633 |  |  | 99% | N/A | 138 | N/A | N/A | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE07322 | Rebld Convert Ft StocktonSw to Plant (Leon Creek-Airport) | Pecos County | Line rebuild | 2021-09-16 |  |  |  | 8009058 |  |  |  | 138 | 138 | 2 | 1926 ACSS | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pre-Construction
NTE07221 | Rebld Convert Ft Stockton Sw to Tarbush (Tarbush-Leon Creek) | Pecos County | Line rebuild | 2021-03-31 |  |  |  | 7026595 |  |  | 75% | 69 | 138 | 18 | 1926 ACSS | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE08921 | White Baker Line Terminal | Pecos County | add line terminal | 2021-04-01 |  |  |  | 3500000 |  |  | 68% | 138 | N/A | N/A | N/A | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
STE05321 | ALVIN SUB | BRAZORIA COUNTY | High side rebuild add terminal | 2021-03-01 |  |  |  | 12451446 |  |  | 40% | 138 | N/A | N/A | N/A | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
STE09517 | Alvin-freeway Park | Brazoria/Galveston | T-Line rebuild | 2021-02-08 |  |  |  | 22000000 |  |  | 55% | 138 | N/A | 17.38 | 795 ACSS | Steel | 60 | 17.38 | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE07721 | Sanderson Heavy Maint | Pecos County | STR C/OUT | 2021-04-01 |  |  |  | 2525826 |  |  | 75% | 69 | N/A | N/A |  | CONCRETE | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE07711 | Walnut Springs to Glen Rose Heavy Maint. | Bosque/Sommervell | STR C/OUT | 2021-08-15 |  |  |  | 2519838 |  |  | 20% | 69 | N/A | N/A | N/A | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
STE02321 | Angleton Sub Gambit Terminal Addition | BRAZORIA COUNTY | Line Terminal | 2021-01-15 |  |  |  | 1625584 |  |  | 99% | 138 | N/A | N/A | N/A | Steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
STE07521 | Angleton Gambit T-Line | BRAZORIA COUNTY | Transmission Line | 2021-02-15 |  |  |  | 1645026 |  |  | 99% | 138 | 138 | 0.41 | 795 ACSS | Steel | 60 | 0.41 | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
TXG02421 | Power Transformer Asset Mgmt | Brazoria, Galveston, Pecos County | Power XFMR replacements due to age/major costly repairs/pgrades | 2021-04-30 |  |  |  | 6000376 |  |  | 85% |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
STE07421 | Phillips 5 Substation Relay Upgrade | Brazoria County | Relay Protection Upgrade | 2021-02-01 |  |  |  | 997160 |  |  | 5% |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
STE07621 | Transmission Switch Replacementst | Brazoria County | Transmission Switch upgrade as part of the TNMP System Assessment to eliminate ERCOT identify contingencies | 2021-02-01 |  |  |  | 750861 |  |  | 5% |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE07621 | Climax 2nd Source-Thistle Switching Station | Collin County | Construct new Thistle Switching Station | 2021-03-29 |  |  |  | 8703247 |  |  | 40% |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE08721 | New Switching Station Airport Tarbush Tie | Pecos County | Construct the initial phase of Leon Creek Switching Station | 2021-01-01 |  |  |  | 6463817 |  |  | 75% |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE02421 | Airport Substation 2nd XFMR | Pecos County | Add a second power transformer at Airport Station for reliability purposes | 2021-01-01 |  |  |  | 3520216 |  |  | 40% |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE03021 | Tarbush Line South Terminal | Pecos County | Build new 138kv line terminal at Tarbush to connect Tarbush and planned Leon Creek station | 2021-01-01 |  |  |  | 2183004 |  |  | 95% | [9 empty] | 25.101(c)(5)(B) | In Construction
STE02621 | Freeway Park 138kv BRKR Replacement | Galveston County | Replace BRKR's at Freeway Park Sub with 138KV BRKRS | 2021-01-15 |  |  |  | 452602 |  |  | 98% |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
STE02721 | Byrd Ranch-Energy Resource | Brazoria County | New metered 138kv line terminal to comply with Interconnection agreement with Byrd Ranch | 2021-01-15 |  |  |  | 1687199 |  |  | 50% |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE08511 | Pyote-Jup Swoose II ESR Trans Line | Ward County | add transmission line between Pyote Sub and Jup Swoose II ESR | 2021-04-01 |  |  |  | 399612 |  |  | 99% |  | 138 | 0.1 | 795 ACSR | CONCRETE | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE08611 | Flat Top-Jup Flower Valley ESR Trans line | Reeves County | add transmission line between Flat Top Sub and Jup FV ESR | 2021-04-01 |  |  |  | 399000 |  |  | 99% |  | 138 | 0.1 | 795 ACSR | CONCRETE | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pending final charges
NTE07411 | St.Jo-Nocona line Rebuild | Montague County | replace existing H-frame structures with steel monopoles | 2021-04-15 |  |  |  | 2966162 |  |  | 40% |  | 69 | 5.7 miles | 4/0 kcmil | steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE07419 | Graham to Bryson | Young County | replace existing wood pole structures with steel monopoles | 2021-07-15 |  |  |  | 2231222 |  |  | 5% |  | 69 | 2 miles | 2/0 KCMIL 6/1 "QUAIL" ACSR | steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE08011 | Petrolia T-line Heavy Maintenance | Clay County | replace existing wood pole structures with steel monopoles | 2021-06-15 |  |  |  | 2401802 |  |  | 5% |  | 69 | 4.26 miles | 1/0 6/1 ACSR | steel | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | In Construction
NTE03221 | Cholla T-2 Transformer addition | Ward County | adding transformer and distrubution bay | 2021-08-05 | [6 empty] | 0% | 138 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25.101(c)(5)(B) | Pre-Construction
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on L7: Woods, Melanie: MARCH $9,563,791 APRIL $9,657,465