## MCPR Aug. 2021
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | MCPR Row Number | Project Manager
1014910 | TXDOT US 83 Relief Route Rio Grande City-La Grulla (T485) | Starr | Modify existing transmission line (T485), Rio Grande City-La Grulla, to accommodate road expansion by TXDOT. | 2018-11-09 | 2018-11-30 | 2018-11-30 |  | 266000 |  |  | 100 | 138 | 138 | 31.66 | 3x1-795 ACSR/AW "Drake/AW" | Steel Poles | Varies | 31.6 | n/a | n/a | 25.101 (C)(5)(B) |  | 5 | Ellie Ross
1014352 | Leander - Round Rock TL Addition (CCN) | Williamson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to two load-serving substations | 2019-01-02 | 2020-06-04 | 2020-06-04 | T-Line $49 - 81.6M; Substations $ 7M - 10.1M |  |  |  | 100 | 0 | 138 | 14.22 | 3x2- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 60 - 100 | 11-22 | 45866 | 6/6/17 PUC Approved Route LHO-1; approved route cost estimate in CCN application for transmission line $57.6M; substation 1 - $9M; substation 2 - $7M | 7 | Michael Griswold
1017348 | Cooks Point TL Addition (CCN) | Burleson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2020-07-01 | 2021-06-30 | 2021-06-30 | T-Line $ 26.5 - 34.1M; Substation $ 6.1 - 6.7M |  |  |  | 100 | 0 | 138 | 17-23 | 2x1- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 80 | 17-23 | 45838 | 6/17/19 - PUC Approved Route 12; approved route cost estimate in CCN application for transmission line $29M; substation $6.2M | 48 | Manny Garcia
1016356 | Bellville S - Glidden TL Addition (T113) (Bellville S-Glidden TL Storm Hardening - 1016355) | Austin County/Colorado | Replace 11 lattice tangent tower structures with steel pole structures to meet storm hardening requirements; the existing rating of the transmission circuit will be maintained at 110 MVA. | 2018-08-23 | 2019-09-20 | 2019-09-20 |  | 10029000 |  |  | 100 | 69 | 69 | 31.24 | Existing: (1)795 ACSR “Drake” New: Bellville-Str 26 (1)959 ACSS “Suwannee” and Str.27-Glidden (1)795 ACSR “Drake” | Bellville-Str.26 Concrete H-Frame and Steel DE Str. 27-Glidden Steel DE, Lattice Towers, and concrete tangents | 120 | 31.24 | 120 | 31.24 | 25.101 (C)(5)(B) |  | 49 | Thuanny Anderson
1017513 | Airline - Naval Base TL Addition (T475) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-09-24 | 2019-09-30 | 2019-09-30 |  | 993000 |  |  | 100 | 69 | 138 | 6.39 | (1) 795kcl ACSR/AW "Drake" | Steel Monopole | Centerline; 16 | 6.39 | n/a | n/a | 25.101 (C)(5)(D) |  | 57 | Ellie Ross
1017515 | Airline - Naval Base TL Addition (T476) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-03-28 | 2019-04-16 | 2019-04-16 |  | 331000 |  |  | 100 | 69 | 138 | 7.98 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 7.98 | n/a | n/a | 25.101 (C)(5)(D) |  | 58 | Ellie Ross
1018756 | Heines - Naval Base TL Addition (T685) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. (Once Heines Substation Addition is complete, the transmission assets on (T476) will be renumbered to T685 Heines - Naval Base) | 2018-10-03 | 2020-05-07 | 2020-05-07 |  | 894000 |  |  | 100 | 69 | 138 | 5.3 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 5.3 | n/a | n/a | 25.101 (C)(5)(A) |  | 59 | Enayatullah Sharifi
1018755 | Airline - Heines TL Addition (T476) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. | 2018-10-11 | 2020-05-07 | 2020-05-07 |  | 994000 |  |  | 100 | 69 | 138 | 2.57 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 2.57 | n/a | n/a | 25.101 (C)(5)(A) |  | 60 | Enayatullah Sharifi
1018663 | Rio Pecos - Horse Crossing TL Addition (T682) [Horse Cross - Rio Pecos TL Add - 1018600] | Crane | Provide transmission service to a generator. (This circuit will be added to the open position on the structures on the existing (T451) Rio Pecos - Crane, after the project is complete the transmission line will be numbered T682 Rio Pecos - Horse Crossing) | 2021-01-08 17:00 | 2021-05-28 | 2021-06-01 |  | 1871000 |  |  | 100 | 0 | 138 | 0.76 | (2) 795 ACSR Drake | Steel/Concrete Monopoles | 80; Centerline | 0.76 | n/a | n/a | 25.101 (C)(5)(C) |  | 61 | Manny Garcia
1018662 | Rio Pecos - Crane TL Addition (T451) [Horse Cross - Rio Pecos TL Add - 1018600] | Crane | Provide transmission service to a generator. Add fiber on existing T451 between Rio Pecos and Horse Crossing Substation | 2020-12-11 | 2021-05-03 | 2021-06-01 |  | 108000 |  |  | 100 | 138 | 138 | 8.29 | (2)795 ACSR/GA2 "Drake" (1)AFL DNO-11243 | Concrete & Steel poles | 80 | 8.29 | n/a | n/a | 25.101 (C)(5)(C) |  | 267 | Manny Garcia
1019260 | Winchester - Salem T170 TL Addition (T170) (Winchester Autotransformer Addition - 1017413) | Fayette | Install new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-03-25 | 2020-03-25 17:00 |  | 2287000 |  |  | 100 | 138 | 138 | 37.28 | (1) 795 kcl ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100; Centerline | 37.16 | n/a | n/a | 25.101 (C)(5)(A) |  | 62 | Jack Sandel
1017777 | Winchester - Fayetteville TL Addition (T165) (Winchester Autotransformer Addition - 1017413) | Fayette | Install new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-03-26 17:00 | 2020-03-26 17:00 |  | 2535000 |  |  | 100 | 138 | 138 | 18.92 | (1) 795 kcl ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100; Centerline | 18.75 | n/a | n/a | 25.101 (C)(5)(A) |  | 63 | Jack Sandel
1019038 | Plum - La Grange TL Addition (T208) (Riverside Circuit Breaker Addition - 1018925) | Fayette | Increase the reliability of substation equipment at the Riverside Substation. | 2019-01-28 | 2020-12-30 | 2020-10-20 |  | 1873000 |  |  | 100 | 138 | 138 | 8.39 | 795 ACSR. GA2 Drake. 3/8 EHS. OPGW | Wood H-frame | Undefined Centerline | 5.58 | Undefined Centerline | 5.58 | 25.101 (C)(5)(B) |  | 66 | Tyreeta Young
1016702 | Altair - Nada TL Addition (T545) (Glidden Area TL Upgrade - 1016219) | Colorado | OPGW (fiber) installation (T545) and Substation upgrade at Nada and Altair substations from 69kV to 138kV | 2018-12-03 | 2019-05-31 | 2019-05-31 |  | 7068000 |  |  | 100 | 69 | 138 | 14.12 | 795 Drake ASCR & 26/7 & Single | Steel, Wood, & Lattice | Blanket | 14.12 | Blanket | 14.1 | 25.101 (C)(5)(B) |  | 72 | Manny Garcia
1019321 | Lakeway - Marshall Ford T179 Addition (T179) (Lakeway AE Marshall Ford TL SH - 1019096) | Travis | Increase the reliability of circuit (T179) on the Lakeway (AE) – Marshall Ford 2.4 le138 kV transmission line. | 2019-01-25 | 2019-06-21 17:00 | 2019-06-21 |  | 3172000 |  |  | 100 | 138 | 138 | 2.4 | (6x1) 795 ACSR "Drake" | Steel Towers | 100 | 2.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 73 | Amir Toor
1019603 | Lakeway - Marshall Ford Fiber Addition (T179) (LCRA Fiber Backbone FY 19 Telecom Upgrade - 1019084) | Travis | Install 2.42 miles of 72-count OPGW from Lakeway (AE) to Marshall Ford (T179). | 2019-02-13 | 2019-06-21 08:00 | 2019-06-21 |  | 648000 |  |  | 100 | 138 | 138 | 2.4 | (6x1) 795 ACSR "Drake" | Steel Towers | 100 | 2.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 74 | Amir Toor
1019317 | Rockport - Fulton T474 TL Addition (T474) Hurricane Response System Upgrade - 1019095 | Nueces, Aransas | Increase reliability, repair storm damage, & upgrade circuit (T477) on the N Padre Tap-Port Aransas 18.23-le 69-kV TL and circuit (T474) on the Fulton-Rockport 138-kV 7.36-le 69-kV TL. | 2019-02-07 | 2019-09-23 | 2019-09-23 |  | 3836000 |  |  | 100 | 69 | 69 | 7.4 | (1x) 795 ACSR/AW Drake | Steel Monopole, Concrete Monopole | Unknown (AEP-owned) | - | - | - | 25.101 (C)(5)(B) |  | 76 | Robert Badger
1017557 | Deer Creek - Luling TL Addition (T538) (Darst Creek Circuit Breaker Addition - 1017352) | Guadalupe | Add four 138-kV, 3000A, 40kAIC circuit breakers in a ring bus configuration to Darst Creek substation | 2019-02-22 | 2019-05-23 | 2019-05-23 |  | 1104000 |  |  | 100 | 69 | 69 | 15.84 | Drake 795 ACSR, Single | Concrete & Steel | Blanket | 15.84 | Blanket | 15.84 | 25.101 (C)(5)(B) |  | 77 | Manny Garcia
1019133 | Rim Rock - Turtle Creek TL Addition (T270) (Rim Rock - Turtle Creek TL Storm Hardening - 1018968) | Kerr | Increase the reliability of circuit (T270) on the Rim Rock - Turtle Creek 7.6 le 138kV transmission line | 2020-09-16 | 2021-05-05 17:00 | 2021-05-05 |  | 11350000 |  |  | 100 | 138 | 138 | 7.6 | (1x) 795 ACSR Drake | Steel Monopole | 60; 100 | 7.6 | 60; 100 | 7.6 | 25.101 (C)(5)(B) |  | 79 | Jacob Miller
1018599 | Bakersfield - Solstice TL Addition (CCN) | Pecos | Construct a new 345-kV transmission line to connect LCRA TSC's existing Bakersfield station and AEP Texas' Solstice Switch Station | 2020-01-07 | 2020-12-17 | 2020-12-17 | T-line $148 - $192M; Bakersfield Substation - $6M; Solstice Switch Station (AEP) - $38M |  |  |  | 100 | 0 | 345 | 130-190 | 1926.9 kcl ACSS/Cumberland (LCRA TSC) and 1590 ACSS (AEP Texas) | Double-circuit steel lattice towers | 0 | 0 | 150 | 68 - 92 | 48787 | 5/28/19 PUC Approved Route 24; approved route cost estimate in CCN application for transmission line $155.9M; LCRA TSC's Bakersfield substation $6.5M; AEP's Solstice Switch Station $38.4M | 82 | Glenn Brunson
1017897 | Culberson - Kunitz TL Addition (T271) (Culberson-KunitzTL Overhaul - 1017896) | Culberson | Structure replacement upgrades to steel and concrete Poles | 2019-05-28 | 2020-06-01 | 2020-06-01 10:46 |  | 2015000 |  |  | 100 | 138 | 138 | 28.88 | Linnet; 336kcl; 0.721” | Wood | 100 | 28.88 | n/a | n/a | 25.101 (C)(5)(B) |  | 83 | Danny Hartsell
1019319 | N. Padre Tap - Port A. (T-477) (Hurricane Response System Upgrade - 1019095) | Nueces | Increase the reliability, repair storm damage, and upgrade circuit (T477) on the North Padre Tap – Port Aransas 18.23-le 69-kV transmission line and circuit (T474) on the Fulton – Rockport 138-kV 7.36-le 69-kV transmission line. | 2019-10-14 | 2019-12-20 | 2019-12-27 |  | 3748000 |  |  | 100 | 69 | 69 | 15 | 795 ACSS/AW Drake x1 | Steel monopole, Concrete Monopole, Hybrid Steel/Concrete | (AEP-owned) | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 89 | Robert Badger
1019337 | Elroy - Wolf Lane (T-582) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-03-18 | 2019-05-13 | 2019-05-13 |  | 2078000 |  |  | 100 | 138 | 138 | 3.78 | 795 Drake ACSR GA2 | Wood H-frame, LD Steel H-frame, Steel Pole, Tower | 100 | 3.78 | n/a | n/a | 25.101 (C)(5)(B) |  | 90 | Robert Badger
1020260 | Red Creek - Amos Creek TL Addition (T424) (Amos Creek Substation Addition - 1020230) | Concho | Transmission line cut-in to provide transmission service to a generator. | 2019-09-03 | 2020-03-12 13:48 | 2020-03-12 13:48 |  | 2630000 |  |  | 100 | 345 | 345 | 49 | 1590 ACSR Falcon x2 | Steel Lattice tower | 100 | 49 | n/a | n/a | 25.101 (C)(5)(B) |  | 91 | Robin Mims
1019327 | Austrop - Garfield (T182) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-04-15 | 2019-11-22 | 2019-11-27 |  | 4182000 |  |  | 100 | 345 | 345 | 8.33 | Bundled 795 ACSR "Drake" | Lattice Tower | 170; Centerline | 8.33 | n/a | n/a | 25.101 (C)(5)(B) |  | 92 | Robert Badger
1019374 | Marshal Ford - McNeil T161 TL Addition (T161) (Marshall Ford-McNeil TL Relocation - 1019212) | Travis | Increase transmission service reliability to the Austin Energy Hamilton Substation. | 2019-05-01 | 2019-06-12 | 2019-06-12 |  | 1893000 |  |  | 100 | 69 | 69 | 13.4 | 4/0 & 795 kcl ACSR | Lattice Towers & Steel Poles | 100 | 13.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 93 | Robert Badger
1021300 | Granite Mountain – Marble Fall TL Upgrade [Marble Falls Double Circuit TL Upgrade - 1020559] | Burnet | Increase the reliability of transmission facilities on the T195 Granite Mountain – Marble Falls 4.1-le 138-kV transmission line | 2019-11-01 | 2020-04-03 17:00 | 2020-04-03 17:00 |  | 4204000 |  |  | 100 | 138 | 138 | 4.08 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies 80; 100 | 4.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 95 | Tony Rhodes
1016579 | Fair Oaks Ranch - Esperanza TL Addition (T503) [Esperanza Substation Addition - 1016187] | Kendall | LCRA TSC will build a 138kV substation and cut-in T503 to provide transmission/ metering services and real-time monitoring facilities | 2019-09-06 | 2019-10-25 | 2019-10-25 |  | 1179000 |  |  | 100 | 138 | 138 | 8.25 | Single 795 kcl ACSR | Steel Poles | 100 | 8.11 | 80 | 8.25 | 25.101 (C)(5)(B) |  | 96 | Robin Mims
1019301 | Kendall - Comfort T243 TL Addition (T243) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-le 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-le 138-kV transmission circuit (T243) | 2019-10-21 | 2020-02-03 | 2020-01-31 |  | 2658000 |  |  | 100 | 138 | 138 | 1.08 | Bundled 959.6 SUWANNEE ACSS/TW | Steel Single Poles/ Tower/ Steel H-frame | 100 | 1.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 99 | Tyreeta Young
1019303 | BoerneCico - Comfort T148 TL Addition (T148) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-le 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-le 138-kV transmission circuit (T243) | 2019-09-03 08:00 | 2020-05-11 | 2020-05-11 |  | 8237000 |  |  | 100 | 138 | 138 | 16.93 | Bundled 795 DRAKE ACSR | Steel Single Poles | 100 | 16.93 | n/a | n/a | 25.101 (C)(5)(B) |  | 100 | Tyreeta Young
1018934 | Fayetteville - Winchester TL Upgrade (T165) [Fayetteville-Winchester TL Upgrade - 1018933] | Fayette | Increase capacity and capability of circuit T165 on the Fayetteville – Winchester 138-kV upgrade | 2019-09-01 | 2020-03-23 17:00 | 2020-03-23 17:00 |  | 15240000 |  |  | 100 | 138 | 138 | 18.9 | 1433 kcl ACSS/TW Merrimack | steel monopoles | 100 | 18.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 101 | Amir Toor
1019122 | Giddings - Lyle Wolz TL Addition (T155) [Lexington CB Addition - 1018914] | Lee | Add two new structures to accommodate substation expansion. Increase transmission service reliability to the Lexington Substation. | 2019-08-12 | 2019-10-01 | 2019-10-01 |  | 360000 |  |  | 100 | 138 | 138 | 21 | 795 ASCR | steel monopoles | 100 | 21 | n/a | n/a | 25.101 (C)(5)(B) |  | 102 | Vaibhav Pitale
1017394 | Mountain Home TL Addition (CCN) | Kerr, Gillespie, Kimble | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2021-08-27 | 2022-12-27 17:00 |  | T-line $46.5 - $58.5M; Substation $7.1 - $7.5M |  |  |  | 0 | 0 | 138 | 21-29 | 795 Kcl 26/7 ACSR “Drake” | tbd; steel or concrete poles | 0 | 0 | varies; 100 | 21-29 | 49523 | 7/6/20 - PUC Approved Route Hunt 37A; approved route cost estimate in CCN application for transmission line $47M; substation $7.3M | 103 | Bradley Wallner
1019026 | Fayetteville - Glidden TL Addition (T176) [Fayette Area TL Upgrades - 1018913] | Fayette, Colorado | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) | 2019-09-16 | 2020-05-14 | 2020-05-14 |  | 14488000 |  |  | 100 | 138 | 138 | 20.02 | Single 959.6 ACSS/TW Suwannee & Single OPGW (AFL DNO-11243) Static | Steel Monopoles, Hybrid H-Frames | 100 | 20 | n/a | n/a | 25.101 (C)(5)(B) |  | 105 | Hooman Larimi
1020270 | Amos Creek - Bow Wood TL Addition (T709) [Amos Creek Substation Addition - 1020230 ] | Concho, Tom Green | Provide transmission service to a generator | 2019-09-03 | 2020-03-12 09:36 | 2020-05-14 |  | 335000 |  |  | 100 | 138 | 138 | 49.33 | (2x) - 1590 kcl ACSR Falcon | Steel Lattice, Steel monopole | 160 | 49.33 | n/a | n/a | 25.101 (C)(5)(B) |  | 106 | Robin Mims
1019325 | McNeil - Gilleland Creek (T147) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2020-01-20 | 2020-03-31 17:00 | 2020-03-31 17:00 |  | 1989000 |  |  | 100 | 138 | 138 | 7.62 | 1433.6 ACSS/TW "MERRIMACK" / Single | Steel Monopoles & Tower | 100 | 7.62 | n/a | n/a | 25.101 (C)(5)(B) |  | 107 | Robert Badger
1019341 | Paige - Winchester TL Addition (T615) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Bastrop | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-09-23 | 2019-12-18 | 2020-05-14 |  | 3339000 |  |  | 100 | 138 | 138 | 14.85 | Bundled Linnit and Single Drake | Steel Mono Pole, Wood H-Frames, Concrete # Poles | 100 | 14.85 | n/a | n/a | 25.101 (C)(5)(B) |  | 108 | Robert Badger
1019335 | Wells Branch - Round Rock (T527) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis, Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-09-16 | 2019-11-01 | 2019-11-01 |  | 1555000 |  |  | 100 | 138 | 138 | 5.28 | (2) 795 KCL ACSR/GA2 “DRAKE” | Steel/concrete Pole, Concrete H-Frame | 100 | 5.28 | n/a | n/a | 25.101 (C)(5)(B) |  | 109 | Robert Badger
1017767 | Sim Gideon - Winchester TL Addition (T152) [Winchester Autotransformer Additions - 1017413] | Bastrop | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 986000 |  |  | 100 | 138 | 138 | 20.74 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (75;100) | 20.74 | Varies (75;100) | 20.84 | 25.101 (C)(5)(B) |  | 110 | Jack Sandel
1017769 | Smithville - Winchester TL Addition (T175) [Winchester Autotransformer Additions - 1017413] | Bastrop | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 737000 |  |  | 100 | 138 | 138 | 15.1 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (80; 100) | 15.1 | Varies (80; 100, Aerials to 180) | 14.7 | 25.101 (C)(5)(B) |  | 111 | Jack Sandel
1017771 | Winchester - Piney Creek TL Addition (T186) [Winchester Autotransformer Additions - 1017413] | Fayette | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-03-18 17:00 | 2020-05-14 |  | 709000 |  |  | 100 | 138 | 138 | 1.38 | Single 1433.6 54/19 ACSR/TW Merrimack/TW | Lattice Towers & Steel Poles | 100 | 1.38 | 100 | 1.59 | 25.101 (C)(5)(B) |  | 112 | Jack Sandel
1017773 | Winchester - Giddings TL Addition (T222) [Winchester Autotransformer Addition - 1017413] | Bastrop | Install new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-03-17 | 2020-05-14 |  | 837000 |  |  | 100 | 138 | 138 | 10.51 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies 75; 100 | 10.51 | Varies 75; 100 | 10.68 | 25.101 (C)(5)(B) |  | 113 | Jack Sandel
1017775 | Paige - Winchester TL Addition (T615) [Winchester Autotransformer Additions - 1017413] | Lee | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 850000 |  |  | 100 | 138 | 138 | 14.83 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | 100; Centerline | 14.83 | 100; Centerline | 15.09 | 25.101 (C)(5)(B) |  | 114 | Jack Sandel
1018759 | Crane - Rio Pecos TL Addition (T451) [Castle Mountain Substation Addition - 1018744] | Upton, Crane | Cut-in T451 to a new substation, Provide transmission service (new Castle Mountain substation) for Solar Prime LLC. | 2019-09-05 | 2020-03-27 17:00 | 2020-05-14 |  | 463000 |  |  | 100 | 138 | 138 | 0.4 | Bundled 795 ACSR Drake, Single 3/8 EHS Static & Single DNO-11243 OPGW | Steel Monopole Dead End | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 115 | Dave Ilges
1017649 | LaGrange - FPP 138kV TL Addition (T263) [FPP 138kV - La Grange TL Overhaul - 1017648] | Fayette | Increase the reliability and capability of circuit T263 on the FPP 138kV – La Grange 7.9-le 138-kV transmission line | 2020-01-02 | 2020-05-15 | 2020-05-15 17:00 |  | 4096000 |  |  | 100 | 138 | 138 | 7.89 | Single 795 ACSR Drake & 2 OPGW (AFL DNO-11243) & (ALCOA 52 OPT-GW) | Steel Monopole Dead Ends, Wooden H-Frame Tangents | 100 | 7.8 | n/a | n/a | 25.101 (C)(5)(B) |  | 116 | Jacob Miller
1019333 | Round Rock - Chief Brady (T378) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-11-01 | 2019-11-18 | 2019-11-18 |  | 1174000 |  |  | 100 | 138 | 138 | 1.2 | (1) 795 ACSR/GA2 "Drake"; RR AF to #55B has (2) 959 ACSS/TW HS "Suwannee" | steel H-frame, steel lattice | 100; Centerline | 1.2 | n/a | n/a | 25.101 (C)(5)(B) |  | 117 | Robert Badger
1019329 | Chief Brady - Georgetown (T355) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-12-16 | 2020-03-02 | 2020-03-02 |  | 2469000 |  |  | 100 | 138 | 138 | 3.17 | (1) 795 ACSR/GA2 "Drake" | Steel Lattice and pole, Steel H-Frame | 100 | 3.0 | n/a | n/a | 25.101 (C)(5)(B) |  | 118 | Robert Badger
1019339 | Georgetown - Rivery (T597) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2020-01-31 | 2020-11-30 | 2020-11-18 |  | 2591000 |  |  | 100 | 138 | 138 | 5.1 | (1) 795 ACSR/GA2 "Drake" | steel H-frame, concrete pole, steel pole | 50 Centerline; blanket | 5.10 | n/a | n/a | 25.101 (C)(5)(B) |  | 119 | Robert Badger
1021975 | Altair - Glidden TL Addition (T544) [Kleimann (Columbus) CB Addition - 1018910] | Upton, Crockett | Increase reliability of transmission facilities on the T544 Glidden-Altair 12.22-le 69-kV TL. | 2019-11-18 | 2020-02-10 | 2020-05-14 |  | 1365000 |  |  | 100 | 69 | 138 | 3.33 | 795 ACSR Drake, single | Steel & Concrete monopoles | 80; Blanket | 12.41 | 80; Blanket | n/a | 25.101 (C)(5)(B) |  | 120 | David Marshall
1017538 | Goforth-Turnersville TL Addition (T272) [Crosswinds Substation Addition-1017349] | Hays | Acquire 7.5 acres and expand new LCRA TSC facilities with a three-ring bus configuration | 2020-03-10 | 2020-05-14 | 2020-05-14 |  | 1038000 |  |  | 100 | 138 | 138 | 3.77 | 795 ACSR Drake, single | Lattice, Wood H-frame, Steel monopole | 100 | 6.69 | 100 | 3.77 | 25.101 (C)(5)(B) |  | 121 | Andres Villegas
1017540 | Crosswinds-Goforth TL Addition (T661) [Crosswinds Substation Addition-1017349] | Hays | Acquire 7.5 acres and expand new LCRA TSC facilities with a three-ring bus configuration | 2020-03-10 | 2020-05-14 | 2020-05-14 |  | 10000 |  |  | 100 | 138 | 138 | 3.31 | 795 ACSR Drake, single | Wood H-frame, Steel monopole | 100 | n/a | 100 | n/a | 25.101 (C)(5)(B) |  | 123 | Andres Villegas
1014015 | Camp Wood - Leakey TL Addition (T269) [Camp Wood - Leakey TL Overhaul - 1016183] | Real | Increase the reliability of transmission facilities on the T269 Camp Wood-Leakey 17.3 le 69-kV transmission line and upgrade the line to 795 ACSR Drake conductor (111 MVA at 69-kV), 138-kV capable with an OPGW shield wire. | 2020-11-30 17:00 | 2021-06-30 | 2021-06-30 |  | 43428000 |  |  | 100 | 69 | 138 | 17.32 | Single 795 ACSR Drake | Steel & Lattice | Varies; 60 | 17.32 | n/a | n/a | 25.101 (C)(5)(B) |  | 125 | Sarah Wilson
1019114 | Zorn - Pooley Rd TL Addition (T158) [Luling-Zorn TL Overhaul - 1019113] | Guadalupe | Increase the reliability of transmission facilities on the T373 Schulenburg - Glidden 20.25- | 2020-02-03 | 2021-08-31 | 2021-05-06 |  | 7228000 |  |  | 95 | 138 | 138 | 28.02 | 795 ACSR Drake | Concrete and Steel poles | 100 | 28.02 | n/a | 28.02 | 25.101 (C)(5)(B) |  | 126 | Vaibhav Pitale
1020454 | Harris Branch - McNeil TL Relocation/Addition (T146) [Harris Branch - McNeil TL Relocation - 1020379] | Travis | Provide transmission service reliability improvements | 2020-02-20 | 2020-05-07 | 2020-05-07 |  | 1408000 |  |  | 100 | 138 | 138 | 6.87 | 795 ACSR Drake. | Steel Lattice Tower and Monopole | 100 | 6.87 | 100' | n/a | 25.101 (C)(5)(B) |  | 128 | Bradley Wallner
1022277 | Roma - Rio Grande City TL Addition (T465) [Escobares Substation Addition - 1022173] | Starr | Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Escobares Substation. Provide a transmission point of interconnection. | 2020-10-19 | 2021-02-04 | 2021-02-04 |  | 2327000 |  |  | 100 | 138kV | 138kV | 13.7 | (1) Drake ACSR | Steel Monopoles | Varies 50; 80 | 12.7 | Varies;40-100 | 0.5 | 25.101 (C)(5)(B) |  | 129 | Glenn Brunson
1022830 | Giddings - Warda TL Addition (T137) [Gidding-Warda TL Upgrade - 1022731] | Fayette, Lee | Increase the reliability of transmission facilities on the T137 Giddings - Warda 9.66-le 69-kV transmission line by converting the line to 138-kV operation and increasing the transmission capacity. | 2020-04-01 | 2020-10-19 12:00 | 2020-10-16 |  | 12383000 |  |  | 100 | 0kv (De-energized) | 138kv | 9.66 | (1) 959.6 ACSS "Suwannee" | Steel and Concrete Monopoles | 100 | 9.66 | 100 | n/a | 25.101 (C)(5)(B) |  | 130 | Manny Garcia
1021401 | Burnet - Lampasas TL Addition (T219) [Andice-Bertram-Burnet TL Upgrade - 1021209] | Burnet, Lampasas | Upgrade and reconfigure Burnet Substation to facilitate the Pedernales Electric Cooperative project to upgrade and convert the Andice-Bertram-Burnet 69-kV transmission line to 138-KV operation | 2020-03-15 | 2021-05-14 | 2021-05-11 |  | 2456000 |  |  | 100 | 138 | 138 | 23.3 | Single 795 ACSR Drake | Wood H-frames | Centerline | 23.3 | Centerline | n/a | 25.101 (C)(5)(B) |  | 131 | Haley Jewell
1020552 | Burnet - Lampasas TL Addition (T219) [Burnet-Lampasas TL Overhaul - 1020371] | Burnet, Lampasas | Increase the reliability of transmission facilities on the T219 Burnet - Lampasas 23.4-le 138-kV transmission line. | 2020-03-15 | 2021-10-01 | 2021-05-11 |  | 19159000 |  |  | 100 | 138 | 138 | 23.3 | Single 795 ACSR Drake | Wood H-frames | Centerline | 23.3 | Centerline | n/a | 25.101 (C)(5)(B) |  | 132 | Haley Jewell
1019285 | T271 TL Addition (T271) [Pinnacle Substation Addition - 1019007] | Culberson | LCRA TSC will build a new substation (Pinnacle) adjacent to T271 to interconnect the new 186.3 MW solar generation facility. Replace transmission structures to allow for substation cut-in and upgraded conductor and OPGW. | 2020-01-29 | 2020-10-14 17:00 | 2020-10-14 17:00 |  | 10800000 |  |  | 100 | 69 | 138 | 18.1 | Single 1433 ACSS/TW Merrimack | Steel monopole | 100 | 18.1 | 100 | n/a | 25.101 (C)(5)(B) |  | 134 | Jeremy Svagdis
1017435 | Elgin Sw - Gilleland Creek TL Addition (T421) [Kimbro Substation Addition - 1017433] | Travis, Williamson | Provide transmission service to generator. | 2020-04-06 17:00 | 2021-04-30 | 2021-02-26 |  | 853000 |  |  | 100 | 138 | 138 | 12.9 | (1) per phase Merrimack ACSS | Steel Dead-end Monopole | 100 | 12.9 | NA | NA | 25.101 (C)(5)(B) |  | 135 | Vaibhav Pitale
1016698 | Glidden - Altair TL Addition (T544) [Glidden Area TL Upgrade - 1016219] | Colorado | Increase the capacity and reliability of transmission facilities on the Glidden-Altair 12.2 le 69-kV transmission line (T544) and the Altair-Nada 14.12 le 69-kV transmission line (T545). | 2021-08-19 | 2021-09-10 |  |  | 858000 |  |  | 0 | 138 | 138 | 12.2 | 795 ACSR Drake | Steel & Concrete | 80 | 12.2 | 80 | 12.3 | 25.101 (C)(5)(B) |  | 136 | Danny Hartsell
1016491 | Cushman - Hwy 123 TL Addition (T572) [Meadow Lake Substation Addition - 1016198] | Guadalupe | Provide transmission service along with metering and real-time monitoring facilities for GVEC's new Meadow Lake Substation. Replace structure #30 with two large angle dead end structures to route T572 into and out of the new LCRA/GVEC owned Meadow Lake. | 2020-08-17 17:00 | 2020-12-21 | 2020-12-18 |  | 658000 |  |  | 100 | 138 | 138 | 6.48 | Single 795 ACSR Drake | Steel Monopole | 80 | 6.48 | n/a | n/a | 25.101 (C)(5)(B) |  | 137 | Robin Mims
1023677 | Asherton - Bevo TL Addition (T603) [Asherton - Bevo TL Relocation - 1022882] | Dimmit | Relocate dead-end structure #1 on the T603 Bevo to Asherton 138-kV transmission line to outside of the AEP-owned Asherton Substation. Re-route and re-ternate T603 to a new point-of-interconnection (POI) structure owned by AEP and installed by AEP outside of the Asherton Substation. | 2021-11-01 | 2021-12-22 |  |  | 447000 |  |  | 0 | 138 | 138 | 8.05 | (1) 795 Drake ACSR | Steel monopoles | AEP owned | AEP owned | AEP owned | AEP owned | 25.101 (C)(5)(B) |  | 139 | Glenn Brunson
1016493 | Cushman - Meadow Lake TL Addition (T647) [Meadow Lake Substation Add - 1016198] | Guadalupe | Provide transmission service along with metering and real-time monitoring facilities for GVEC's new Meadow Lake Substation. | 2020-08-17 17:00 | 2020-12-21 | 2020-12-18 |  | 643000 |  |  | 100 | 138 | 138 | 3.6 | Single 795 ACSR Drake | Steel monopole | 80 | 3.6 | n/a | n/a | 25.101 (C)(5)(B) |  | 140 | Robin Mims
1020445 | HiCross - Turner TL Addition (T143) [HiCross-Turner TL Storm Harden-1020386] | Travis, Hays | Increase the reliability of transmission facilities on the T143 Hi Cross - Turnersville 8.8-le 138-kV transmission line. | 2020-06-03 08:00 | 2021-04-06 | 2021-04-06 |  | 5618000 |  |  | 100 | 138 | 138 | 7.9 | bundled 795 ACSR Drake | Concrete and Steel monopoles | 100 | 7.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 141 | Sarah Wilson
1022213 | Hi-Cross - Turnersville TL Addition (T143) [LCRA Fiber Backbone FY20 - 1021196] | Travis, Hays | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2020-11-09 08:00 | 2021-04-06 | 2021-04-06 |  | 1065000 |  |  | 100 | 138 | 138 | 7.9 | bundled 795 ACSR Drake | Concrete and Steel monopoles | 100 | 7.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 142 | Sarah Wilson
1019265 | Fayetteville - Bellville S TL Addition (T216) [New Bremen CB Add - 1018919] | Austin, Colorado, Fayette | Increase the reliability of transmission facilities on the T216 Fayetteville – Bellville South 28.19-les 138-kV transmission Line | 2021-05-03 17:00 | 2021-05-06 | 2021-05-06 |  | 416000 |  |  | 100 | 138 | 138 | 0.5 | 1433.6 ACSS MERRIMACK | Steel Pole | 100 | 0.05 | n/a | n/a | 25.101 (C)(5)(B) |  | 143 | Tyreeta Young
1021775 | Twin Buttes - Brown (T551) TL Addition [Amos Creek Circuit Breaker Addition - 1021517] | Tom Green, Concho | Cut-in T551 to existing substation to provide transmission services to a generator | 2020-10-07 | 2020-11-24 | 2020-11-19 |  | 1147000 |  |  | 100 | 345 | 345 | 88.3 | 1590 ACSR Falcon Bundled | Steel Pole | 160 | 88.3 | n/a | n/a | 25.101 (C)(5)(B) |  | 144 | Robin Mims
1023668 | Gabriel - Glasscock TL Addition (T359) [Gabriel Substation Upgrade - 1020410] | Williamson | LCRA TSC will upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-05-19 | 2022-09-16 |  |  | 361000 |  |  | 15 | 138 | 138 | 6.59 | Single 795 ACSR Drake | Steel Pole | 80 | 6.59 | n/a | n/a | 25.101 (C)(5)(B) |  | 146 | Dave Ilges
1021176 | Gabriel - Jarrell TL Addition (T224) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-09-16 |  |  | 1083000 |  |  | 15 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B) |  | 147 | Dave Ilges
1021174 | Gabriel - Georgetown East TL Addition (T223) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-09-16 |  |  | 1083000 |  |  | 15 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B) |  | 148 | Dave Ilges
1023667 | Gabriel - Rivery TL Addition (T457) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-05-19 | 2022-09-16 |  |  | 361000 |  |  | 15 | 138 | 138 | 2.43 | Bundled 795 ACSR Drake | Steel Pole | Varies | 2.43 | n/a | n/a | 25.101 (C)(5)(B) |  | 149 | Dave Ilges
1023966 | Fairland - Lago Vista TL Addition (T414) [Transmission Connector Shunt NORTH - FY 2020 System Upgrade - 1023813] | Burnet, Travis | Improve the reliability of transmission facilities by installing transmission connector shunts on the 12.6-le Coronado-Fairland, 5-le Lakeway-Marshall Ford and 21.4-le Fairland-Lago Vista 138-kV transmission lines. | 2020-06-23 | 2020-07-28 | 2020-07-21 17:00 |  | 668000 |  |  | 100 | 138 | 138 | 21 | 795 Condor ACSR 795 Drake ACSR | Lattice Towers | 100 | 21 | n/a | n/a | 25.101 (C)(5)(B) |  | 150 | Jeremy Svagdis
1023967 | Coronado - Fairland TL Addition (T110) [Transmission Connector Shunt NORTH - FY 2020 System Upgrade - 1023813] | Burnet, Llano | Improve the reliability of transmission facilities by installing transmission connector shunts on the 12.6-le Coronado-Fairland, 5-le Lakeway-Marshall Ford and 21.4-le Fairland-Lago Vista 138-kV transmission lines. | 2020-06-01 | 2020-11-05 | 2020-06-12 17:00 |  | 415000 |  |  | 100 | 138 | 138 | 12.4 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | 100 | 12.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 151 | Jeremy Svagdis
1023949 | Fayetteville - Salem TL Addition (T177) [Transmission Connector Shunt EAST - FY 2020 System Upgrade - 1023812] | Austin, Washington, Fayette | Improve the reliability of transmission facilities by installing transmission connector shunts on the 19.3-le double circuit consisting of FPP Yard #1-Salem 345-kV and Fayetteville-Salem 138-kV transmission lines. | 2020-09-14 17:00 | 2020-09-17 | 2020-09-17 |  | 246000 |  |  | 100 | 138 | 138 | 19.32 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | Varies | 19.32 | n/a | n/a | 25.101 (C)(5)(B) |  | 152 | Jeremy Svagdis
1023948 | FPP Yard #1 - Salem TL Addition (T211) [Transmission Connector Shunt EAST - FY 2020 System Upgrade - 1023812] | Austin, Washington, Fayette | Improve the reliability of transmission facilities by installing transmission connector shunts on the 19.3-le double circuit consisting of FPP Yard #1-Salem 345-kV and Fayetteville-Salem 138-kV transmission lines. | 2020-09-14 17:00 | 2020-09-17 | 2020-09-17 |  | 459000 |  |  | 100 | 345 | 345 | 27.43 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | Varies | 27.43 | n/a | n/a | 25.101 (C)(5)(B) |  | 153 | Jeremy Svagdis
1023901 | Lockhart - Luling TL Addition (T184) [transmission Connector Shunt SOUTH - FY 2020 System Upgrade - 1023814] | Caldwell | Improve the reliability of transmission facilities by installing transmission connector shunts on the 16.8-le Lockhart-Luling and 17.1-le Lockhart-Red Rock 138-kV transmission lines. | 2020-07-15 | 2020-08-05 | 2020-08-05 |  | 119000 |  |  | 100 | 138 | 138 | 16.83 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers, Wood H-Frames | Varies | 16.83 | n/a | n/a | 25.101 (C)(5)(B) |  | 154 | Jeremy Svagdis
1023918 | Lockhart - Red Rock TL Addition (T578) [transmission Connector Shunt SOUTH - FY 2020 System Upgrade - 1023814] | Bastrop, Caldwell | Improve the reliability of transmission facilities by installing transmission connector shunts on the 16.8-le Lockhart-Luling and 17.1-le Lockhart-Red Rock 138-kV transmission lines. | 2020-07-15 | 2020-08-06 | 2020-08-06 |  | 133000 |  |  | 100 | 138 | 138 | 17.11 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers, Wood H-Frames | Varies | 17.11 | n/a | n/a | 25.101 (C)(5)(B) |  | 155 | Jeremy Svagdis
1014165 | Goldthwaite - Lampasas TL Addition (T128) [Goldthwaite - Lampasas TL Overhaul - 1015217] | Mills, Hamilton, Lampasas | Increase the reliability of circuits T128 & T672 on the Goldthwaite - Lampasas 49.77-le 138-kV transmission line. | 2020-07-01 | 2021-05-16 | 2021-05-13 |  | 4617000 |  |  | 100 | 138 | 138 | 23.74 | Single 795 Drake ACSR | Steel poles, Steel & Wood Hframes | 100; Centerline | 23.74 | n/a | n/a | 25.101 (C)(5)(B) |  | 156 | Robert Badger
1021428 | Sherwood Shores - Coronado TL Addition (T635) [Coronado-Sherwood Shores TL SH - 1021211] | Burnet | Increase the reliability of circuit T635 on the Coronado – Sherwood Shores 12.2-le 138-kV transmission line | 2020-09-14 08:00 | 2022-05-14 17:00 |  |  | 12145000 |  |  | 5 | 138 | 138 | 12.15 | Single 795 Drake ACSR | Steel Poles/Steel Lattice | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 157 | Robert Badger
1020467 | Gabriel - Rivery TL Addition (T457) [Gabriel-Rivery TL SH - 1019092] | Williamson | Increase the capacity and reliability of circuit T457 on the Gabriel – Rivery 2.4-le 138-kV transmission line | 2020-11-02 | 2021-07-30 | 2021-05-15 |  | 7622000 |  |  | 100 | 138 | 138 | 2.43 | Bundled 795 Drake ACSR | Steel Poles | 40;100 | 2.4 | 60; 80;120; 130;150 | 2.4 | 25.101 (C)(5)(B) |  | 158 | Tolu Odunlami
1019172 | Turtle Creek - Hunt TL Addition (T240) [Turtle Creek Substation Upgrade - 1018970] | Kerr | Increase Reliability to the Turtle Creek substation | 2020-09-09 08:00 | 2020-10-06 | 2020-10-06 17:00 |  | 519000 |  |  | 100 | 138 | 138 | 0.1 | Single 336 ACSR Linnet | Wood poles | n/a | n/a | 80 (Temporary) | 0.1 (Temporary) | 25.101 (C)(5)(B) |  | 160 | Jacob Miller
1019170 | Turtle Creek - Verde Creek TL Addition (T221) [Turtle Creek Substation Upgrade - 1018970] | Kerr | Increase Reliability to the Turtle Creek substation | 2020-09-09 08:00 | 2020-11-14 | 2020-11-16 |  | 1119000 |  |  | 100 | 138 | 138 | 0.1 | Single 336 ACSR Linnet | Wood poles | n/a | n/a | 80 (Temporary) | 0.1 (Temporary) | 25.101 (C)(5)(B) |  | 161 | Jacob Miller
1023941 | Evant - Lampasas TL Addition (T672) [Goldthwaite–Lampasas TL OH - 1015217] | Lampasas, Coryell | Increase the reliability of circuits T128 & T672 on the Goldthwaite - Lampasas 49.77-le 138-kV transmission line. | 2020-07-01 | 2021-03-15 | 2021-03-15 |  | 5412000 |  |  | 100 | 138 | 138 | 26.02 | Single 795 Drake ACSR | Steel poles, Steel & Wood Hframes | 100; Centerline | 26.02 | n/a | n/a | 25.101 (C)(5)(B) |  | 162 | Robert Badger
1024000 | Lakeway - Marshall Ford TL Addition (T180) [transmission Connector Shunt North-FY 2020 System Upgrade - 1023813] | Travis | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-07-27 | 2020-07-28 | 2020-07-28 |  | 57000 |  |  | 100 | 138 | 138 | 0.27 | Single 795 Condor ACSR/SD | Lattice Towers | 100 | 0.27 | n/a | n/a | 25.101 (C)(5)(B) |  | 163 | Jeremy Svagdis
1024054 | FPP - Lytton T255 TL Repair Addition [FPP Yard 2 - Lytton Springs transmission Line Upgrade - 1024058] | Fayette | Replace damaged equipment on the T255 FPP Yard #2 – Lytton Springs transmission line and increase the reliability of the line by installing new transmission line structure components and replacing original REDWING conductor with bundled Drake conductor. | 2020-04-17 | 2020-10-23 | 2020-05-18 |  | 4024000 |  |  | 100 | 345 | 345 | 61.1 | Bundled 715.5 Redwing ACSR; top phase between structures #30 to #77 Bundled 795 Drake ACSR | Lattice | 100 | 61.1 | n/a | n/a | 25.101 (C)(4) |  | 164 | Jack Sandel
1020874 | Fayetteville - Frelsburg TL Addition (T176) [Frelsburg Circuit Breaker Addition 1020378] | Fayette, Colorado | Increase transmission service reliability to the Frelsburg Substation. | 2020-08-10 | 2021-03-03 | 2021-03-03 |  | 892000 |  |  | 100 | 138 | 138 | 20.06 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11243 (1)3/8" EHS Steel | Steel monopoles | 125; 75 Centerline | 20.06 | n/a | n/a | 25.101 (C)(5)(B) |  | 165 | Bradley Wallner
1019024 | Plum - Flatonia TL Addition (T133) [Fayette Area TL Upgrades - 1018913] | Fayette | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) and the Flatonia to Plum 138-kV transmission circuit (T133). | 2020-09-08 | 2021-05-14 | 2021-05-14 |  | 10196000 |  |  | 100 | 138 | 138 | 19.63 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11242 (1)3/8" EHS Steel | Single pole and H-Frame (Steel, Wood, Concrete) | 100 | 19.53 | n/a | n/a | 25.101 (C)(5)(B) |  | 166 | Hooman Larimi
1020876 | Fayetteville - Mockingbird TL Addition (T714) [Frelsburg Circuit Breaker Addition 1020378] | Fayette, Colorado | Increase transmission service reliability to the Frelsburg Substation. | 2020-08-10 | 2021-03-03 | 2021-03-03 |  | 44000 |  |  | 100 | 138 | 138 | 10.2 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11243 (1)3/8" EHS Steel | Steel monopoles | 75 | 10.2 | n/a | n/a | 25.101 (C)(5)(B) |  | 167 | Bradley Wallner
1020465 | Gabriel - Glasscock TL Addition (T359) [Gabriel - Glasscock TL Storm Hardening - 1019091] | Williamson | Increase the reliability and capability of circuit T359 on the Gabriel - Glasscock 6.6-le 138-kV transmission line. | 2020-10-27 | 2021-04-09 | 2021-04-07 |  | 4412000 |  |  | 100 | 138 | 138 | 6.59 | Single 795 ACSR Drake | Single Steel Monopoles | 80 | 6.59 | n/a | n/a | 25.101 (C)(5)(B) |  | 168 | Tolu Odunlami
1021444 | Paleface - Miller Creek TL Addition (T124) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Travis, Hays, Blanco, | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124 and replacing four structures | 2020-08-03 | 2021-08-26 |  |  | 3764000 |  |  | 20 | 138 | 138 | 17 | Single 795 ACSR Drake | Single Steel Monopoles | 80 | 17 | n/a | n/a | 25.101 (C)(5)(B) |  | 169 | Robert Badger
1019263 | Bevo - Rosita Creek TL Addition (T463) [Dimmit CB Addition - 1018912] | Maverick, Dimmit | Increase the reliability of transmission facilities on the T463 Rosita Creek – Bevo 47.63-le 138-kV transmission line. | 2021-03-02 | 2021-11-12 17:00 |  |  | 1539000 |  |  | 60 | 138 | 138 | 36.85 | Single 795 ACSR Drake | Steel monopoles | Centerline | 36.85 | n/a | n/a | 25.101 (C)(5)(B) |  | 170 | Tolu Odunlami
1022229 | T626 TL Addition [LCRA Fiber Backbone FY20 - 1021196] | Travis | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-05-25 | 2021-05-28 | 2021-05-28 |  | 580000 |  |  | 100 | 138 | 138 | 0.92 | 795 ACSR "Drake" 3/8" EHS Steel AFL DNO-11243 AFL ADSS "AC0729C621BE1" | Steel Lattice, H-frame, poles | 100 | .92 | n/a | n/a | 25.101 (C)(5)(B) |  | 171 | Sarah Wilson
1023975 | Bergheim – Kendall TL Addition (T656) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-23 | 2020-12-10 | 2020-12-10 |  | 490000 |  |  | 100 | 345 | 345 | 27.23 | Bundled 795 ACSR/SD Condor | Lattice Tower | 100 | 27.23 | n/a | n/a | 25.101 (C)(5)(B) |  | 172 | Jeremy Svagdis
1023976 | Bergheim – Hays Energy TL Addition (T389) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Hays | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-11-04 | 2020-12-15 | 2020-12-15 |  | 765000 |  |  | 100 | 345 | 345 | 34.18 | Bundled 795 ACSR/SD Condor | Lattice Tower | 100 | 34.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 173 | Jeremy Svagdis
1023982 | Bergheim – Fair Oaks TL Addition (T238) Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 59000 |  |  | 100 | 138 | 138 | 4.08 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 4.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 174 | Jeremy Svagdis
1023980 | Esperanza – Fair Oaks Ranch TL Addition (T503) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-05 | 2020-12-01 | 2020-12-01 |  | 73000 |  |  | 100 | 138 | 138 | 4.36 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 4.36 | n/a | n/a | 25.101 (C)(5)(B) |  | 175 | Jeremy Svagdis
1023977 | Kendall – Welfare TL Addition (T584) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-23 | 2020-11-03 | 2020-11-03 |  | 100000 |  |  | 100 | 138 | 138 | 10.16 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 10.16 | n/a | n/a | 25.101 (C)(5)(B) |  | 176 | Jeremy Svagdis
1023979 | Boerne – Esperanza TL Addition (T657) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-30 | 2020-10-02 | 2020-10-02 |  | 110000 |  |  | 100 | 138 | 138 | 3.9 | Single 795 ACSR/SD Condor | Lattice Tower | 85 | 3.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 177 | Jeremy Svagdis
1023978 | Boerne – Welfare TL Addition (T228) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-28 | 2020-09-30 | 2020-09-30 |  | 150000 |  |  | 100 | 138 | 138 | 9.5 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 9.5 | n/a | n/a | 25.101 (C)(5)(B) |  | 178 | Jeremy Svagdis
1023986 | Highway 46 – River Oaks TL Addition (T518) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-11-04 | 2020-11-04 | 2020-11-04 |  | 100000 |  |  | 100 | 138 | 138 | 8.64 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B) |  | 179 | Jeremy Svagdis
1023987 | River Oaks - Henne TL Addition (T237) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-21 | 2020-10-22 | 2020-10-22 |  | 78000 |  |  | 100 | 138 | 138 | 3.79 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 3.79 | n/a | n/a | 25.101 (C)(5)(B) |  | 180 | Jeremy Svagdis
1023983 | Antler – Bergheim TL Addition (T493) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-09 | 2020-11-18 | 2020-11-18 |  | 123000 |  |  | 100 | 138 | 138 | 7.18 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 7.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 181 | Jeremy Svagdis
1023985 | Antler – Highway 46 TL Addition (T610) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-19 | 2020-11-13 | 2020-11-13 |  | 132000 |  |  | 100 | 138 | 138 | 10.4 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 10.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 182 | Jeremy Svagdis
1021481 | Brenham - Highway 36 Substation (T468) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2020-08-06 | 2020-11-05 | 2020-11-05 |  | 895000 |  |  | 100 | 138 | 138 | 2.3 | (1)959.6 ACSS Suwannee TW (1)3/8" EHS Steel NEW (1)AFL DNO-11243 | Steel/Concrete Single pole & H-Frame | Centerline; 75 | 2.3 | n/a | n/a | 25.101 (C)(5)(B) |  | 183 | Robert Badger
1021465 | Brenham - Salem TL Addition (T199) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2020-09-14 | 2020-12-17 | 2020-12-17 |  | 725000 |  |  | 100 | 138 | 138 | 3.18 | 959.6 kcmil ACSS/TW | Steel H-frame | 100 | 3.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 184 | Robert Badger
1022278 | Pooley Rd - Luling TL Addition (T712) [Luling - Zorn TL Overhaul - 1019113] | Guadalupe, Caldwell | Increase the reliability of transmission facilities on T158 | 2020-08-17 08:00 | 2021-08-31 | 2021-05-06 |  | 3723000 |  |  | 95 | 138 | 138 | 28.02 | (1) 795 ACSR Drake | Steel & Concrete SC Monopoles | Centerline; 80-100 | 28.02 | n/a | n/a | 25.101 (C)(5)(B) |  | 187 | Vaibhav Pitale
1024067 | Sim Gideon - Bastrop TL Addition (T172) [Sim Gideon - Structure 13 TL Upgrade 1023964] | Bastrop, Travis | Increase the reliability of transmission facilities on the T171 Austrop – Sim Gideon and T172 Bastrop – Sim Gideon 2.6-mile 138-kV double-circuit transmission line by removal and replacement of Structure #4 and Structure #5. | 2020-09-21 | 2020-12-18 | 2020-12-18 |  | 568000 |  |  | 100 | 138 | 138 | 4.15 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 4.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 188 | Aldo Romero
1024084 | Sim Gideon - Austrop TL Addition (T171) [Sim Gideon - Structure 13 TL Upgrade 1023964] | Bastrop, Travis | Increase the reliability of transmission facilities on the T171 Austrop – Sim Gideon and T172 Bastrop – Sim Gideon 2.6-mile 138-kV double-circuit transmission line by removal and replacement of Structure #4 and Structure #5. | 2020-09-21 | 2020-12-18 | 2020-12-18 |  | 572000 |  |  | 100 | 138 | 138 | 15.61 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 15.61 | n/a | n/a | 25.101 (C)(5)(B) |  | 189 | Aldo Romero
1023421 | Sim Gideon - Austrop T171 TL Addition (T171) [Austrop-Sim Gideon Str 7 TL SH-1024417] | Bastrop, Travis | Reduce the flood risk and potential for damage to substation equipment on T547 Altair - Eagle Lake and T171 Sim Gideon - Austrop transmission lines. | 2020-10-26 | 2020-12-18 | 2020-12-18 |  | 254000 |  |  | 100 | 138 | 138 | 15.61 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 15.61 | n/a | n/a | 25.101 (C)(5)(B) |  | 190 | Jack Sandel
1024055 | Lincoln T731 TL Addition (T731) [Lincoln Substation Upgrade - 1022729] | Lee | Provide transmission service/reactive power support to new load at the Lincoln Substation. LCRA TSA will construct a new 138-kV transmission line from the existing Lincoln Substation to the new point of interconnect at the Enterprise Substation. | 2020-09-23 | 2020-09-25 | 2020-09-25 |  | 1160000 |  |  | 100 | 0 | 138 | 0.03 | 3x1 795 DRAKE ACSR | Concrete Dead-end | n/a | n/a | BBEC Owned within Sub. | BBEC Owned within Sub. | 25.101 (C)(5)(B) |  | 191 | Manny Garcia
1021973 | T723 Motorman-Upton TL Addition (T723) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2022-09-10 | 2023-03-10 |  |  | 679000 |  |  | 0 | 138 | 138 | 17.97 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 17.97 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 192 | Glenn Brunson
1023799 | T441 LCRACrane-Motorman TL Addition (T441) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2022-09-10 | 2023-03-10 |  |  | 16000 |  |  | 0 | 138 | 138 | 12.16 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 30.14 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 193 | Glenn Brunson
1019051 | McCarty Ln-Hilltop T375-TL Addition (T375) [Ranch Road 12 CB Addition - 1018923] | Hays | Increase the reliability of transmission facilities on the T375 McCarty Lane – Hilltop 10.65-mile 138kV transmission line. | 2020-10-26 | 2021-04-02 | 2021-04-01 |  | 1117000 |  |  | 100 | 138 | 138 | 3.96 | 927.2 Greeley | H-Frame, Steel Pole, Lattice Tower | Varies 85 - 125 | 85/125 | n/a | n/a | 25.101 (C)(5)(B) |  | 194 | Tolu Odunlami
1018763 | Crane-Rio Pecos TL Addition (T451) [Soda Lake Substation Addition - 1018745] | Crane | Provide transmission service to a generator | 2021-04-02 | 2021-05-14 | 2021-06-03 |  | 692000 |  |  | 100 | 138 | 138 | 12.24 | (2) 795 kcmil ACSR "Drake" | Concrete pole, steel pole | Centerline; 80 | 12.24 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 195 | Scott Stacher
1023874 | Hornsby TL Addition (T510), (T511) & (T738) [Hornsby Substation Addition -1023852] | Guadalupe, Williamson, Travis, Caldwell | Provide transmission service to a load-serving substation. | 2022-05-16 | 2023-09-15 |  |  | 3400000 |  |  | 0 | 345 | 345 | 74.6 (T510) 71.0 (T511) | (2) bundled 959 ACSS/TW Suwannee | Steel lattice and monopoles | Varies 100 - 200 | 74.6 (T510) 71.0 (T511) | 165 | 74.6 (T510) 51.0 (T511) 20.0 (T738) | 25.101 (C)(5)(A) |  | 196 | Dave Ilges
1024249 | Austin Energy Hornsby TL Addition (AEN924), (AEN1008) & (AEN1099) [Hornsby Substation Addition -1023852] | Travis | Provide transmission service to a load-serving substation. | 2021-01-19 | 2021-04-15 | 2021-04-15 |  | 625000 |  |  | 100 | 138 | 138 | 7.2 (AEN924) 7 (AEN1008) | (2) bundled 795 ACSR Drake | Steel lattice and monopoles | Varies 90 - 100 | 7.2 (AEN924) 6 (AEN1008) 1 (AEN1099) | 80 | 7.2 (AEN924) 7 (AEN1008) | 25.101 (C)(5)(A) | Project was added to the MCPR for transparency with regard to construction on (AEN924), (AEN1008) & (AEN1099) lines. The costs presented in this table are included in the Substation Subproject. | 197 | Dave Ilges
1020471 | Eckert - Nebo TL Addition (T126) [Eckert - Nebo TL Overhaul - 1020377] | Gillespie | Increase the reliability of circuit T126 on the Eckert- Nebo 0.7 mile 69 Kv transmission line | 2021-01-15 | 2021-04-14 | 2021-04-14 |  | 2198000 |  |  | 100 | 69 | 138 | 0.7 | Single 795 Drake | Steel Tangents H-Frames | 100 | 0.7 | n/a | n/a | 25.101 (C)(5)(B) |  | 198 | Robin Mims
1023831 | Wingarten TL Addition [Wingarten Substation Upgrade - 1022733] | Zavala | Increase transmission service reliability to the Wingarten Substation. Reroute the existing line tap of the La Pryor-Turtle Creek TL from its current configuration to a newly installed AEP owned box structure. | 2020-12-14 | 2020-12-18 | 2020-12-16 |  | 600000 |  |  | 100 | 69 | 138 | 0.05 | 795 kcmil ACSR (26/7), one conductor/phase | Concrete pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | work within substation | 199 | Jeremy Svagdis
1022221 | T635 TL Addition [LCRA Fiber Backbone FY20 - 1021196] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-09-16 | 2022-05-14 |  |  | 821000 |  |  | 0 | 138 | 138 | 12.15 | Single 795 ACSR Drake | Steel Monopole | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 200 | Robert Badger
1021471 | Waller - Chappell Hill TL Addition (T232) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington, Waller | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-02-01 | 2021-05-16 | 2021-05-14 |  | 1088000 |  |  | 100 | 138 | 138 | 15.93 | Single 795 ACSR Drake | Wood H-Frame | Varies 75 -85 | 15.93 | n/a | n/a | 25.101 (C)(5)(B) |  | 201 | Robert Badger
1021477 | Miller Creek - Mountaintop TL Addition (T426) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Blanco | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-09-03 | 2021-09-18 |  |  | 1743000 |  |  | 0 | 138 | 138 | 4.81 | (1x) 1433 ACSS/TW Merrimack | Steel Monopole | Centerline 60 - 100 | 4.81 | n/a | n/a | 25.101 (C)(5)(B) |  | 202 | Robert Badger
1023406 | Warda-Winchester (T170) TL Addition [Warda - Winchester TL Upgrade 1023202] | Fayette | Increase the transmission capacity of T170: Warda – Winchester 138-kV transmission circuit. LCRA TSC will upgrade T170: Warda - Winchester transmission line to a minimum 105 degree F ambient temperature rating of 580 MVA at 138-kV using single 1433 Merr | 2020-11-29 12:00 | 2021-05-14 | 2021-05-14 |  | 5053000 |  |  | 100 | 138 | 138 | 4.11 | 1-1433.6 ACSS/TW/MA3 "Merrimack" | Steel Pole | 100 | 4.11 | n/a | n/a | 25.101 (C)(5)(B) |  | 203 | Tanya Noujaim
1023877 | Ft Mason-Mason TL Addition (T651) [Fort Mason Circuit Breaker - 1023806] | Mason | Provide transmission service to a generator; Upgrade 138-kV ring bus to accommodate new circuit termination | 2021-02-01 | 2021-04-30 | 2021-04-30 |  | 929000 |  |  | 100 | 138 | 138 | .035 | 1-795 ACSR DRAKE | Steel Dead-End Pole | n/a | n/a | 100 | .018 | 25.101 (C)(5)(A) |  | 204 | Robin Mims
1023860 | Lakeway-Marshall TL Addition (T180) [Lakeway - Marshall Ford TL Upgrade - 1023808] | Travis | Increase the reliability of transmission facilities on the T180 Lakeway – Marshall Ford 0.27-mile 138-Kv transmission line by replacing the existing Condor conductor from Marshall Ford Substation structure #1A to structure #1B. | 2021-01-11 | 2021-02-04 | 2021-02-04 |  | 854000 |  |  | 100 | 138 | 138 | 5 | Single 959 ACSS Suwannee conductor (0.27 mile from Marshall Ford Substation to Str. 1A to Str. 1B) | Steel Lattice Towers | 100 | 4.5 | n/a | n/a | 25.101 (C)(5)(B) |  | 205 | Tyreeta Young
1021459 | Wolf Lane - Wyldwood TL Addition (T141) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Bastrop | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-03-01 | 2021-05-16 | 2021-05-13 |  | 1980000 |  |  | 100 | 138 | 138 | 5.76 | 1 x 795 Drake ACSR | steel lattice towers, wood/steel H-frame, steel monopoles | 100 | 5.76 | n/a | n/a | 25.101 (C)(5)(B) |  | 206 | Robert Badger
1024390 | OPGW Addition (T187) 1023373 [Ferguson to Wirtz Fiber Upgrade-1023373] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated Optical Ground Wire (OPGW) from Ferguson to Wirtz to improve telecommunication system reliability. | 2021-02-01 | 2021-05-15 | 2021-05-07 |  | 600000 |  |  | 100 | 138 | 138 | 9.4 | 795 Drake ACSR | Lattice Towers | 100 | 9.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 207 | Christopher Grimes
1023950 | T-187 TL Addition [Ferguson - Wirtz TL Storm Hardening - 1023805] | Burnet, Llano | Increase the reliability of transmission facilities on the T187 Ferguson – Sherwood Shores 9.3-mile 138-kV transmission line from Ferguson Substation to Wirtz Substation. | 2021-02-01 | 2021-05-15 | 2021-05-07 |  | 3575000 |  |  | 100 | 138 | 138 | 9.4 | 795 Drake ACSR | Lattice Towers | 100 | 9.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 208 | Christopher Grimes
1020882 | Ferguson - Sherwood Shores TL Addition Storm Hardening (T187) [Ferguson - Sherwood Shores TL Storm Hardening - 1020881] | Burnet, Llano | Increase the reliability of circuit T187 on the Ferguson – Sherwood Shores 3.5-mile 138-kV transmission line from Sherwood Shores Substation to the Wirtz Split. | 2021-01-06 | 2021-05-17 | 2021-05-17 |  | 6634000 |  |  | 100 | 138 | 138 | 3.4 | 795 Drake ACSR | Steel Monopoles | centerline | 3.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 209 | Christopher Grimes
1021982 | SherWShores-Wirtz Split TL Addition (T187) [LCRA Fiber Backbone FY20 - 1021196] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-04-26 | 2021-05-14 | 2021-05-14 |  | 280000 |  |  | 100 | 138 | 138 | 3.4 | 795 Drake ACSR | Steel Monopoles | centerline | 3.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 210 | Sarah Wilson
1024927 | G-T255 FPP to Lyton Springs Structure Stress Remediation Add [GA FY 21 TSC-G-T255 Str. Stress - 1024926] | Fayette | Install new dead-end assemblies that will be connected to the cage of structure 46 on the T255 FPP to Lytton Springs transmission line. New dead-end hardware will be required with new conductor for jumpers. | 2021-01-25 | 2021-04-23 | 2021-04-23 |  | 243000 |  |  | 100 | 345 | 345 | 61.08 | Top Phase: Bundled (2) 795 Drake ACSR Middle and Bottom Phases: Bundled (2) 715.5 Redwing ACSR | Tower | 100' | 61.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 211 | Lindsay Mijares
1024192 | Gilleland-Silicon Hill TL Addition (T734) [Gilleland Creek Circuit Breaker Addition - 1024005] | Travis | Upgrade 138-kV bay to breaker-and-a-half to accommodate new circuit termination. | 2021-01-04 | 2021-12-31 |  |  | 389000 |  |  | 95 | 138 | 138 | .04 | 795 ACSR | Steel DE Monopole | 80' | n/a | 80' | n/a (POI) | 25.101 (C)(5)(A) |  | 212 | Aldo Romero
1023420 | Altair - Eagle Lake TL Addition (T547) Ph. II [Flood Mitigation Phase II – FY 2021 - 1023189] | Colorado | Reduce the flood risk and potential for damage to substation equipment on T547 Altair - Eagle Lake and T171 Sim Gideon - Austrop transmission lines. | 2021-02-16 | 2021-05-07 | 2021-05-07 |  | 2012000 |  |  | 100 | 138 | 138 | 8.4 | 795 ACSR | Steel DE 3 Pole / Steel HF | Blanket | 8.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 213 | Jack Sandel
1021422 | Redwood - McCarty TL Addition (T262) [Rattler Substation Addition - 1020484] | Hays | Provide transmission service to a load-serving substation. Provide metering facilities. Provide real-time monitoring facilities at the Substation. | 2021-03-01 | 2021-05-12 | 2021-05-12 |  | 719000 |  |  | 100 | 138 | 138 | 2.3 | (2) Drake ACSR | steel monopoles, concrete H-frames | 50' | 2.3 | n/a | n/a | 25.101 (C)(5)(A) |  | 214 | Sarah Wilson
1020865 | Clearfork-Lockhart TL Addition (T601) [Clear Fork-Lockhart TL OH - 1020864] | Caldwell | Increase the reliability and capability of circuit T601 on the Clear Fork – Lockhart transmission line | 2021-05-17 | 2021-09-17 |  |  | 4132000 |  |  | 80 | 69 | 138 | 3.04 | Existing (1)4/0 ACSR "Penguin" New (2)959.6 ACSS/TW/HS "Suwannee" | Wood/Steel H-frame, Steel Monopole | Centerline (Varies) | 3.04 | 100 | n/a | 25.101 (C)(5)(B) | ROW per Easement Enhancement FY19 System Upgrade - 1019090 | 215 | Jack Sandel
1020838 | Lampasas-Kempner TL Addition (T154) [Kempner Circuit Breaker Addition-1020381] | Lampasas | Increase transmission service reliability to the Kempner Substation and Lampasas Substation. Increase the reliability and capability of transmission facilities on the T154 Copperas Cove (PEC) - Lampasas 13.5-mile 138kV transmission line. | 2021-05-17 | 2021-09-05 |  |  | 2529000 |  |  | 70 | 138 | 1.38 | 8.04 | (1)795kcmil ACSR/GA2 "Drake" | Wood & Steel H-frame, Tower and monopole | Centerline (varies) | 8.04 | n/a | n/a | 25.101 (C)(5)(A) | Additional landowners notified; Supplemental notice affidavit filed 4/15/21 | 216 | David Rich
1020969 | Kempner-Copperas Cove TL Addition (T721) [Kempner Circuit Breaker Addition-1020381] | Lampasas | Increase transmission service reliability to the Kempner Substation and Lampasas Substation. Increase the reliability and capability of transmission facilities on the T154 Copperas Cove (PEC) - Lampasas 13.5-mile 138kV transmission line. | 2021-05-17 | 2021-09-05 |  |  | 1819000 |  |  | 60 | 138 | 138 | 5.62 | (1)795kcmil ACSR/GA2 "Drake" | Wood & Steel H-frame, Tower and monopole | Centerline (varies) | 5.62 | n/a | n/a | 25.101 (C)(5)(A) |  | 217 | David Rich
1020856 | Clearfork-Robert Brown TL Addition (T519) [Clear Fork-Robert Brown Jr TL Overhaul - 1020855] | Caldwell | Increase the reliability and capability of circuit T519 on the Clear Fork – Robert Brown Jr 8.8-mile 69-kV transmission line. | 2021-11-15 | 2022-04-15 |  |  | 7550000 |  |  | 0 | 69 | 138 | 8.75 | (2)959.6kcmil ACSS/TW/HS "Suwannee" | Steel Monopole | Centerline | 8.75 | 80 | 8.75 | 25.101 (C)(5)(B) | ROW per Easement Enhancement FY19 System Upgrade - 1019090 | 218 | Jack Sandel
1025542 | F - T550 Divide-TB TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Coke, Tom Green | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 13:00 | 2021-02-21 | 2021-02-21 | 109000 | 214844 |  |  | 100 | 345 | 345 | 30.8 | Bundled 1590 kcmil ACSR Falcon | Steel Lattice | 160 | 30.8 | n/a | n/a | 25.101 (C)(3) |  | 219 | Tony Rhodes
1025575 | F - T438 FtLncstr-FrdRnch TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Crockett, Pecos, Terrell | February 2021 winter storm emergency repair and restoration work. | 2021-02-16 12:11 | 2021-02-20 08:46 | 2021-02-20 08:46 | 5000 | 7539 |  |  | 100 | 138 | 138 | 43.45 | Bundled 795 kcmil ACSR Drake | Concrete Pole | 80 | 43.45 | n/a | n/a | 25.101 (C)(3) |  | 220 | Tony Rhodes
1025452 | F - T431 Divide-GasCrk TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Coke, Sterling | February 2021 winter storm emergency repair and restoration work. | 2021-02-12 | 2021-02-20 | 2021-02-20 | 141000 | 278626 |  |  | 100 | 345 | 345 | 5.89 | Bundled 1590 kcmil ACSR Falcon | Steel Lattice | 160 | 5.89 | n/a | n/a | 25.101 (C)(3) |  | 221 | Tony Rhodes
1025537 | F - T440 Skywst-Sprbry TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Midland | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 01:53 | 2021-02-17 21:43 | 2021-02-17 21:43 | 24000 | 63547 |  |  | 100 | 138 | 138 | 9.06 | Single 1233.6 kcmil ACSS/TW Yukon | Concrete Pole | Varies - 75& Blanket | 9.06 | n/a | n/a | 25.101 (C)(3) |  | 222 | Tony Rhodes
1025534 | F - T610 Antler-Hwy 46 TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Comal | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 | 2021-02-17 | 2021-03-12 | 151000 | 340625 |  |  | 100 | 138 | 138 | 10.4 | Single 795 kcmil ACSR/TW/GA2 Condor | Steel Lattice | 100 | 10.4 | n/a | n/a | 25.101 (C)(3) |  | 223 | Tony Rhodes
1025551 | F - T391 Mac-Hockley TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Harris, Waller | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 18:09 | 2021-02-16 14:38 | 2021-02-16 14:38 | 5000 |  |  |  | 100 | 138 | 138 | 12.06 | Single 959.6 kcmil ACSS/TW Suwannee | Concrete Pole | 80 | 12.06 | n/a | n/a | 25.101 (C)(3) |  | 224 | Tony Rhodes
1025549 | F - T558 BH - Kendall TL Repair [Big Hill – Kendall Transmission Line Restoration - 1025819] | Gillespie, Kendall, Kerr, Kimble, Schleicher | February 2021 winter storm emergency repair and restoration work. | 2021-02-13 20:02 | 2021-02-26 10:26 | 2021-07-22 | 1023000 | 2004000 |  |  | 100 | 345 | 345 | 139.17 | Bundled 1926.7 kcmil ACSS/TW Cumberland | Steel Lattice | Varies | 139.17 | n/a | n/a | 25.101 (C)(3) |  | 225 | Tony Rhodes
1025544 | F - T493 Antler-Brghm TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Comal | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 11:33 | 2021-02-16 07:29 | 2021-03-09 | 118000 | 294019 |  |  | 100 | 138 | 138 | 7.18 | Single 795 Condor ACSR/SD | Steel Lattice | 100 | 7.18 | n/a | n/a | 25.101 (C)(3) |  | 226 | Tony Rhodes
1025545 | F - T559 BH-Kendall TL Repair [Big Hill – Kendall Transmission Line Restoration - 1025819] | Gillespie, Kendall, Kerr, Kimble, Schleicher | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 10:36 | 2021-02-26 10:51 | 2021-07-22 | 1023000 | 2005000 |  |  | 100 | 345 | 345 | 139 | (2)1926.9 ACSS/TW "Cumberland" | Steel Lattice | 120 | 139 | n/a | n/a | 25.101 (C)(3) |  | 227 | Tony Rhodes
1025454 | F - T487 Hunt-Ingram TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Kerr | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 | 2021-02-17 | 2021-05-10 | 64000 | 295133 |  |  | 100 | 138 | 138 | 6.39 | (1)336.4 ACSR "Linnet" | Steel Lattice | 60 Centerline | 6.39 | n/a | n/a | 25.101 (C)(3) |  | 228 | Tony Rhodes
1025450 | F - T448 Gillspie-HSBay TL Repair [Gillespie - Horseshoe Bay Transmission Line Restoration and Upgrade - 1025920] | Gillespie, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 | 2021-08-18 | 2021-02-19 | 174000 | 1118000 |  |  | 85 | 138 | 138 | 36.42 | (1)795 ACSR "Drake" | Steel Lattice | 75 Centerline | 36.42 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work ongoing | 229 | Jeremy Svagdis
1025558 | F - T110 Corondo-Flnd TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Burnet, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-11 22:49 | 2021-02-12 15:20 | 2021-02-12 15:20 | 11000 |  |  |  | 100 | 138 | 138 | 12.5 | (1)795 ACSR "Drake" | Steel Lattice | 100 Centerline | 12.5 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work ongoing | 230 | Tony Rhodes
1025576 | F - T221 TrtlCrk-VrdeCrk TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Kerr | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 03:14 | 2021-02-17 14:33 | 2021-04-15 | 11000 | 22062 |  |  | 100 | 138 | 138 | 10.34 | (1)336.4 ACSR "Linnet" | Wood Pole | 80 M&B, 100, Centerline | 10.34 | n/a | n/a | 25.101 (C)(3) |  | 231 | Tony Rhodes
1025449 | F - T192 Ferg-Gillspie TL Repair [Gillespie - Horseshoe Bay Transmission Line Restoration and Upgrade - 1025920] | Gillespie, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 | 2021-08-18 | 2021-02-19 | 165000 | 1090000 |  |  | 85 | 138 | 138 | 39.18 | (1)795 ACSR "Drake" | Steel Lattice | 30,M&B, Centerline | 39.18 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work ongoing | 232 | Jeremy Svagdis
1025547 | F - T389 Berghm-Hays E TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Comal, Hays | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 11:33 | 2021-02-17 15:16 | 2021-03-12 | 94000 | 355760 |  |  | 100 | 345 | 345 | 33.92 | 795 CONDOR ACSR/SD (BUNDLED) 1433.6 MERRIMACK ACSS/TW (BUNDLED) | Steel Lattice | 170 Centerline 100' M & B | 33.92 | n/a | n/a | 25.101 (C)(3) |  | 233 | Tony Rhodes
1025557 | F - T422 Divide to TB TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Coke, Tom Green | February 2021 winter storm emergency repair and restoration work. | 2021-02-11 06:11 | 2021-02-22 10:07 | 2021-02-22 10:07 | 216000 | 392117 |  |  | 100 | 345 | 345 | 30.86 | 1590 FALCON ACSR (BUNDLED) | Steel Lattice | 160 Centerline | 30.86 | n/a | n/a | 25.101 (C)(3) |  | 234 | Tony Rhodes
1025453 | F - T564 Big Hill-TB TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Schleicher, Tom Green | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 | 2021-02-20 | 2021-04-04 | 565000 | 2315966 |  |  | 100 | 345 | 345 | 37.89 | 1926.9 CUMBERLAND ACSS/TW (BUNDLED) | Steel Pole | 140-160 | 37.89 | n/a | n/a | 25.101 (C)(3) |  | 235 | Tony Rhodes
1025550 | F - T148 BC-Comfort TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Kendall | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 16:26 | 2021-02-20 12:55 | 2021-04-28 | 285000 | 642717 |  |  | 100 | 138 | 138 | 16.93 | 795 DRAKE ACSR (BUNDLED) | Steel Pole | 75-140 Centerline Blanket | 16.93 | n/a | n/a | 25.101 (C)(3) |  | 236 | Tony Rhodes
1025568 | F - T266 Gillspie-Nimtz TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 00:52 | 2021-02-17 16:00 | 2021-05-14 | 42000 | 203128 |  |  | 100 | 138 | 138 | 2.92 | 795 DRAKE ACSR (SINGLE) | Steel Lattice | Varies | 2.92 | n/a | n/a | 25.101 (C)(3) |  | 237 | Tony Rhodes
1025559 | F - T548 EagleLk-El Cmp TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Colorado | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 23:42 | 2021-02-15 15:04 | 2021-02-15 15:04 | 44000 | 47597 |  |  | 100 | 69 | 69 | 38.176 | 795 ARBUTUS AAC (SINGLE) 795 DRAKE ACSR (SINGLE) 4/0 PENGUIN ACSR (SINGLE) 336.4 LINNET ACSR (SINGLE) 1/0 RAVEN ACSR (SINGLE) | Wood H-Fram | Blanket CL | 38.18 | n/a | n/a | 25.101 (C)(3) |  | 238 | Tony Rhodes
1025540 | F - T342 Kendall-MtnTop TL Repair [Kendall – Mountain Top Fiber Restoration and Upgrade - 1025820] | Blanco, Gillespie, Kendall | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 16:40 | 2021-02-26 | 2021-06-08 | 418000 |  |  |  | 100 | 138 | 138 | 35.27 | Single 1433.6 Merrimack ACSS/TW | Steel monopole | 60, 100 | 35.27 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work tentatively planned to occur in April | 239 | Sarah Wilson
1025535 | F - T288 Hrpr-LvOak TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie | February 2021 winter storm emergency repair and restoration work. | 2021-02-13 | 2021-02-17 | 2021-02-17 | 117000 | 119378 |  |  | 100 | 69 | 69 | 21.67 | (1)2/0 ACSR "Quail"/ (1)1/0 ACSR "Raven" | Wood pole | 40 | 21.66 | n/a | n/a | 25.101 (C)(3) |  | 240 | Tony Rhodes
1025447 | F - T130 Gillspie-SndStne TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-19 | 2021-02-19 | 2021-02-19 | 127000 | 140329.79 |  |  | 100 | 69 | 69 | 36.22 | ACSR (12/7) Cochin/ACSR (26/7) Linnet/ACSR (26/7) Drake 4/0 ACSR (6/1) Penguin | Wood H-Frames | 100 | 36.22 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work tentatively planned to occur in April | 241 | Tony Rhodes
1025536 | F - T508 Doss - Harper TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie | February 2021 winter storm emergency repair and restoration work. | 2021-02-12 | 2021-02-17 | 2021-02-17 | 196000 | 207161 |  |  | 100 | 69 | 69 | 14.09 | (1)4/0 ACSR "Penguin" | Wood Pole | Centerline | 14.09 | n/a | n/a | 25.101 (C)(3) |  | 242 | Tony Rhodes
1025533 | F - T255 FPP-Lytt Sprgs TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Bastrop, Caldwell, Fayette | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 | 2021-02-17 | 2021-02-17 | 203000 |  |  |  | 100 | 345 | 345 | 61.12 | Double Bundle 715.5 ACSR 30/19 Redwing | Steel Lattice | 100 | 61.12 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work tentatively planned to occur in June | 243 | Tony Rhodes
1025448 | F - T214 FtMason-Gillspie TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie, Mason | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 | 2021-02-25 | 2021-02-25 | 414000 | 876218 |  |  | 100 | 138 | 138 | 12.86 | Single 795 MCM ACSR (26/7) Drake | Wood H-Frames | 75, 100 | 12.86 | n/a | n/a | 25.101 (C)(3) |  | 244 | Tony Rhodes
1025621 | F-T151 Sim Gideon-Paige TL Repairr [Winter Storm - FY 2021 System Restoration - 1025756] | Bastrop | February 2021 winter storm emergency repair and restoration work. | 2021-04-24 | 2021-04-24 | 2021-04-24 | 15864.43 | 15864 |  |  | 100 | 138 | 138 | 9.77 | (1) 795 Drake ACSR | Wood H-Frame, Lattice Tower, Steel Pole | Varies | 9.77 | n/a | n/a | 25.101 (C)(3) |  | 266 | Tony Rhodes
1023652 | Hilltop-RR 12 TL Addition (T375) [Hilltop - Ranch Road 12 TL Upgrade - 1023190] | Hays | Increase the reliability of transmission facilities on the T375: Hilltop – Ranch Road 12 3.95-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-09-20 | 2022-09-16 |  |  | 9300000 |  |  | 0 | 138 | 138 | 3.97 | 3x1 ~ 1433.6 ACSS/TW "Merrimack" | Steel Poles | Varies | 3.97 | n/a | n/a | 25.101 (C)(5)(B) |  | 245 | Dave Ilges
1023723 | T699 McCarty Lane-RR 12 TL Addition [McCarty Lane - Ranch Road 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-20 | 2022-06-10 |  |  | 9710000 |  |  | 0 | 138 | 138 | 6.67 | 3x1 ~ 1433.6 ACSS/TW "Merrimack" | Steel Poles | Varies,100 | 6.67 | n/a | n/a | 25.101 (C)(5)(B) |  | 246 | Dave Ilges
1024076 | T233 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays, Comal | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-20 | 2022-06-10 |  |  | 827000 |  |  | 0 | 138 | 138 | 6.56 | 3x1 ~ 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 6.56 | n/a | n/a | 25.101 (C)(5)(B) |  | 247 | Dave Ilges
1023795 | T262 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-20 | 2022-06-10 |  |  | 976000 |  |  | 0 | 138 | 138 | 2.3 | 3x2 ~ 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 2.3 | n/a | n/a | 25.101 (C)(5)(B) |  | 248 | Dave Ilges
1024074 | T324 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-20 | 2022-06-10 |  |  | 815000 |  |  | 0 | 138 | 138 | 0.1 | 2x3 ~ 795 ACSR "Drake" | Steel Pole | Varies | 0.1 | n/a | n/a | 25.101 (C)(5)(B) |  | 249 | Dave Ilges
1024151 | Coronado-Fairland TL Addition (T110) [Coronado - Fairland TL Upgrade - 1023802] | Coronado | Increase the reliability of transmission facilities on the T110 Coronado – Fairland conductor by replacing 12.4 mile 138-kV transmission line of existing Condor conductor and 25 structures. | 2021-08-30 | 3/22/2022 |  |  | 6492000 |  |  | 0 | 138 | 138 | 12.4 | Single 795 ACSR Drake | Lattice Towers and Steel Monopoles | 100 Centerline | 12.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 250 | Hooman Larimi
1020859 | Red Rock-Tahitian T153 TL Addition (T153) [Red Rock-Tahitian TL Upg - 1020858] | Bastrop | Increase the reliability of transmission facilities on the T153 Red Rock – Tahitian Village 12.6-mile 138-kV transmission line. | 2021-09-16 | 2022-05-13 |  |  | 12818000 |  |  | 0 | 138 | 138 | 12.67 | (1)959.6 ACSS/TW/HS "Suwannee" (1) 995.0 kcmil Type 13 ACCS/TW/C7-TP (1)AFL DNO-11243 OPGW | Steel Monopole | 100 | 12.67 | n/a | n/a | 25.101 (C)(5)(B) |  | 251 | Jack Sandel
1020868 | TurtleCreek-VerdeCreek TL Addition (T221) [Turtle Crk-Verde Crk TL OH-1020867] | Kerr | Increase the reliability of transmission facilities on the T221 Turtle Creek – Verde Creek 10.3-mile 138-kV transmission line. | 2021-08-01 | 2022-03-30 |  |  | 4826000 |  |  | 1 | 138 | 138 | 10.26 | Single 795 ACSR "Drake" & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopoles | 100, Meets & Bounds | 10.26 | n/a | n/a | 25.101 (C)(5)(B) |  | 252 | David Rich
1024946 | Flatonia-Plum TL Addition (T133) [Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2021-08-16 | 4/21/2022 |  |  | 6400000 |  |  | 0 | 138 | 138 | 11.07 | (1) 959.6 ACSS/TW "Suwannee" (1) DNO-11243 (1) 3/8" EHS & (1) 3/8" HS | Steel poles, H-frames, Lattice tower | 100 | 19.64 | n/a | n/a | 25.101 (C)(5)(A) |  | 253 | Bradley Wallner
1019041 | Schulenberg - Glidden TL Addition (T373) [Weimar Circuit Breaker Addition - 1018928] | Colorado | Increase transmission service reliability to the Weimar Substation. Increase the reliability of transmission facilities on the T373 Schulenburg - Glidden 20.25- mile 138-kV transmission line. | 2021-08-30 | 2022-02-01 |  |  | 535000 |  |  | 0 | 138 | 138 | 12.88 | (1) 795 ACSR/GA2 “DRAKE” | Steel poles, H-frames, Lattice tower | Blanket | 12.88 | n/a | n/a | 25.101 (C)(5)(B) |  | 254 | Tyreeta Young
1021249 | Coronado - Graphite Mine TL Addition (T109) [Graphite Mine CB Addition - 1020373] | Burnet, Lampasas | Increase transmission service reliability to the Graphite Mine Substation. | 2021-12-15 | 2021-11-19 |  |  | 2789000 |  |  | 85 | 138 | 138 | 5.61 | Single 795 ACSR Drake & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopole, Concrete Monopole | 100 | 5.61 | n/a | n/a | 25.101 (C)(5)(A) |  | 255 | David Rich
1021355 | Lampasas - Graphite Mine TL Addition (T715) [Graphite Mine CB Addition - 1020373] | Burnet, Lampasas | Increase transmission service reliability to the Graphite Mine Substation. | 2021-12-15 | 2021-11-19 |  |  | 7200 |  |  | 5 | 138 | 138 | 21.93 | Single 795 ACSR Drake & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopole, Concrete Monopole, Lattice Tower | 100 & Centerline | 21.93 | n/a | n/a | 25.101 (C)(5)(A) |  | 256 | David Rich
1020123 | Magnolia Mercer-Luling TL Addition (T701) [Magnolia Mercer CB Addition - 1018915] | Caldwell | Increase the reliability of substation equipment at the Magnolia Mercer Substation | 2021-09-08 | 2022-05-15 |  |  | 186000 |  |  | 0 | 69 | 138 | 15.83 | (1) 795 ACSR /GA2 "Drake" Conductor (1) DNO-11243 Shield Wire | Wood H-frames, Tower | Centerline | 15.83 | n/a | n/a | 25.101 (C)(5)(B) |  | 257 | Manny Garcia
1019178 | Luling-Mercer TL Addition (T157) [Magnolia Mercer CB Addition - 1018915] | Caldwell | Increase the reliability of substation equipment at the Magnolia Mercer Substation | 2021-09-08 | 2022-05-15 |  |  | 557000 |  |  | 0 | 69 | 69 | 15.83 | (1) 336 ACSR "Linnet" Conductor (1) 4/0 ACSR "Penguin" Shield Wire | Tower | Centerline | 15.83 | n/a | n/a | 25.101 (C)(5)(B) |  | 258 | Manny Garcia
1019331 | Schulenburg-Glidden TL Addition (T373) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Fayette, Colorado | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2021-09-16 | 2022-02-02 |  |  | 6500000 |  |  | 0 | 138 | 138 | 7.57 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and Hybrid Monopoles | Blanket; 20 | 7.57 | n/a | 7.57 | 25.101 (C)(5)(B) |  | 259 | Robert Badger
1023940 | Weimar-Glidden TL Addition(T704) [LCRA TSC Fiber Build Out FY19 - 1019097] | Colorado | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2021-09-16 | 2022-02-02 |  |  | 8646000 |  |  | 0 | 138 | 138 | 12.86 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and Hybrid Monopoles | Blanket; 20 | 12.86 | n/a | 12.86 | 25.101 (C)(5)(B) |  | 260 | Robert Badger
1024827 | Cedar Canyon-HiLonesm BESS TL Addition (T741) [Cedar Canyon Circuit Breaker Addition - 1024678] | Iraan, Crockett | This project provides a point of interconnection for a new 50.6 MW Battery Energy Storage at the 345-kV Cedar Canyon Substation by adding a new bay into a double bus/double breaker configuration to accommodate the new interconnection. | 2021-10-22 | 2022-02-01 |  |  | 702000 |  |  | 0 | n/a | 345 | <1mi (374ft) | Bundled 959 Suwannee | Steel Monopole | n/a | n/a | 200 X 200 plot | 200' X 200 plot | 25.101 (C)(5)(A) |  | 261 | Sarah Wilson
1025114 | King Mountain-North McCamey TL Addition (T452) [King Mountain - North McCamey Transmission Line Relocation Project - 1024877] | Crane, Upton | Relocate and modify transmission facilities on the DC T455/T452 King Mountain – North McCamey 138kV transmission line. | 2021-10-12 | 2021-12-15 |  |  | 1617000 |  |  | 0 | 138 | 138 | 10.44 | (2x) 795 ACSR Drake | Steel Poles, Concrete Poles | 80 | 10.44 | n/a | n/a | 25.101 (C)(5)(D) |  | 262 | Melissa Horn
1025115 | King Mountain-North McCamey TL Addition (T455) [King Mountain - North McCamey Transmission Line Relocation Project - 1024877] | Crane, Upton | Relocate and modify transmission facilities on the DC T455/T452 King Mountain – North McCamey 138kV transmission line. | 2021-10-12 | 2021-12-15 |  |  | 983000 |  |  | 0 | 138 | 138 | 10.44 | (2x) 795 ACSR Drake | Steel Poles, Concrete Poles | 80 | 9 | n/a | n/a | 25.101 (C)(5)(D) |  | 263 | Melissa Horn
1023353 | King Mountain - Crane II TL Addition (T732) [King Mountain Substation Upgrade - 1023073] | Crane | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. | 2021-10-22 | 2022-03-11 |  |  | 2301000 |  |  | 0 | n/a | 138 | 0.13 | (1) 959.6 KCMIL ACSS "Suwannee" | Steel Monopole | n/a | n/a | 80 | 0.13 | 25.101 (C)(5)(A) |  | 264 | Dave Ilges
1020853 | San Marcos-Robert Brown TL Addition (T220) [Robert Brown Jr-San Marcos TL Overhaul -1020852] | Hays, Caldwell | Increase the reliability and capability of circuit T220 on the Robert Brown Jr – San Marcos 4.91-mile 69-kV transmission line. | 2022-04-15 | 2022-09-15 |  |  | 5187000 |  |  | 0 | 69 | 138 | 4.9 | (2)959.6 ACSS/TW/HS "Suwannee" (2)995.0 T13 ACSS/TW/C7-TP (1)AFL DNO-11243 | Steel Monopole | Varies | 4.9 | 100 | 4.9 | 25.101 (C)(5)(B) |  | 265 | Jack Sandel
1025785 | A-frame (T373) Replacement Weimar Substation [G-T373 Replace frame Weimar Sub – 1025785] | Weimar, Colorado | Replace existing T373 A-Frame at Weimar Substation | 2021-12-07 | 2022-02-01 |  |  | 130000 |  |  | 0 | 138 | 138 | 7.57 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and hybrid monopoles, Superduty A-Frame | Varies | 7.57 | n/a | n/a | 25.101 (C)(5)(B) |  | 268 | David Marshall