## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
1501620 | Gyp - Benjamin | King/Knox | Construct 10.1 miles of single pole, single circuit | 2021-01-11 |  |  | 10020000 | 6962408 |  |  | 55% | NA | 138 | 10.1 | 1433 ACSS/TW | Single Pole Concrete or Steel | NA | NA | 100 | 10.1 | 47691 | CCN Order 08/30/18
1402321 | Cogdell - Clairemont | Scurry/Kent | Construct 12.2 miles of single pole, single circuit | 2020-08-10 |  | 2020-12-30 | 10197500 | 8014900 |  |  | 100% | NA | 138 | 12.2 | 959.6 ACSS/TW | Single Pole Concrete or Steel | NA | NA | 70 | 12.2 | 47808 | CCN Order 1/17/18
1901220 | Downing-Rising Star Rebuild | Comanche | Rebuild 21.7miles of single pole, single circuit | 2020-09-21 |  |  | 14907222.84 | 9682340 |  |  | 99% | 69 | 138 | 21.7 | 959 ACSS-TW | Single Pole Concrete or Steel | 60 | 21.58 | NA | 0 | 25.101(c)(5)(B) | Affidavit to be filed upon request
1805321 | Midway - Calbvert Sw Rebuild | Falls & Miliam | Rebuild 20.5 miles of single circuit, single pole circuit from Midway to Pleasant Grove to Calvert Substation | 2020-09-21 |  |  | 11932289.62 | 10638834 |  |  | 65% | 69 | 138 | 20.5 | 959 ACSS-TW | Single Pole Concrete or Steel | 60 | 20.4 | NA | 0 | 25.101(c)(5)(B) | Affidavit to be filed upon request
1901222 | Rising Star-Nimrod Rebuild | Eastland | Rebuild 14.5 miles of single pole, double circuit from Rising Star Substation to Nimrod Substation | 2021-01-25 |  |  | 20806925.85 | 13601100 |  |  | 75% | 69 | 138 | 14.5 | 959 ACSS-TW | Single Pole Concrete or Steel | 60 | 14.5 | NA | 0 | 25.101(c)(5)(B) | Affidavit to be filed upon request
1901221 | Rising Star-Holder Rebuild | Brown/ Comanche | Rebuild 14.3 miles of single pole, double circuit from Rising Star Substation to Holder Substation | 2021-09-13 |  |  | 2979786.72 |  |  |  | 0% | 69 | 138 | 14.3 | 959 ACSS-TW | Single Pole Concrete or Steel | 60 | 14.3 | NA | 0 | 25.101(c)(5)(B) | Affidavit to be filed upon request
20004 | Swimmer Switch Structure | Parker | Swimmer P.O.I./ Switch Structure | 2020-11-01 |  |  | 787250 | 1102595.85 |  |  | 100% | NA | 138 | 0.05 | 959 ACSS-TW | Single Pole Concrete or Steel | NA | NA | 100 | 0.05 | 25.101(c)(5)(B) | Affidavit to be filed upon request
902420 | Josey Transmission | Denton | Construct 0.072 miles of single pole, double circuit to connect Oncor's Austin Ranch substation to BEPC's Josey Substation | 2021-06-14 |  |  | 1031696.83 | 734535.02 |  |  | 45% | NA | 138 | 0.072 | 959 ACSS-TW | Single Pole Concrete or Steel | NA | NA | 100 | 0.072 | 25.101(c)(5)(B) | Affidavit to be filed upon request
Note on H2: aboling: Please enter only a single integer, if possible.
Note on I2: aboling: Please enter only a single integer, if possible.
Note on M2: aboling: If applicable.
Note on N2: aboling: If applicable.