## MonthlyReportForm-AEPTX North
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
42483912 | Bison to Powell Field Rebuild | Crockett/Reagan | Upgrade Powell Field Station | 2016-12-01 | 2017-05-31 | 2017-08-08 |  | 539000 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
42624777 | Abliene Distribution Automation Circuit Reconfiguration- Transmission Assets Only | Taylor | Transmission High-Side work to automate distribution feeder breakers and station regulators at 8 Abilene area stations. | 2017-11-15 | 2018-08-15 | 2018-10-05 |  | 2374000 |  |  | 99 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Within existing Station Property
42611234 | Rankin Sub | Upton | Upgrade fuses and circuit switcher | 2017-12-11 | 2018-06-30 | 2018-05-30 |  | 650000 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42598596 | SW Vernon | Wilbarger | Upgrade transformer and equipment (replace existing station). | 2018-01-02 | 2018-12-31 | 2018-12-14 |  | 7700000 |  |  | 99 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42724179 | Tardis 138-kV Station | Knox | Build a new 138-kV three breaker ring bus 3000 Amps/ 40 kA (ultimate design will be limited to a four breaker ring bus). Add SCADA at the station. | 2018-05-10 | 2018-03-31 | 2019-10-29 |  | 6263000 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42724196 | Benjamin 69-kV Substation | Benjamin/Knox | Expand existing Benjamin 69-kV station with 138-kV bus and switches and add a 138/12-kV transformer. | 2018-06-01 | 2019-09-15 | 2019-12-20 |  | 3282000 |  |  | 99 | 69 | 69/138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42611170a | Ely REA Tap (Capella Box Bay) - Merkel 69-kV Rebuild | Taylor | Rebuild and reconductor the Ely REA Tap (Capella Box Bay) to Merkel 4.55 miles segment of the Ely REA Tap (Capella Box Bay) to Eskota 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-01-02 | 2018-04-30 | 2020-05-21 |  | 3000000 |  |  | 99 | 69 |  | 4.55 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 4.55 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noitced. Utilizing existing easements.
42578959 | Carver Station | Sutton | Carver Station: Construct new 138-kV 3000 amps, 40 kA four breaker-ring station. | 2018-02-05 | 2019-12-31 | 2019-11-12 |  | 9527329 |  |  | 98 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42578960 | Carver Station | Sutton | Sonora Station: Replace 138-kV circuit breakers | 2018-02-05 | 2019-12-31 |  |  | 1054914 |  |  | 40 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42578953 | Carver Station | Sutton | Reterminate the Friend Ranch - Sonora 138-kV transmission line into New Carver Station. | 2018-02-05 | 2019-12-31 | 2019-11-12 |  | 820481 |  |  | 98 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42578954 | Carver Station | Sutton | Reterminate Live Oak - Sonara 138-kV transmission line into New Carver Station. | 2018-02-05 | 2019-12-31 |  |  | 848021 |  |  | 40 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42578957 | Carver Station | Sutton | Reterminate the Hamilton Road - Sonora 138-kV transmission line into New Carver Station. | 2018-02-05 | 2019-12-31 | 2019-11-12 |  | 640456 |  |  | 95 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42578963 | Carver Station | Sutton | Friend Ranch Station: Update relay towards Sonora Station. | 2018-02-05 | 2019-12-31 |  |  | 250725 |  |  | 40 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42729882 | Carver Station | Sutton | El Dorado Live Oak Station: Update relay towards Sonora Station. | 2018-02-05 | 2019-12-31 |  |  | 272399 |  |  | 40 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42730541 | Carver Station | Sutton | Carver Bus Tie: Install a bus tie from Sonora Station 138-kV bus to New Carver Station 138-kV bus. | 2018-02-05 | 2019-12-31 |  |  | 815390 |  |  | 40 |  | 138 | 0.2 | 477 KCM ACSR "Hawk" | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within Station Property
42579281 | Vernon Main St. Substation | Vernon/Wilbarger | Install two 14.4 MVAR Capacitor Banks to the Vernon Main St. Substation 138-kV bus | 2018-02-05 | 2018-06-29 | 2018-12-20 |  | 2113300 |  |  | 99 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42630204 | Vernon Main St. Substation | Vernon/Wilbarger | Relocate transmission line structures on Vernon Main St. - Oklaunion 138-kV line to accommodate 1- 14.4 MVAR capacitor bank. | 2018-02-05 | 2018-06-29 | 2018-10-30 |  | 382057 |  |  | 99 | 138 |  | 0.03 | 795 KCM ACSR "Drake" | Steel H-Frame |  |  |  |  | 16 TAC 25.83(a)(3) | Within Station Property
42738417 | Abilene Maple St station - DACR Gridsmart upgrades- Transmission Assets Only | Abilene/Taylor | Transmission High-Side work for Distribution Automation Circuit Reconfiguration upgrades and associated circuit breaker upgrades | 2018-02-26 | 2018-06-29 | 2018-08-07 |  | 368611 |  |  | 98 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42598869 | Alpine - Alpine REA 69-kV Rebuild | Alpine/Brewster | Rebuild, reconductor, and partially relocate 69-kV transmission line to 138-kV standards. Continue to operate at 69 kV. | 2018-02-05 | 2018-11-16 | 2018-12-11 |  | 9079106 |  |  | 99 | 69 |  | 8.16 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 8.16 | 100 | 1.32 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landonwers Noticed. Consent and new easement & supplements were acquired as necessary.
42629573a | Paint Creek - Haskell Tap 69-kV Rebuild | Haskell | Rebuild 2.03 miles of wood double circuit H-frame and 9.53 miles of wood single circuit single pole transmission line from Paint Creek to Haskell Tap. New structures will be steel single pole with the 2 mile section rebuilt for continued double circuit operation and capable of 138-kv operation, but will continue to operate at 69 kV this time. One circuit reconductor is included for this project. | 2019-01-17 | 2019-05-10 | 2019-04-23 |  | 14204835 |  |  | 99 | 69 |  | 11.56 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 11.56 | 100 | 2 | 16 TAC 25.101 (c)(5)(B) | Landowner consent aquired as necessary for Blow-out requirements. Landowners Noticed.
42629583 | Haskell to Paint Creek 69-kV Rebuild | Haskell | Reconductor of 2.03 miles of the rebuilt double circuit H-frame in Project No. 42629573a that goes from Paint Creek to Haskell. | 2019-01-17 | 2019-05-10 | 2019-04-23 |  | 2334222 |  |  | 99 | 69 |  | 2.03 | 795 KCM ACSS "Drake" |  |  | 2.03 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42578748 | Lotebush Station | Reeves | Pig Creek to Permian Basin 138-kV: Terminate the Pig Creek to Permian Basin 138-kV transmission line into new Lotebush 138-kV Station. | 2018-02-24 | 2018-11-02 | 2018-12-05 |  | 882118 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within New Station Property
42583744 | Crane - McElroy 69-kV Rebuild | Crane | Rebuild and reconductor the Crane to McElroy 69-kV transmission line to 138-kV Standards. Will continue to operate at 69 kV. | 2018-02-24 | 2018-04-18 | 2018-11-29 |  | 5331005 |  |  | 99 | 69 |  | 2.27 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 2.27 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42694371 | Radium: Replace CB 5905 and upgrade relays | Jones | Replace CB-5905, disconnect switches; Install New Hamlin Line Circuit Breaker; Install 69kV bus CCVT's; Add 16ft x 18ft DICM expansion, Removed old control house. | 2018-03-05 | 5/31/218 | 2021-05-17 |  | 1966260 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42612173 | Anson Substation | Anson/Jones | Install new DICM, breakers, and switches. | 2018-03-15 | 2019-01-25 | 2019-01-23 |  | 3458211 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42583750 | Kinnison Box Bay | Crane | Construct 138-kV Box Bay at Crane Tap #2. Will operate at 69 kV. | 2018-03-19 | 2018-06-28 | 2018-10-18 |  | 1326140 |  |  | 99 |  | 69 |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.83(a)(3) | Constructed within existing easements. Landowners Noticed.
42583736 | Crane - Kinnison 69-kV Rebuild | Crane | Rebuild and Reconductor the Crane to New Kinnison Box Bat 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-03-19 | 2018-06-28 | 2018-10-18 |  | 3566650 |  |  | 99 | 69 |  | 1.09 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 1.09 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42583730 | Texas-New Mexico Pipeline (TXNMP) - Sage 69-kV Rebuild | Crane | Rebuild and reconductor the TXNMP to Sage 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-03-19 | 2018-06-28 | 2019-01-10 |  | 6625576 |  |  | 99 | 69 |  | 2.53 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 2.53 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42583749 | Cardona Switch | Crane | Construct 138-kv platform switch with H-frame structure at Cardona (fomerly Crane Airport SW 6698). All serier equipment shall be rated for a minimum of 1200 Amps. Will continue to operate at 69 kV. | 2018-03-19 | 2018-06-28 | 2018-12-07 |  | 469838 |  |  | 99 | 69 |  |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.83(a)(3) | Constructed within existing easements. Landowners Noticed.
42681653 | Kelton Switch | Crane | Construct 138-kv platform switch with H-frame structure at Kelton (fomerly Crane Airport SW 6697). All series equipment shall be rated for a minimum of 1200 Amps. Will continue to operate at 69 kV. | 2018-03-19 | 2018-06-28 | 2018-12-07 |  | 469840 |  |  | 99 | 69 |  |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.83(a)(3) | Constructed within existing easements. Landowners Noticed.
42614412a | Anson - Hawley Exxon Tap 69-kV Rebuild | Anson/Jones | Rebuild and reconductor the Anson to Hawley Exxon Tap 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-09-24 | 2019-03-11 | 2019-07-29 |  | 10086113 |  |  | 99 | 69 |  | 9.95 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 9.95 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42705005 | Rio Pecos - Sun Valley 69-kV Rebuild | Crane Pecos | Rebuild and reconductor the Rio Pecos to Sun Valley 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-05-04 | 2018-10-10 | 2018-10-05 |  | 7886632 |  |  | 99 | 69 |  | 9.5 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 9.5 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42705002 | Sun Valley - Masterson Field 69-kV Rebuild | Pecos | Rebuild and reconductor the Sun Valley to Masterson Field 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-08-23 | 2018-12-21 | 2018-12-21 |  | 6032579 |  |  | 99 | 69 |  | 7.2 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 7.2 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42630437 | Elm Creek Station: Breaker Replacement | Abilene/Taylor | Replace 138-kV Circuit Breaker 5985,5980, and 5465. Replace 138-kV Circuit Switches 5010, 4728, and 4718. | 2018-06-05 | 2018-12-31 | 2018-12-26 |  | 5120115 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within existing Station Property
42673514 | Rule 69-kV Station: Rebuild | Rule/Haskell | Expand Station Property and Rebuild the Rule 69-kV Station to a 2000A, 40kA, Three-Breaker Box Bay. | 2018-06-05 | 2018-05-03 | 2019-10-30 |  | 3587873.3 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property purchased
42630281 | Vernon Station (ERCOT): Breaker Replacement | Vernon/Wilbarger | Replace 69-kV Circuit Breakers 6050,5460,3720,1535, and 130. | 2018-10-05 | 2019-06-26 |  |  | 4303464 |  |  | 50 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within existing property
42707034 | Abilene Northwest: Remote End Work | Abilene/Taylor | Install 138-kV CCVT's and arresters. | 2018-08-09 | 2018-12-31 | 2018-10-10 |  | 454016.2 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within existing property
42707035 | Mulberry Creek: Remote End Work | Abilene/Jones | Install 138-kV CCVT's, wavetrap, arresters, and carrier equipment. | 2018-08-09 | 2018-12-31 | 2019-01-25 |  | 514330.3 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within existing property
42705000 | Masterson Field - Pecos Valley 69-kV Rebuild | Pecos | Rebuild and reconductor the Masterson Field to Pecos Valley 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-06-05 | 2019-06-06 | 2018-12-21 |  | 7522606 |  |  | 99 | 69 |  | 8.96 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 8.96 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42624955 | Pecos Valley - TNMP Gomez 69-kV Rebuild | Pecos | Rebuild and reconductor the Pecos Valley to TNMP Gomez 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-06-05 | 2019-10-02 | 2019-07-19 |  | 11815275 |  |  | 99 | 69 |  | 14.23 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 14.23 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42624954 | TNMP Gomez - Ft. Stockton SS 69-kV Rebuild | Pecos | Rebuild and reconductor the TNMP Gomez to Fort Stockton SS 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-06-05 | 2019-12-20 | 2019-08-30 |  | 6249223 |  |  | 99 | 69 |  | 4.83 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 4.83 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42625102 | Bronte Atlantic - Miles 69-kV Rebuild | Miles/Runnels, Coke | Rebuild and reconductor the Bronte Atlantic to Miles 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-09-01 | 2019-05-15 | 2020-02-17 |  | 18245883 |  |  | 99 | 69 |  | 17.61 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 17.61 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42630529 | Chillicothe - Vernon 69-kV Rebuild | Chillicothe, Hardeman/Vernon, Wilbarger | Rebuild and reconductor the Chillicothe to Vernon 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-07-09 | 2018-12-21 | 2018-12-22 |  | 11992158 |  |  | 99 | 69 |  | 14.72 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 14.72 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42630265 | Childress - Kirkland 69-kV Rebuild | Kirkland/Childress | Partially rebuild and reconductor the Childress to Kirkland 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-08-28 | 2020-11-30 | 2020-11-17 |  | 7900000 |  |  | 99 | 69 |  | 5.67 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 5.67 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42614412b | Abilene NW - Onyx 69-kV Rebuild | Taylor Jones | Rebuild and reconductor the Abilene NW to Onyx REA 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-09-24 | 2020-05-15 |  |  | 3730481 |  |  | 15 | 69 |  | 3.55 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 3.55 | 100 | 1.02 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowner consent aquired as necessary. Utilizing existing easements. Landowners Noticed.
42738858 | Abilene NW - Ft. Phantom 138-kV Line: Raise Conductor | Taylor | Install structures to raise existing Abilene NW to Ft. Phantom 138-kV transmission line to provide clearance for Abilene NW to Onyx 69-kV Rebuild. | 2018-09-24 | 2019-05-15 | 2019-02-20 |  | 710882 |  |  | 99 | 138 |  |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Consent Aquired
42738864 | Abilene NW - Paint Creek 138-kV Line: Raise Conductor | Taylor Jones | Install structures to raise existing Abilene NW to Paint Creek 138-kV transmission line to provide clearance for the Abilene NW to Onyx 69-kV Rebuild. | 2018-09-24 | 2019-05-15 | 2019-01-21 |  | 1081901 |  |  | 99 | 138 |  |  |  | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Consent Aquired
42625105 | Edith Humble - Robert Lee 69-kV Rebuild | Coke | Partially rebuild and reconductor the Edith Humble to Robert Lee 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-08-24 | 2019-12-05 | 2020-01-13 |  | 10377325 |  |  | 99 | 69 |  | 9 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 9 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42630552 | Yellowjacket - Menard Phillips Tap 69-kV Rebuild | Menard/Mendard, Kimble | Rebuild and reconductor the Yellowjacket to Menard Phillips Tap 69-kV transmission line to 138--kV standards. Will continue to operate at 69 kV. | 2019-09-16 | 2021-03-31 |  |  | 13982601 |  |  | 99 | 69 |  | 15.4 | 795 KCM ACSS "Drake" | Steel Mono Pole | 50 | 15.4 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42630266 | Kirkland - Acme Best Wall 69-kV Rebuild | Kirkland/Childress, Hardeman | Partially rebuild and reconductor the Kirkland to Acme Best Wall 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-08-28 | 2020-04-30 | 2020-04-22 |  | 6748748 |  |  | 99 | 69 |  | 13.3 | 477 kcmil 72/ACSR "Hawk" | Concrete Mono Pole | Centerline | 13.3 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42707020 | Acme Best Wall - Quanah 69-kV Rebuild | Quanah/Hardeman | Partially rebuild and reconductor the Acme Best Wall to Quanah 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-08-28 | 2019-12-20 | 2019-12-18 |  | 6257476 |  |  | 99 | 69 |  | 3.73 | 477 kcmil 72/ACSR "Hawk" | Concrete Mono Pole | Centerline | 3.73 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42643899 | Bison Station | Crockett | Bison Station: Construct new 69-kV 3000 amps, 40 kA, three braker-ring bus station. | 2018-09-05 | 2019-05-31 | 2019-07-18 |  | 4749189 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42785355 | Solstice Station: Add 138-kV Terminal | Pecos | Add new 138-kV, 4000A, 63kA line terminal at Solstice Station for the Solstice to Saragosa 69-kV transmission line rebuild and conversion to 138-kV. Install DICM expansion module to accommodate new relay for new terminal. | 2018-09-10 | 2019-05-10 | 2019-12-19 |  | 3379053 |  |  | 98 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42704987 | Menard Phillips Tap - Junction 69-kV Rebuild | Junction/Kimble | Rebuild, reconductor, and partially relocate the Menard Phillips Tap to Junction 69-kV tranmission line to 138-kV standards. Will continue to operate at 69 kV. | 2020-09-16 | 2021-12-31 |  |  | 10431757 |  |  | 80 | 69 |  | 13.95 | 795 KCM ACSS "Drake" | Steel Mono Pole | 50 | 13.95 | 100 | 0.97 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowner consent acquired as necessary. Utilitizing existing easements. Landowners Noticed.
42641117 | Sonora - Sonora Atlantic 69-kV Rebuild | Sonora/Sutton | Rebuild and reconductor the Sonora to Sonora Atlantic 69-kV transmission line to 138-kV standards. Will continue to be operated at 69 kV. | 2018-11-04 | 2019-05-03 | 2019-04-26 |  | 8199637 |  |  | 99 | 69 |  | 11.63 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 11.63 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42718258 | Paint Creek Station: Breaker Replacement | Haskell | Replace 8 OCB's & associated switches, repalce 6 - 69-kV switches, all cap & pin insulators and copper bus tubing. | 2018-10-04 | 2020-07-17 | 2021-03-05 |  | 5683074 |  |  | 99 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Within existing Station Property
42624963 | Cross Plains - Santa Anna Tap 69-kV Rebuild | Cross Plains/Callahan, Brown, Coleman | Rebuild and reconductor the Cross Plains to Santa Anna Tap 69-kV transmission line to the 138-kV standard. Will continue to operate at 69 kV. | 2018-11-05 | 2019-12-31 | 2019-12-21 |  | 13412957 |  |  | 99 | 69 |  | 14.94 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 14.94 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42761447 | Santa Anna Tap - Santa Anna 69-kV Rebuild | Santa Anna/Colemen | Rebuild and reconductor the Santa Anna Tap to Santa Anna 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-11-05 | 2019-12-31 | 2019-12-20 |  | 11204749 |  |  | 99 | 69 |  | 13.6 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 13.6 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42729405 | Crockett Heights - Friend Ranch 69-kV Rebuild | Crockett | Rebuild and reconductor the Crockett Heights to Friend Ranch 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-11-02 | 2019-05-31 | 2019-05-15 |  | 1632994.6 |  |  | 99 | 69 |  | 1.23 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 1.23 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42630526 | Lake Pauline - Chillicothe 69-kV Rebuild | Chillicothe/ Hardeman | Rebuild and reconductor the existing Lake Pauline to Chillicothe 69-kV transmission line to 138-kv standards. Will continue to operate at 69 kV. | 2019-01-07 | 2019-04-26 | 2019-04-09 |  | 8300500 |  |  | 99 | 69 |  | 9 | 447 kcmil T2/ACSR "Hawk" | Steel Mono Pole | Centerline | 9 |  |  | 16 TAC 25.101 (c)(5)(B) | Easements supplemented as necessary. Utilitizing existing easements. Landowners Noticed.
42763540a | Saragosa - Solstice 69-kV Rebuild | Revees Pecos | Rebuild and reconductor a 15.26 mile segment of the existing Saragosa to Solstice 69-kV transmission line to 138-kV standards and upgrade voltage to operate 138 kV when Project is fully completed. | 2018-12-02 | 2019-09-06 | 2019-12-19 |  | 15099957 |  |  | 98 | 69 | 138 | 15.26 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 15.26 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42858377 | Ft. Stockton Plant - Solstice 138-kV: Raise Structures | Pecos | Install 32 structures along the Solstice to Ft. Stockton Plant 138-kV transmission line in order to increase the MOT from 203 degrees F to 239 degrees F, and provide a 202 MVA Rating. | 2019-08-01 | 2019-12-20 | 2019-08-15 |  | 2306157 |  |  | 95 | 138 |  |  |  | H-Frame Wooden Poles | Centerline |  |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42658127 | Woodward 2 Substation | Pecos | Upgrade DME, SDR, and associated metering equipment at Generator-Owned Woodward 2 Substation. | 2019-01-04 | 2019-01-31 |  |  | 432028 |  |  | 98 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Generator-Owned Station Property
42700008 | Bobcat Hills Solar Interconnect: Rio Pecos 138-kV Station | Pecos | Rio Pecos Station: Compelet the Crane #4 position at the Rio Pecos substation by installing one breaker, two switches and associated terminal equipment. | 2019-01-07 | 2019-05-31 | 2019-12-06 |  | 2169978 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42729399 | Sonora Atlantic - Crockett Heights 69-kV Rebuild | Sutton Crockett | Rebuild and reconductor the Sonora Atlantic to Crockett Heights 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2019-01-05 | 2022-02-08 |  |  | 13463999.2 |  |  | 25 | 69 |  | 15.06 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 15.06 | 100 | 1.6 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowner consent aquired as necessary. Utilizing existing easements. Landowners Noticed.
42725092 | East Munday - Paducah Clare St. 138-kV Line Cut-in | Knox | Terminate the East Munday to Paducah Clare St 138-kV transmission line into new Tardis Station. | 2019-02-04 | 2019-03-15 | 2019-10-29 |  | 1120785 |  |  | 99 |  | 138 |  | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Landowner constent obtained
42644755 | Big Lake Substation: Update Relays | Big Lake/Reagan | Add DICM expansion, CB, and update relaying to accommodate the New Bison Station. | 2019-02-03 | 2019-06-21 |  |  | 1181700 |  |  | 25 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42611170b | Merkel - Scott REA Tap 69-kV Rebuild | Merkel/Taylor | Rebuild and reconductor the Merkel to Scott REA Tap 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2019-02-18 | 2019-04-30 | 2019-10-22 |  | 3000000 |  |  | 99 | 69 |  | 4.1 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 4.1 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements. Landowners Noticed.
42629566a | Onyx SW - Ft. Phantom Clear Fork Pump Station 69-kV Rebuild | Abilene/Jones | Rebuild and reconductor the Onyx SW - Ft. Phantom Clear Fork Pump Station 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2019-02-22 | 2019-04-24 |  |  | 17283518 |  |  | 0 | 69 |  | 6.82 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 6.82 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements. Landowners Noticed.
42762075 | Heartland - Yellowjacket TNC | Brady/McCulloch, Menard | Heartland to Yellowjacket: Build 18.75 miles of new transmission line to 138-kV standard and operate at 69 kV. | 2019-03-07 | 2019-10-21 |  | 19824000 | 19824000 |  |  | 95 |  | 69 | 18.75 | 959.6 ACSR/TW | Single Pole Brace Post |  |  | 100 | 18.75 | 46234 | CCN approved on 8/31/2017. AEP Texas North Division Portion Only
42762039 | Heartland Station | Brady/McCulloch | Hearland 69-kV Substation: Construct new four breaker ring bus, 69-kV substation, and accommodate for a future138-kV expansion. | 2019-03-04 | 2019-09-30 |  |  | 4781000 |  |  | 99 |  | 138/69 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42785349 | Saragosa Substation | Reeves | Saragosa 138-kV Substation: Construct 138-kV four-ring breaker substation laid out as a breaker and a half. | 2019-03-04 | 2019-12-31 | 2019-12-19 |  | 9613715 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner constent provided. Construction access and property transfer agreement under development.
42775581 | Cryo Substation | Reeves | Cryo 138-kV Substation: Construct 138-kV four-ring breaker substation laid out as a breaker and a half. | 2019-03-19 | 2019-11-20 | 2020-03-09 |  | 8448990 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner constent provided. Construction access and property transfer agreement under development.
42828772 | Bobcat Hills Solar Interconnect: Rio Pecos - LCRA Crane 138-kV Line Termination | Pecos | Build one span from the station dead-end to a pole owned by AEP outside Rio Pecos Station. Conductor rating should be 440 MVA. Install (1) OPGW shield wire, as the second path is currently in use. | 2019-04-06 | 2020-12-01 | 2021-06-02 |  | 331233 |  |  | 99 |  | 138 | 0.1 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within Station Property
42841255 | Crossover 138-kV Box Bay | Upton | Construct POD Box Bay with 3000A Moter-Operated switches, metering, & wavetrap. | 2019-04-06 | 2019-06-30 | 2019-07-10 |  | 1759100 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Exclusive easement obtained
42841282 | Crossover 138-kV Tap | Upton | Construct new Crossover 138-kV Tap line from new Drossover 138-kV Box Bay to Customer's substation. | 2019-04-06 | 2019-06-30 | 2019-07-10 |  | 887124 |  |  | 99 |  | 138 |  | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.1 | 16 TAC 25.101 (c)(5)(A) | Landowner constent obtained
42841258 | N. McCamey - Santa Rita 138-kV Line | Upton | Terminate the existing N. McCamey to Santa Rita 138-kV transmission line into new Crossover 138-kV Box Bay. | 2019-04-06 | 2019-06-30 | 2019-10-28 |  | 851258 |  |  | 99 |  | 138 |  | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Landowner constent obtained
42781716 | Solstice - Permian Basin 138-kV Line | Reeves | Terminate the Solstice to Permian Basin 138-kV transmission line new Basin Box Bay. | 2019-04-15 | 2019-06-28 |  |  | 510835 |  |  | 0 | 138 |  | 0.02 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 0.02 |  |  | 16 TAC 25.101 (c)(5)(A) | Utilizing existing easements
42968468 | Tardis - Benjamin Tap 138-kV Line | Knox | Construct approximately 1.74 miles of new 138-kV transmission line. | 2019-04-15 | 2019-07-15 | 2019-12-20 | 3264000 |  |  |  | 99 |  | 138 | 1.74 | 795 KCM T2 "Drake" | Steel Mono Pole |  |  | 100 | 1.74 | 48633 | PUC Docket 48633 Approved 01/04/2019
42643886 | Benjamin Tap - Benjamin 69-kV Line | Benjamin/Knox | Rebuild, reconductor, and convert the Benjamin Tap to Benjamin 69-kV transmission line to 138-kV standards and operate at 138-kV. | 2019-05-17 | 2019-09-15 | 2019-12-20 |  | 5006000 |  |  | 99 | 69 | 138 | 8 | 795 KCM T2 "Drake" | Steel Mono Pole | Centerline | 8 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements
42631273 | Belknap Station | Abilene/Jones | Construct a three 69-kV breaker ring station at 2000A, 40kA, expandable to six 69-kV breaker ring (2000A) and six 138-kV breaker ring bus (3000A) & add SCADA. | 2019-06-03 | 2020-06-30 |  |  | 4739642 |  |  | 0 |  | 138/69 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42629566b | Ft. Phantom Clear Fork Pump Station - Nugent Tap 69-kV Rebuild | Abilene/Jones | Rebuild, reconductor, and partially relocate the Ft. Phantom Clear Fork Pump Station to Nugent Tap 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2019-07-09 | 2019-08-30 |  |  | 1000000 |  |  | 0 | 69 |  | 0.7 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 0.7 | 100 | 0.24 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowner consent aquired as necessary. Utilizing existing easements. Landowners Noticed.
42763540b | Saragosa - Solstice 69-kV Rebuild & Conversion to 138-kV 69-kV Rebuild | Reeves Pecos | Rebuild and reconductor the remaining 3.44 miles of the existing Saragosa to Solstice 69-kV transmission line to 138-kV standards and upgrade voltage to operate at 138 kV. | 2019-07-08 | 2019-10-31 | 2019-12-19 |  | 3403922 |  |  | 98 | 69 | 138 | 3.44 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 3.3 | 100 | 3.44 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowners consent obtained
42629561 | Rainey Creek - Ft. Phantom Spillway 69-kV Rebuild | Taylor, Abilene/Jones | Rebuild and reconductor the Rainey Creek to Ft. Phantom Spillway 69-kV transmission line (Structuer 4/1) to 138-kV standards. Will continue to operate at 69 kV. | 2019-07-29 | 2019-12-17 |  |  | 8361163 |  |  | 0 | 69 |  | 7.6 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 7.6 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42766225 | Junction 69-kV Substation Rebuild | Junction/Kimble | Construct a new 69-kV Substation with two 2000A - 69-kV breakers adjacent to the existing Junction 69-kV Substation. Install circuit switcher. Install DICM. Remote station relay settings. | 2019-09-09 | 2020-03-31 | 2020-05-19 |  | 3298623 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42766490 | Junction - Yellowjacket 69-kV T-Line Retermination | Junction/Kimble | Reteriminate the Junction to Yellowjackt 69-kV transmission line into the rebuilt Junction 69-kV Substation. | 2019-11-04 | 2020-03-31 | 2020-05-01 |  | 429905 |  |  | 99 | 69 |  | 0.01 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
42766247 | Junction - Mason SW 69-kV T-line Retermination | Junction/Kimble | Reterminate the Junction to Mason SW 69-kV transmission line into the rebuilt Junction 69-kV Substation. | 2020-01-20 | 2020-03-31 | 2020-05-26 |  | 303678 |  |  | 99 | 69 |  | 0.01 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
42629573b | Haskell Tap - Stamford (Str. 339) 69-kV Rebuild | Haskell | Rebuild and reconductor the Haskell Tap tp Stamford (Structure 339) 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2019-08-10 | 2019-11-15 | 2020-01-15 |  | 12151884 |  |  | 99 | 69 |  | 9.6 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 9.6 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements. Landowners Noticed.
42629573c | Haskell Tap - Stamford (Str. 339 - Str. 332) 69-kV Rebuild | Haskell | Rebuild and reconductor the Haskell Tap to Stamford (Structure 339 to Structure 332) 69-kV transmission line to 138-kV standards. Will continue to operate at 693kv | 2019-09-23 | 2019-12-21 | 2020-01-15 |  | 545853.79 |  |  | 99 | 69 |  | 0.43 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 0.43 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements. Landowners Noticed.
42629793 | Wolfgang 69-kV Substation | Kent | Construct a new 69-kv, 2000 A, 40 kA, three breaker ring bus. Install (1) DICM along with all necessary panels, racks, and relays. All three line terminals at the substation will utilize fiber for line protection. | 2019-10-04 | 2020-05-15 |  |  | 5561412 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42935497 | Clairemont Tap Switch | Kent | Install 138-kV rated Monopole POP structure with SCADA controlled motor operated switches. | 2019-10-04 | 2020-05-15 |  |  | 784400 |  |  | 99 | 69 |  |  | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 |  |  |  | 16 TAC 25.83(a)(3) | Utilizing Existing Easements
42598593 | Cross Plains 69-kV Substation: Replace Control Building & Equipment | Cross Plains/Callahan | Replace control house with DICM and associated equipment. Replace CB 5130, MOS 2909, and SW 5068 and associated equipment. | 2019-10-13 | 2020-05-15 | 2021-06-05 |  | 3750735 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42629573d | Haskell Tap - Stamford (Str. 316 Stamfrod) 69-kV Rebuild | Haskell, Stamford/Jones | Rebuild and reconductor the Haskell Tap to Stamford Substation (Structure 316 - Stamford) 69-kV transmission line to 138-kV standards. Will continue to operate at 69-kV. | 2019-10-21 | 2020-02-18 | 2020-01-15 |  | 1662949.84 |  |  | 99 | 69 |  | 1.31 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 1.31 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements. Landowners Noticed.
42817457 | North Brady 69-kV Substation: Install relays | Brady/McCulloch | Install new current differntial relays at North Brady 69-kV Substation. | 2019-11-15 | 2020-04-01 |  |  | 530774 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42817462 | Mason 69-kV Substation: Replace relays | Brady/McCulloch | Replace relays at Mason 69-kV Substation. | 2019-11-15 | 2020-04-01 |  |  | 599941 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.101 (c)(5)(A) | Within Station Property
42762085 | Heartland to South Brady: Retermination | Brady/McCulloch | Construct 0.25 miles of 69-kV line with 138-kV construction standards between the South Brady Substation and the new Heartland Substation. | 2019-11-15 | 2020-04-01 |  |  | 829797 |  |  | 99 | 69 |  | 0.25 | Merline 336.4 ACSR 18/1 | [5 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42817452 | Eden - Yellowjacket Rebuild | Brady/McCulloch, Menard | Heartland to Yellowjacket Project: Rebuild a 0.20 mile portion of the Eden to Yellowjacket 69-kV line to double-circuit with the new line from Yellowjacket to Hearland in order to terminate the new line from Hearland into the Yellowjacket station. | 2019-11-05 | 2019-12-30 |  |  | 538623 |  |  | 99 | 69 |  | 0.2 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Landowner constent obtained
42629573e | Haskell Tap (Str. 332) - Stamford (Str. 316) 69-kV Rebuild | Haskell | Rebuild and reconductor the Haskell Tap (Str. 332) to Stamford Substation (Str. 316) 69-kV transmissionline to 138-kV standards. Will continue to operate at 69 kV. | 2019-12-09 | 2019-02-18 | 2020-01-15 |  | 1218650.26 |  |  | 99 | 69 |  | 0.96 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 0.96 | 100 | 0.4 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Utilizing existing easements. Landowners Noticed. Landowner constent aquired as necessay.
42753347 | Solstice Expansion for 345-kV Station | Pecos | Expand Solstice Station to build 345-kV station section in a breaker and a half configuration to add two 345-kV double-circuit transmission line termination, two 345/13-8kV, 675 MVA LTC autotransformers, and cut in the existing 138-kV station. Includes SCADA, equipment house, breakers, all other associated station protection and control equipment. | 2020-01-04 | 2020-12-31 |  | 35457000 | 42630708 |  |  | 97 |  | 345 | [7 empty] | 48787 | CCN approved on 5/28/2019 Additional Property Purchased
42629573f | Stamford - Corinth Tap 69-kV Rebuild | Stamford/Jones | Rebuild and reconductor the Stamford Substation to Corinth Tap 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2020-01-06 | 2020-07-31 | 2020-09-10 |  | 10980546.9 |  |  | 99 | 69 |  | 8.65 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 8.65 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements. Landowners noticed.
42917328 | Taygete Interconnection: Pig Creek 138-kV Substation | Pecos | Install one(1) 138-kV Breaker, SSO Relaying, and EPS Metering at Pig Creek 138-kV Substation in order to interconnect Taygete 250 MW Solar Farm. | 2020-01-18 | 2020-03-18 |  |  | 2200000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42786105 | Far West Texas Project: Solstice to Bakersfield 345-kV T-Line | Pecos | Build approximately 35.51 miles of new 345-kV double-circuit capable transmission line with OPGW from AEP Texas' Solstice 345-kV Substation to LCRA's Brakersfield 345-kV Substation. Only one circuit will be installed at constuction of this Project. | 2020-01-16 | 2020-11-20 |  | 78593000 |  |  |  | 98 |  | 345 | 35.51 | 1590 ACSS (Bundled) "Falcon" | Lattice Towers |  |  | 150 | 35.51 | 48787 | CCN approved on 5/28/2019
42872920 | Far West Texas Project: Solstice to Sand Lake 345-kV T-Line | Pecos | Build approximately 22.21 miles of new 345-kV double-circuit capable transmission line with OPGW from AEP Texas' Solstice 345-kV Substation to ONCOR's Sand Lake 345-kV Substation. Only one circuit will be installed at constuction of this Project. | 2020-01-16 | 2020-11-20 |  | 48424462 | 47992021 |  |  | 99 |  | 345 | 22.21 | 1590 ACSS (Bundled) "Falcon" | Lattice Towers |  |  | 150 | 22.21 | 48785 | CCN approved on 6/26/2019
42889865 | Abilene NW 69/138-kV Substation | Abilene/Taylor | Replace two 69-kV circuit breakers, associated switches, and one relay. | 2020-02-22 | 2020-04-29 |  |  | 835084 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42906795 | Rio Pecos - Crane 138-kV Line | Crane | Relocate two structures along the Rio Pecos to Crane 138-kV transmission line at the Hwy 385 crossing, as requested by TXDOT. | 2020-02-22 | 2020-04-02 | 2020-03-24 |  | 530640 |  |  | 99 | 138 |  | 0.44 | 795 KCM ACSS "Drake" | Wood H-Frame Steel Pole Dead End | Centerline |  |  |  | 16 TAC 25.101 (c)(5)(F) | Landowner Noticed
42763651 | Rio Pecos 138-kV Substation | Crockett | Install (3) 138-kV circuit breakers (3000A, 40kA) and disconnect switches. All series equipment shall be rated to a minimum 3000 Amps. Upgrade RTU. Add relay panels in ETT's control house. Remote end relay changes. | 2020-02-22 | 2021-04-15 |  |  | 3530114 |  |  | 10 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42764060 | Rio Pecos 138-kV Substation | Crockett | Replace Auto #1 with a 138/69 kV autotransformer with LTC (SCADA controlled). | 2020-02-22 | 2020-03-20 | 2020-05-05 |  | 2707529 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42762083a | N. Brady - Mason 69-kV Line: Cut-In | Brady/McCulloch | Cut-in N. Brady to Mason 69-kV transmission line north segament into new Heartland Substation. | 2020-02-22 | 2020-04-01 |  |  | 1607563 |  |  | 99 | 69 |  | 0.63 | Merline 336.4 ACSR 18/1 |  |  |  | 75 | 0.63 | 16 TAC 25.101 (c)(5)(A) | Landowner Easements Obtained
42762083b | N. Brady - Mason 69-kV Line: Cut-In | Brady/McCulloch | Cut-in N. Brady to Mason 69-kV transmission line south segament into new Heartland Substation. | 2020-02-22 | 2020-04-01 |  |  | 1607570 |  |  | 99 | 69 |  | 0.64 | Merline 336.4 ACSR 18/1 |  |  |  | 75 | 0.64 | 16 TAC 25.101 (c)(5)(A) | Landowner Easements Obtained
42657763 | Eskota Tap - Eskota 69-kV Rebuild | Fisher, Nolan | Rebuild and reconductor the Eskota Tap to ONCOR Eskota double-circuit transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2020-03-06 | 2020-06-01 |  |  | 2684944 |  |  | 98 | 69 |  | 5.58 | 795 KCM ACSS "Drake" | Steel Mono Pole | Center | 2.79 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements. Landowners noticed.
42840284a | Jayton-Rotan 69-kV: Cut-In to Wolfgang 69-kV Substation | Kent | Terminate the Jayton to Rotan 69-kV transmission line into new Wolfgang 69-kV Substation & rebuild a segment of transmission line from Structure 20/4 to 20/3A. | 2020-03-18 | 2020-05-15 | 2020-12-18 |  | 239088.6667 |  |  | 99 | 69 |  | 0.22 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 0.22 |  |  | 16 TAC 25.101 (c)(5)(A) & 16 TAC 25.101 (c)(5)(B) | Consent Obtained Landowner Noticed
42840284b | Jayton-Rotan 69-kV: Cut-In to Clairmont Sun Oil Tap | Kent | Rebuild and reconductor a segment of the Jayton to Rotan 69-kV transmission line from Structure 28/1 to 27/6. | 2020-03-18 | 2020-05-15 | 2021-04-13 |  | 456442 |  |  | 99 | 69 |  | 0.45 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 0.45 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed
42840284c | Wolfgang-Rotan 69-kV: Rebuild | Kent/Stonewall | Rebuild and reconductor a segment of the Wolfgang to Rotan 69-kV transmission line from Structure 20/3C to 19/1 | 2020-09-15 | 2020-11-01 |  |  | 1358458.3333 |  |  | 30 | 69 |  | 1.22 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 1.22 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed
42839809 | Wolfgang - Mozart 69-kV Construction | Kent | Terminate the existing Mozart Tap line from new POI into new Wolfgang 69-kV Substation. | 2020-03-18 | 2020-05-15 | 2020-11-12 |  | 491418.26 |  |  | 99 | 69 |  | 0.22 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 0.22 |  |  | 16 TAC 25.101 (c )(5)(A) | Within Station Property
42935497 | Clairmont Sun Oil 69-kV Tap: POP Switch | Kent | Install new 138-kV rated Monopole Phase-Over-Phase Structure with SCADA-Controlled Switches at Clairmont Sun Oil Tap. Will be operated at 69-kV. | 2020-03-18 | 2020-05-15 | 2021-04-12 |  | 784400 |  |  | 99 | 69 |  |  | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 |  |  |  | 16 TAC 25.83(a)(3) | Within Existing Easement
42998495 | Clairmont Sun Oil Tap 69-kV Reterminate | Kent | Install new structures 1/1 & 1/2, reconductor & reterminate the Jayton to Rotan 69-kV transmission line into Clairmont Sun Oil Tap. | 2020-03-18 | 2020-05-15 | 2021-04-13 |  | 194568 |  |  | 99 | 69 |  | 0.08 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 0.08 |  |  | 16 TAC 25.101 (c )(5)(A) | Within Existing Easement Consent Obtained
42611547 | Rainey Creek-Spillway 69-kV T-Line: Cut-In to new Belknap Substation | Jones | Terminate the Rainey Creek to Spillway 69-kV transmission line from 0.30 mile west of new Belknap Substation into new Belknap 69-kV Substation. | 2020-05-01 | 2020-07-31 |  |  | 1681267 |  |  | 0 | 69 |  | 0.3 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 0.3 |  |  | 16 TAC 25.101 (c )(5)(A) | Landowner Consent Obtained
42764083 | Albany-Rainey Creek 69-kV T-Line: Cut-In to new Belknap Substation | Jones | Terminate the Albany to Rainey Creek 69-kV transmission line into new Belknap 69-kV Substation. | 2020-05-01 | 2020-07-31 |  |  | 480254.4 |  |  | 0 | 69 |  | 0.1 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 0.1 |  |  | 16 TAC 25.101 (c )(5)(A) | Landowner Consent Obtained
42765553 | Spillway-Belknap 69-kV T-Line: Cut-In to new Belknap Substation | Jones | Terminate the Spillway to Belknap 69-kV transmission line from 0.50 mile west of new Belknap Substation into new Belknap 69-kV Substation. This line section will be built double-circuit capable with only one circuit installed. Will be built to 138-kV standards but operated at 69-kV. | 2020-05-01 | 2020-07-31 |  |  | 1523912 |  |  | 0 | 69 |  | 0.5 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 0.5 |  |  | 16 TAC 25.101 (c )(5)(A) | Landowner Consent Obtained
42629573g | Corinth Tap - Anson 69-kV Rebuild | Anson/Jones | Rebuild and reconductor the Corinth Tap to Anson 69-kV transmission line to 138-kV standards. Will continue to be operated at 69-kV. | 2020-04-27 | 2020-09-15 | 2020-09-10 |  | 8797131.79 |  |  | 99 | 69 |  | 6.93 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 6.93 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easements Landowners Noticed
42786055 (P17089001) | Solstice 345-kV Station: Install 50-MVAR Reactor | Pecos | Install one 50-MVAR 345-kV line reactor and associated station equipment at Solstice. Install 345-kV shunt reactor, 3000 amps, 50-kA. Install 345-kV breaker, circuit switcher, motor operated switch. SCADA and other associated equipment | 2020-05-04 | 2020-12-31 |  | 3000000 | 3452738 |  |  | 98 |  | 345 | [7 empty] | 48787 | CCN approved on 5/28/2019
T10053124 (P17093002) | Solstice - Ft. Stockton SW 69-kV: Rebuild & Conversion to 138-kV | Pecos | Rebuild and reconductor the existing Solstice to Ft. Stockton SW 69-kV transmission line to 138-kV standards and upgrade voltage to operate 138 kV when Project is fully completed. | 2020-05-04 | 2020-12-18 |  |  | 13035466 |  |  | 95 | 69 | 138 | 16.12 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 16.12 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
42919582 (P18145001) | Pig Creek 138-kV Substation Expansion | Pecos | Expand the existing Pig Creek 138-kV Ring Bus. Configure to 3 ring breaker and half. Install 3-138-kV breakers. Add new switch and relaying for Tarbush connection. | 2020-06-04 | 2020-11-15 |  |  | 6560000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
43017833 (P19002001) | Pershing Permanent 138-kV Box Bay | Taylor | Construct a 3000A, 40kA, 138-kV Box Bay with Motor-Operated Switches. Install B2500 Cabinet, RTU, Metering, & SCADA. This Project is for an interconnect with Taylor County Electric CoOp and Golden Spread Electric CoOp. | 2020-07-15 | 2020-11-02 | 2020-12-04 |  | 1924593 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner Consent Obtained
42977077 (P18237001) | Solstice 138/345-kV Station: Install PST | Pecos | Moving the spare PST from Nelson Sharpe to Solstice and installing it on the Ft Stockton Plant to Solstice 138-kV line. Install a 14.4 MVAR capacitor bank on the 138 kV bus. | 2020-07-08 | 2021-03-30 |  |  | 6570640 |  |  | 70 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42977755 (P18168001) | Lynx 138-kV Station: Add Third Ring | Pecos | Construct the third rung in the breaker and half, add three breakers, and associated terminal equipment. Add tie line metering on the 16th Street and Rio Pecos lines. | 2020-07-04 | 2021-03-30 |  |  | 4068582 |  |  | 98 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42785822 (A18018008) | Lake Pauline 138-kV Station: Rehab | Hardeman | Replace 138-kV CBs 4905 and 3710 due to asset health scores. Replace 138/69-kV Auto 130 MVA with LTC and SCADA Control. Install 138-kV breaker (3000A, 40kA) at the high side of the new auto. | 2020-09-16 | 2021-05-14 | 2021-05-14 |  | 3702361 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42841911 (P17093009) | Solstice 138-kV Station | Pecos | Install one additional 3000A, 40 kA 138-kV breaker for new Ft Stockton SW terminal | 2020-10-04 | 2020-12-17 |  |  | 1187395 |  |  | 90 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42824787 (P17093010) | Rio Pecos 138-kV Station | Pecos | Install four 3000A, 40 kA 138 kV breakers, Update 138-kV bus differential relaying, and modify relays for old 69-kV Barrilla Junction terminal | 2020-10-04 | 2021-01-09 |  |  | 2946140 |  |  | 80 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42673516 (A15707333) | Aspermont 69-kV Substation: Rebuild 69-kV Yard | Aspermont / Stonewall | Rebuild Aspermont 69-kV yard to the east on property addition, Replace the 138/69 kV Autotransformer, Install a 138-kV CB on the high side of the autotransformer, Install new three phase 69-kV bus CCVTs, Install new 138-kV, 50 kVA Power PT, & Install a new DICM. | 2020-11-14 | 2021-12-10 |  |  | 6841057 |  |  | 60 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased for Expansion
42918004 (P18164002) | Goodlett 69-kV Substation | Hardeman | Construct new in-and-out station at 138-kV operated at 69-KV, add three 138-KV motor operated switches, one 138-KV bus tie SW, circuit switcher for dist bank, install SCADA | 2020-12-11 | 2021-10-01 |  |  | 2932796 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10129591 (P18245004) | Bond Road 69-kV Substation: Expand EPIC Tap | Sonora/Sutton | Extend bus to accommodate switch tap to EPIC. Install Metering, RTU, & SCADA. | 2020-01-15 | 2021-05-15 |  |  | 1222128 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42840275 (P16128003) | Jayton 69-kV Substation | Jayton/Kent | Install new switches and upgrade relay panels | 2020-12-04 | 2020-12-30 |  |  | 1223810 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42977711 (P18168002) | Lynx 138-kV Switch Station: Line Span to terminate 16th St. 138-kV line. | Pecos | Line Span to terminate the 16th St. side of the 16th St. to Rio Pecos 138-kV transmission line into Lynx 138-kV Station. | 2020-12-04 | 2020-12-31 |  |  | 437149 |  |  | 99 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Texas Property
42977749 (P18168003) | Lynx 138-kV Switch Station: Line Span to terminate Rio Pecos 138-kV line. | Pecos | Line Span to terminate the Rio Pecos side of the 16th St. to Rio Pecos 138-kV transmission line into Lynx 138-kV Station. | 2020-12-04 | 2020-12-31 |  |  | 437149 |  |  | 99 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Texas Property
T10129078 (P18168009) | Rio Pecos 138-kV Station: Reterminate 16th St. Terminal | Pecos | Line span to terminate the Lynx–Rio Pecos (TNMP) 138-kV transmission line at Rio Pecos. | 2020-12-04 | 2020-12-31 |  |  | 347582 |  |  | 95 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Texas Property
T10053225 (P17093005) | Sun Valley 138-kV Substation | Pecos | Construct new 138-kV substation in & out with circuit switcher. Replace 69-kV switches with 3000A 138-kV switches. | 2021-01-04 | 2021-08-23 |  |  | 2843990 |  |  | 50 | 69 | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10053364 (P17093008) | Ft. Stockton 138-kV Switch Station | Pecos | Construct new 3000A, 40kA, 138-kV three-breaker ring bus station and install metering. | 2021-02-05 | 2021-07-12 |  |  | 6347326 |  |  | 80 | 69 | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42998141 (P19109003) | Taygete II Solar Interconnection: Pig Creek 138-kV Substation | Pecos | Install one(1) 138-kV Breaker, SSO Relaying, and EPS Metering at Pig Creek 138-kV Substation in order to interconnect Taygete 256.25 MW Solar Farm. | 2021-01-04 | 2021-01-31 |  |  | 1919999 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10132172 (P19109001) | Taygete II Solar Interconnection: Pig Creek 138-kV Substation | Pecos | Construct dead-end POI at Pig Creek 138-kV Substation in order to interconnect Taygete 256.25 MW Solar Farm. | 2021-01-04 | 2021-01-31 |  |  | 1919999 |  |  | 0 |  | 138 | 0.02 | 795 KCM ACSS "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
T10076859 (P19050001) | Hayter 138-kV Box Bay | Pecos | Construct new 138-kV POD Box Bay with revenue metering. | 2021-01-04 | 2021-05-31 |  |  | 1888728 |  |  | 15 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within AEP Texas Property
T10076861 (P19050002) | Alamito Creek - Solstice 138-kV Line: Cut-In to Hayter 138-kV Box Bay | Pecos | Terminate the Alamito Creek to Solstice 138-kV transmission line into new Hayter Box Bay | 2021-01-04 | 2021-05-31 |  |  | 1061504 |  |  | 15 | 138 |  | 0.25 | 795 KCM ACSS "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Texas Property
T10127113 (P19228003) | Avenger 69-kV Switch: Construct POD w/3 switches | Cross Plains /Callahan | Install 138-kV rated Monopole POP structure with SCADA controlled motor operated switches. | 2021-01-11 | 2021-03-30 | 2021-05-05 |  | 1026417 |  |  | 99 |  | 69 |  |  | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | TEC Consent Obtained
T10127123 (P19228007) | Avenger 69-kV Switch: Cut-in POD w/3 Switches | Cross Plains /Callahan | Reterminate Cross Plains to Putnam 69-kV transmission line into the new Avenger 69-kV Switch | 2021-01-11 | 2021-03-30 | 2021-05-05 |  | 663660 |  |  | 99 | 69 |  | 0.01 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.01 | 16 TAC 25.101 (c)(5)(A) | TEC Consent Obtained
T10179002 (P19228011) | Avenger 69-kV Switch: New DE and POI | Cross Plains /Callahan | Construct a dead-end POI from the new Avenger 69-kV Switch to the TEC Atwell POI | 2021-01-11 | 2021-03-30 | 2021-05-05 |  | 325851 |  |  | 99 |  | 69 | 0.02 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.02 | 16 TAC 25.101 (c)(5)(A) | TEC Consent Obtained
42614313 (P16096001) (P16096002) | Burma 69-kV Switch Station | Tom Green | Construct new 2000 amp three breaker ring bus station. Install SCADA at the new station. | 2021-02-12 | 2021-12-31 |  |  | 7632812 |  |  | 60 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42624938 (P16096003) | N. San Angelo - Grape Creek 69-kV T-Line | Tom Green | Terminate the N. San Angelo to Grape Creek 69-kV transmission line into new Burma 69-kV Switch Station. | 2021-09-01 | 2021-12-31 |  |  | 903898 |  |  | 5 | 69 |  | 0.02 | 795 KCM ACSS "Drake" | [5 empty] | 16 TAC 25.101 (c)(5)(A) | Within Purchased Station Property
42624942 (P16096004) | Burma - Sterling 69-kV T-Line | Tom Green | Terminate the Burma to Sterling 69-kV transmission line into new Burma 69-kV Switch Station. | 2021-09-01 | 2021-12-31 |  |  | 896315 |  |  | 5 | 69 |  | 0.02 | 795 KCM ACSS "Drake" | [5 empty] | 16 TAC 25.101 (c)(5)(A) | Within Purchased Station Property
42899607 (P16096010) | Burma - College Hills West 69-kV T-Line | Tom Green | Terminate the Burma to College Hill West 69-kV transmission line into new Burma 69-kV Switch Station. | 2021-09-01 | 2021-12-31 |  |  | 539988 |  |  | 5 | 69 |  | 0.02 | 795 KCM ACSS "Drake" | [5 empty] | 16 TAC 25.101 (c)(5)(A) | Within Purchased Station Property
42944763 (P16096007) | Sterling City Relay Upgrades | Sterling | Ugrade Station & Relays to coordinate with new Burma 69-kV Switch Station/Line Terminal | 2021-04-15 | 2021-12-31 |  |  | 1685669 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42998736 (P16042006) (P16042017) | Benjamin - Gyp (Brazos) 138-kV Line | Benjamin/Knox | Benjamin-Gyp 138-kV: Build 9.00 of new 138-kV transmission line and operate at 138-kV. This is approximately one-half of the Benjamin-Gyp 18 miles of 138-kV transmission line as approved in Joint CCN Application with Brazos Electric Cooperative | 2021-08-01 | 2021-12-15 |  | 10020000 | 15195943 |  |  | 0 |  | 138 |  | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 9 | 47691 | CCN approved on 08/30/2018
42840275 (P16128003) | Jayton 69-kV Substation: Upgrade Terminal | Kent | Upgrade 69-kV terminal at Jayton to accommodate the new Wolfgang Substation | 2021-03-15 | 2021-07-01 | 2021-07-14 |  | 1223810.35 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10065838 (P19206005) (P19206006) | Garnet 138-kV Substation | Runnels | Construct new 138-kV station operated as a ring, but capable of future expansion to breaker and a half. Install three (3) 138-kV 3000A, 40 kA breakers and two (2) rungs. Install RTU, EPS meter, and SSO relay. | 2021-04-14 | 2021-10-01 |  |  | 10165598 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10094875 (DP19N01C1) | Miles 69-kV Substation: T-Line Assets | Runnels | Install Tap for temporary transformer/ SKID. Rebuild high side. Possibly move wood deadend structure, could be in the way of improvements. | 2021-03-06 | 2021-05-15 | 2021-06-26 |  | 556892 |  |  | 99 | 69 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within Station Property
T10094875 (DP19N01D0) | Miles 69-kV Substation: T-Station Assets | Runnels | Remove fuses and fuse cutouts. Install 69-kV switches. Install Circuit Switcher. | 2021-03-06 | 2021-05-15 |  |  | 766046 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10224186 (A19374001) | Paint Creek - Rainey Creek 138-kV Line | Haskell, Jones, Taylor | Telecom Modernization Program: Install 45.1 miles of 48 count ADSS fiber via the "Fort Phantom-Paint Creek 138-kV Line" and "Fort Phantom Plant-East Abilene 138-kV Line." For connectivity at Paint Creek and Rainy Creek station. | 2021-03-06 | 2022-01-28 |  |  | 2191842 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
T10225515 (A19374032) | Munday East - Paducah Clare St. 138-kV Line | Knox, Foard, Cottle | Telecom Modernization Program: Install 62 miles of 96 count ADSS fiber via transmission on the East Munday-Paducah Clare Street 138-kV Line. For connectivity at Munday East, Tardis, and Paducah Clare. | 2021-03-06 | 2021-09-03 |  |  | 2855037 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
42729725 (A18018004) | Sonora/Carver Rehab | Sonora/Sutton | Replace 12-kV breakers 4805 & 4810, remove Auto Transfomer, remove breaker 3960. | 2021-04-05 | 2021-06-15 |  |  | 4369694 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
42729722 (A18018002) | Sonora/Carver Rehab Rplc(T) | Sonora/Sutton | Replace 12-kV breakers 4805 & 4810, remove Auto Transfomer, remove breaker 3960. | 2021-04-05 | 2021-06-15 |  |  | 719069 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
T10053260 (P17093006) | Pecos Valley 138-kV Station | Pecos | Build 138-kV station in and out using two mono pole POP dead-end with a circuit switcher, distribution transformer (138/12 kV), and urban distribution bay | 2021-04-08 | 2021-08-17 |  |  | 3130974 |  |  | 40 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10139822 (P20020005) (P20020004) | Perigee 345-kV Station | Haskell | Construct new three (3) breaker ring, 345-kV station. Install three (3) 345-kV, minimum of 3000A breakers, install wave traps & carrier equipment, Install RTU, EPS meter, and SSO relay. | 2021-04-05 | 2021-11-17 |  |  | 18692600 |  |  | 0 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Property acquired
T10139849 (P20020001) (P20020006) | Mulberry Creek - Oklaunion 345-kV T-Line: Cut-In | Haskell | Terminate the Mulberry Creek - Oklaunion 345-kV transmission line into the new Perigee 345-kV Station | 2021-11-11 | 2021-11-17 |  |  | 2044935.2 |  |  | 0 | 345 |  | 0.1 | 954 KCM ACSR "Cardinal" | Steel Mono Pole | 150 | 0.1 |  |  | 16 TAC 25.101 (c)(5)(A) | Within existing easements Landowner Noticed
T10139859 (P20020002) (P20020003) | Perigee – Apogee 345-kV: Tie Line | Haskell | Construct a dead-end POI 345-kV tie line between Perigee 345-kV Substation and Apogee Wind Interconnection's POI. | 2021-08-11 | 2021-08-31 |  |  | 512973 |  |  | 0 |  | 345 | 0.1 | 954 KCM ACSR "Cardinal" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10062623 (P19206001) (P19206002) | Ballinger-Oak Creek 138-kV Line: Cut in | Runnels | Terminate the Ballinger to Oak Creek 138-kV transmission line into the new Garnet 138-kV Substation. | 2021-07-01 | 2021-12-15 |  |  | 1154220 |  |  | 0 | 138 |  | 0.03 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.03 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10131252 (P19206003) | Garnet-Norton POI 138-kV Line | Runnels | Construct POI dead-end structure and terminate into Norton 138-kV Substation | 2021-08-31 | 2021-12-15 |  |  | 384647 |  |  | 0 |  | 138 | 0.1 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10072289 (P19206007) | Oak Creek 138-kV Substation | Coke | Add wave trap and carrier equipment (3000A). Upgrade relays | 2021-10-01 | 2021-12-15 |  |  | 646665 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10072295 (P19206008) | Ballinger 138-kV Substation | Runnels | Add wave trap and carrier equipment (3000A). Upgrade relays | 2021-09-01 | 2021-12-15 |  |  | 554318 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T100535450 (P17093017) | Pecos Valley - Ft Stockton SW 138-kV Line | Pecos | Re-terminate the Pecos Valley to Ft Stockton 138-kV transmission line into Pecos Valley, and Ft Stockton SW | 2021-06-01 | 2021-09-15 |  |  | 1042440 |  |  | 10 | 138 |  | 0.26 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.24 | 16 TAC 25.101 (c)(5)(A) | Within station property at Pecos Valley 138-kV Substation Landowner consent obtained for Ft. Stockton 138-kV SW
T10157726 (P19244004) | Conan 69-kV Box Bay w/Capacitor Bank | Callahan | Construct a fenced 69-kV Box Bay with 3 motor operated switches, install a DICM, RTU, SCADA, batteries and a 69-kV shunt 7.2 MVAR Capacitor Bank. | 2021-06-28 | 2022-01-26 |  |  | 3164816 |  |  | 10 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10156572 (P19244001) | Santa Anna - Cross Plains 69-kV Line: Cut-in | Callahan | Terminate the Santa Anna to Cross Plains 69-kV transmission line into new Conan 69-kV Box Bay. Upgrade line settings at the remote ends and replace structures 30/6 - 30/9. | 2021-06-28 | 2022-01-26 |  |  | 1056063 |  |  | 0 | 69 |  | 0.3 | 795 KCM ACSS "Drake" & OPGW | Steel Mono Pole |  |  | 100 | 0.3 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10193351 (P19244007) | Conan - Dressy (CCEC) 69-kV Line: POI | Callahan | Install POI Dead-End Structure and reterminate the Conan to Dressy transmission line into Conan 69-kV Box Bay. | 2021-06-28 | 2022-01-26 |  |  | 480885 |  |  | 0 | 69 |  | 0.03 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.03 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T100535510a (P17093015) | Pecos Valley - Rio Pecos 138-kV Line | Pecos | Re-terminate the Pecos Valley to Rio Pecos 138-kV transmission lIne into Sun Valley and Pecos Valley Substations. | 2021-08-02 | 2021-10-15 |  |  | 1075179 |  |  | 0 | 138 |  | 0.3 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
42960970 (P18162005) | San Angelo Concho 69-kV Station | San Angelo/ Tom Green | Terminate S.A. Concho to Eldorado Live Oak 69-kV transmission line into S.A. Concho Station. Replace CTs at S.A. Concho with a minimum rating of 2021 Amps. | 2022-01-03 | 2022-04-04 |  |  | 570000 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.101 (c)(5)(A) & 16 TAC 25.83(a)(3) | Within station property
42961360 (P18162007) | Christoval 69-kV Substation | Christoval/ Tom Green | Replace 1590 AAC conductor and 2" AL tube with a minimum rating of 2021 Amps. Replace Switch 2176. | 2021-08-02 | 2022-12-15 |  |  | 655000 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42961379 (P18162008) | Arrott 69-kV Substation | Schleicher | Replace 69-kV switches with motor-operated switches and bus with a minimum rating of 2021 Amps. Replace 69-kV SW 4952 with new 69-kV switch. Install SCADA. | 2021-08-02 | 2022-12-15 |  |  | 1082000 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42960685 (P18162001) (P18162002) (P18162003) | SA Concho- Live Oak 69-kV Line | Tom Green, Schleicher | Rebuild and reconductor multiple segments of the existing 69-kV transmission line from the San Angelo Concho Substation to the Eldorado Live Oak Substation that were not included in prior rebuild work of this transmission line in prior years. The transmission line will be built to 138-kV standards but will continue to operate at 69-kV. | 2021-08-02 | 2022-04-04 |  |  | 10005250 |  |  | 0 | 69 |  | 3.38 | 795 KCM ACSS "Drake" | Steel Monopoles | Centerline | 3.38 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easement Landowners Noticed
42898144 (A20217002) | Merkel 69-kV Substation: RTU Install | Merkel/Taylor | Merkel RTU Install - Install new RTU | 2021-08-16 | 2021-10-01 |  |  | 337949 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Project is being revised. Will be added back after revision have been made. Within Station property
42898142 (A20217003) | Alpine REA 138-kV Substation: RTU Reliability | Brewster | Alpine REA: Replace / upgrade RTU | 2021-09-13 | 2021-10-22 |  |  | 330071 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Project is being revised. Will be added back after revision have been made. Within Station property
42898157 (A20217001) | Robertson Prison 69-kV Substation: RTU Install | Abilene/Jones | Robertson Prison: Remove existing DART RTU and replace with newer standard | 2021-09-15 | 2021-10-21 |  |  | 301221 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Project is being revised. Will be added back after revision have been made. Within Station property
42898139 (A20217004) | Marfa 69-kV Substation: RTU Reliability Install | Marfa/Presidio | Marfa: RTU Reliability - Install new RTU | 2021-10-18 | 2021-11-12 |  |  | 257610 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Project is being revised. Will be added back after revision have been made. Within Station property
42898094 (A20217010) | Peacock (WT) 69-kV Substation: RTU Reliability | Stonewall | Peacock (WT): Remove existing IBOX RTUs and replace with new Cooper RTUs | 2021-11-08 | 2021-12-09 |  |  | 323603 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10048599 (A19034001) | North McCamey 138-kV Station: Breaker Replacement | Upton | Replace breaker with new 138-kV, 3000A breaker. Replace circuit switchers with new 138-kV circuit switchers. | 2021-09-16 | 2021-11-19 |  |  | 666044 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42843057 (P17107016) | Lake Pauline 69-kV Substation: MSLE Upgrades | Hardeman | Replace all Lake Pauline to Vernon Main St. 69-kV MLSE equipment below 1200A with 2000A, 40kA. Replace all Lake Pauline to Vernon Main St. 138-kV MLSE equipment below 1200A with 3000A, 40kA. Install new jumpers, strain bus, switches, and fiber with all associated equipment. Replace 69-kV switches with 2000A, 40kA switches. Add communication equipment. | 2021-09-03 | 2021-12-08 |  |  | 815922 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property?
42781610 (P17107017) (P17107018) (P17107001) | Lake Pauline - Chillicothe 69-kV Rebuild | Hardeman,Wilbarger | Rebuild and reconductor multiple segments of the existing 69-kV transmission line from the Lake Pauline Substation to the Chillicothe substation that were not included in prior rebuild work of this transmission line in prior years. Relocate a segment of this transmission line due to an existing encroachment. The transmission line will be built to 138-kV standards but will continue to operate at 69-kV. | 2021-09-03 | 2021-12-08 |  |  | 4562662 |  |  | 0 | 69 |  | 3 | 795 KCM ACSS "Drake" | Steel Mono Pole | Various | 2.07 | 100 | 0.93 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Utilizing existing easements. Landowners Noticed. Landowner consent obtained as necessary.
T10329372 (P17107022) | Lake Pauline 69-kV Bus Tie Line | Hardeman | Reconstruct & reterminate the existing 69-kV single circuit Bus Tie line between the western and eastern bays on the south side of the Lake Pauline Substation. New construction will be constructed at 69-kV standards. Will also support a single circuit 795KCM 26/7 ACSS "Drake"/ACSS shielded by a conventional shield wire. | 2021-09-03 | 2021-12-08 |  |  | 754384 |  |  | 0 | 69 |  | 0.05 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP property
T100590830 (P19195001) | Flomot 69-kV Tap | Motley | Install new 138-kV 2000A three-way Phase-Over-Phase Switch on transmission structure with motor-operator and SCADA Control. | 2021-09-08 | 2021-11-12 |  |  | 846325 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Landowner consent obtained
T10168102 (P19195003) (P19195006) | Flomot Tap - Flomot 69-kV T-Line | Motley | Terminate the Flomot Tap to Flomot 69-kV transmission line into new Flomot 69-kV POP Switch. | 2021-09-16 | 2021-11-12 |  |  | 3275215 |  |  | 0 | 69 |  | 0.02 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 0.02 | 100 | 0.02 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
42961388b (P18162011) | Hulldale REA 69-kV Substation: Shoe-Fly | Schleicher | Install a temporary shoe-fly for installation of the Hulldale POD Box Bay. | 2021-09-27 | 2021-12-15 |  |  | 160000 |  |  | 0 | 69 |  | 0.15 | 556.5 KCM ACSS "Dove" | Steel Monopoles |  |  | 100 | 0.15 | 16 TAC 25.101 (c)(5)(A) | Landowner consent ontained
42961388a (P18162011) | Hulldale REA 69-kV Substation | Schleicher | Install POD box bay to replace 69-kV switches with a minimum rating of 2021 Amps. Install SCADA. | 2021-10-06 | 2021-12-15 |  |  | 1425000 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Landowner consent ontained
T10307962 (A18907001) | Eldorado 69-kV Substation: T-Station Assets | Eldorado/Schleicher | Rebuild Eldorado Substation transmission assets - Replace four (4) switches with motor operated switches and SCADA. Demolish old station. | 2021-09-08 | 2022-03-28 |  |  | 1575249 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10169370 (A15707334) | Aspermont - Hamlin 69-kV T-line: Cut-In | Aspermont / Stonewall | Reterminate the Aspermont to Hamlin 69-kV transmission line into the newly rebuilt Aspermont 69-kV Substation. | 2021-10-18 | 2021-12-10 |  |  | 656307 |  |  | 0 | 69 |  | 0.15 | 447 kcmil T2/ACSR "Hawk" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowners noitced. Structures within public ROW.
T10169421 (A15707335) | Aspermont - Jayton 69-kV T-line: Cut-In | Aspermont / Stonewall | Reterminate the Aspermont to Jayton 69-kV transmission line into the newly rebuilt Aspermont 69-kV Substation. | 2021-10-25 | 2021-12-11 |  |  | 412384 |  |  | 0 | 69 |  | 0.15 | 447 kcmil T2/ACSR "Hawk" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowners noitced. Structures within public ROW.
T10169436 (A15707336) | Aspermont - Pointer 69-kV T-line: Cut-In | Aspermont / Stonewall | Reterminate the Aspermont to Pointer 69-kV transmission line into the newly rebuilt Aspermont 69-kV Substation | 2021-10-11 | 2021-12-12 |  |  | 288065 |  |  | 0 | 69 |  | 0.15 | 447 kcmil T2/ACSR "Hawk" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowners noitced. Structures within public ROW.
T10169442 (A15707337) | Aspermont - Rule 69-kV T-line: Cut-In | Aspermont / Stonewall | Reterminate the Aspermont to Rule 69-kV transmission line into the newly rebuilt Aspermont 69-kV Substation | 2021-10-11 | 2021-12-13 |  |  | 552697 |  |  | 0 | 69 |  | 0.15 | 447 kcmil T2/ACSR "Hawk" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowners noitced. Structures within public ROW.