## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
10-022-01 | Cross Station Security Projects | Hall | Security System Upgrade - Cyber and Physcial Sercurity (to meet CIP stds) | 2021-06-03 |  |  | N/A | 1050000 |  |  | 97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-022-02 | Railhead Station Security Projects | Carson | Security System Upgrade - Cyber and Physcial Sercurity (to meet CIP stds) | 2021-06-04 |  |  | N/A | 1150000 |  |  | 97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-022-03 | Gray Station Security Projects | Gray | Security System Upgrade - Cyber and Physcial Sercurity | 2021-07-06 |  |  | N/A | 1380000 |  |  | 97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10-022-05 | Allen Creek Security Project | Donley | Security System Upgrade - Cyber and Physcial Sercurity | 2021-11-01 |  |  | N/A | 149000 |  |  | 97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.