## MonthlyReportForm-SWEPCO
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
42678576 | Wilkes 345-kV: Replace breakers and auto transformer | Marion | Replace 138-kV Breakers and Bus and one 138/345-kV auto transformer | 2018-04-01 | 2021-05-14 | 2021-06-02 |  | 13776933 |  |  | 99 | 345 / 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42707036 | Vernon Station (SPP): Breaker Replacement | Vernon/Wilbarger | Replace 69-kV Circuit Breakers 122 | 2018-07-02 | 2019-05-01 | 2019-04-30 |  | 797621 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within exisiting property
42872933 | Richmond Rd - NW Texarkana SWAEC Tap 69-kV Line Rebuild | Texarkana/Bowie | Rebuild and Reconductor 1.10 miles of the NW Texarkana SWAEC Tap to Richmond Road 69-kV T-Line to 138-kV standard but will continue to operate at 69 kV. | 2020-12-01 | 2021-05-31 | 2021-05-06 |  | 2046020 |  |  | 99 | 69 |  | 1.1 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 1.1 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilitzing exisiting easements. Landowners noticed.
42944083 | North Mineola Substation Rebuild | Mineola/Wood | Replace circuit breakers and associated breaker jumpers. Replace disconnect switches. Replace PTs with (3) new CCVTs on Mineola line terminal and Quitman line terminals. | 2020-02-10 | 2020-11-02 | 2020-10-29 |  | 2019063 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42905185 | Cookville 69-kV Box Bay | Titus | Construct new 138-KV Box Bay POD (operating at 69-KV) at the Cookville 69-kV Tap with three (3) MOAB switches and remove two (2) existing switches. Add fiber transition into station along the line. No auto-sectionalizing required. | 2020-05-18 | 2020-09-29 | 2020-09-28 |  | 1876457 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner Consent Obtained
42905186 | Buford Survey 69-kV Box Bay | Morris | Construct new 138-KV Box Bay POD (operating at 69-KV) at the Buford Survey 69-kV Tap with three (3) MOAB switches and remove three (3) existing switches. Add fiber transition into station along the line. Auto-sectionalizing required. | 2020-06-22 | 2020-10-28 | 2020-10-27 |  | 1908905 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner Consent Obtained
42905190 | Dekalb to Mt. Pleasant 69-kV transmission line: Cut- Ins to new Box Bays | Titus,Morris | Terminate the existing DeKalb to Mt. Pleasant 69-kV transmission line into the new Cookville 69-kV Box Bay and Buford Survey 69-kV Box Bay. Will be built to 138-kV Standards but operated at 69-kV. | 2020-05-12 | 2020-10-28 | 2020-10-27 |  | 1390988 |  |  | 99 | 69 |  | 0.3 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 0.3 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10104999 | Cookville 69-kV Tap: Cut-In to new Cookville Box Bay | Titus | Terminate the existing Cookville 69-kV Tap into the new Cookville 69-kV Box Bay. Will be built to 138-kV Standards but operated at 69-kV. | 2020-05-12 | 2020-09-29 | 2020-09-28 |  | 571219 |  |  | 99 | 69 |  | 0.1 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 0.1 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10105018 | Buford Survey 69-kV Tap: Cut-In to new Buford Survey Box Bay | Morris | Terminate the existing Buford Survey 69-kV Tap into new Buford Survey 69-kV Box Bay. Will be built to 138-kV Standards but operated at 69-kV. | 2020-05-12 | 2020-10-28 | 2020-10-27 |  | 275761 |  |  | 99 | 69 |  | 0.1 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 0.1 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42944074 (P18222007) | Mineola 69-kV Substation Upgrade & Expansion | Wood | Replacement of one 69-kV breaker and upgrade of another. Replacement of four switches, (9) ccvts and 3 arresters. Rebuild of existing bus for increased rating needed and relocate existing arresters and other equipment for the rebuild. Install new DICM to replace switch house equipment. Expand substation property. | 2020-06-15 | 2021-04-21 | 2021-02-05 |  | 4153685 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42941298 (P18222001) | New Quitman 69-kV Substation | Wood | Construct a new 69-kV, 40kA, 2000A, (4) four-breaker ring bus design substation on a new station pad on 10 acres of purchased property located about 0.6 miles to the northeast of existing Quitman Substation. | 2020-06-15 | 2021-11-24 | 2021-11-19 |  | 5674838 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42631655 (A16806006) | 39th Street - NW Texarkana SWAEC Tap 69-kV Line Rebuild | Texarkana/Bowie | Rebuild and Reconductor 4.92 miles of the 39th Street to NW Texarakana SWAEC Tap 69-kV T-Line to 138-kV standards but will continue to operate at 69-kV. | 2020-08-03 | 2021-02-28 | 2021-03-04 |  | 15062764 |  |  | 99 | 69 |  | 4.92 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 4.92 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilitzing exisiting easements. Landowners noticed.
42944077 (P18222008) | Grand Saline 69-kV Substation Upgrade & Expansion | Grand Saline/ Van Zandt | Replacement of two 69-kV breakers. Replacement of four breaker disconnect switches. Replacement of two breaker disconnect switches with new circuit switchers. Remove two bypass switches. All 69-kV cap and pin bus support insulators will be replaced. Install new DICM to replace switch house equipment. Expand substation property. | 2020-08-03 | 2021-05-26 | 2021-05-26 |  | 4228148 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42941390 (P18215001) | Lydia 345-kV Station | Bowie | Convert the Lydia 345kV station to a ring bus configuration, eliminating the 3-terminal line by adding breakers. A new station will be built in the clear on newly purchased property; the existing station will be retired. | 2020-09-14 | 2022-05-11 |  |  | 15843030 |  |  | 50 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10068530 (DP20S05D0) | Alba 69-kV Substation Upgrade: T-Station | Alba/Wood | Rebuild Alba substation with new station deadend, bus work, SSVT, and relaying. | 2020-10-04 | 2020-12-15 | 2020-12-29 |  | 658792.77 |  |  | 90 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10068526 (DP20S05C0) | Alba 69-kV Substation Upgrade: T-Line | Alba/Wood | Install one transmission structure to feed the new station rebuild | 2020-10-04 | 2020-12-15 | 2020-12-29 |  | 425355 |  |  | 90 | 69 |  | 0.02 | T2 477 KCM ACSR | Steel Dead-End |  |  |  |  | 16 TAC 25.83(a)(3) | Within Station Property
T10076668 (A19084001) | Bann - NW Texarkana 138-kV T-Line Interstate 30 TxDOT Relocation | Bowie | Relocate one structure along the Bann to NW Texarkana 138-kV transmission line to make room for access roads being built along Interstate Highway 30 (IH 30) as requested by the Texas Department of Transportation (TxDOT) | 2020-11-16 | 2020-12-07 | 2021-05-14 |  | 228227 |  |  | 99 | 138 |  |  | 1590 ACSR 54/19 Falcon | Concrete Mono Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(F) | Landowners Noticed
T10076671 (A19084002) | Bann-New Boston 69-kV T-Line: Interstate 30 TxDOT Relocation | Bowie | Relocate two structures along the Bann to New Boston 69-kV transmission line to make room for access roads being built along Interstate Highway 30 (IH 30) as requested by the Texas Department of Transportation (TxDOT) | 2020-11-16 | 2021-01-12 | 2021-06-08 |  | 561506 |  |  | 99 | 69 |  |  | 1272 ACSR 54/19 Pheasant | Steel Mono Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(F) | Landowners Noticed
42904905 (A15706010) | NW Texarkana Tap Switch | Texarkana/Bowie | Replace existing 2-way phase over phase switch with 2000A phase-over-phase MOS with auto-sectionalizing. Switch and structure will be built to 138-kV standards, but operated at 69-kV. | 2020-12-07 | 2021-04-30 | 2021-04-29 |  | 1349735 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Easement Landowners Noticed
42905248 (A16806068) | NW Texarkana Tap Switch & Redick Tap Switches: T-line Retermination | Texarkana/Bowie | T-line Retermination work associated and required for rebuild of NW Texarkana Tap Switch and both Redlick Tap Switches | 2020-12-07 | 2021-11-13 | 2021-11-13 |  | 749638 |  |  | 99 | 69 |  | 0.02 | 1272 ACSR 54/19 Pheasant | Steel Dead-End | Varies | 0.02 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowners Noticed
42904907 (A15706022) | Telecomm fiber transitions from T-line into stations | Texarkana/Bowie | Install telecomm fiber transitions from T-line into station at Bann Station, Richmond Road Station, and 39th Street Station | 2021-01-04 | 2021-11-13 | 2021-11-13 |  | 242392 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10132489 (A18806054) | Lone Star South - Failed Relay | Lone Star/Morris | Replace failed transformer differential relay panel on 138/69kV transformer | 2021-01-11 | 2021-02-21 | 2021-04-15 |  | 404220 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42952896 (A18106011) | N Marshall 69-kV Substation: Construct Box Bay | Marshall/Harrison | The 69-kV portion of the station will be replaced with a box bay. Breaker 7570 with be replaced with new 2000 A breaker as part of this rebuild. A DICM will be installed to house all of the new transmission relay equipment. | 2021-02-01 | 2021-12-31 |  |  | 3940359 |  |  | 0 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
42963433 (A18106017) | N Marshall - Marshall 69-kV Retermination | Marshall/Harrison | Terminate the existing N Marshall to Marshall 69-kV line into new Box Bay as part of the Jefferson station rebuild | 2021-02-01 | 2021-12-31 |  |  | 514806 |  |  | 0 | 69 |  | 0.02 | 795 KCM ACSR "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Property
42952898 (A18106002) (A18106004) | Woodlawn - N Marshall 69-kV Rebuild | Marshall/Harrison | Rebuild and reconductor the Woodlawn to N. Marshall 69-kV transmission line to 138-kV standards but will continue to operate at 69 kV. | 2021-02-01 | 2021-12-31 |  |  | 8098078 |  |  | 0 | 69 |  | 7.55 | 795 KCM ACSR "Drake" | Steel Mono Pole | Centerline | 7.55 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easement Landowners Noticed
T10139440 (A18806048) | Overton 138-kV Substation | Overton/Rusk | Replace failed PLC carrier set on Overton - NW Henderson 138kV line as well as line protection relays. | 2021-03-06 | 2021-03-31 | 2021-05-28 |  | 481660 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10139442 (A18806050) | NW Henderson 138-kV Substation | Henderson/Rusk | Replace failed PLC carrier set on Overton - NW Henderson 138kV line as well as line protection relays. | 2021-03-06 | 2021-03-31 | 2021-03-24 |  | 406827 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10142089 (A18806059) | South Texas Eastman Failed LCBIII | Longview/Gregg | Replace failed primary line differential protection relay and breaker controls on South Texas Eastman - Eastex SW 138kV line. | 2021-03-24 | 2021-05-20 | 2021-05-28 |  | 867948 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10142112 (A18806061) | Eastex SW Failed LCBIII | Longview/Gregg | Replace failed primary line differential protection relay and breaker controls on South Texas Eastman - Eastex SW 138kV line. | 2021-03-24 | 2021-05-20 | 2021-05-28 |  | 459668 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42939973 (P18231001) (P18231002) | Carthage T 138-kV Box Bay | Panola | Install 3 new138-kV breakers in current box bay. Expand station site to accommodate DICM. Install line relaying and breakers controls in new control house. | 2021-04-14 | 12/085/2021 |  |  | 3830879 |  |  | 75 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased for Expansion
T10236276 (A15713062) | Rock Hill - Marshall 69-kV Line | Marshall/Harrison, Rusk | Telecom Modernization Program: Install 18.5 miles of 96 count ADSS fiber via Transmission between Marshall 69-kV Station and Rock Hill Station. For connectivity at Marshall 69kV Station, Rosborough Station and Rock Hill Station to support CES and ICON network. | 2021-03-06 | 2021-06-01 |  |  | 1309447 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
T10236194 (A15713129) | LeBrock-Roseborough Telecom Fiber | Harrison | Telecom Modernization Program: Install 3.58 miles of 48 count ADSS via Distribution between LeBrock Station and Rosborough Station. For connectivity at LeBrock Station and Rosborough Station to support CES and ICON network. | 2021-04-26 | 2021-05-15 |  |  | 361888 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236204 (A15713187) | Lydia 345-kV Switch Station Fiber Extension North | Bowie | Telecom Modernization Program: Install 5.5 miles of 48 count ADSS fiber via underground build between Lydia station and an existing splice point into fiber on the "Mount Pleasant‐New Boston 138-kV transmission line." For connectivity at Lydia Station. | 2021-03-06 | 2021-06-30 |  |  | 1607011 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236272 (A15713189) | Lydia 345-kV Switch Station Fiber Extension South | Bowie | Telecom Modernization Program: Install 5.6 miles of 48 count ADSS fiber via underground build between Lydia station and an existing splice point into fiber on the "Mount Pleasant‐New Boston 138-kV transmission line." For connectivity at Lydia Station. | 2021-03-06 | 2021-06-30 |  |  | 914863 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236307 (A19351067) | Marshall - Pirkey 138-kV Line | Marshall/Harrison | Telecom Modernization Program: Install 7.5 miles of 96 count ADSS fiber between Marshall Station and Pirkey Station. For connectivity at Marshall Station and Pirkey Station to support CES and ICON network. | 2021-05-17 | 2021-08-19 |  |  | 662819 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
T10138035 (A18806036) | Pirkey 138-kV Substation | Harrison | Replace Legacy DFR Monitoring | 2021-04-10 | 2021-06-15 | 2021-06-27 |  | 354385 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10180035 (A18806075) | Lone Star South 138-kV Substation | Lone Star/Morris | Replace Line Relaying with AEP standard panels and a breaker control panel. | 2021-04-26 | 2021-10-20 |  |  | 362215 |  |  | 50 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10180047 (A18806076) | Pittsburg 138-kV Substation | Pittsburg/Camp | Replace Line Relaying with AEP standard panels and a breaker control panel. | 2021-04-26 | 2021-10-20 |  |  | 355252 |  |  | 50 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42941326 (P18222003) | Grand Saline - Quitman 69-kV Line | Wood | Terminate the existing Grand Saline to Quitman 69-kV transmission line into New Quitman 69-kV Substation. Project inlcudes 69-kV shoo-fly. | 2021-05-01 | 2021-10-01 | 2021-11-19 |  | 1131471 |  |  | 99 | 69 |  | 0.1 | 556.5 ACSR 26/7 "Dove" | Steel Mono Poles |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
42904903 (A15706009) | Redlick Tap 69-kV Switches | Bowie | Replace existing phase-over-phase switch with horizontal 1-way load break switch on new H-frame structure. Install new 1-way phase-over-phase load break switch on a separate new T-line structure. Switches will each be mounted on separate structures, separated by approximately 750 feet. Install 2 PTs, 1 motor operator, SCADA control, battery, and 2 arresters at each location. Structure and switches will be built to 138-kV, but operated at 69-kV. | 2021-06-07 | 2021-11-30 | 2021-11-13 |  | 1923038 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Landowner Consent Obtained
42941332 (P18222004) | Quitman - Winnsboro 69-kV T-Line | Quitman/Wood | Terminate the Quitman to Winnsboro 69-kV transmission line into New Quitman 69-kV Substation. | 2021-07-01 | 2021-10-14 | 2021-11-19 |  | 614664 |  |  | 99 | 69 |  | 0.1 | 1272 ACSR 54/19 "Pheasant" | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
T10138569 (P18222005) | Quitman - WCEC Connection 69-kV T-Line | Quitman/Wood | Terminate the Quitman to WCEC Connection 69-kV transmission line into New Quitman 69-kV Substation. And cut-in to existing customer WCEC station because of removal of old Quitman Substation. | 2021-07-01 | 2021-10-14 | 2021-11-19 |  | 550829 |  |  | 75 | 69 |  | 0.2 | 1272 ACSR 54/19 "Pheasant" | Steel, Single Pole | 100 | 0.05 |  |  | 16 TAC 25.101 (c)(5)(A) | Utilizing Existing Easement Landowners Noticed Terminations Within Station Property
42941322 (P18222002) | Quitman - North Mineola 69-kV T-Line | Quitman/Wood | Terminate the Quitman to North Mineola 69-kV transmission line into New Quitman 69-kV Substation. Rebuild 6 spans from New Quitman Substation to existing/removed Quitman Substation. | 2021-07-01 | 2021-11-24 |  |  | 1080458 |  |  | 20 | 69 |  | 0.4 | 1272 ACSR 54/19 "Pheasant" | Steel, Single Pole | 100 | 0.3 |  |  | 16 TAC 25.101 (c)(5)(A) | Utilizing Existing Easement Landowners Noticed Terminations Within Station Property
42907518 (A18093001) | Bann - Red Springs REA 138-kV T-Line | Bowie | Rebuild and Reconductor the Bann to Red Springs REA 138-kV transmission line. | 2021-10-01 | 2022-05-25 |  |  | 5778818 |  |  | 0 | 138 |  | 3.08 | 1590 ACSR/AW 54/19 "Falcon" | Steel, Single Pole | 100 | 3.08 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42907529 (A18093003) | IPC Domino - Red Springs REA 138-kV T-Line | Bowie,Cass | Rebuild and Reconductor the IPC Domino to Red Springs REA 138-kV transmission line. | 2021-08-01 | 2022-02-25 |  |  | 16929647 |  |  | 35 | 138 |  | 8.29 | 1590 ACSR/AW 54/19 "Falcon" | Steel, Single Pole | 100 | 8.29 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
T10319108 (A18093009) | Telecomm fiber transitions from T-line into stations | Bowie,Cass | Install telecomm fiber transitions from T-line into station at Bann Station, Red Springs Station, and IPC Domino Station | 2021-08-01 | 2022-05-25 |  |  | 335489 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10169344 (A18089003) | Frederick Junction (Str. 8/6) - Vernon Main St. 69-kV Rebuild | Wilbarger | Rebuild and reconductor the Texas portion (beginning at Structure 8/6) of the Frederick Junction to Vernon Main St. 69-kV transmission line to 138-kV standards but will continue to operate at 69 kV. | 2021-08-02 | 2021-12-31 |  |  | 5192281 |  |  | 0 | 69 |  | 7.6 | 1272 ACSR 54/19 "Pheasant" | Steel, Single Pole | Centerline | 7.6 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easement Landowners Noticed
42939973 (P18231001) (P18231002) | Carthage T 138-kV Box Bay | Panola | Install three (3) new 138-kV breakers in existing Carthage T 138-kV Box Bay. Expand box bay site to accommodate DICM. Install line relaying and breaker controls in new control house. | 2021-08-02 | 2021-12-01 |  |  | 2987560 |  |  | 75 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased for Expansion
42939973 (P18225001) (P18225003) | Bruton 69-kV Box Bay | Morris | Install three 69-kV breakers at Bruton Box Bay. New DICM will be installed to accommodate relaying. | 2021-09-03 | 2022-01-31 |  |  | 3169448 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased for Expansion
42941398 (P18215002) | Lydia - Valiant 345-kV Line: Retermination | Bowie | Reterminate the Lydia - Valliant 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 |  |  | 994017 |  |  | 0 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42941406 (P18215005) | Lydia - NW Texarkana 345-kV Line: Retermination | Bowie | Reterminate the Lydia - NW Texarkana 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 |  |  | 1263867 |  |  | 0 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42941408 (P18215006) | Lydia - Welsh 345-kV Line: Retermination | Bowie | Reterminate the Lydia - Welsh 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 |  |  | 996635 |  |  | 0 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
43003713 (A19020001) | MidValley - Longview Tap 69-kV Line | Greg | Relocate three structures along the MidValley - Longview Tap 69-kV transmission line to accommodate the widening of FM 2206 as requested by the Texas Department of Transportation (TxDOT) | 2021-09-06 | 2021-10-12 | 2021-10-12 |  | 1384842.39 |  |  | 99 | 69 |  | 0.08 | 2/0 ACSR 6/1 "Quail" | Steel Pole Mono | Centerline | 0.08 | 100 | 0.08 | 16 TAC 25.101 (c)(5)(F) | Landowner consent obtained
T10277140 (P20215003) | Avinger 138-kV Tap: Install 138-kV Temporary Tap | Cass | Replace two (2) dead-end structures and install temporary bypass line and customer (NTEC POD) tap terminated at the SWEPCO Petty - Wilkes 138-kV transmission line. | 2021-10-04 | 2021-10-29 |  |  | 317002 |  |  | 0 | 138 |  | 0.1 | 1272 ACSR 54/19 "Pheasant" | Three-Pole Wooden Structure | 100 | 0.1 | 175 | 0.1 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained for Temporary Easement
TL0043281 (A21065503) | Longwood - Wilkes 345-kV Transmission Line | Marion | Install one galvanized steel, H-frame structure on the Longwood-Wilkes 345 kV transmission line between structures 169 & 170. | 2021-10-04 | 2021-10-09 |  |  | 305065 |  |  | 0 | 345 |  | 0.1 | 2-1024 ACAR | H-Frame Steel | 100 | 0.1 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed No new easement necessary
T10365950 (A21062001) | NW Texarkana - Welsh 345-kV Transmission Line | Cass,Bowie | Install two 3-Pole mid-span structures consisting of one laminated wood pole supporting each phase independently at two locations between spans 161-162 and 162-163. | 2021-12-06 | 2021-12-31 |  |  | 1839321 |  |  | 0 | 345 |  | 0.1 | 1-2156 Bluebird 84/19 ACSR | Laminated Wood Poles | varies | 0.1 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed No new easement necessary
T10224575 (A18806086) | Red Springs 138-kV Station: Bann - IPC Domino Relay Replacement | Bowie | Replace line relaying at Red Springs 138-kV Station to match relaying at Bann station. | 2021-12-06 | 2022-02-25 |  |  | 684857 |  |  | 15 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10224577 (A18806087) | IPC Domino 138-kV Station Bann - IPC Domino Relay Replacement | Cass | Replace line relaying at IPC Domino 138-kV Station to match relaying at Bann station. | 2022-01-10 | 2022-02-25 |  |  | 663726 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42963930 (P19057001) (P19057002) | Morton to E Burges 138-kV Transmission Line | Van Zandt | Construct a new 2.57 mile 138-kV transmission line from a cut-in near the SWEPCO Morton 138-kV Substation to a cut-in near the WCEC E Burges 138-kV Substation. | 2022-05-01 | 2022-11-02 |  |  | 4185088 |  |  | 0 |  | 138 | 2.57 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  | 100 | 2.57 | 50669 | PUCT Docket 50669 Approved on 05/07/2021
T10329431 (P20025001) (P20025003) | Murvaul 138-kV Box Bay | Panola | Construct a new 138-kV box bay with Scada controlled switches. | 2022-01-31 | 2022-05-05 |  |  | 1548080 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner consent obtained
T10356096 (P20025002) | Carthage T - Tenaha 138-kV T-Line | Panola | Construct a temporary tap prior to the permanent box bay installation. Re-terminate the existing Carthage T to Tenaha transmission line into new Murvaul Tap 138-kV Box Bay. | 2022-01-17 | 2022-06-23 |  |  | 1348733 |  |  | 0 |  | 138 | 0.2 | 1272 KCM 54/19 ACSR | Steel Mono Pole |  |  | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
42965029 (P18231006) | Carthage Connection 138/69-kV POD | Panola | Update relay settings and tuner at Carthage 69/138kV POD. | 2022-01-12 | 2022-06-23 |  |  | 224032 |  |  | 0 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42908317 (A15706581) | Childress Airport 69-kV Substation | Childress | Replace switches 6147 and 6153 with 2000 A switches. Upgrade upper and lower bus. | 2022-01-10 | 2022-02-23 |  |  | 443841 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
43002631 (A16806635) | Clarendon - W. Childress 69-kV T-Line | Childress | Add Fiber Transitions at the substations along the Clarendon to NW Memphis to W Childress 69-kV transmission line. | 2022-01-10 | 2023-06-14 |  |  | 755188 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3)