## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
W.O. 1192140 | Enstor 138 kV Transmission Line Dkt 34650 | Liberty | New 138 kV transmission line at the end of Entergy Transmission Line 82 | TBD | TBD |  | $981,531 T-Line |  |  |  | 0% | na | 138 | 1.96 | 795 kcmil ACSR 26/7 "Drake" | Single pole, 70-90 ft, steel/concrete | na | na | 100 | 1.96 | 34650 | ROW acquisition plan and construction schedule being developed.
TBD | PS40 | Polk | New 138 kV transmission line from Entergy Transmission line to new PS40 Substation | TBD | 2021-09-01 |  | $216,150 T-Line |  |  |  | 0% | na | 138 | 0.68 | 795 kcmil ACSR 26/7 "Drake" | Single pole, 70-90 ft, steel/concrete | na | na | 100 | 0.34091 | §25.83 §25.101.C | Project delayed.
W.O. 1412801 | Luce Bayou 138 kV Transmission Line | Liberty | New 138 kV double circuit transmission line tapped off Entergy Transmission Line 870 | 2017-05-01 | 2017-12-31 | Q4 2020 | $5,540,260 Substation; $10,500,110 T-Line |  |  |  | 0% | na | 138 | 18.94 | 795 kcmil ACSR 26/7 "Drake" | Single pole, 85-115 ft, steel/concrete | 100 | 9.47 | 100 | 0 | 43847 | Construction & Cleanup complete; Energized Q4 2020
TBD | Fred 138kV Transmission Line | Tyler | New 138kV transmission line from Entergy transmission line or SHECO Fork Creek substation to new SHECO Fred substation | 2021-02-01 | 2022-09-01 |  | $3,500,000.00 Substation; $18,999,267 - $33,502,135 T-Line |  |  |  | 0% | na | 138 | 16.5-29.1 | 795 kcmil ACSR 26/7 "Drake" | Single pole, 85-115 ft, steel/concrete | na | na | 100 | 16.5-29.1 | 50485 | CCN application filed on 2/13/2020; Settlement documentation filed on 12/28/2020