## MonthlyReportForm-SWEPCO
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
42872935 | Bann - Redlick 69-kV Rebuild | Bowie | Rebuild and Reconductor the Bann to Redlick 69-kV T-Line (exisiting double circuit with Bann to New Boston 138-kV transmission line) to 138-kV Standards but will continue to operate at 69 kV. | 2019-09-03 | 2019-12-13 | 2019-12-14 |  | 2815625 |  |  | 99 | 69 |  | 1.5 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Various | 1.5 | 100 | 1.5 | 16 TAC 25.101 (c)(5)(B) | Landowners Consent Obtained
42633475 | Bann - North New Boston 138-kV Line Rebuild | Bowie | Rebuild and Reconductor 1.50 miles of the Bann to North New Boston 138-kV T-Line (exisiting double circuit with Bann to Redlick 69-kV transmission line). | 2019-09-03 | 2019-12-12 | 2019-12-12 |  | 2695041 | 2235576 | -17.05% | 100 | 138 |  | 1.5 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 1.5 | 100 | 1.5 | 16 TAC 25.101 (c)(5)(B) | Landowners Consent Obtained
42644732 | Adora Tap - West Mt. Pleasant | Mt. Pleasant/Titus | Rebuild and Reconductor 0.86 miles of 69-kV T-Line to 138-kV Standards. Continues to operate at 69 kV. | 2018-03-19 | 2109-05-01 |  |  | 1360000 |  |  | 0 | 69 |  | 0.86 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 0.86 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing exisiting easements. Landowners noticed.
42622941a | Pilgrims Pride - Winfield Rehab (Pilgrims Pride - Adora Tap) | Titus | Rebuild and Reconductor 1.61 miles of 69-kV T-Line to 138-kV Standards. Continues to operate at 69 kV. | 2018-01-15 | 2019-03-16 |  |  | 1416964 |  |  | 5 | 69 |  | 1.61 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Various | 1.61 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing exisiting easements. Landowners noticed.
42678576 | Wilkes 345-kV: Replace breakers and auto transformer | Marion | Replace 138-kV Breakers and Bus and one 138/345-kV auto transformer | 2018-04-01 | 2021-05-14 |  |  | 13776933 |  |  | 80 | 345 / 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42707036 | Vernon Station (SPP): Breaker Replacement | Vernon/Wilbarger | Replace 69-kV Circuit Breakers 122 | 2018-07-02 | 2019-05-01 | 2019-04-30 |  | 797621 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within exisiting property
42763999 | Pirkey - Tenaska Rusl County 345-kV Line Relocate | Harrison | Relocate a 1.50 mile section of the exisiting SWEPCO Pirkey -Tenaska Rusk County 345-kV transmission line to faciliate advancement of mining at Sabine Mine. Relocation occurs between Pirkey Substation and Lebrock Substation. | 2019-01-07 | 2019-06-14 |  |  | 9048389 |  |  | 15 | 345 |  | 2.7 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | 150 | 1.5 | 150 | 2.7 | 16 TAC 25.101 (c)(5)(E) | Landowner Consent Obtained
42872933 | Richmond Rd - NW Texarkana SWAEC Tap 69-kV Line Rebuild | Texarkana/Bowie | Rebuild and Reconductor 1.10 miles of the NW Texarkana SWAEC Tap to Richmond Road 69-kV T-Line to 138-kV standard but will continue to operate at 69 kV. | 2020-12-01 | 2021-05-31 |  |  | 2046020 |  |  | 15 | 69 |  | 1.1 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 1.1 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilitzing exisiting easements. Landowners noticed.
42896414 | Hill Lake | Panola | Hill Lake 138-kV Extension: Terminate the Logansport - Rock Hill - Tenaha 138-kV transmission line with double-circuit structues into new Hill Lake Station | 2019-03-26 | 2019-08-31 | 2019-08-28 |  | 1680114 |  |  | 99 |  | 138 | 0.5 | 1272 ACSR 54/19 (Pheasant) | Steel, Single Pole |  |  | 100 | 0.25 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42879422 | Brandy Branch 138-kV Box Bay | Harrison | Terminate the Knox Lee - Pirkey 138-kV transmission line into Brandy Branch 138-kVPOD Box Bay. This will also include the temporary hard tap for the customer. | 2019-07-15 | 2020-03-26 | 2020-05-21 |  | 386742 |  |  | 99 | 138 |  | 0.19 | Bundled CURLEW 1033.5 ACSR/SD TYPE 5 42/7 | Steel, Single Pole | Varies | 0.19 |  |  | 16 TAC 25.101 (c)(5)(A) | Transmission line within Company owned property. No additional easement required.
42986367 | IPC 138-kV Expansion: T-Station Asset | Cass | Install one bi-lvl bus support and bus work to get to the new switch in front of the circuit switcher. | 2019-08-01 | 2020-03-30 | 2020-03-25 |  | 335446 | 211430 | -36.97% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42872872 | Mt. Pleasant to Cookville Tap 69-kV Line Rebuild | Mt. Pleasant/Titus | Rebuild and Recondutor Mt. Pleasant to Cookville Tap 69-kV T-Line to 138-kV standards but will continue to operate at 69 kV. | 2019-07-04 | 2020-04-19 | 2020-03-12 |  | 8771835 | 7365941 | -16.03% | 100 | 69 |  | 8.16 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 8.16 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilitzing exisiting easements. Landowners noticed.
42879407 | Brandy Branch 138-kV Box Bay | Harrison | Construct a new 138-kV POD Box Bay with 2-3000A MO. Scada-Controlled switches with SF6 Interrupters. 1-3000A MO. Scada-Controlled Tap Switch, and 1-3000A Maintenance Switch on the Knox Lee - Pirkey 138-kV transmission line. | 2020-01-13 | 2020-05-21 | 2020-05-21 |  | 1776292 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within Company-Owned property. No additional easement required.
42905188 | Mt.Pleasant 69/138-kV substation | Mt. Pleasant/Titus | Upgrade switch 4112 and accosciated breakers and bus jumpers to 2000amps. Upgraded strain bus in west 69 kV bay. Install OPGW fiber. Work includes mobil hook up and use. | 2020-01-13 | 2020-03-10 | 2020-03-11 |  | 402442 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42872934 | Richmond Rd - Redlick Tap 69-kV Line Rebuild | Texarkana/Bowie | Rebuild and Reconductor 2.8 miles of the Redlick Tap to Richmond Road 69-kV T-Line to 138-kV standards but will continue to operate at 69 kV. | 2019-12-01 | 2020-05-29 | 2020-05-06 |  | 7257264 |  |  | 99 | 69 |  | 2.87 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 2.87 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilitzing exisiting easements. Landowners noticed.
42944083 | North Mineola Substation Rebuild | Mineola/Wood | Replace circuit breakers and associated breaker jumpers. Replace disconnect switches. Replace PTs with (3) new CCVTs on Mineola line terminal and Quitman line terminals. | 2020-02-10 | 2020-11-02 | 2020-10-29 |  | 2019063 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42626681 | Anderson Creek 138-kV Substation | Bowie | Remote end relay upgrade work. Replace exisiting CTs and PTs with new CT/PT combo metering. New 3 phase CCVT's will be installed. Install new 3-bay transclosure unit with DC power system. | 2020-03-21 | 2020-05-22 | 2020-05-26 |  | 1082184 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42905185 | Cookville 69-kV Box Bay | Titus | Construct new 138-KV Box Bay POD (operating at 69-KV) at the Cookville 69-kV Tap with three (3) MOAB switches and remove two (2) existing switches. Add fiber transition into station along the line. No auto-sectionalizing required. | 2020-05-18 | 2020-09-29 | 2020-09-28 |  | 1876457 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner Consent Obtained
42905186 | Buford Survey 69-kV Box Bay | Morris | Construct new 138-KV Box Bay POD (operating at 69-KV) at the Buford Survey 69-kV Tap with three (3) MOAB switches and remove three (3) existing switches. Add fiber transition into station along the line. Auto-sectionalizing required. | 2020-06-22 | 2020-10-28 | 2020-10-27 |  | 1908905 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner Consent Obtained
42905190 | Dekalb to Mt. Pleasant 69-kV transmission line: Cut- Ins to new Box Bays | Titus,Morris | Terminate the existing DeKalb to Mt. Pleasant 69-kV transmission line into the new Cookville 69-kV Box Bay and Buford Survey 69-kV Box Bay. Will be built to 138-kV Standards but operated at 69-kV. | 2020-05-12 | 2020-10-28 | 2020-10-27 |  | 1390988 |  |  | 99 | 69 |  | 0.3 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 0.3 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10104999 | Cookville 69-kV Tap: Cut-In to new Cookville Box Bay | Titus | Terminate the existing Cookville 69-kV Tap into the new Cookville 69-kV Box Bay. Will be built to 138-kV Standards but operated at 69-kV. | 2020-05-12 | 2020-09-29 | 2020-09-28 |  | 571219 |  |  | 99 | 69 |  | 0.1 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 0.1 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10105018 | Buford Survey 69-kV Tap: Cut-In to new Buford Survey Box Bay | Morris | Terminate the existing Buford Survey 69-kV Tap into new Buford Survey 69-kV Box Bay. Will be built to 138-kV Standards but operated at 69-kV. | 2020-05-12 | 2020-10-28 | 2020-10-27 |  | 275761 |  |  | 99 | 69 |  | 0.1 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 0.1 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42944074 (P18222007) | Mineola 69-kV Substation Upgrade & Expansion | Wood | Replacement of one 69-kV breaker and upgrade of another. Replacement of four switches, (9) ccvts and 3 arresters. Rebuild of existing bus for increased rating needed and relocate existing arresters and other equipment for the rebuild. Install new DICM to replace switch house equipment. Expand substation property. | 2020-06-15 | 2021-04-21 | 2021-02-05 |  | 4153685 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42941298 (P18222001) | New Quitman 69-kV Substation | Wood | Construct a new 69-kV, 40kA, 2000A, (4) four-breaker ring bus design substation on a new station pad on 10 acres of purchased property located about 0.6 miles to the northeast of existing Quitman Substation. | 2020-06-15 | 2021-11-24 |  |  | 5674838 |  |  | 35 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42631655 (A16806006) | 39th Street - NW Texarkana SWAEC Tap 69-kV Line Rebuild | Texarkana/Bowie | Rebuild and Reconductor 4.92 miles of the 39th Street to NW Texarakana SWAEC Tap 69-kV T-Line to 138-kV standards but will continue to operate at 69-kV. | 2020-08-03 | 2021-02-28 | 2021-03-04 |  | 15062764 |  |  | 99 | 69 |  | 4.92 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole | Varies | 4.92 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilitzing exisiting easements. Landowners noticed.
42944077 (P18222008) | Grand Saline 69-kV Substation Upgrade & Expansion | Grand Saline/ Van Zandt | Replacement of two 69-kV breakers. Replacement of four breaker disconnect switches. Replacement of two breaker disconnect switches with new circuit switchers. Remove two bypass switches. All 69-kV cap and pin bus support insulators will be replaced. Install new DICM to replace switch house equipment. Expand substation property. | 2020-08-03 | 2021-05-26 |  |  | 4228148 |  |  | 50 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42976121 (P18254001) | NW Texarkana 138-kV Station | Texarkana/Bowie | Add an additional 138-kV line terminal, circuit breaker, and necessary relaying for the Bann - NW Texarkana 138-kV transmission line so the Bann & North New Boston 138-kV lines can be separated and terminated at different station dead ends. | 2020-08-31 | 2020-11-19 | 2020-11-24 |  | 2121390 |  |  | 98 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42976124 (P18254002) | Bann - NW Texarkana 138-kV T-Line | Texarkana/Bowie | Reterminate the Bann - NW Texarkana 138-kV transmission line to new station line terminal with (2) new spans. | 2020-09-14 | 2020-11-19 | 2020-11-24 |  | 995987 |  |  | 99 | 138 |  | 0.07 | 1272 ACSR 54/19 Pheasant | Steel Dead-End | 100 | 0.07 |  |  | 16 TAC 25.101 (c)(5)(A) | Utilizing existing easements Landowners noticed
42976122 (P18254006) | North New Boston 138-kV Substation | New Boston/Bowie | Upgrade relaying and replace CCVT's at remote end station | 2020-09-23 | 2020-10-29 | 2020-10-29 |  | 576263 |  |  | 98 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42976123 (P18254007) | Bann 138-kV Substation | Bowie | Upgrade relaying at remote end station | 2020-10-19 | 2020-11-19 | 2020-11-24 |  | 348808 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42941390 (P18215001) | Lydia 345-kV Station | Bowie | Convert the Lydia 345kV station to a ring bus configuration, eliminating the 3-terminal line by adding breakers. A new station will be built in the clear on newly purchased property; the existing station will be retired. | 2020-09-14 | 2022-05-11 |  |  | 15843030 |  |  | 9 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10068530 (DP20S05D0) | Alba 69-kV Substation Upgrade: T-Station | Alba/Wood | Rebuild Alba substation with new station deadend, bus work, SSVT, and relaying. | 2020-10-04 | 2020-12-15 | 2020-12-29 |  | 658792.77 |  |  | 90 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10068526 (DP20S05C0) | Alba 69-kV Substation Upgrade: T-Line | Alba/Wood | Install one transmission structure to feed the new station rebuild | 2020-10-04 | 2020-12-15 | 2020-12-29 |  | 425355 |  |  | 90 | 69 |  | 0.02 | T2 477 KCM ACSR | Steel Dead-End |  |  |  |  | 16 TAC 25.83(a)(3) | Within Station Property
T10076668 (A19084001) | Bann - NW Texarkana 138-kV T-Line Interstate 30 TxDOT Relocation | Bowie | Relocate one structure along the Bann to NW Texarkana 138-kV transmission line to make room for access roads being built along Interstate Highway 30 (IH 30) as requested by the Texas Department of Transportation (TxDOT) | 2020-11-16 | 2020-12-07 |  |  | 228227 |  |  | 10 | 138 |  |  | 1590 ACSR 54/19 Falcon | Concrete Mono Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(F) | Landowners Noticed
T10076671 (A19084002) | Bann-New Boston 69-kV T-Line: Interstate 30 TxDOT Relocation | Bowie | Relocate two structures along the Bann to New Boston 69-kV transmission line to make room for access roads being built along Interstate Highway 30 (IH 30) as requested by the Texas Department of Transportation (TxDOT) | 2020-11-16 | 2021-01-12 |  |  | 561506 |  |  | 0 | 69 |  |  | 1272 ACSR 54/19 Pheasant | Steel Mono Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(F) | Landowners Noticed
42904905 (A15706010) | NW Texarkana Tap Switch | Texarkana/Bowie | Replace existing 2-way phase over phase switch with 2000A phase-over-phase MOS with auto-sectionalizing. Switch and structure will be built to 138-kV standards, but operated at 69-kV. | 2020-12-07 | 2021-04-30 |  |  | 1349735 |  |  | 25 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Easement Landowners Noticed
42905248 (A16806068) | NW Texarkana Tap Switch & Redick Tap Switches: T-line Retermination | Texarkana/Bowie | T-line Retermination work associated and required for rebuild of NW Texarkana Tap Switch and both Redlick Tap Switches | 2020-12-07 | 2021-11-13 |  |  | 749638 |  |  | 5 | 69 |  | 0.02 | 1272 ACSR 54/19 Pheasant | Steel Dead-End | Varies | 0.02 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowners Noticed
42904907 (A15706022) | Telecomm fiber transitions from T-line into stations | Texarkana/Bowie | Install telecomm fiber transitions from T-line into station at Bann Station, Richmond Road Station, and 39th Street Station | 2021-01-04 | 2021-11-13 |  |  | 242392 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10132489 (A18806054) | Lone Star South - Failed Relay | Lone Star/Morris | Replace failed transformer differential relay panel on 138/69kV transformer | 2021-01-11 | 2021-02-21 |  |  | 404220 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42952896 (A18106011) | N Marshall 69-kV Substation: Construct Box Bay | Marshall/Harrison | The 69-kV portion of the station will be replaced with a box bay. Breaker 7570 with be replaced with new 2000 A breaker as part of this rebuild. A DICM will be installed to house all of the new transmission relay equipment. | 2021-02-01 | 2021-12-31 |  |  | 3940359 |  |  | 0 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
42963433 (A18106017) | N Marshall - Marshall 69-kV Retermination | Marshall/Harrison | Terminate the existing N Marshall to Marshall 69-kV line into new Box Bay as part of the Jefferson station rebuild | 2021-02-01 | 2021-12-31 |  |  | 514806 |  |  | 0 | 69 |  | 0.02 | 795 KCM ACSR "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Property
42952898 (A18106002) (A18106004) | Woodlawn - N Marshall 69-kV Rebuild | Marshall/Harrison | Rebuild and reconductor the Woodlawn to N. Marshall 69-kV transmission line to 138-kV standards but will continue to operate at 69 kV. | 2021-02-01 | 2021-12-31 |  |  | 8098078 |  |  | 0 | 69 |  | 7.55 | 795 KCM ACSR "Drake" | Steel Mono Pole | Centerline | 7.55 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easement Landowners Noticed
T10139440 (A18806048) | Overton 138-kV Substation | Overton/Rusk | Replace failed PLC carrier set on Overton - NW Henderson 138kV line as well as line protection relays. | 2021-03-06 | 2021-03-31 |  |  | 481660 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10139442 (A18806050) | NW Henderson 138-kV Substation | Henderson/Rusk | Replace failed PLC carrier set on Overton - NW Henderson 138kV line as well as line protection relays. | 2021-03-06 | 2021-03-31 |  |  | 406827 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10142089 (A18806059) | South Texas Eastman Failed LCBIII | Longview/Gregg | Replace failed primary line differential protection relay and breaker controls on South Texas Eastman - Eastex SW 138kV line. | 2021-03-24 | 2021-05-20 |  |  | 867948 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10142112 (A18806061) | Eastex SW Failed LCBIII | Longview/Gregg | Replace failed primary line differential protection relay and breaker controls on South Texas Eastman - Eastex SW 138kV line. | 2021-03-24 | 2021-05-20 |  |  | 459668 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42939973 (P18231001) (P18231002) | Carthage T 138-kV Box Bay | Panola | Install 3 new138-kV breakers in current box bay. Expand station site to accommodate DICM. Install line relaying and breakers controls in new control house. | 2021-04-14 | 12/085/2021 |  |  | 3830879 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased for Expansion
T10236276 (A15713062) | Rock Hill - Marshall 69-kV Line | Marshall/Harrison, Rusk | Telecom Modernization Program: Install 18.5 miles of 96 count ADSS fiber via Transmission between Marshall 69-kV Station and Rock Hill Station. For connectivity at Marshall 69kV Station, Rosborough Station and Rock Hill Station to support CES and ICON network. | 2021-03-06 | 2021-06-01 |  |  | 1309447 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
T10236194 (A15713129) | LeBrock-Roseborough Telecom Fiber | Harrison | Telecom Modernization Program: Install 3.58 miles of 48 count ADSS via Distribution between LeBrock Station and Rosborough Station. For connectivity at LeBrock Station and Rosborough Station to support CES and ICON network. | 2021-04-26 | 2021-05-15 |  |  | 361888 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236204 (A15713187) | Lydia 345-kV Switch Station Fiber Extension North | Bowie | Telecom Modernization Program: Install 5.5 miles of 48 count ADSS fiber via underground build between Lydia station and an existing splice point into fiber on the "Mount Pleasant‐New Boston 138-kV transmission line." For connectivity at Lydia Station. | 2021-03-06 | 2021-06-30 |  |  | 1607011 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236272 (A15713189) | Lydia 345-kV Switch Station Fiber Extension South | Bowie | Telecom Modernization Program: Install 5.6 miles of 48 count ADSS fiber via underground build between Lydia station and an existing splice point into fiber on the "Mount Pleasant‐New Boston 138-kV transmission line." For connectivity at Lydia Station. | 2021-03-06 | 2021-06-30 |  |  | 914863 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236307 (A19351067) | Marshall - Pirkey 138-kV Line | Marshall/Harrison | Telecom Modernization Program: Install 7.5 miles of 96 count ADSS fiber between Marshall Station and Pirkey Station. For connectivity at Marshall Station and Pirkey Station to support CES and ICON network. | 2021-05-17 | 2021-08-19 |  |  | 662819 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
T10138035 (A18806036) | Pirkey 138-kV Substation | Harrison | Replace Legacy DFR Monitoring | 2021-04-10 | 2021-06-15 |  |  | 354385 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10180035 (A18806075) | Lone Star South 138-kV Substation | Lone Star/Morris | Replace Line Relaying with AEP standard panels and a breaker control panel. | 2021-04-26 | 2021-06-15 |  |  | 362215 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10180047 (A18806076) | Pittsburg 138-kV Substation | Pittsburg/Camp | Replace Line Relaying with AEP standard panels and a breaker control panel. | 2021-04-26 | 2021-06-15 |  |  | 355252 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42941326 (P18222003) | Grand Saline - Quitman 69-kV Line | Wood | Terminate the existing Grand Saline to Quitman 69-kV transmission line into New Quitman 69-kV Substation. Project inlcudes 69-kV shoo-fly. | 2020-05-01 | 2021-10-01 |  |  | 1131471 |  |  | 0 | 69 |  | 0.1 | 556.5 ACSR 26/7 "Dove" | Steel Mono Poles |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property