## C-4.1
EL PASO ELECTRIC COMPANY
2021 TEXAS RATE CASE FILING
SCHEDULE C-4.1: CWIP BY FUNCTIONAL GROUP
SPONSOR: LARRY J. HANCOCK
PREPARER: LARRY J. HANCOCK / GREGORY SHEARMAN
FOR THE TEST YEAR ENDED DECEMBER 31, 2020
|  | (a) | (b) | (c) |  | (d) |  | (e) | (f) | (g) | (h)
LINE NO. |  | DESCRIPTION | PROJECT # (1) | TOTAL ESTIMATED INSTALLED COST (2) |  | ESTIMATED AFUDC (2) |  | CUMULATIVE NON-AFUDC EXPENDITURES AS OF TEST YEAR END | CUMULATIVE AFUDC AS OF TEST YEAR END | CUMULATIVE EXPENDITURES AS OF TEST YEAR END | ESTIMATED COMPLETION DATE (5)
PRODUCTION
1 |  | PALO VERDE UNIT 1 CAPITAL IMPROVEMENTS | GP009 |  |  |  |  | 4278708 | 431487 | 4710195 | BLANKET
2 |  | PALO VERDE UNIT 2 CAPITAL IMPROVEMENTS | GP009 |  |  |  |  | 2981789 | 493309 | 3475098 | BLANKET
3 |  | PALO VERDE UNIT 3 CAPITAL IMPROVEMENTS | GP009 |  |  |  |  | 8249398 | 481110 | 8730508 | BLANKET
4 |  | PALO VERDE COMMON FACILITIES CAP IMPRV | GP009 |  |  |  |  | 15073204 | 2045512 | 17118716 | BLANKET
5 |  | PALO VERDE WATER RECLAMATION FACILITY | GP009 |  |  |  |  | 5689064 | 275204 | 5964268 | BLANKET
6 |  | TOTAL PALO VERDE | GP009 | 39338677 | (4) | 2479015 | (4) | 36272163 | 3726622 | 39998785 | BLANKET
7 |  | NEWMAN CAPITAL BLANKET | GN003 | 906524 | (4) | 61045 | (4) | 2138666 | 55017 | 2193683 | BLANKET
8 |  | NEWMAN U4 STEAM INSTRUMENTATION UPGRADE | GN186 | 3099699 |  | 96455 |  | 3003244 | 96455 | 3099699 | 2021
9 |  | NEWMAN U4 GT1 INSTRUMENTATION UPGRADES | GN185 | 2700251 |  | 92327 |  | 2607924 | 92327 | 2700251 | 2021
10 |  | NEWMAN U4 GT2 INSTRUMENTATION UPGRADES | GN184 | 2644951 |  | 84107 |  | 2560844 | 84107 | 2644951 | 2021
11 |  | NEWMAN U5 GT4 WET COMPRESSION UPGRADE | GN140 | 1607166 |  | 63512 |  | 1543654 | 63512 | 1607166 | 2021
12 |  | NEWMAN U3 BOILER PARTS REPLCMNTS | GN207 | 2484902 |  | 39737 |  | 610534 | 4210 | 614744 | 2021
13 |  | NEWMAN UNIT 6 - INITIAL CONSTRUCTION | GN208 | 152152650 |  | 15318434 |  | 23576824.62 | 489535.93 | 24066361 | 2023
14 |  | NEWMAN U3 BOILER ECONOMIZER SECTION REP | GN258 | 1311094 |  | 14587 |  | 602337 | 5507 | 607844 | 2021
15 |  | NEWMAN U4 HALON FIRE SYSTEM UPGRADE | GN220 | 591235 |  | 11429 |  | 579806 | 11429 | 591235 | 2020
16 |  | NEWMAN U3 BOILER REHEAT SECTION REPLACE | GN257 | 1061326 |  | 13087 |  | 354070 | 4001 | 358071 | 2021
17 |  | NEWMAN U4 NEW VACUUM PUMP SYSTEM | GN147 | 468135 |  | 21026 |  | 291485 | 7843 | 299328 | 2021
18 |  | NEWMAN U4 SOFT STARTERS TO VFD UPGRADE | GN216 | 134677 |  | 5808 |  | 128869 | 5808 | 134677 | 2021
19 |  | TOTAL NEWMAN |  | 169162610 |  | 15821554 |  | 37998258 | 919752 | 38918010
20 |  | MONTANA UNIT 1 CAPITAL IMPROVEMENTS | GM002 |  |  |  |  | 0 | 0 | 0 | BLANKET
21 |  | MONTANA UNIT 2 CAPITAL IMPROVEMENTS | GM002 |  |  |  |  | 0 | 0 | 0 | BLANKET
22 |  | MONTANA UNIT 3 CAPITAL IMPROVEMENTS | GM002 |  |  |  |  | 99944 | 221 | 100165 | BLANKET
23 |  | MONTANA COMMON CAPITAL IMPROVEMENTS | GM002 |  |  |  |  | 351811 | 3121 | 354932 | BLANKET
24 |  | TOTAL MONTANA BLANKET | GM002 | 1268723 | (4) | 95996 | (4) | 451755 | 3342 | 455097 | BLANKET
25 |  | MONTANA BLACK START SYSTEM IMPLEMENTATION | GM105 | 2491658 |  | 49448 |  | 2442210 | 49448 | 2491658 | 2022
26 |  | MONTANA UNIT 3 PARTIAL HOT SECTION REPLACEMENT | GM128 | 2694051 |  | 24870 |  | 2669181 | 24870 | 2694051 | 2021
27 |  | MONTANA CAPITAL SPARES | GM116 | 678439 |  | 61279 |  | 105108 | 1761 | 106869 | 2021
28 |  | TOTAL MONTANA |  | 7132871 |  | 231593 |  | 5668254 | 79421 | 5747675
29 |  | RIO GRANDE - UNIT 8 CAPITAL IMPROVEMENTS | GR014 |  |  |  |  | 85808 | 4623 | 90431 | BLANKET
30 |  | RIO GRANDE - UNIT 9 CAPITAL IMPROVEMENTS | GR014 |  |  |  |  | 55748 | 361 | 56109 | BLANKET
31 |  | RIO GRANDE - COMMON CAPITAL IMPROVEMENTS | GR014 |  |  |  |  | 120434 | 294 | 120728 | BLANKET
32 |  | TOTAL RIO GRANDE CAPITAL IMPROVEMENTS | GR014 | 633404 | (4) | 5362 | (4) | 261990 | 5278 | 267268 | BLANKET
33 |  | RIO GRANDE WELL #2 RELOCATION | GR172 | 250472 |  | 2076 |  | 248396 | 2076 | 250472 | 2021
34 |  | RIO GRANDE UNIT 8 DRUM LEVEL UPGRADE | GR169 | 325960 |  | 6279 |  | 128216 | 2234 | 130450 | 2021
35 |  | RIO GRANDE 480V & 2300V SYSTEM UPGRADE | GR139 | 129228 |  | 15102 |  | 114126 | 15102 | 129228 | 2021 | SCHEDULE C-4.1 PAGE 1 OF 4
36 |  | TOTAL RIO GRANDE CAPITAL IMPROVEMENTS |  | 1339064 |  | 28819 |  | 752728 | 24690 | 777418
37 |  | COPPER CAPITAL IMPROVEMENT BLANKET | GC003 | 179934 |  | 9611 |  | 167594 | 1070 | 168664 | BLANKET
38 |  | COPPER HOT GAS PATH OUTAGE IMPROVEMENTS | GC107 | 9492566 |  | 161217 |  | 9331349 | 161217 | 9492566 | 2021
39 |  | COPPER CAPITAL SPARE PARTS | GC108 | 7500310 |  | 137344 |  | 7362966 | 137344 | 7500310 | 2021
40 |  | COPPER GENERATOR STATOR REPLACEMENT | GC113 | 896951 |  | 3910 |  | 893041 | 3910 | 896951 | 2021
41 |  | COPPER SILENCER SECTION REPLACEMENT | GC114 | 219876 |  | 729 |  | 219147 | 729 | 219876 | 2021
42 |  | TOTAL COPPER STATION CAPITAL IMPROVEMENTS |  | 18289637 |  | 312811 |  | 17974097 | 304270 | 18278367
43 |  | NMSU SOLAR PLUS STORAGE PROJECT | GS123 | 4069734 |  | 68306 |  | 1801631.32 | 5721.86 | 1807353 | 2021
44 |  | TOTAL RENEWABLE SOLAR |  | 4069734 |  | 68306 |  | 1801631.32 | 5721.86 | 1807353
45 |  | TOTAL PRODUCTION |  | 239332593 |  | 18942098 |  | 100467131 | 5060477 | 105527608
TRANSMISSION
46 |  | RIO GRANDE - SUNSET 115KV LINE | TL101 | 21161388 |  | 2830440 |  | 6998768 | 1118167 | 8116935 | 2024
47 |  | AFTON NORTH TO AIRPORT 115KV LINE | TL178 | 18813307 |  | 2486670 |  | 2665878 | 726581 | 3392459 | 2024
48 |  | TEXAS DEPT OF TRNSPRTN PHASE 2 LOOP 375 CROSSING UPGRADE | TL283 | 229413 |  | 129225 |  | 3126533 | 103178 | 3229711 | 2021
49 |  | TEXAS DEPT OF TRNSPRTN PHASE 1 LOOP 375 CROSSING UPGRADE | TL282 | 110653 |  | 96077 |  | 2814192 | 72476 | 2886668 | 2021
50 |  | AFTON NORTH SUBSTATION | TH171 | 17503559 |  | 1914380 |  | 1955523 | 209363 | 2164886 | 2020
51 |  | JORNADA - MOONGATE LINE CONSTRUCTION | TL119 | 8215493 |  | 354891 |  | 1729830 | 138913 | 1868743 | 2021
52 |  | SPARKS-WRANGLER LINE REBUILD | TL106 | 3155660 |  | 92749 |  | 1319471 | 57490 | 1376961 | 2021
53 |  | PICANTE TRANSMISSION SUBSTATION REACTOR ADDITION | TS125 | 3672174 |  | 107886 |  | 1176123 | 87073 | 1263196 | 2022
54 |  | VADO TRANSMISSION SUBSTATION CONSTRUCTION | TS139 | 9633801 |  | 137023 |  | 837078 | 0 | 837078 | 2024
55 |  | FT. BLISS SUBSTATION 30 MVAR CAPACITOR ADDITION | TS113 | 894073 |  | 89144 |  | 601949 | 59449 | 661398 | 2021
56 |  | HIDALGO SUBSTATION CIRCUIT BREAKER REPLACEMENT | TS135 | 493790 |  | 3058 |  | 517283 | 1225 | 518508 | 2021
57 |  | NEWMAN UNIT 6 SUBSTATION ADDITION | TS148 | 7290868 |  | 187669 |  | 329362 | 5964 | 335326 | 2022
58 |  | NEWMAN 345KV SYNCHRONIZED BREAKER | TS157 | 410458 |  | 9166 |  | 274072 | 1929 | 276001 | 2021
59 |  | TRIUMPH SUBSTATION TRANSM LINE TAP | TL277 | 503588 |  | 6144 |  | 268032 | 4233 | 272265 | 2021
60 |  | CALIENTE AUTO TRANSFORMER & CIRCUIT BREAKER REPLACEMENTS | TS149 | 4062112 |  | 120464 |  | 258281 | 9933 | 268214 | 2023
61 |  | MACHO SPRINGS CIRCUIT BREAKER REPLACEMENT | TS143 | 426501 |  | 1712 |  | 243873 | 873 | 244746 | 2020
62 |  | VARIOUS SUBSTATION CAPITAL IMPROVEMENTS | TS063 | 171898 |  | 2870 |  | 199990 | 9287 | 209277 | BLANKET
63 |  | TRANSMISSION ROW RENEWALS & ACQUISITIONS | TT080 | 89320 |  | 0 |  | 209226 | 0 | 209226 | BLANKET
64 |  | NEW APOLLO TO COX 115KV LINE CONSTRUCTION | TL241 | 3811533 |  | 33672 |  | 206368 | 70 | 206438 | 2020
65 |  | PINE SUBSTATION CONSTRUCTION | TS120 | 9661990 |  | 135636 |  | 201169 | 0 | 201169 | 2024
66 |  | NEWMAN GROUND GRID ADDITION | TS155 | 163307 |  | 4875 |  | 158432 | 4875 | 163307 | 2020
67 |  | RELAY UPGRADES - VARIOUS SUBSTATIONS | TS065 | 355419 |  | 3355 |  | 134988 | 8311 | 143299 | BLANKET
68 |  | WOOD POLE REPLACEMENTS | TL253 | 1020064 |  | 1593 |  | 132860 | 807 | 133667 | 2020
69 |  | DIABLO-LUNA DEADEND STRUCTURE REPLACEMENT | TL272 | 581606 |  | 4136 |  | 122893 | 2406 | 125299 | 2021
70 |  | TALAVERA SUBSTATION CONSTRUCTION | TL254 | 1844564 |  | 53626 |  | 109284 | 2273 | 111557 | 2021
71 |  | TOTAL TRANSMISSION |  | 114276539 |  | 8806461 |  | 26591458 | 2624876 | 29216334
DISTRIBUTION
72 |  | TRIUMPH SUBSTATION CONSTRUCTION | DT391 | 10384100 |  | 452164 |  | 8985076 | 306113 | 9291189 | 2021
73 |  | MOONGATE SUBSTATION CONSTRUCTION | DN145 | 9627367 |  | 677395 |  | 5793182 | 346466 | 6139648 | 2021
74 |  | TEXAS COMMERCIAL CONSTRUCTION BLANKET | DT069 | 9086330 |  | 281590 |  | 4086466 | 152935 | 4239401 | BLANKET
75 |  | TEXAS DISTRIBUTION BETTERMENT BLANKET | DT062 | 6492589 |  | 239060 |  | 4053172 | 167964 | 4221136 | BLANKET
76 |  | RIO BOSQUE SUBSTATION TRANSFORMER & SWITCHGEAR ADDNS | DT158 | 3308649 |  | 88074 |  | 3083036 | 87169 | 3170205 | 2021
77 |  | TALAVERA SUBSTATION CONSTRUCTION | DN185 | 10865775 |  | 329069 |  | 2847252 | 152602 | 2999854 | 2021
78 |  | RIO GRANDE SUBSTATION UPGRADES | DN179 | 3098463 |  | 239762 |  | 2305905 | 84524 | 2390429 | 2024
79 |  | INTERCONNECTION NMSU SOLAR STORAGE | DN217 | 2997783 |  | 23203 |  | 1696959 | 0 | 1696959 | 2021
80 |  | HORIZON SUBSTATION EXPANSION | DT434 | 3456092 |  | 72365 |  | 1412725 | 12600 | 1425325 | 2021
81 |  | DALLAS SUBSTATION UPGRADES/REPLC | DT387 | 9907889 |  | 731685 |  | 954163 | 438227 | 1392390 | 2023
82 |  | MCNUTT SUBSTATION (NEW) | DN200 | 12388707 |  | 857216 |  | 854698 | 98558 | 953256 | 2028 | SCHEDULE C-4.1 PAGE 2 OF 4
83 |  | ALAMO VOLTAGE REGULATOR REPLACEMENT | DT428 | 1894266 |  | 101847 |  | 818155 | 26105 | 844260 | 2021
84 |  | SHEARMAN SUBSTATION CONSTRUCTION | DT420 | 11096440 |  | 398226 |  | 800584 | 2973 | 803557 | 2022
85 |  | LAS CRUCES AIRPORT SUBSTATION RINGBUS ADDITIONS | DN195 | 11148192 |  | 863605 |  | 642732 | 147320 | 790052 | 2025
86 |  | NEW MEXICO COMMERCIAL CONSTRUCTION BLANKET | DN069 | 2491744 |  | 74220 |  | 696994 | 28600 | 725594 | BLANKET
87 |  | RE-CABLE DOWNTOWN NETWORK FEEDERS | DT234 | 1917918 |  | 149336 |  | 695127 | 3492 | 698619 | 2022
88 |  | VARIOUS TEXAS SUBSTATION CIRCUIT BREAKER REPLACEMENTS | DT188 | 5192766 |  | 46119 |  | 693338 | 0 | 693338 | BLANKET
89 |  | VARIOUS TEXAS AREA 4KV CONVERSIONS | DT189 | 5874129 |  | 0 |  | 658176 | 0 | 658176 | 2026
90 |  | VISTA SUBTATION RECONFIGURATION & UPGRADES | DT411 | 1058102 |  | 82638 |  | 596549 | 38363 | 634912 | 2022
91 |  | NETWORK SYSTEM UPGRADE BY EATON | DT354 | 2306224 |  | 295376 |  | 571788 | 32584 | 604372 | 2022
92 |  | LANE SUBSTATION T2 TRANSFORMER REPLACEMENT | DT380 | 5214126 |  | 155123 |  | 562283 | 33351 | 595634 | 2022
93 |  | DYER SUBSTATION EXPANSION | DT398 | 7323011 |  | 321692 |  | 526535 | 57712 | 584247 | 2023
94 |  | TEXAS CABLE REPLACEMENT PROGRAM BLANKET | DT121 | 354740 |  | 8801 |  | 572028 | 5428 | 577456 | BLANKET
95 |  | RIO BOSQUE SUBSTATION FEEDER ADDITIONS | DT446 | 872647 |  | 9658 |  | 556904 | 5711 | 562615 | 2021
96 |  | NEW MEXICO RESIDENTIAL CONSTRUCTION BLANKET | DN061 | 2270379 |  | 49465 |  | 546983 | 12032 | 559015 | BLANKET
97 |  | NEW SPARKS SUBSTATION T2 FEEDERS | DT350 | 500057 |  | 9042 |  | 491015 | 9042 | 500057 | 2021
98 |  | ALAMO SUBSTATION UPGRADE | DT335 | 1541363 |  | 100099 |  | 343030 | 47981 | 391011 | 2021
99 |  | HAWKINS SUBSTATION CONSTRUCTION | DT328 | 8059148 |  | 305826 |  | 333659 | 53479 | 387138 | 2022
100 |  | NEW MEXICO DISTRIBUTION BETTERMENT BLANKET | DN062 | 1718188 |  | 52501 |  | 369718 | 14763 | 384481 | BLANKET
101 |  | TEXAS DISTRIBUTION DAMAGE BLANKET | DT065 | 1131056 |  | 26146 |  | 380361 | 2511 | 382872 | BLANKET
102 |  | TEXAS SUBSTATION BETTERMENT BLANKET | DT063 | 431407 |  | 13885 |  | 358336 | 16676 | 375012 | BLANKET
103 |  | SUNSET SUBSTATION BUS UPGRADE | DT433 | 1748222 |  | 103480 |  | 333601 | 10395 | 343996 | 2022
104 |  | NEW MEXICO SUBSTATION BETTERMENT BLANKET | DN063 | 340540 |  | 14471 |  | 313294 | 7913 | 321207 | BLANKET
105 |  | TEXAS POLE REPLACEMENTS & IMPROVEMENTS BLANKET | DT372 | 911319 |  | 64728 |  | 279885 | 8018 | 287903 | BLANKET
106 |  | NEW MEXICO DISTRIBUTION DAMAGE BLANKET | DN065 | 501941 |  | 13777 |  | 229887 | 2623 | 232510 | BLANKET
107 |  | ARROYO SUBSTATION CIRCUIT BREAKER REPLACEMENT | DN211 | 396784 |  | 3389 |  | 230603 | 630 | 231233 | 2021
108 |  | SANTA FE SUBSTATION FEEDER IMPROVEMENTS | DT317 | 0 |  | 0 |  | 203728 | 8039 | 211767 | BLANKET
109 |  | TEXAS SUBSTATION RELAY UPGRADES BLANKET | DT015 | 242447 |  | 8339 |  | 178739 | 7490 | 186229 | BLANKET
110 |  | LEASBURG SUBSTATION CONSTRUCTION | DN180 | 7928187 |  | 243964 |  | 172320 | 0 | 172320 | 2022
111 |  | FELIPE SUBSTATION 21 FEEDER | DT355 | 522237 |  | 4302 |  | 170339 | 1272 | 171611 | 2022
112 |  | NEW MEXICO SUBSTATION RELAY UPGRADES BLANKET | DN015 | 264230 |  | 11159 |  | 155006 | 6329 | 161335 | BLANKET
113 |  | VERDE SUBSTATION CONSTRUCTION | DN136 | 8548063 |  | 116306 |  | 149354 | 4961 | 154315 | 2023
114 |  | CE-3 (NAME NOT YET DETERMINED) NEW SUBSTATION | DT409 | 10457129 |  | 506400 |  | 146113 | 0 | 146113 | 2026
115 |  | CLINT SUBSTATION UPGRADES | DT448 | 891552 |  | 15102 |  | 144837 | 841 | 145678 | 2021
116 |  | QUITMAN MOUNTAIN DISTRIBUTION LINE UPGRADES | DT443 | 140635 |  | 0 |  | 140635 | 0 | 140635 | 2020
117 |  | TALAVERA SUBSTATION GETAWAYS AND FEEDERS | DN178 | 667008 |  | 20526 |  | 130697 | 6629 | 137326 | BLANKET
118 |  | GLOBAL REACH SUBSTATION FEEDERS | DT270 | 0 |  | 0 |  | 131826 | 3470 | 135296 | BLANKET
119 |  | MOONGATE SUBSTATION GETAWAY & FEEDERS | DN164 | 548463 |  | 17593 |  | 111215 | 20049 | 131264 | BLANKET
120 |  | SAN FELIPE SUBSTATION CONSTRUCTION | DT395 | 14211952 |  | 517908 |  | 124411 | 1095 | 125506 | 2021
121 |  | LAS CRUCES AIRPORT SUBSTATION INTERCONNECTIONS | DN199 | 1668919 |  | 197104 |  | 111875 | 13101 | 124976 | 2021
122 |  | VALLEY SUBSTATION CAPACITOR BANK REPLACEMENT | DT293 | 1140856 |  | 39605 |  | 118636 | 4600 | 123236 | 2022
123 |  | TEXAS LIGHTING BLANKET | DT064 | 609750 |  | 14132 |  | 128798 | -6280 | 122518 | BLANKET
124 |  | TOTAL DISTRIBUTION |  | 205749881 |  | 8967473 |  | 50992728 | 2486456 | 53479184
GENERAL & INTANGIBLE
125 |  | GENERATION MAXIMO IMPLEMENTATION | SS224 | 7692677 |  | 302347 |  | 7157720 | 302085 | 7459805 | 2021
126 |  | CUSTOMER CARE & BILLING SYSTEM UPGRADE | SS243 | 12463960 |  | 479615 |  | 4571655 | 6243 | 4577898 | 2021
127 |  | PANDEMIC READINESS PROJECT | SS311 | 1316967 |  | 0 |  | 1316967 | 0 | 1316967 | 2021
128 |  | LABOR - CWIP CLEARING PROJECT | AP701 | 703214 |  | 0 |  | 703214 | 0 | 703214 | Clearing
129 |  | PROTECTION SIGNALING UPGRADES BLANKET | SC153 | 1971475 |  | 0 |  | 680300 | 14464 | 694764 | Blanket
130 |  | TRANSPORTATION EQUIPMENT ACQUISITION BLANKET | SS005 | 7090500 |  | 0 |  | 647065 | 0 | 647065 | Blanket
131 |  | STANTON TOWER FIRE PUMP REPLACEMENT | SS161 | 568113 |  | 746 |  | 567367 | 746 | 568113 | 2021
132 |  | STANTON TOWER GENERATOR REPLACEMENT | SF134 | 17206400 |  | 1687693 |  | 518705 | 18442 | 537147 | 2023
133 |  | GIS VERSION 10.6.1 SYSTEM UPGRADE | SS254 | 645095 |  | 5442 |  | 571669 | 2738 | 574407 | 2021
134 |  | STANTON TOWER BOILER REPLACEMENT | SF139 | 6760252 |  | 1107641 |  | 312608 | 10896 | 323504 | 2022 | SCHEDULE C-4.1 PAGE 3 OF 4
135 |  | STANTON TOWER CHILLER REPLACEMENT | SF140 | 8912709 |  | 1104140 |  | 308565 | 10620 | 319185 | 2022
136 |  | STANTON TOWER BASEMENT & COURTYARD IMPROVEMENTS | SF138 | 312823 |  | 11971 |  | 300852 | 11971 | 312823 | 2021
137 |  | WIRELESS NETWORK SYSTEM UPGRADE | SS259 | 285505 |  | 6832 |  | 278673 | 6832 | 285505 | 2021
138 |  | ASSET RESOURCE MANAGEMENT T&D WAVE 2 | SS226 | 272272 |  | 2574 |  | 269698 | 2574 | 272272 | 2021
139 |  | ENERGY MANAGEMENT SYSTEM UPGRADE | ST107 | 7769383 |  | 439430 |  | 524500 | 678 | 525178 | 2022
140 |  | LAND MANAGEMENT RECORD DIGITIZATION | SS229 | 655851 |  | 29726 |  | 257660 | 6020 | 263680 | 2021
141 |  | FACILITY SERVICES CAPITAL IMPROVEMENT BLANKET | SF007 | 1156943 |  | 51941 |  | 232984 | 6852 | 239836 | Blanket
142 |  | EASTSIDE OPERATION CENTER SAFETY TRAINING BUILDOUT | SS236 | 10121652 |  | 287618 |  | 230040 | 1421 | 231461 | 2022
143 |  | STANTON TOWER CAPITAL REPLACEMENTS | SF114 | 198868 |  | 7591 |  | 191277 | 7591 | 198868 | 2021
144 |  | CASCADE SYSTEM IMPROVEMENTS | SS256 | 230326 |  | 2739 |  | 185636 | 463 | 186099 | 2021
145 |  | PHYSICAL SECURITY SYSTEMS BLANKET | SS070 | 220522 |  | 21601 |  | 166349 | 682 | 167031 | Blanket
146 |  | OPERATIONAL TECHNOLOGY NETWORK IMPROVEMENTS BLANKET | SC050 | 109185 |  | 0 |  | 133228 | 4275 | 137503 | Blanket
147 |  | DEPLOY CYBERSECURITY TO SUBSTATIONS | ST114 | 758702 |  | 54134 |  | 133411 | 1255 | 134666 | 2022
148 |  | SECURITY OPERATIONS IMPROVEMENTS | SS190 | 134023 |  | 1318 |  | 132705 | 1318 | 134023 | 2021
149 |  | RANSOMWARE PROTECTION IMPLEMENTATION | ST112 | 124136 |  | 518 |  | 119966 | 265 | 120231 | 2021
150 |  | ENVIRONMENTAL SYSTEMS RESEARCH INSTITUTE CASCADE IMPLMNTN | SS261 | 117686 |  | 2828 |  | 114858 | 2828 | 117686 | 2021
151 |  | FABENS CUSTOMER SERVICE CENTER BUILDOUT | SS246 | 1992069 |  | 56076 |  | 103714 | 653 | 104367 | 2021
152 |  | VARIOUS CAPITAL ACCRUALS | AP720 | 103152 |  | 0 |  | 103152 | 0 | 103152 | 2021
153 |  | EASTSIDE OPERATIONS CENTER FLEET STORAGE BUILDING | SS237 | 214465 |  | 3205 |  | 100257 | 1075 | 101332 | 2021
144 |  | TOTAL GENERAL & INTANGIBLE |  | 90108925 |  | 5667726 |  | 20934795 | 422987 | 21357782
145 |  | SUBTOTAL PROJECTS OVER $100,000 |  | 649467938 |  | 42383758 |  | 198986112 | 10594796 | 209580908
146 |  | OTHER PROJECTS UNDER $100,000 | [7 empty] | 4481311.77
|  | TOTAL CWIP AT DECEMBER 31, 2020 | [7 empty] | 214062220 | -3
| (1) | PROJECT NUMBERS MAY INCLUDE SEVERAL WORK ORDERS
| (2) | TOTAL ESTIMATED COSTS AND AFUDC FOR PROJECTS NOTED AS "BLANKET" REFLECT
ONE YEAR OF FORECAST EXPENDITURES
| (3) | THE COMPANY IS NOT REQUESTING ANY CWIP IN RATE BASE IN THIS FILING
| (4) | PROJECT IS NOT FORECASTED BY UNIT
| (5) | FOR BLANKETS, COMPLETION DATES VARY AS INDIVIDUAL PROJECTS ARE COMPLETED.
SCHEDULE C-4.1 PAGE 4 OF 4