## H-6.1b
EL PASO ELECTRIC COMPANY | [7 empty] | SCHEDULE H-6.1b
2021 TEXAS RATE CASE FILING | [7 empty] | PAGE 1 OF 1
SCHEDULE H-6.1b: NUCLEAR UNIT OUTAGE DATA
SPONSOR: DAVID C. HAWKINS
PREPARER: AARON A. ARZAGA
FOR THE TEST YEAR ENDING DECEMBER 31, 2020
PALO VERDE GENERATING STATION: REFUELING AND MID-CYCLE OUTAGES
|  | DATE OF | SCHEDULED | SCHEDULED | SCHEDULED | ACTUAL | ACTUAL | ACTUAL
UNIT | OUTAGE | COMMERCIAL | START | END | LENGTH OF | START | END | LENGTH OF
NAME | NUMBER | OPERATION | DATE | DATE | OUTAGE | DATE | DATE | OUTAGE
| (A) | (B) | (C) |  | (DAYS) |  |  | (DAYS)
PVGS1 | U1R22 | 1986-01-28 | 2020-10-10 | 2020-11-22 | 44 | 2020-10-10 | 2020-12-03 | 54
PVGS2 | U2R22 | 1986-09-19 | 2020-04-04 | 2020-05-03 | 30 | 2020-04-03 | 2020-05-05 | 31
Notes:
(A) | U = Unit; R = Refueling Outage
(B) | Nuclear Regulatory Commission Monthly Operating Report
(C) | EPE's prior year budget assumptions