## Form
| Project Number: | [8 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | MPS Gas Compressor A&B 8,000hr New Kit Replacement Assembly
| Total Project Capital Cost: |  |  | 825955
| Reporting Date: |  |  | 2019-03-26
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Trey Frisbie |  |  |  | Project Manager Phone Number: |  | 915-258-5320
Owning Cost Center: |  | 5140 MONTANA POWER STATION |  |  |  | Major Project Location: |  | 50 - TX MONTANA POWER STATION - COMMON
Project Functional Class: |  | Other Production |  |  |  | Business Segment: |  | 180 MONTANA PWR STATION - COMMON
Associated Projects: |  | None
In-Lieu of Component
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | Remove gas compressor A & B for shipping to Houston for installation of New 8,000 hour replacement kit assembly.
Business Justification: |  | Kobelco recommends installation of new asssembly kit to be performed after 8,000-12,000 hours of run time. The new kits will have improved seals. This work needs to be performed to ensure that the compressor is reliable for our summer run.
Project Risks and Constraints: |  | While the work is being performed we would not have a spare gas compressor avialable.
Primary Reason for Expenditure |  |  | Reliability
Secondary Reason for Expenditure |  |  | Quality Improvement/Enhancement
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost
0
Estimated Start Date: |  |  | 2019-05-01 |  |  | Estimated Completion Date: |  |  | 2019-06-28
If applicable, describe and identify asset being replaced/retired
The gas compressor New Kit Replacement Assembly.
Please descrive the potential Cost Savings and/or Cost Avoidance for this project:
The cost savings would be seen in the improved availabiliy of this piece of equipment.
Describe alternatives considered:
None
What was the reason for selecting the proposed project over the alternatives considered?
Kobelco is the OEM and the only qualified to perform the work.
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Status Quo - Do Nothing
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 825955 |  |  | 825955 |  | 771740.2476 |  | 771740.2476
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 132173.783 |  |  | -528398.2906 |  | 105247.6009 |  | -50699.243
Income Tax Exp (Benefit): |  | 216418 |  |  | 555943 |  | 149477.1481 |  | 252933.3486
TOTAL COSTS |  | 1174546.783 |  |  | 853499.7094 |  | 1026464.9966 |  | 973974.3533
BENEFITS
Revenue Requirement: |  | 1107041.212 |  |  | 1871471.1935 |  | 785762.8475 |  | 1062079.4567
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 17270.2287 |  |  | 17270.2287 |  | 16136.6304 |  | 16136.6304
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 1124311.4407 |  |  | 1888741.4222 |  | 801899.4779 |  | 1078216.0871
BENEFIT-COST RATIO | [6 empty] | 0.78122 |  | 1.107
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Remove gas compressor "B" for shipping to Houston. | [7 empty] | 2019-04-30
Install compressor 8,000 hr. replacement kit assembly. | [7 empty] | 2019-05-17
Oil flush piping with external pumping unit. | [7 empty] | 2019-05-10
Ship gas compressor back to El Paso and install. | [7 empty] | 2019-05-17
Complete start up checks and put back inservice. | [7 empty] | 2019-05-18
Remove gas compressor "A" for shipping to Houston. | [7 empty] | 2019-06-01
Install compressor 8,000 hr. replacement kit assembly. | [7 empty] | 2019-06-12
oil flush piping with external pumping unit, complete startup checks and put back inservice. | [7 empty] | 2019-06-28
Please list internal and external resources assigned to this project:*
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Kobelco |  | Trey Frisbie |  |  |  |  | If no, explain why not:
B&M |  | Trey Frisbie |  |  |  |  | If no, explain why not:
ITC |  | Trey Frisbie |  |  |  |  | If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Trey Frisbie
| Date: | 2019-03-26
Sponsor / Approver Signature:
Name: |  | Albert Montano
| Date: | 2019-03-26
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Note on C42: Complete Capital Expenditure Section in CFFA and CBA tab. This should tie to the Upload Template
Note on C43: Complete O&M Expense Section in CFFA and CBA tab.
Note on C44: Calculated field. Financing Costs are related to the Interest Expense as result of additional debt to fund the project. Financial Benefits are avoidable increase in debt and interest expense due to additional revenue stream from revenue requirements in rates
Note on C48: Calculated field. Revenue Requirements are the expected increase in rate relief needed to sustained the allowable Rate of Return approved by the commissions
Note on C49: Complete Cost Savings section in CFFA and CBA tab.
Note on C50: Complete Cost Avoidance section in CFFA and CBA tab.
Note on C51: Calculated field.
Note on C52: Complete Other Benefits section in CFFA and CBA tab.