## Form
| Project Number: |  |  | GM126 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | MPS lightning protection
| Total Project Capital Cost: |  |  | 311798
| Reporting Date: |  |  | 2019-06-25
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Lusheng Su |  |  |  | Project Manager Phone Number: |  | 915-235-7087
Owning Cost Center: |  | 5140 MONTANA POWER STATION |  |  |  | Major Project Location: |  | 50 - TX MONTANA POWER STATION - COMMON
Project Functional Class: |  | General |  |  |  | Business Segment: |  | 180 MONTANA PWR STATION - COMMON
Associated Projects: |  | None
In-Lieu of Component
Project Priority |  | MEDIUM - Important but Not Urgent
Project overview/scope: |  | Install lightning protection for MPS
Business Justification: |  | On 08/23/2016 at a time of 9:52 PM unit1 was struck, unit 2 took a lightning strike 20 minutes later. This damaged GE90-30 PLC which is obsoleted in October, 2015. So MPS upgraded the PLC to GE RX31 platform which cost $77,766. Baca lightning protection LLC performed a site tour, and recommended to design and install the lightning protection by an LPI certified Master Installer Designer to meet the requirements specified by NFPA-780. In order to prevent such incidents happening again, a lightning protection system is recommended to be installed for the plant.
Project Risks and Constraints:
Primary Reason for Expenditure |  |  | Safety & Security
Secondary Reason for Expenditure |  |  | System Reliabilty & Improvement
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2019-08-01 |  |  | Estimated Completion Date: |  |  | 2019-12-31
If applicable, describe and identify asset being replaced/retired
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
The lightning struck the MPS U1 in 2016 which caused unit shut down due to thermo couple cards fried and $77,766 for repair.
Describe alternatives considered:
What was the reason for selecting the proposed project over the alternatives considered?
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 311798 |  |  | 311798 |  | 311798 |  | 311798
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 45859.1491 |  |  | -208677.1225 |  | 40195.9566 |  | -21598.3017
Income Tax Exp (Benefit): |  | 90716 |  |  | 208541 |  | 65357.0242 |  | 101699.559
TOTAL COSTS |  | 448373.1491 |  |  | 311661.8775 |  | 417350.9808 |  | 391899.2573
BENEFITS
Revenue Requirement: |  | 450089.7705 |  |  | 694299.9098 |  | 334575.3814 |  | 425636.4516
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 3693.3778 |  |  | 3693.3778 |  | 3693.3778 |  | 3693.3778
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 453783.1483 |  |  | 697993.2875 |  | 338268.7592 |  | 429329.8293
BENEFIT-COST RATIO | [6 empty] | 0.81051 |  | 1.0955
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Lightning protection installallation completed | [7 empty] | 2019-12-31
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Lusheng Su |  | Power Gen/EPE |  |  |  |  | If no, explain why not:
Contractor TBD |  | External |  |  |  |  | If no, explain why not: | In the process of bidding out
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Lusheng Su
| Date: | 2019-06-25
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function