## Form
| Project Number: |  |  | GMxxx | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | MPS3 CO Catalyst Gasket Retention System
| Total Project Capital Cost: |  |  | 111573
| Reporting Date: |  |  | 2019-07-09
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Albert Montaño |  |  |  | Project Manager Phone Number: |  | 9155432074
Owning Cost Center: |  | 5140 MONTANA POWER STATION |  |  |  | Major Project Location: |  | 54 - TX MONTANA POWER STATION - UNIT 3
Project Functional Class: |  | General |  |  |  | Business Segment: |  | 183 MONTANA PWR STATION - UNIT 3
Associated Projects: |  | None
In-Lieu of Component |  | None
Project Priority |  | MEDIUM - Important but Not Urgent
Project overview/scope: |  | A Gasket Retention System for the CO catalyst in the SCR was installed on MPS units 1 and 2 and Rio Grande Unit 9 in 2019. The LMS100 fleet SCR’s were inspected during the summer preparation outages this spring and the CO Catalyst gaskets have fallen out and require reinstallation or adjustments to the water flow into the turbine combustion section. Reinstallation of the gasket requires a complete unstacking of the CO modules and a 5-day outage. The gaskets seal in between the catalyst modules. With the gaskets out of place CO emissions exceedances can occur due to bypass or leakage around the catalyst. Sisu Energy & Environmental, LLC (Sisu) has created a Gasket Retention System that is a new enhancement in order to keep the gaskets in place. By use of the Sisu’s “H-Trays” the gasket is retained or captured in place and does not allow for the gasket to come loose or fall out of place. The project includes the new gasket retention system, remova/reinstallationl of the catalyst, scaffolding, and a confined space attendant for $110,000 per unit.
Business Justification: |  | New retention system will keep CO catalyst gasket in place. Catalyst removal and reinstallation of gasket is being performed frequently and requires a 5-day outage. This new system will resolve this issue and insure there is no CO bypass in the SCR. This system has been implemented on MPS1, MPS2 and RG9.
Project Risks and Constraints: |  | CO Catalyst modules may get damaged during installation. Work can be performed during the summer preparation outages.
Primary Reason for Expenditure |  |  | Quality Enhancement
Secondary Reason for Expenditure |  |  | Regulatory/Compliance/Environmental
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
110000
Estimated Start Date: |  |  | 2020-02-01 |  |  | Estimated Completion Date: |  |  | 2020-02-28
If applicable, describe and identify asset being replaced/retired
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
Avoiding removal of CO catalyst to reinstall gaskets frequently and insure that the exhaust gas is passing thru the catalyst and not bypassing it.
Describe alternatives considered:
No other technology or system is available to address this issue. Sisu has become the OEM supplier for the LMS100 Fleet.
What was the reason for selecting the proposed project over the alternatives considered?
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 111573 |  |  | 111573 |  | 104249.4744 |  | 104249.4744
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 18154.1181 |  |  | -73520.2161 |  | 14454.2411 |  | -7138.3697
Income Tax Exp (Benefit): |  | 29199 |  |  | 76845 |  | 20041.6777 |  | 34487.454
TOTAL COSTS |  | 158926.1181 |  |  | 114897.7839 |  | 138745.3932 |  | 131598.5587
BENEFITS
Revenue Requirement: |  | 150159.9368 |  |  | 257238.7705 |  | 106166.3771 |  | 144646.6839
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 3361.4284 |  |  | 3361.4284 |  | 3140.788 |  | 3140.788
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 153521.3652 |  |  | 260600.1989 |  | 109307.1651 |  | 147787.4719
BENEFIT-COST RATIO | [6 empty] | 0.78783 |  | 1.123
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Payment for Services | [7 empty] | 2019-03-01
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Sisu Maintenance Staff |  | Sisu |  |  |  |  | If no, explain why not:
O&M Staff |  | Power Gen, EPE |  |  |  |  | If no, explain why not: | Only preliminary planning has been performed
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Albert Montaño
| Date: | 2019-07-09
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function