## Form
| Project Number: |  |  | GN209 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | GT3 Boiler Feed Pump Upgrade
| Total Project Capital Cost: |  |  | 159237
| Reporting Date: |  |  | 2019-02-06
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Juan A. Sanchez Jr |  |  |  | Project Manager Phone Number: |  | 915-543-2940
Owning Cost Center: |  | 5110 POWER PLANT NEWMAN |  |  |  | Major Project Location: |  | 11 - TX NEWMAN - UNIT 5
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 115 NEWMAN - UNIT 5 GT3
Associated Projects: |  | N/A
In-Lieu of Component |  | N/A
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | Upgrade and replace kit parts to Newman GT3 Boiler Feed Pump
Business Justification: |  | Pump was removed due to pump failure and due to time restraints to upgrade and return this pump back in time for our summer run, we had no choice but to have this pump sent to the OEM for review and upgrade of pump. This pump suffered a catastrophic event on or about June 1, 2018 which rendered this unit inoperable. The pump was sent to a repair shop for dissasemble, clean and inspect (DCI) and a quote has been provided with a detailed quote depicting labor and kit (parts) list and prices. This pump is required for reliability of Unit 5's HRSG 3 unit. The pump was sent to the OEM repair shop for sole sourcing.
Project Risks and Constraints: |  | If we don’t get this pump back in time for our Summer run, we risk on operating Newman's Block 5 fleet to a less than optimal operation. Newman Block 5 has two HRSG units and each one has a Boiler Feed Pump that is the main piece of equipment to feed water to the Heat Recovery Steam Generator (HRSG). Without this pump, the steam turbine will is reduced to half load.
Primary Reason for Expenditure |  |  | Reliability
Secondary Reason for Expenditure |  |  | Quality Improvement/Enhancement
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost
0
Estimated Start Date: |  |  | 2019-04-08 |  |  | Estimated Completion Date: |  |  | 2019-04-30
If applicable, describe and identify asset being replaced/retired
Replacement of internal pump kit(s).
Please descrive the potential Cost Savings and/or Cost Avoidance for this project:
risk on operating Newman's Block 5 fleet to a less than optimal operation.
Describe alternatives considered:
None
What was the reason for selecting the proposed project over the alternatives considered?
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 159237 |  |  | 159237 |  | 148784.8633 |  | 148784.8633
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 25623.5344 |  |  | -102884.4697 |  | 20402.8423 |  | -9911.6286
Income Tax Exp (Benefit): |  | 41706 |  |  | 108004 |  | 28746.2441 |  | 48914.0384
TOTAL COSTS |  | 226566.5344 |  |  | 164356.5303 |  | 197933.9497 |  | 187787.2731
BENEFITS
Revenue Requirement: |  | 213720.0906 |  |  | 362900.8741 |  | 151499.3221 |  | 205316.824
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 3816.1158 |  |  | 3816.1158 |  | 3565.6303 |  | 3565.6303
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 217536.2064 |  |  | 366716.99 |  | 155064.9524 |  | 208882.4543
BENEFIT-COST RATIO | [6 empty] | 0.78342 |  | 1.1123
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Quote | [7 empty] | 2019-01-11
Capital request | [7 empty] | 2019-01-11
Purchase Requisition | [7 empty] | 2019-01-14
Purchase Order | [7 empty] | 2019-01-21
Pump received on site | [7 empty] | 2019-02-25
Invoiced | [7 empty] | 2019-03-04
PO Closed | [7 empty] | 2019-04-30
Click here to enter a date.
Please list internal and external resources assigned to this project:*
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Juan A. Sanchez |  | Power Generation |  |  |  |  | If no, explain why not:
Repair Shop |  | Flowserve |  |  |  |  | If no, explain why not:
Enrique Acosta |  | Supply Chain Management |  |  |  |  | If no, explain why not: | Waiting on all approvals
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Juan A. Sanchez Jr.
| Date: | 2019-02-13
Sponsor / Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Note on C42: Complete Capital Expenditure Section in CFFA and CBA tab. This should tie to the Upload Template
Note on C43: Complete O&M Expense Section in CFFA and CBA tab.
Note on C44: Calculated field. Financing Costs are related to the Interest Expense as result of additional debt to fund the project. Financial Benefits are avoidable increase in debt and interest expense due to additional revenue stream from revenue requirements in rates
Note on C48: Calculated field. Revenue Requirements are the expected increase in rate relief needed to sustained the allowable Rate of Return approved by the commissions
Note on C49: Complete Cost Savings section in CFFA and CBA tab.
Note on C50: Complete Cost Avoidance section in CFFA and CBA tab.
Note on C51: Calculated field.
Note on C52: Complete Other Benefits section in CFFA and CBA tab.