## Form
| Project Number: |  |  | GN210 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | U4/GT1 & GT2 Turbine Capital Replacement Parts (W501B6)
| Total Project Capital Cost: |  |  | 6894966.4
Reporting Date:
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Chris Carroll |  |  |  | Project Manager Phone Number: |  | 915-
Owning Cost Center: |  | 5110 POWER PLANT NEWMAN |  |  |  | Major Project Location: |  | 10 - TX NEWMAN - UNIT 4
Project Functional Class: |  | Other Production |  |  |  | Business Segment: |  | 114 NEWMAN - UNIT 4
Associated Projects:
In-Lieu of Component
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | Procurement of replacement capital parts for Newman GT1 and GT2 - W501B6 units.
Business Justification: |  | Have a complete (one ) set of turbine components for GT1 and GT2 in the event parts need to be replaced with urgency reliable operation.
Project Risks and Constraints:
Primary Reason for Expenditure |  |  | Reliability
Secondary Reason for Expenditure |  |  | Quality Improvement/Enhancement
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost
0
Estimated Start Date: |  |  | 2019-05-29 |  |  | Estimated Completion Date: |  |  | 2020-04-30
If applicable, describe and identify asset being replaced/retired
Turbine components of the W501B6 units (NM4 GT1 & GT2) will be replaced as needed with the replacement parts being procured as part of this project.
Please descrive the potential Cost Savings and/or Cost Avoidance for this project:
Having turbine components readily available will reduce GT1/GT2 shut down time for equipment failure referred to turbine components.
Describe alternatives considered:
Bying replacement parts as needed.
What was the reason for selecting the proposed project over the alternatives considered?
Extremely long lead times.
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Status Quo - Do Nothing
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 6894966.4 |  |  | 6894966.4 |  | 6019517.4967 |  | 6019517.4967
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 1120676.7115 |  |  | -3946876.4956 |  | 824303.429 |  | -338261.3095
Income Tax Exp (Benefit): |  | 1611987 |  |  | 4457863 |  | 1081163.3027 |  | 1945249.6085
TOTAL COSTS |  | 9627630.1115 |  |  | 7405952.9044 |  | 7924984.2284 |  | 7626505.7956
BENEFITS
Revenue Requirement: |  | 8421571.202 |  |  | 15353470.6863 |  | 5756813.2915 |  | 8217273.4386
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 81673.7619 |  |  | 81673.7619 |  | 71303.7033 |  | 71303.7033
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 8503244.9639 |  |  | 15435144.4482 |  | 5828116.9948 |  | 8288577.1419
BENEFIT-COST RATIO | [6 empty] | 0.73541 |  | 1.0868
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Letter of Intent to EthosEnergy for replacement capital parts procurement | [7 empty] | 2019-05-29
Issue PO to EthosEnergy | [7 empty] | 2019-06-15
Manufacturing of Parts | [7 empty] | 2020-03-31
Delivery of First Set - Stationary Parts | [7 empty] | 2020-04-01
Delivery of Second Set of Parts | [7 empty] | 2020-04-30
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:*
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Chris Carroll
| Date: | 2019-05-29
Sponsor / Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Note on C42: Complete Capital Expenditure Section in CFFA and CBA tab. This should tie to the Upload Template
Note on C43: Complete O&M Expense Section in CFFA and CBA tab.
Note on C44: Calculated field. Financing Costs are related to the Interest Expense as result of additional debt to fund the project. Financial Benefits are avoidable increase in debt and interest expense due to additional revenue stream from revenue requirements in rates
Note on C48: Calculated field. Revenue Requirements are the expected increase in rate relief needed to sustained the allowable Rate of Return approved by the commissions
Note on C49: Complete Cost Savings section in CFFA and CBA tab.
Note on C50: Complete Cost Avoidance section in CFFA and CBA tab.
Note on C51: Calculated field.
Note on C52: Complete Other Benefits section in CFFA and CBA tab.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes