## Form
| Project Number: | [8 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | NW U3 UNINTERUPTIBLE POWER SUPPLY UPGRADE
| Total Project Capital Cost: |  |  | 293672
| Reporting Date: |  |  | 2019-06-26
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Jesus Marquez |  |  |  | Project Manager Phone Number: |  | 915-543-2935
Owning Cost Center: |  | 5110 POWER PLANT NEWMAN |  |  |  | Major Project Location: |  | 9 - TX NEWMAN - UNIT 3
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 113 NEWMAN - UNIT 3
Associated Projects: |  | NONE
In-Lieu of Component
Project Priority |  | MEDIUM - Important but Not Urgent
Project overview/scope: |  | Turnkey Project to Upgrade current UPS to new 20kva UPS to include engineering , removal and installation. Also to include line condtioner,battery charger and all required panels to critical equipment.
Business Justification: |  | The current UPS was installed in 1995, the last two years we have had issue with the UPS failing. The failures have caused units to trip and go off line. On 5/17/2019 we tripped Unit 1 and Unit 3 due to a failure on the UPS, further we are having a hard time finding parts to repair the UPS and the repairs are very costly.
Project Risks and Constraints:
Primary Reason for Expenditure |  |  | System Reliability & Improvement
Secondary Reason for Expenditure |  |  | Quality Enhancement
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2020-01-06 |  |  | Estimated Completion Date: |  |  | 2020-05-15
If applicable, describe and identify asset being replaced/retired
SCI 20KVA UPS ,battery charger with 2 input sources.
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
Upgrading UPS will reduce unit trips. The trips are costly due to unit downtime .
Describe alternatives considered:
What was the reason for selecting the proposed project over the alternatives considered?
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 293672 |  |  | 293672 |  | 274395.7019 |  | 274395.7019
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 48049.3889 |  |  | -195417.0027 |  | 38255.424 |  | -19046.731
Income Tax Exp (Benefit): |  | 76824 |  |  | 203822 |  | 52618.8786 |  | 91060.9026
TOTAL COSTS |  | 418545.3889 |  |  | 302076.9973 |  | 365270.0045 |  | 346409.8736
BENEFITS
Revenue Requirement: |  | 395785.4576 |  |  | 681018.621 |  | 279461.9292 |  | 381771.626
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 9760.0781 |  |  | 9760.0781 |  | 9119.4376 |  | 9119.4376
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 405545.5356 |  |  | 690778.6991 |  | 288581.3668 |  | 390891.0636
BENEFIT-COST RATIO | [6 empty] | 0.79005 |  | 1.1284
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Issue PO | [7 empty] | 2019-10-01
Receive equipment | [7 empty] | 2020-02-01
Install equipment | [7 empty] | 2020-04-01
Complete installation and testing | [7 empty] | 2020-04-14
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Jesus Marquez |  | Power Gen/EPE |  |  |  |  | If no, explain why not:
TBD |  | Power Gen/EPE |  |  |  |  | If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Jesus Marquez
| Date: | 2019-06-26
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function