## Form
| Project Number: | [8 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | NW U4 COOLING TOWER TRANSFORMER REPLACEMENT
| Total Project Capital Cost: |  |  | 119609
| Reporting Date: |  |  | 2019-06-26
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Jesus Marquez |  |  |  | Project Manager Phone Number: |  | 915 543-935
Owning Cost Center: |  | 5110 POWER PLANT NEWMAN |  |  |  | Major Project Location: |  | 10 - TX NEWMAN - UNIT 4
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 114 NEWMAN - UNIT 4
Associated Projects: |  | NONE
In-Lieu of Component
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | Cooling tower transformer, disconnect switch and under ground cable replacement
Business Justification: |  | On May 16, 2019. the transformer of the A side to the cooling tower load center faulted. The fault damaged the disconnect switch and the under ground feeder cable. The cooling tower switch gear has a redundant transformer and is currently running on that side. The A side transformer, switch and underground cable needs to be replaced ASAP to assure Unit 4 stays on line. Loss of the B side will cause a total loss of Block 4
Project Risks and Constraints:
Primary Reason for Expenditure |  |  | System Reliability & Improvement
Secondary Reason for Expenditure |  |  | Safety & Security
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
117000
Estimated Start Date: |  |  | 2019-07-01 |  |  | Estimated Completion Date: |  |  | 2019-10-31
If applicable, describe and identify asset being replaced/retired
1500 kva transformer 4160v /480v 3 phase , 4160v switch and 1500ft of 250 mcm cable.
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
If we lose the B side of load center there will be a loss of 268 mw
Describe alternatives considered:
What was the reason for selecting the proposed project over the alternatives considered?
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 119609 |  |  | 119609 |  | 119609 |  | 119609
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 17689.7063 |  |  | -80865.2714 |  | 15504.5759 |  | -8402.5745
Income Tax Exp (Benefit): |  | 34808 |  |  | 80622 |  | 25026.4136 |  | 39135.2396
TOTAL COSTS |  | 172106.7063 |  |  | 119365.7286 |  | 160139.9894 |  | 150341.6651
BENEFITS
Revenue Requirement: |  | 172951.6613 |  |  | 267889.1334 |  | 128394.5054 |  | 163719.0397
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 1776.1473 |  |  | 1776.1473 |  | 1776.1473 |  | 1776.1473
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 174727.8085 |  |  | 269665.2807 |  | 130170.6527 |  | 165495.187
BENEFIT-COST RATIO | [6 empty] | 0.81286 |  | 1.1008
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Issue PO for Transformer | [7 empty] | 2019-07-08
Issue PO for Switch | [7 empty] | 2019-07-08
Install equipment | [7 empty] | 2019-09-16
Complete installation and testing | [7 empty] | 2019-10-01
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Jesus Marquez |  | Power Gen/EPE |  |  |  |  | If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Jesus Marquez
| Date: | 2019-06-26
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function