## Form
| Project Number: |  |  | GN228 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | U2 GENERATOR PROTECTION RELAY UPGRADE
| Total Project Capital Cost: |  |  | 172194
| Reporting Date: |  |  | 2019-06-25
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Lusheng Su |  |  |  | Project Manager Phone Number: |  | 915-235-7087
Owning Cost Center: |  | 5110 POWER PLANT NEWMAN |  |  |  | Major Project Location: |  | 8 - TX NEWMAN - UNIT 2
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 112 NEWMAN - UNIT 2
Associated Projects: |  | NONE
In-Lieu of Component
Project Priority |  | MEDIUM - Important but Not Urgent
Project overview/scope: |  | Replace ABB relays to SEL relays for U2
Business Justification: |  | SEL relays can be synchronized to GPS so that each trip or misoperation can be analyzed on one sitieth of a second level. While the ABB relay's time stamp is hard to set, it is difficult to analyze the root cause of the trip or misoperations with the time stamp ABB relay provided. So it is hard to decide the orders of events. With the function of event reports from SEL relays, it is easy to decide the root cause of the unit trip or misoperation PRC-004. Plus, the SEL relays will provide live phase analysis and advanced protection elements.
Project Risks and Constraints:
Primary Reason for Expenditure |  |  | System Reliabilty & Improvement
Secondary Reason for Expenditure |  |  | New Technology
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2019-11-01 |  |  | Estimated Completion Date: |  |  | 2020-03-31
If applicable, describe and identify asset being replaced/retired
Five ABB relays will be replaced by SEL relays
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
SEL relay will help analyze the root cause of unit trip or misoperation.
Describe alternatives considered:
What was the reason for selecting the proposed project over the alternatives considered?
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 172194 |  |  | 172194 |  | 162719.6856 |  | 162719.6856
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 28710.8198 |  |  | -103124.7485 |  | 23019.8418 |  | -8165.1334
Income Tax Exp (Benefit): |  | 44956 |  |  | 111993 |  | 31246.5911 |  | 51830.1494
TOTAL COSTS |  | 245860.8198 |  |  | 181062.2515 |  | 216986.1185 |  | 206384.7016
BENEFITS
Revenue Requirement: |  | 229982.8537 |  |  | 381942.6629 |  | 164076.8743 |  | 219460.1881
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 1855.3156 |  |  | 1855.3156 |  | 1738.902 |  | 1738.902
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 231838.1693 |  |  | 383797.9784 |  | 165815.7764 |  | 221199.0902
BENEFIT-COST RATIO | [6 empty] | 0.76418 |  | 1.0718
Please list major milestones:
Milestone: | [7 empty] | Completed by:
SEL relays mounted and wires terminated | [7 empty] | 2020-03-01
SEL relays programmed and commissioned | [7 empty] | 2020-03-30
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Lusheng Su |  | Power Gen/EPE |  |  |  |  | If no, explain why not:
TBD | [6 empty] | If no, explain why not: | In the process of bidding out
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Lusheng Su
| Date: | 2019-06-25
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function