## Form
| Project Number: |  |  | GN238 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | NM2 LPT Packing Replacement
| Total Project Capital Cost: |  |  | 342040
| Reporting Date: |  |  | 2020-01-08
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Eustacio Alderette |  |  |  | Project Manager Phone Number: |  | 9155434086
Owning Cost Center: |  | 5110 POWER PLANT NEWMAN |  |  |  | Major Project Location: |  | 8 - TX NEWMAN - UNIT 2
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 112 NEWMAN - UNIT 2
Associated Projects: |  | WK151014.0014 - U2 TURBINE JOURNAL BEARING 3; WK180909.0007 - U2 TURBINE JOURNAL BEARING 2
In-Lieu of Component |  | New replacement parts (packing, gland steam seals) are being fabricated to address steam leaks.
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | Replacement of NM2 low pressure turbine packing replacement to address steam leaking, blow-by.
Business Justification: |  | The steam leak creates operational, reliability, and safety concerns.
Project Risks and Constraints: |  | There is a specific time constraint to address the issue to avoid impacting reliability. There are a limited number of vendors who can reverse engineer the packing and perform installation.
Primary Reason for Expenditure |  |  | System Reliability & Improvement
Secondary Reason for Expenditure |  |  | Safety & Security
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2020-01-09 |  |  | Estimated Completion Date: |  |  | 2020-03-31
If applicable, describe and identify asset being replaced/retired
Newman Unit 2 Low Pressure Turbine Gland Seal Steam Packing.
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
EPE avoids delaying resolution and running the risk of an unplanned outage. Also, EPE avoids maintaining a safety issue and concern.
Describe alternatives considered:
Continue to run without fully addressing the issue.
What was the reason for selecting the proposed project over the alternatives considered?
An unplanned outage runs the risk of higher costs during peak season (with tighter resource constraints - contractors, reliability, replacement power).
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 342040 |  |  | 342040 |  | 319588.8811 |  | 319588.8811
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 55962.9789 |  |  | -227603.7171 |  | 44556.01 |  | -22184.1571
Income Tax Exp (Benefit): |  | 89478 |  |  | 237401 |  | 61285.6847 |  | 106060.4892
TOTAL COSTS |  | 487480.9789 |  |  | 351837.2829 |  | 425430.5758 |  | 403465.2133
BENEFITS
Revenue Requirement: |  | 460972.3342 |  |  | 793184.318 |  | 325490.0197 |  | 444650.4304
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 11367.5703 |  |  | 11367.5703 |  | 10621.4158 |  | 10621.4158
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 472339.9044 |  |  | 804551.8882 |  | 336111.4356 |  | 455271.8463
BENEFIT-COST RATIO | [6 empty] | 0.79005 |  | 1.1284
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Contractor to mobilize to site | [7 empty] | 2020-01-10
Operations Turnover | [7 empty] | 2020-01-27
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Eustacio Alderette |  | Outage Department |  |  |  |  | If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Eustacio Alderette
| Date: | 2020-01-08
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function