## Form
| Project Number: |  |  | GN263 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | NW U4GT1 Generator Hydrogen Cooler Retube
| Total Project Capital Cost: |  |  | 114679
| Reporting Date: |  |  | 2020-09-03
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Nathaniel Campos |  |  |  | Project Manager Phone Number: |  | 915-238-7718
Owning Cost Center: |  | 5110 POWER PLANT NEWMAN |  |  |  | Major Project Location: |  | 10 - TX NEWMAN - UNIT 4
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 117 NEWMAN - GAS TURBINE 1
Associated Projects: |  | GN264 GT2 Generator Hydrogen Cooler Retube
In-Lieu of Component
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | Brimhall Industries will retube the 2 generator hydrogen coolers and prepare them for shipment back to El Paso Electric.
Business Justification: |  | The retubing is done as preventative maintenacne. These coolers were inspected during the 2020 Major Inspection. They were in poor condition and a retube was recomeneded. The retube did not fit the schedule, so it was postponed and scheduled for the DCS upgrade. If the tubes fail, water will leak into the generator causing high risk or arcing.
Project Risks and Constraints: |  | If the tubes fail, water will leak into the generator and the risk of arcing will be high. Arcing can leak to extensive generator damage, and possible rewind. The cost associated with the failure is very high.
Primary Reason for Expenditure |  |  | System Reliabilty & Improvement
Secondary Reason for Expenditure |  |  | Quality Enhancement
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2020-10-01 |  |  | Estimated Completion Date: |  |  | 2021-01-01
If applicable, describe and identify asset being replaced/retired
Old generator hydrogen cooler tubes and tube sheets.
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
The cost associated with the failure of the hydrogen coolers is extremely high. The RG 7 rewind was $2.5 million. The GT1 FO caused by arcing was $942,000.
Describe alternatives considered:
none
What was the reason for selecting the proposed project over the alternatives considered?
N/A
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 114679 |  |  | 114679 |  | 107917.2775 |  | 107917.2775
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 18501.2766 |  |  | -67849.9193 |  | 14797.9297 |  | -5669.4919
Income Tax Exp (Benefit): |  | 29998 |  |  | 73479 |  | 20945.7685 |  | 34345.3813
TOTAL COSTS |  | 163178.2766 |  |  | 120308.0807 |  | 143660.9756 |  | 136593.167
BENEFITS
Revenue Requirement: |  | 152604.0438 |  |  | 251186.5462 |  | 109147.8424 |  | 145233.3993
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 439.9938 |  |  | 439.9938 |  | 415.6218 |  | 415.6218
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 153044.0376 |  |  | 251626.54 |  | 109563.4642 |  | 145649.0211
BENEFIT-COST RATIO | [6 empty] | 0.76265 |  | 1.0663
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Bidding to start | [7 empty] | 2020-08-01
Award of Contract | [7 empty] | 2020-08-20
Procurment of parts (Tubes) | [7 empty] | 2020-09-01
Coolers sent offsite | [7 empty] | 2020-10-09
Coolers back onsite | [7 empty] | 2020-11-21
Coolers reinstalled | [7 empty] | 2020-11-27
Completed | [7 empty] | 2020-11-27
In service date | [7 empty] | 2020-12-19
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Nathaniel Campos |  | Outage |  |  |  |  | If no, explain why not:
Mark Brimhall |  | Brimhall Industries |  |  |  |  | If no, explain why not:
EPE Employee |  | Mechanics |  |  |  |  | If no, explain why not: | Preliminary stage of project.
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Nathaniel Campos
| Date: | 2020-09-03
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function