## Form
| Project Number: |  |  | GR165 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | RG PLANT WELL WATER PIPING REPL
| Total Project Capital Cost: |  |  | 388523
| Reporting Date: |  |  | 2019-06-21
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | JESUS JIMENEZ |  |  |  | Project Manager Phone Number: |  | 915-543-2972
Owning Cost Center: |  | 5131 POWER PLANT RIO GRANDE |  |  |  | Major Project Location: |  | 17 - NM RIO GRANDE - COMMON
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 120 RIO GRANDE - JOINT
Associated Projects: |  | N/A
In-Lieu of Component
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | Replace deteiorated sections of the well piping supplying cooling water to the Rio Grande Power Plant
Business Justification: |  | The well water piping supplying cooling water to Rio Grande was installed iapproximately 40 years ago. During the 2019 summer run, 20 ft of pipe was replaced due to pipe deterioration and subsequent pipe rupture. The power plant was required to install a temporary patch to complete summer run.. If pipe ruptures continue, Rio Grande Power Plant may exerience complete loss of cooling water. This BCO is submitted for the replacement of 2300 linear feet of pipe.
Project Risks and Constraints: |  | Project Risk - MW Curtailment/ Potential Outage due to loss of cooling water Project Contraints - Rio Grande Operational Schhedule
Primary Reason for Expenditure |  |  | System Reliabilty & Improvement
Secondary Reason for Expenditure |  |  | Safety & Security
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2020-01-01 |  |  | Estimated Completion Date: |  |  | 2020-07-31
If applicable, describe and identify asset being replaced/retired
Well Field Distribution Piping
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
Describe alternatives considered:
Initiate Eddy Testing on the existing piping, determine condition of piping and continue monitoring existing piping
What was the reason for selecting the proposed project over the alternatives considered?
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 388523 |  |  | 388523 |  | 363020.7895 |  | 363020.7895
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 63568.6214 |  |  | -258532.4997 |  | 50611.3332 |  | -25198.2491
Income Tax Exp (Benefit): |  | 101637 |  |  | 269657 |  | 69613.6551 |  | 120472.3139
TOTAL COSTS |  | 553728.6214 |  |  | 399647.5003 |  | 483245.7778 |  | 458294.8544
BENEFITS
Revenue Requirement: |  | 523616.9202 |  |  | 900975.0591 |  | 369723.0229 |  | 505076.8515
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 12912.4152 |  |  | 12912.4152 |  | 12064.8589 |  | 12064.8589
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 536529.3354 |  |  | 913887.4743 |  | 381787.8818 |  | 517141.7104
BENEFIT-COST RATIO | [6 empty] | 0.79005 |  | 1.1284
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Order Pipe | [7 empty] | 2019-11-01
Pipe Delivery | [7 empty] | 2020-01-01
Perform Eddy Current Testing | [7 empty] | 2020-01-01
Commence Excavation | [7 empty] | 2020-02-15
Install Piping | [7 empty] | 2020-03-01
Complete Pipe Install | [7 empty] | 2020-04-30
Final Invoicing | [7 empty] | 2019-05-30
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Jesus Jimenez |  | Power Generation -Rio Grande Engineering |  |  |  |  | If no, explain why not:
Environmental Rep |  | EPE - Environmental Group |  |  |  |  | If no, explain why not: | Project SOW in Deveopment
Contractor Replacing Pipe |  | TBD |  |  |  |  | If no, explain why not: | Project SOW in Deveopment
Contractor Performing Eddy Current Testing |  | TBD |  |  |  |  | If no, explain why not: | Project SOW in Deveopment
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Jesus Jimenez
| Date: | 2019-06-21
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function