## Form
| Project Number: | [8 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | Replace Power Rail on 100 Ton Crane
| Total Project Capital Cost: |  |  | 172385
| Reporting Date: |  |  | 2019-07-08
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Ronald L Heckman |  |  |  | Project Manager Phone Number: |  | 915-472-0697
Owning Cost Center: |  | 5131 POWER PLANT RIO GRANDE |  |  |  | Major Project Location: |  | 17 - NM RIO GRANDE - COMMON
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 120 RIO GRANDE - JOINT
Associated Projects: |  | NONE
In-Lieu of Component
Project Priority |  | MEDIUM - Important but Not Urgent
Project overview/scope: |  | Replace existing Duct-o-Bar power rail with a span guard power rail system
Business Justification: |  | We installed the Duct-O-Bar system in 2005. At the time it was $24,784 less than a better system. Since that time we have spent $73,600 on maintenance. At todays rates it will cost $26,430 more to install the improved system over a bar system.
Project Risks and Constraints:
Primary Reason for Expenditure |  |  | Quality Enhancement
Secondary Reason for Expenditure |  |  | Cost Savings
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2019-10-01 |  |  | Estimated Completion Date: |  |  | 2019-12-30
If applicable, describe and identify asset being replaced/retired
The existing Duct-O-Rail power system is being replaced.
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
With the new system we will save approximately $4,000 per year on equipmental rental and $1,000 per year contractor cost for maintenance of the power rail
Describe alternatives considered:
there were additional quotes using a Bar system one was more expensive and one was less.
What was the reason for selecting the proposed project over the alternatives considered?
The proposed system is a continuous run with no joints and the collector system will withstand 6 inch movement both horizontal and vertical.
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 172385 |  |  | 172385 |  | 172385 |  | 172385
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 25075.3956 |  |  | -113044.656 |  | 21980.5393 |  | -11606.0664
Income Tax Exp (Benefit): |  | 50132 |  |  | 113507 |  | 36264.7807 |  | 55877.5558
TOTAL COSTS |  | 247592.3956 |  |  | 172847.344 |  | 230630.3199 |  | 216656.4894
BENEFITS
Revenue Requirement: |  | 248007.0834 |  |  | 379436.3247 |  | 184841.1208 |  | 234064.8611
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 1015.0784 |  |  | 1015.0784 |  | 1015.0784 |  | 1015.0784
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 249022.1617 |  |  | 380451.4031 |  | 185856.1991 |  | 235079.9395
BENEFIT-COST RATIO | [6 empty] | 0.80586 |  | 1.085
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Bids already completed | [7 empty] | 2019-07-09
Write PO awaiting Project number to write work order | [7 empty] | 2019-08-01
Start Work 9/1/2019 | [7 empty] | 2019-09-01
Complete Work 10/1/2019 | [7 empty] | 2019-10-01
billing 12/15/2019 | [7 empty] | 2019-12-15
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Ronald L Heckman |  | Power Gen Engineer |  |  |  |  | If no, explain why not:
Twin City Crane |  | Sub Contractor |  |  |  |  | If no, explain why not:
United Rental | [6 empty] | If no, explain why not: | Project planning stage
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Ronald L Heckman
| Date: | 2019-07-09
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function