## Form
| Project Number: |  |  | GR175 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | Rio 8 4160V Switchgear Breaker Upgrade
| Total Project Capital Cost: |  |  | 283851
| Reporting Date: |  |  | 2020-04-30
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Jeff Hughes |  |  |  | Project Manager Phone Number: |  | 915-543-2958
Owning Cost Center: |  | 5131 POWER PLANT RIO GRANDE |  |  |  | Major Project Location: |  | 20 - NM RIO GRANDE - UNIT 8
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 128 RIO GRANDE - UNIT 8
Associated Projects: |  | NONE
In-Lieu of Component
Project Priority |  | MEDIUM - Important but Not Urgent
Project overview/scope: |  | Upgrade the 4160 Volt switchgear breakers from the OEM install of 1973.
Business Justification: |  | To ensure proper circuit disconnect on a 4160V trip event in order to protect downstream equipment.
Project Risks and Constraints: |  | Unit must be in outage to exchange breakers.
Primary Reason for Expenditure |  |  | Safety & Security
Secondary Reason for Expenditure |  |  | System Reliabilty & Improvement
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost
0
Estimated Start Date: |  |  | 2020-03-01 |  |  | Estimated Completion Date: |  |  | 2020-04-30
If applicable, describe and identify asset being replaced/retired
Qty 10, GE OEM breakers AM-4.76-250-7H 1200A, AM-4.76-250-7H 2000A
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
Minimize risk of a failed circuit disconnect on 4160V switchgear.
Describe alternatives considered:
N/A
What was the reason for selecting the proposed project over the alternatives considered?
N/A
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 283851 |  |  | 283851 |  | 265219.3413 |  | 265219.3413
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 45929.4859 |  |  | -185217.68 |  | 36570.2806 |  | -17914.56
Income Tax Exp (Benefit): |  | 74317 |  |  | 194013 |  | 51117.2796 |  | 87466.9869
TOTAL COSTS |  | 404097.4859 |  |  | 292646.32 |  | 352906.9014 |  | 334771.7682
BENEFITS
Revenue Requirement: |  | 381495.1336 |  |  | 650658.1018 |  | 270078.1299 |  | 366990.925
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 7674.6904 |  |  | 7674.6904 |  | 7170.9324 |  | 7170.9324
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 389169.824 |  |  | 658332.7922 |  | 277249.0623 |  | 374161.8574
BENEFIT-COST RATIO | [6 empty] | 0.78562 |  | 1.1177
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Order Breakers for build up. | [7 empty] | 2019-10-31
Receive and inspect breakers. | [7 empty] | 2020-01-31
Install and Commission by contracotor. | [7 empty] | 2020-03-30
Training for Sire personnell on Operation and Maintenance. | [7 empty] | 2020-03-31
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Wilson Tademy |  | Generation |  |  |  |  | If no, explain why not:
Kyle Olson |  | Generation |  |  |  |  | If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Jeff Hughes
| Date: | 2019-07-16
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function