## Form
| Project Number: |  |  | GR176 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | RG U8 FEED WATER REGULATORS UPGRADE
| Total Project Capital Cost: |  |  | 283211
| Reporting Date: |  |  | 2019-07-16
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Jeff Hughes |  |  |  | Project Manager Phone Number: |  | 915-543-2958
Owning Cost Center: |  | 5131 POWER PLANT RIO GRANDE |  |  |  | Major Project Location: |  | 20 - NM RIO GRANDE - UNIT 8
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 128 RIO GRANDE - UNIT 8
Associated Projects: |  | NONE
In-Lieu of Component
Project Priority |  | MEDIUM - Important but Not Urgent
Project overview/scope: |  | Upgrade. Specify design and install new Main and Start Up Feed Water Regulators.
Business Justification: |  | Ensure proper control of boiler feed water and eliminate unit swings due to stepping movement of current regulator.
Project Risks and Constraints: |  | Rio 8 must be in outage for installation. Current FW regulator is extremely de-tuned to prevent swings.
Primary Reason for Expenditure |  |  | System Reliability & Improvement
Secondary Reason for Expenditure |  |  | Growth & Increased Capacity
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost
0
Estimated Start Date: |  |  | 2019-10-01 |  |  | Estimated Completion Date: |  |  | 2020-04-01
If applicable, describe and identify asset being replaced/retired
Mogas Air actuated ball valves with position control.
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
Improved reliability and response of the Feed Water system.
Describe alternatives considered:
N/A
What was the reason for selecting the proposed project over the alternatives considered?
N/A
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 283211 |  |  | 283211 |  | 269588.6372 |  | 269588.6372
O&M Expenses: |  | 2000 |  |  | 2000 |  | 1868.7223 |  | 1868.7223
Financing Costs (Benefit): |  | 48927.4685 |  |  | -170524.7232 |  | 39445.1935 |  | -12422.8028
Income Tax Exp (Benefit): |  | 74119 |  |  | 186154 |  | 51407.3155 |  | 85744.3246
TOTAL COSTS |  | 408257.4685 |  |  | 300840.2768 |  | 362309.8684 |  | 344778.8813
BENEFITS
Revenue Requirement: |  | 382351.9984 |  |  | 636138.376 |  | 272993.6903 |  | 365293.4525
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 4707.3371 |  |  | 4707.3371 |  | 4427.6023 |  | 4427.6023
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 387059.3355 |  |  | 640845.713 |  | 277421.2927 |  | 369721.0549
BENEFIT-COST RATIO | [6 empty] | 0.7657 |  | 1.0723
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Specify Valves | [7 empty] | 2019-10-31
Engineer installation | [7 empty] | 2019-12-31
Installation by contractor. | [7 empty] | 2020-03-01
Calibrate, commission and test valves. | [7 empty] | 2020-03-31
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Wilson Tademy |  | Generation |  |  |  |  | If no, explain why not:
Kyle Olson |  | Generation |  |  |  |  | If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Jeff Hughes
| Date: | 2019-07-16
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function