## Form
| Project Number: |  |  | GR177 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | RIO GRANDE DCS CIP_CYBER IMPRVMNTS
| Total Project Capital Cost: |  |  | 232496
| Reporting Date: |  |  | 2019-08-23
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | J Kyle Olson |  |  |  | Project Manager Phone Number: |  | 915-521-4678
Owning Cost Center: |  | 5131 POWER PLANT RIO GRANDE |  |  |  | Major Project Location: |  | 17 - NM RIO GRANDE - COMMON
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 120 RIO GRANDE - JOINT
Associated Projects: |  | N/A
In-Lieu of Component
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | Plant wide Digital Control System improvements to comply with Critical Intrastructure Protection-003-7 and improve overall Digital Control System cyber security systems.
Business Justification: |  | Needed to comply with Critical Intrastructure Protection-0003-7 and improve Digital Control System Cyber Security Systems
Project Risks and Constraints: |  | Short timeline due to Critical Intrastructure Protection-003-7 becoming effective 1/1/2020
Primary Reason for Expenditure |  |  | Regulatory/Compliance/Environmental
Secondary Reason for Expenditure |  |  | System Reliabilty & Improvement
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2019-12-01 |  |  | Estimated Completion Date: |  |  | 2019-12-31
If applicable, describe and identify asset being replaced/retired
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
Describe alternatives considered:
What was the reason for selecting the proposed project over the alternatives considered?
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 232496 |  |  | 232496 |  | 232496 |  | 232496
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 33447.6277 |  |  | -149359.7684 |  | 29321.7346 |  | -15206.061
Income Tax Exp (Benefit): |  | 67584 |  |  | 150700 |  | 49084.5621 |  | 74895.4352
TOTAL COSTS |  | 333527.6277 |  |  | 233836.2316 |  | 310902.2966 |  | 292185.3742
BENEFITS
Revenue Requirement: |  | 333373.0604 |  |  | 505848.9016 |  | 249112.7495 |  | 314005.864
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 0 |  |  | 0 |  | 0 |  | 0
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 333373.0604 |  |  | 505848.9016 |  | 249112.7495 |  | 314005.864
BENEFIT-COST RATIO | [6 empty] | 0.80126 |  | 1.0747
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Issue Purchase Order | [7 empty] | 2019-09-15
Parts on site | [7 empty] | 2019-11-15
Installation Complete | [7 empty] | 2019-12-15
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
Kyle Olson |  | Power Generation |  |  |  |  | If no, explain why not:
Tanisha House |  | Power Generation |  |  |  |  | If no, explain why not:
Tracy Van Slyke |  | Operation Technology |  |  |  |  | If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | J Kyle Olson
| Date: | 2019-08-23
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function